## Work List
Exported on: 2026-08-16 19:41:45
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: KANERA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001001/AV/22012034469412 — shanti dham - tal ke pura ke niche kanera | Completed | 281062.92 | 277864.03 | 2019-12-26 | 2020-05-13
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001001/AV/22012034469413 — shanti dham - taliya ka pura ke niche | Completed | 281063.03 | 273349.6 | 2020-02-12 | 2020-06-30
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001001/AV/22012034469414 — shanti dham - pachoriyan ke pura ke niche | Completed | 281063.03 | 272835.03 | 2020-01-11 | 2020-05-29
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001001/AV/22012034469415 — Play ground - tal ke pura ke paas kanera | Deleted | 0 | 0 | 2019-08-15
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001001/AV/22012034516424 — Aganwadi Bhawan Kanera | Completed | 180000 | 178980 | 2020-09-14 | 2021-02-24
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702001001/AV/22012034548832 — गौशाला निर्माण ग्राम कनेरा | Deleted | 0 | 0 | 2020-11-26
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001001/AV/22012034615834 — panchayat bhawan kanera | Completed | 514000 | 512073 | 2022-03-23 | 2022-09-02
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001001/AV/4359 — Anganwadi bajariya | Completed | 330000 | 175629 | 2016-02-10 | 2017-09-01
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001001/AV/4360 — Anganwadi/Other Rural Infrastructure,ATER | Completed | 330000 | 329378 | 2016-01-20 | 2020-04-28
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001001/AV/4361 — Anganwadi/Other Rural Infrastructure,ATER | Completed | 330000 | 330055 | 2016-01-20 | 2020-04-28
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Feeder Canal for Community / Construction of Feeder Canal for Community | Construction of Canal | 1702001001/DP/22012034523250 — Charagah Nirman Kanera | Closed | 0 | 0 | 2020-11-26
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1702001001/DP/22012034594266 — अमृत वाटिका कार्य ग्राम कनेरा | Closed | 0 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001001/DP/22012034597926 — अमृत वाटिका अमृत सरोवर तालाब के पास ग्राम कनेरा | Closed | 55847.4 | 0 | 2023-04-14
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034366217 — kachha nala nirman ( bhind porsa sadak ke kinare supar school ke samne se anjani nagar ke or ) | Completed | 578521.89 | 247380 | 2020-08-01 | 2020-10-16
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034624175 — Nali nirman - ramdas ke makan se nariaya ke or taliya ka pura | Completed | 15150 | 15054 | 2021-05-21 | 2021-07-02
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034624176 — Nali nirman - main awadi pokhar ka pura gram kanera | Completed | 30300 | 30108 | 2021-05-20 | 2021-07-02
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034625214 — nali nirman - suresh singh ke darwaje se bahadur singh ke darwaje ke or pokhari ka pura | Completed | 20201 | 19686 | 2021-06-04 | 2021-08-09
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034625216 — nali nirman - phool singh ke darwaje se ramveer ke makan ke or | Completed | 20201 | 19686 | 2021-06-04 | 2021-07-02
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034625217 — nali nirman - bahadur ke goda se niche daddariya ke or | Completed | 20201 | 19686 | 2021-06-04 | 2021-08-09
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001001/FP/22012034625218 — nali nirman - kholai ke darwaje se vijay singh ke darwaje ke or | Closed | 20201 | 0 | 2021-05-18
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001001/IF/22012034353605 — वृक्षारोपण गोवत. प्राइमरी एवं मिडिल स्कूल, आगनबाडी भवन, स्वास्थ्य केंद्र कनेरा | Deleted | 335000 | 0 | 2017-06-15
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001001/IF/22012034353610 — वृक्षारोपण नहर के किनारे कनेरा | Deleted | 335000 | 0 | 2017-06-15
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001001/IF/22012034727091 — nadef tanka - mangal singh / hari singh | Completed | 12507.57 | 11265.8 | 2021-07-02 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001001/IF/22012034727095 — nadef tanka - lakhan kumar / suratram taliya ka pura | Completed | 12507.57 | 11265.8 | 2021-06-18 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001001/IF/22012034727101 — nadef tanka - brajesh / purusottam | Completed | 12507.57 | 11265.8 | 2021-06-18 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001001/IF/22012034727106 — nadef tanka - jitendra / indrajeet taliya ka pura | Completed | 12507.57 | 11265.8 | 2021-06-18 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001001/IF/22012034727107 — nadef tanka - ramniwas/ murlidhar | Completed | 12507.57 | 11265.8 | 2021-06-25 | 2021-08-28
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001001/IF/22012035323616 — खेत तालाब रामनरेश /रामकरन कनेरा | Physically Completed | 147621.16 | 102024.42 | 2025-05-12 | 2026-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001001/IF/22012035418783 — खेत तालाब मेवाराम/जगन्नाथ कनेरा | Physically Completed | 147621.16 | 101670.9 | 2025-05-12 | 2026-04-19
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001001/IF/22012035418913 — खेत तालाब देवीदयाल/छोटेलाल कनेरा | Completed | 147621.16 | 108053.1 | 2025-05-17 | 2026-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001001/IF/22012035418997 — खेत तालाब रामस्वरूप/सुघरसिंह कनेरा | Physically Completed | 147621.16 | 98656.56 | 2025-05-12 | 2026-04-29
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001001/IF/22012035638891 — maa ke bagiya Meera bohare | Ongoing | 263511.37 | 64154.59 | 2025-11-16
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698391 — Farm Bunding- Deshraj/ Guru dayal | Completed | 29287 | 23850 | 2015-12-30 | 2016-04-15
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698393 — Farm Bunding- Shyam Kumar/ Suratram | Completed | 29600 | 20988 | 2015-12-23 | 2016-04-20
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698395 — Farm Bunding- Lakhan Kumar/ Ram Swaroop | Completed | 29600 | 20034 | 2015-12-23 | 2016-04-20
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698396 — Farm Bunding- Avadh Kumar/ Ram Swaroop | Completed | 29600 | 20988 | 2015-12-23 | 2016-04-20
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698398 — Farm Bunding- Brij Kishore/ Suratram | Completed | 29600 | 20829 | 2015-12-23 | 2016-04-20
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698400 — Farm Bunding- Kailash/ Brijkishore | Completed | 16530 | 16059 | 2015-12-30 | 2016-04-20
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702001001/IF/9993698401 — Farm Bunding- Ramhet/ Chotelal | Completed | 16530 | 15582 | 2015-12-30 | 2016-04-20
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993698402 — Cattle Shed- Ram Vikas/ Tunde | Deleted | 65000 | 0 | 2015-12-19
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993698404 — Cattle Shed- Kedar Singh/ Samokhi Singh | Completed | 90000 | 86242 | 2015-12-23 | 2017-09-01
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737651 — Cattle shed Jaynarayan | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737652 — Cattle shed Ramasare | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737653 — Cattle shed Jagdeesh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737654 — Cattle shed Ganga prashad | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737655 — Cattle shed Rampravesh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737656 — Cattle shed Guddee | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737657 — Cattle shed RAmprakash | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737658 — Cattle shed Samokhi | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737659 — Cattle shed Rakesh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737660 — Cattle shed Bedari shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737661 — Cattle shed Kalyan | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737662 — Cattle shed Bhule | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737663 — Cattle shed Banbari | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737664 — Cattle shed Badan shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737665 — Cattle shed Mohardal shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737666 — Cattle shed Laturi shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737667 — Cattle shed Mahendra shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737668 — Cattle shed Ramnivas | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737669 — Cattle shed Kedar shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737670 — Cattle shed Shital shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737671 — Cattle shed Suresh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737672 — Cattle shed Chotelal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737673 — Cattle shed Avdesh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737674 — Cattle shed Harnarayan | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737675 — Cattle shed Tunde shingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737676 — Cattle shed Brajkishor | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737677 — Cattle shed Kailash narayan | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737678 — Cattle shed Tehsil shigh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737679 — Cattle shed Guddu | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001001/IF/9993737680 — Cattle shed Hari om | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/125536 — Construction of IAY House -IAY REG. NO. MP-02-001-001-001/62 | Completed | 14310 | 10354 | 2016-08-03 | 2020-04-28
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/3715914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117891921 | Physically Completed | 18360 | 16380 | 2022-12-27 | 2024-11-21
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4520800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113998024 | Approved | 23490 | 0 | 2024-09-12
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4744554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113997772 | Ongoing | 23490 | 21924 | 2026-05-13
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4744557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113997989 | Approved | 23490 | 0 | 2024-09-30
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4744559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113998256 | Approved | 23490 | 0 | 2024-09-30
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4753372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117892156 | Approved | 23490 | 0 | 2024-10-01
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4753373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117892275 | Approved | 23490 | 0 | 2024-09-30
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4791373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142112383 | Physically Completed | 23490 | 9135 | 2025-11-09 | 2026-07-19
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4793085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142314432 | Approved | 23490 | 0 | 2024-09-30
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/4861650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113997887 | Physically Completed | 23490 | 16965 | 2025-11-09 | 2026-07-19
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001001/IF/IAY/80114 — Construction of IAY House -IAY REG. NO. MP-02-001-001-001/80 | Completed | 14310 | 10354 | 2016-08-10 | 2020-04-28
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001001/LD/127 — मेढबन्‍धान कनैरा उम्‍मेदपुरा | Completed | 0 | 22000 | 2010-07-11 | 2010-07-24
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572761 — bhumi samtalikaran and maid bandan - sadhuri ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572763 — bhumi samtalikaran and maid bandan - parsram / ajeet singh ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572764 — bhumi samtalikaran and maid bandan - shyam kumar / suratram ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572765 — bhumi samtalikaran and maid bandan - ramkaran / khyali ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572767 — bhumi samtalikaran and maid bandan - moziram / asharam ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572768 — bhumi samtalikaran and maid bandan - dhaniram / ramdeen ke khet par | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572770 — bhumi samtalikaran and maid bandan - ram vilash / devi dayal ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572771 — bhumi samtalikaran and maid bandan - badshah / bagwan singh ke khet par | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572772 — bhumi samtalikaran and maid bandan - kishan lal / prathvipal ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572774 — bhumi samtalikaran and maid bandan - munnalal / prathvipal ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572775 — bhumi samtalikaran and maid bandan - girja devi / rosanlal ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572776 — bhumi samtalikaran and maid bandan - lakhan kumar / ramswaroop ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572777 — bhumi samtalikaran and maid bandan - braj kumar / suratram ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572779 — bhumi samtalikaran and maid bandan - raj kumar / suratram ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572780 — bhumi samtalikaran and maid bandan - ajay kumar / surat ram ke keht me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572781 — bhumi samtalikaran and maid bandan - Vanshi dhar ke khet par | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572782 — bhumi samtalikaran and maid bandan - Devidayal ke khet me | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702001001/LD/22012034572784 — bhumi samtalikaran and maid bandan - Mehrwan ke khet par | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034171589 — Pahuch March Nirman Rambharose ke pura se main sadak ki taraf( Bhag-1) | Deleted | 500000 | 0 | 2013-04-14
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034171594 — Rambharose ke pura se main road (part-1) rd 0 m to 627m | Completed | 500000 | 339008.9 | 2013-06-19 | 2016-05-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034213937 — Pahuch Margh Nirman C.C.Road se mata mandir tak | Completed | 944000 | 112222 | 2014-03-12 | 2014-08-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034230084 — Pacuch marg kaloney se bag ka pura | Completed | 472000 | 115395 | 2014-09-24 | 2015-03-31
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034231056 — Panuch marg Rambharoshe ka Pura [Kapitan singh ke khet ] se main road ki or | Completed | 818000 | 352829 | 2014-10-22 | 2016-05-23
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034267245 — CC ROAD Pravat chove house to Ram barn bhaghel House | Completed | 192800 | 190808.2 | 2015-09-02 | 2015-10-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034267253 — Gravel Road Nahar Taliya ka pura to Nahar singh ka pura | Completed | 1347000 | 495603 | 2015-07-15 | 2016-07-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034284989 — C.C. Road from Dhadiram Sharma house to Avad Kumar Sharma house Taliyapura | Completed | 315000 | 394896 | 2015-09-23 | 2017-09-01
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034286914 — CC ROAD From Dadhiram sharma house to Hanuman mandir | Completed | 100200 | 98763 | 2015-10-21 | 2015-11-30
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034310032 — CC ROAD | Deleted | 0 | 0 | 2016-04-01
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034313124 — C.C.road Hari Shankar Shukla Ke Makan Se Sethiyan Ke Kunya ki or | Completed | 225000 | 224088 | 2017-10-04 | 2020-05-17
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034314409 — CC road Ram mohan house to Bhaulal house Tal ka pura | Completed | 211000 | 178844 | 2016-08-24 | 2020-04-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034325934 — C.C.Road Mangal Singh Ke Darwaje Se Dheer Singh ke Darwaje Ki Or Pachorin ka pura | Completed | 236000 | 235860 | 2017-02-08 | 2020-05-17
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034348111 — सी.सी.रोड मय नाली राममूर्ति शर्मा के दरवाजे से सुरेन्द्र के दरवाजे तक ताल का पूरा कनेरा | Completed | 88500 | 107328 | 2017-11-01 | 2020-04-28
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034365532 — C.C.Road Ram aasre ke makan se Suresh Baghel ke makaan tak, Pachoriyan ka pura , kanera | Completed | 44250 | 41760 | 2018-04-11 | 2020-04-28
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034365534 — C.C.Road Main Road Bajaraiya Se Angad Singh Ke Makan Ki Or, Bajariya Kanera | Completed | 44250 | 20640 | 2018-02-28 | 2020-04-28
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034365536 — C.C.Road Main Road Bajariya Se Hospital Tak, Kanera | Completed | 132750 | 132288 | 2018-01-31 | 2020-04-28
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034365538 — C.C.Road Shri Krishna Balmik Ke Darwaje se Kacchi Sadak Tak, Kanera | Completed | 93000 | 88740 | 2019-02-14 | 2020-01-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034365705 — C.C.Road Ramdas Sharma Ke Makan Se Guddu Sharma Ke Darwaje Tak Taal Ka Pura, Kanera | Completed | 44250 | 43848 | 2018-05-25 | 2020-04-28
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034373261 — cc road | Deleted | 0 | 0 | 2018-01-26
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034379560 — C.C.Raod Suresh Sharma Ke Darwaje Se Kamal Singh Ke Darwaje Tak, Kanera Taal | Deleted | 69750 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034381938 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034382461 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034438767 — सी सी रोड (रामलखन बघेल के गौडा से पहलवान बघेल के दरवाजे तक तलिया का पुरा ) | Completed | 93000 | 93324 | 2019-03-01 | 2020-01-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034438770 — सी सी रोड ( उदय सिंह के दरवाजे से अभिलाख सिंह के दरवाजे की ओर ) | Completed | 69750 | 69564 | 2019-03-01 | 2020-01-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034438771 — सी सी रोड ( नाथू प्रजापति के दरवाजे से राधेश्याम के दरवाजे की ओर बागका पुरा ) ) | Completed | 69750 | 70488 | 2019-02-15 | 2020-01-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034438775 — सी सी रोड ( मायाराम के दरवाजे से नेकराम के दरवाजे तक इमली का पुरा ) | Completed | 46500 | 46440 | 2019-03-01 | 2020-01-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034438782 — सी सी रोड ( मैन रोड से हरिदत्त शर्मा के दरवाजे तक | Completed | 139500 | 135576 | 2019-03-01 | 2020-01-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034442385 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034450182 — सी.सी.रोड मय नाली निर्माण पूरन सिंह के दरवाजे से दशरथ सिंह के दरवाजे तक , बाग़ का पुरा , कनेरा | Deleted | 93000 | 0 | 2019-01-26
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034450188 — सी.सी.रोड मय नाली निर्माण मेन रोड से रामजानकी मंदिर तक पोखर , कनेरा | Deleted | 69750 | 0 | 2019-01-26
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034450193 — सी.सी.रोड मय नाली निर्माण अमर सिंह गुर्जर के दरवाजे से जवर सिंह गुर्जर के दरवाजे तक , देवी सिंह का | Physically Completed | 69750 | 66528 | 2019-10-01 | 2022-01-25
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466566 — c c road ( Dasrath singh ke darwaje se pooran singh ke darwaje kee or bag ka pura ) | Completed | 93000 | 90816 | 2019-07-04 | 2020-01-25
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466567 — c c road ( chhunna balmik ke darwaje se ramnaresh bohare ke makan ke or bohare ka pura ) | Completed | 111600 | 106656 | 2019-07-17 | 2020-01-25
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466568 — c c road ( mukhya sadak se shala bhawan hote huye vishwanath ke makan ke or tal ka pura ) | Completed | 120900 | 119700 | 2020-09-29 | 2021-04-26
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466569 — c c road ( suresh ke darwaje ke lakhan kumar ke bade ke or taliya ka pura ) | Completed | 69750 | 69540 | 2020-06-05 | 2020-07-16
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466574 — c c road ( hanuman mandir se prathmik shala ke or taliya ka pura ) | Closed | 116250 | 0 | 2019-05-27
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466575 — c c road ( main road se ram janki mandir ki or pokhari ka pura ) | Completed | 69750 | 55584 | 2021-06-04 | 2021-08-09
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466576 — c c road ( bamba se rambharose ke pura ke or ) | Completed | 139500 | 139392 | 2019-08-02 | 2020-01-25
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466577 — c c road (mukhya sadak se purohit thok ki or bajariya) | Closed | 69750 | 0 | 2019-05-27
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034466579 — c c road ( balveer singh ke makan se bhuta bhohare ke makan ki or ) | Closed | 46500 | 0 | 2019-05-27
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034468174 — सी सी रोड ( जनक सिंह के दरवाजे से कुआ की ओर इमली का पुरा ) | Completed | 34875 | 32736 | 2019-09-16 | 2020-01-25
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034468176 — सी सी रोड (नरेश बौहरे के मकान से हनुमान मंदिर & घाटबाले बाबा की ओर बौहरन का पुरा ) ) | Completed | 27900 | 25344 | 2019-09-16 | 2020-01-25
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034468406 — C C Road Nirman Bhind Porsa Road se Tilak Singh ke Makan ki or Bazaria | Physically Completed | 46500 | 45408 | 2019-08-17 | 2021-11-12
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034469934 — CC Road Nirman Arjun Pura Pradhanmatri Sadak se Anand Singh ke makan ki or Devi Singh ka pura | Completed | 55800 | 52800 | 2019-09-16 | 2020-01-25
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034477847 — sudoor road - main sadak bajariya se harishankar ka pura | Deleted | 0 | 0 | 2019-08-15
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034477848 — sudoor sadak - nahar se boharan ka pura kanera | Deleted | 0 | 0 | 2019-08-15
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034506997 — sudoor road ( naveen aganwadi bhawan gram pachaurian ka pura se pradhanmantri sadak nahar kanera tak | Completed | 1244918.71 | 1232487.41 | 2020-05-22 | 2021-01-28
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034506998 — sudoor road (gram tal ka pura nahar se naveen aganwadi bhawan chatuki ka pura kanera ) | Completed | 1171509.71 | 1157512.88 | 2020-01-30 | 2020-07-16
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034514741 — cc road | Deleted | 0 | 0 | 2019-10-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034524435 — c c road (ram lakhan ke makan se pappu ke makan ke or bangla ka pura gram kanera ) | Completed | 23250 | 22800 | 2020-06-12 | 2020-07-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034524438 — c c road ( kachhpura road se rakesh ke makan ke or taliya ka pura ) | Completed | 37200 | 30780 | 2020-06-05 | 2020-07-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034524440 — c c road ( main road se daleep singh ke makan ke or nahar singh ka pura ) | Completed | 37200 | 33060 | 2020-06-12 | 2020-07-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034526561 — c c road ( ramsaran ke makan se ram janki mandir ke or taliya ka pura ) | Completed | 23250 | 21660 | 2020-06-26 | 2020-07-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034528479 — c c road ( shivnath ke goda se mukesh ke makan ke or taliya ka pura ) | Completed | 46500 | 45600 | 2020-08-01 | 2020-08-20
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034537148 — सुदूर रोड ( प्रा० स्व०केन्द्र कनेरा से प्रा० वि० बगलन का पुरा की और बाया हरिशंकर का पुरा कनेरा ) | Deleted | 0 | 0 | 2020-05-05
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034537213 — सुदूर रोड प्रा.स्वा.केन्द्र कनेरा प्रा.वि. बंगलन के पुरा की ओर बाया हरिशंकर का पुरा ग्राम कनेरा . | Deleted | 0 | 0 | 2020-04-14
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001001/RC/22012034537342 — सुदूर रोड़ प्रा॰स्वा॰केन्द्र कनेरा से प्रा॰वि॰बंगलन के पुरा की ओर वाया हरीशंकर का पुरा ग्राम कनेरा.. | Completed | 2492701.32 | 2033292.52 | 2020-09-14 | 2022-07-22
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034542773 — c c road ( main road se shashkiya midil school ke or kanera ) | Closed | 140812 | 0 | 2020-04-14
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034543346 — c c road ( main road se shashkiya midil school ke or bajariya) | Closed | 42375 | 0 | 2020-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034579572 — c c road ( jay singh thok me bag ka pura ) | Completed | 46500 | 45162 | 2021-10-26 | 2022-09-02
BHIND / ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034831051 — c c road school bale tirahe se ram shankar ke makan ke or taliya ka pura kanera | Ongoing | 52000 | 50787 | 2025-01-01
BHIND / ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/22012034831054 — c c road hanuman mandir ke samane se devendra ke goda ke or gram taliya ka pura kanera | Ongoing | 33000 | 32184.06 | 2025-01-08
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001001/RC/248 — cc road nahar se chatukipura tak | Completed | 0 | 117996 | 2012-06-16 | 2013-03-30
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001001/RS/22012034494942 — सामुदायिक शौचालय ग्राम पंचायत कनेरा | Completed | 43000 | 41040 | 2020-09-14 | 2021-02-24
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034516349 — nadev tanka - govt primary school bajariya ke pass | Completed | 12507.57 | 11265.8 | 2021-07-02 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034516350 — nadef tanka - govt midil school bajariya ke pass | Completed | 12507.57 | 11265.8 | 2021-07-02 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034516351 — nadef tanka - govt primary school taliya ke pura ke pass | Completed | 12507.57 | 11265.8 | 2021-06-25 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034516352 — nadef tanka - aganwadi bhawan chatuki ke pura ke pass | Completed | 12507.57 | 11265.8 | 2021-08-06 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034516353 — nadef tanka - govt primary school kanera nahar ke pass | Completed | 12507.57 | 11265.8 | 2021-07-02 | 2021-08-28
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034527700 — segregation sad - kanera | Completed | 45000 | 44004 | 2021-06-22 | 2021-10-26
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034538908 — nadep tanka nirman anjani mata mandir ke pass | Closed | 12630.91 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034538909 — nadep tanka nirman nandu s/o jagdeesh prasad | Closed | 12630.91 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001001/RS/22012034543995 — Nadev Taka Nirman Super School ke pass Bajariya | Completed | 12630.91 | 11265.8 | 2021-09-11 | 2022-09-02
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001001/RS/22012034701355 — सामुदायिक स्वच्छता परिसर कनेरा | Completed | 43000 | 29835 | 2023-09-14 | 2024-06-19
BHIND / ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001001/WC/22012034297432 — Talab nirman Chhatu ki pura | Completed | 325000 | 250633.4 | 2016-07-06 | 2020-04-28
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WC/22012034326758 — Talab Nirman- Taal Ke Pura Ke Peeche, Kanera | Completed | 482919 | 337104 | 2017-05-24 | 2020-04-28
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034438843 — parkolation tank ( munni ke kua ke paas ) | Completed | 292000 | 191940 | 2019-02-14 | 2020-04-28
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034438845 — talab nirman (pachoriyan ka pura ) | Completed | 392000 | 110744 | 2019-03-01 | 2020-08-20
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034438847 — parkolation tank ( kali mata mandir ke paas ) | Completed | 567000 | 484932 | 2019-02-15 | 2020-04-28
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034559150 — parkulation tank ( taliya ka pura ke pass kanera ) | Completed | 743832.28 | 721620 | 2020-06-12 | 2020-08-20
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001001/WC/22012034559440 — Perculation Tank -Taliya Ke Pura ke Pass | Deleted | 0 | 0 | 2020-04-14
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034574458 — Percolation Tank Bouhran ke pura ke pass | Completed | 682095.22 | 351120 | 2020-08-22 | 2021-02-24
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034608570 — Earth Bund- Bouharan ka pura kanera | Completed | 233739.56 | 201780 | 2021-01-14 | 2021-04-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001001/WC/22012034610415 — Earth bund naitor ke pass gram kanera | Completed | 230468.56 | 198360 | 2021-01-28 | 2021-04-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001001/WC/22012034610416 — Earth bund khabda gram kanera | Deleted | 0 | 0 | 2020-11-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034611941 — Earth Bund Khobda Gram Kanera | Completed | 340167.58 | 298434 | 2021-02-11 | 2021-07-02
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034622610 — Earth Bund Kheraki ke Pass Gram Kanera | Completed | 299296.08 | 256770 | 2021-03-18 | 2021-04-30
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034622612 — Perculation Tank Nirman Bangalan ka pura | Completed | 1495244.91 | 506164 | 2021-03-26 | 2021-08-09
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034622613 — Talab Nirman Bangalan ka Pura | Deleted | 0 | 0 | 2021-01-21
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034672595 — Shokpit Nirman Lateeram kushwah thok | Completed | 14467.3 | 13196 | 2021-09-29 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034672623 — Shokpit Nirman Ramdhun Singh Thok Bajariya | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677081 — Shokpit Nirman Jaypraksh Shrivas Thok Bajariya | Completed | 14467.3 | 13196 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677105 — Shokpit Nirman Anjani Mata Mandir ke Pass | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677116 — Shokpit Nirman Nekram Kushwah Thok Emlee Ka pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677136 — Shokpit Nirman Mayaram Kushwah Thok Emlee Ka Pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677163 — Shokpit Nirman Norang Singh Bhadauriya Thok Bagh ka Pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677176 — Shokpit Nirman Haridatt Purohit thok Bagh ka pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677202 — Shokpit Nirman Prajapati Thok Chhatu ki Pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677219 — Shokpit Nirman Ramsharan Thok Taliya ka pura | Completed | 14467.3 | 14354 | 2021-07-17 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677241 — Shokpit Nirman Pramod Chaudhari Thok Taliya ka Pura | Completed | 14467.3 | 14354 | 2021-07-17 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677264 — Shokpit Nirman Premnarayan Baghel Thok Taliya ka Pura | Completed | 14467.3 | 14354 | 2021-07-17 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677280 — Shokpit Nirman Harnarayan Baghel Thok Taliya ka Pura | Completed | 14467.3 | 14354 | 2021-07-17 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677297 — Shokpit Nirman Kaliyan Singh Gurjar Thok Pokhar ka pura | Completed | 14467.3 | 13196 | 2021-09-29 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677316 — Shokpit Nirman Lakhan Kumar Sharma Thok Taliya ka pura | Completed | 14467.3 | 14354 | 2021-07-02 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677332 — Shokpit Nirman Mangal Singh Baghel Thok Pachorin ka Pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677354 — Shokpit Nirman Raju Bohre Thok Bajariya | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677374 — Shokpit Nirman Ramaresh Bohre Thok Bohran ka pura | Completed | 14467.3 | 14354 | 2021-04-29 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034677388 — Shokpit Nirman Bahadur Singh Gaud Thok Bohren ka Pura | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001001/WC/22012034678509 — sok pit - shri krishna sharma thok | Completed | 14467.3 | 14354 | 2021-07-17 | 2021-08-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001001/WC/22012034678511 — sok pit - bahadur singh thok boharan ka pura | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034769914 — Perculation Tank Nirman Shatimata Mandir ke Pass Gram Kanera | Physically Completed | 1383242.99 | 1368622 | 2021-06-29 | 2026-04-17
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034769921 — Earth Bund Nirman Kheraki ke Peeche ki Taraf Gram Kanera | Completed | 537417.94 | 538784.5 | 2021-06-25 | 2021-08-29
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702001001/WC/22012034769927 — Roof Water Harvesting School Evam Aganwadi Bhawan Taliya Ka pura | Completed | 49666.6 | 47085.31 | 2021-06-25 | 2021-08-29
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1702001001/WC/22012034769951 — Sok Pit Nirman Bahadur singh God thok Boharan ka Pura | Completed | 14467.3 | 14354 | 2021-07-17 | 2021-08-29
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1702001001/WC/22012034769952 — Sok Pit Nirman Bahadur singh God thok Boharan ka Pura | Deleted | 0 | 0 | 2021-05-22
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001001/WC/22012034791915 — Sok pit - uttam singh / kedar singh | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001001/WC/22012034791931 — Sok pit - veerbal singh | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001001/WC/22012034796499 — sok pit nirman jagdeesh purohit thok gram kanera | Closed | 14467.3 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034798455 — parkolation tank - bag ka pura gram kanera | Deleted | 0 | 0 | 2021-05-22
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805437 — Sok Pit Nirman Gabbar Singh Bajariya | Completed | 14467.3 | 14354 | 2021-09-11 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805444 — Sok Pit Nirman - Sunder singh Thok Taliya Ka Pura | Completed | 14467.3 | 14354 | 2021-09-11 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805446 — Sok Pit Nirman - Dilliram Thok Taliya ka pura | Completed | 14467.3 | 14354 | 2021-09-11 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805447 — Sok Pit Nirman - Dilliram Thok Taliya ka pura | Closed | 14467.3 | 0 | 2021-07-21
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805449 — Sok Pit Nirman - Ompraksh Thok Bajariya | Closed | 14467.3 | 0 | 2021-07-21
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805450 — Sok Pit Nirman - Arvindra Bohre Thok Bajariya | Completed | 14467.3 | 14354 | 2021-09-11 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805457 — Sok Pit Nirman - Super School ke pass Bajariya | Completed | 14467.3 | 14354 | 2021-09-11 | 2022-07-26
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805461 — Sok Pit Nirman - Ramdas Thok Bajariya | Completed | 14467.3 | 14354 | 2021-09-11 | 2021-11-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012034805464 — Sok Pit Nirman - Hariom Pachori Thok Ummed Pura | Completed | 14467.3 | 14354 | 2021-09-11 | 2022-07-26
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012034946307 — percolation tank nirman bade bharik mata ke khar ke paas kanera | Deleted | 0 | 0 | 2022-04-11
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034947884 — Talab Nirman Badebharik Mata ke Khar ke pass Mauja Kanera | Physically Completed | 1478347.04 | 1404753.52 | 2022-08-16 | 2026-04-17
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012034970850 — अम्रत सरोवर तालाब निर्माण - बड़े भरीक माता के खार के पास | Completed | 1197000 | 1195680 | 2022-05-15 | 2023-04-29
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001001/WC/22012034981563 — Earth check dam - gahrikola ke pass | Deleted | 0 | 0 | 2022-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001001/WC/22012034981566 — Earth check dam - kayitwari ke pass | Deleted | 0 | 0 | 2022-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001001/WC/22012034981569 — Earth check dam - pandyajori ke pass | Deleted | 0 | 0 | 2022-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012035001217 — talab nirman - gehra kola ke pass moja kanera | Physically Completed | 1420824.52 | 1325339.86 | 2022-10-04 | 2026-04-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012035008308 — Talab Nirman Nai ki Tor ke Pass Gram Kanera | Closed | 0 | 0 | 2022-10-02
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012035008309 — Talab Nirman Nai ki Tor ke Pass Gram Kanera | Physically Completed | 1467756.71 | 1348334.99 | 2022-11-08 | 2026-04-17
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001001/WC/22012035008310 — Talab Nirman Baghelan ke ke Bandha ke Neeche Ke pass Gram Kanera | Physically Completed | 1481039.86 | 1343891.87 | 2022-11-15 | 2026-04-17
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012035035038 — Talab nirman karya saajan bari thari ke pass gram kanera | Physically Completed | 976370.49 | 852397 | 2023-04-17 | 2026-04-17
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001001/WC/22012035035040 — Talab nirman karya patiyan bala khar ke pass gram kanera | Completed | 956428.46 | 792642 | 2023-04-02 | 2024-06-19
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001001/WC/22012035073524 — band nirman - joshi ke nariya ke pass kanera | Completed | 995626.05 | 961129 | 2023-06-05 | 2024-06-19
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001001/WC/22012035073527 — band nirman - ram shankar ke tor ke pass kanera | Completed | 1004723.29 | 829192 | 2023-06-05 | 2024-06-19
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001001/WC/22012035073528 — band nirman - dhaniram ke tor ke pass kanera | Completed | 998701.38 | 778141 | 2023-08-10 | 2025-05-08
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001001/WC/22012035093607 — band nirman - Konta ke pass gram kanera | Completed | 967485.17 | 826540 | 2023-10-06 | 2025-05-08
BHIND / ATER | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001001/WC/22012035140329 — Bund nirman badi nariya ke pass gram kanera | Completed | 992634.47 | 782469 | 2024-04-06 | 2024-06-19
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001001/WC/22012035140333 — bund nirman karil bali nariya ke pass gram kanera | Physically Completed | 969178.88 | 770686 | 2024-03-26 | 2026-04-17
BHIND / ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001001/WC/22012035140336 — bund nirman gauchar ke pass gram kanera | Physically Completed | 960709.86 | 743845.08 | 2025-04-19 | 2026-04-17
BHIND / ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012035301761 — Dug well recharge pit bhurimathi koop par kanera | Physically Completed | 25899.46 | 23388.79 | 2025-05-14 | 2026-04-14
BHIND / ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012035301815 — Dug well recharj pit konta ke tirahe bale koop par kanera | Physically Completed | 25899.46 | 20658.4 | 2025-05-12 | 2026-04-14
BHIND / ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012035301824 — Dug well richarj pit kali mata koop par kanera | Approved | 0 | 0 | 2025-04-16
BHIND / ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012035301830 — Dug well richarj pit Sidhhbaba koop par kanera | Approved | 0 | 0 | 2025-04-16
BHIND / ATER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702001001/WC/22012035301838 — Dug well richarj pit nadebalekoop par kanera | Approved | 0 | 0 | 2025-04-16
BHIND / ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001001/WC/6 — तालाब निर्माण | Deleted | 500000 | 0 | 2009-01-22
BHIND / ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001001/WH/19955473 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001001/WH/19956810 — Talab Gahrikaran- School Ke Pass | Completed | 100000 | 63794 | 2016-05-25 | 2016-07-30
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034450212 — Perculation Tank Nirman Nai Ke khar ke pass a | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034450213 — Perculation Tank Nirman Middle School Ke pass Bajariya | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034450237 — Renovation Karya Talab Govt.Middle School ke pass Bajariya | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034450238 — Renovation Karya Talab Bagh ka pura | Physically Completed | 975563.19 | 546576 | 2021-12-01 | 2026-04-17
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034450239 — Renovation Karya Nai ke khar ke Pass | Physically Completed | 965595.72 | 970847.4 | 2021-12-01 | 2026-04-17
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457099 — Renovation work - earthbond kheraki ke pass | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457100 — Renovation work - Earthbond khewada | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457101 — Renovation work - Earthbond new thor ke pass | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457102 — Renovation work - Earthbond boharan ka pura | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457103 — Renovation work - parkolation tank boharan ka pura | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457104 — Renovation work - parkolation tank kali mata mandir ke pass | Deleted | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001001/WH/22012034457105 — Renovation work - taliya ke pura ke pass | Deleted | 0 | 0 | 2021-10-02