## Work List
Exported on: 2026-09-09 14:16:36
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: NAKHLAULI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001016/AV/22012034614737 — khel maidan - mata mandir ke pass madiya | Ongoing | 744199.92 | 208902 | 2022-03-24
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001016/AV/22012034628040 — shanti dham - nakhloli | Closed | 442264.98 | 0 | 2022-10-02
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001016/AV/22012034628041 — khel maidan - gram panchyat nakhloli | Closed | 840101.27 | 0 | 2022-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001016/DP/22012034548156 — maa ke bagiya - shashkiya madhyamik vidhyalaya | Completed | 9283 | 8436 | 2022-02-25 | 2022-10-07
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702001016/DP/22012034573439 — braksha ropan karya - gher ke pass nakhloli | Closed | 0 | 0 | 2022-10-02
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001016/DP/22012034578526 — ब्रक्षारोपण कार्य - ग्राम नखलोली | Closed | 429720.58 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001016/DP/22012034597932 — Amrit Vatika Nirman - Purane gram Nakhloli me Gram Panchayat Nakhloli | Closed | 55847.4 | 0 | 2023-04-14
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001016/FP/22012034631565 — kachcha nala nriman - barua pura se jatav thok ke or | Closed | 0 | 0 | 2022-10-02
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299083 — Cattle shed TotaRam | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299085 — Cattle shed Chadraban | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299086 — Cattle sheds DalChandra | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299087 — Cattle shed Mahesh | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299088 — Cattle shed Ram siya | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299171 — Cattle shed Surendra | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299172 — Cattle shed Rajendra | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299173 — cattle shed Ram vilash | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299174 — Cattle shed Ravi kumar | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299175 — cattle shed Guru narayan | Closed | 90000 | 0 | 2016-08-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299503 — Cattle shed Shteesh | Closed | 90000 | 0 | 2016-09-18
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299505 — Cattle shed Ram kumar | Closed | 90000 | 0 | 2016-09-18
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299506 — Cattle shed Ram kumar/Shri ram | Closed | 90000 | 0 | 2016-09-18
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034299769 — Cattle shed Guru narayan | Deleted | 90000 | 0 | 2016-09-18
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001016/IF/22012034299973 — Const of nadep composting Santos | Deleted | 12000 | 0 | 2016-08-15
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001016/IF/22012034299974 — Const.ofnadep Composting Kanheya lal | Deleted | 0 | 0 | 2016-08-15
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001016/IF/22012034300046 — Const.ofnadep Composting Rajendra | Deleted | 12000 | 0 | 2016-08-15
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001016/IF/22012034300047 — Const.ofnadep Composting Ram ntvas | Deleted | 0 | 0 | 2016-08-05
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001016/IF/22012034300143 — Const.ofnadep Composting Ram nivas | Deleted | 12000 | 0 | 2016-09-21
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001016/IF/22012034352459 — Vriksharopan Sadak Ke Kinare | Completed | 335000 | 22256 | 2017-06-18 | 2020-05-09
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001016/IF/22012034354457 — PLANTATION WORK at mandir , school & talab gram surajpura | Closed | 335000 | 0 | 2017-06-22
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001016/IF/22012034371292 — PLANTATION WORK AT SAMUDAYIK PLACE IN NAKHLOLI | Closed | 335000 | 0 | 2017-04-20
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001016/IF/22012034371293 — PLANTATION WORK AT SURAJPURA | Closed | 335000 | 0 | 2017-04-20
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034677600 — pashu shed - ramsakhi / ganga vishun | Closed | 102033.26 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034677602 — pashu shed - maya devi / anand kumar | Closed | 102033.26 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034677605 — pashu shed - ramkishun / phool sahaya | Closed | 102033.26 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034677609 — pashu shed - radheshyam / mulu | Closed | 102033.26 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034677611 — pashu shed - surendra / Aachhelal | Closed | 102033.26 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/22012034677616 — pashu shed - ashok kumar / nabab prasad | Closed | 102033.26 | 0 | 2021-01-21
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758317 — maid bandan - ramsakhi / ganga vishnu | Completed | 12488.56 | 11001 | 2021-06-20 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758322 — maid bandan - maya devi / anand kumar | Closed | 16832.41 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758327 — maid bandan -kailash narayan / ramswaroop | Completed | 17592.59 | 15440 | 2021-06-11 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758335 — maid bandan -Radheshyam / mulu | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758345 — maid bandan -kaushal kishor / krishna bihari | Completed | 10859.62 | 8106 | 2021-06-11 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758352 — maid bandan -shivam kumar/ ganga vishnu | Completed | 10859.62 | 9264 | 2021-06-11 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758361 — maid bandan -soneram / umashanakar | Completed | 10859.62 | 9264 | 2021-06-11 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758373 — maid bandan -subhalal / bhudu | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758384 — maid bandan -suresh / satyanarayan | Completed | 10859.62 | 9264 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758389 — maid bandan - saroj / ramswaroop | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758395 — maid bandan -dharm singh / bihari lal | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758413 — maid bandan -rambhajan /nathuram | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758426 — maid bandan -dhoop shri / munnalal | Completed | 10859.62 | 9264 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758436 — maid bandan -tilak singh /Achhelal | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034758441 — maid bandan -kaliyan / shayam lal | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764547 — maid bandan -Rakesh / kaliyan | Completed | 19004.33 | 16212 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764553 — maid bandan - rameshwar / ramcharan | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764554 — maid bandan -ramsanehi / bedari | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764558 — maid bandan - machal singh / bedari | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764561 — maid bandan -gutte singh / ram singh | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764565 — maid bandan -dayaram /patiram | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764567 — maid bandan -braj kishor / mulu | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764570 — maid bandan - santoshi / murari lal | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764571 — maid bandan - chandra bhan / nathuram | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034764574 — maid bandan - ashok / nabab prasad | Completed | 18461.36 | 16212 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781746 — maid bandan -sarnam singh / savdhan | Completed | 17918.38 | 15633 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781748 — maid bandan -kaushal kishor / subalal | Completed | 17375.4 | 15054 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781750 — maid bandan -vineet / ganga vishnu | Completed | 16289.43 | 13896 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781752 — maid bandan - randheer / mulu | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781754 — maid bandan - Gaurav / brajesh | Completed | 11402.61 | 10036 | 2021-06-14 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781755 — maid bandan - kalyan / magal | Completed | 16289.43 | 13896 | 2021-06-21 | 2021-10-02
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781757 — maid bandan - Ramkumar / shriram | Closed | 10859.62 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781758 — maid bandan - Ramkishan / phool sahay | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001016/IF/22012034781765 — maid bandan - santosh kumar / nabab prasad | Completed | 11945.58 | 9843 | 2021-06-11 | 2021-10-02
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705788 — farmbunding Soneram | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705789 — farmbunding Sonu | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705790 — farmbunding Vinod | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705791 — farmbunding Ramsaproop | Closed | 12398 | 0 | 2016-01-17
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705792 — farmbunding Dilliram | Completed | 12398 | 11022 | 2016-08-29 | 2016-09-18
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705793 — farmbunding Santosh | Closed | 12398 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705794 — farmbunding Dhupshri | Closed | 19500 | 0 | 2016-01-17
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705795 — farmbunding Kailashnarayan | Completed | 19500 | 18036 | 2016-07-18 | 2016-08-30
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705796 — farmbunding Damodar prasad | Closed | 19500 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705797 — farmbunding Surendar singh | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705798 — farmbunding Abhilakh | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705799 — farmbunding Ramkumar | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705800 — farmbunding Kailashnarayan | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705801 — farmbunding Rajendr | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705802 — farmbunding Gangavishun | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705803 — farmbunding Kaoshalkishor | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705804 — farmbunding Ramkishun | Completed | 29300 | 28056 | 2016-07-18 | 2016-08-30
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705805 — farmbunding Rameshvar | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705806 — farmbunding Kaliyan | Completed | 29300 | 28056 | 2016-07-18 | 2016-08-22
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705807 — farmbunding Randheerprasad | Closed | 29300 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705808 — farmbunding Dayaram | Closed | 9800 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705809 — farmbunding Ramshanar | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705810 — farmbunding Surendr kumar | Completed | 24400 | 23046 | 2016-08-29 | 2016-09-18
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705811 — farmbunding Ramprakash | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705812 — farmbunding Vijaysingh | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705813 — farmbunding Mahaveer | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705814 — farmbunding Ghamndilal | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705815 — farmbunding Shrikurshan | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705816 — farmbunding Bedari prashad | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705817 — farmbunding Gurunarayan | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705818 — farmbunding Chandrsen | Completed | 24400 | 23046 | 2016-08-29 | 2016-09-30
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705819 — farmbunding Tilak singh | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001016/IF/9993705820 — farmbunding Ganedalal | Closed | 24400 | 0 | 2016-01-17
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733684 — cattle - shed dilliram / biharilal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733688 — cattle shed - kailash narayan / ochhelal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733693 — cattle shed - sunrendra kumar / ochhelal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733697 — cattle - shed kaliyan / mulu purvansi | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733825 — cattle shed - rameshwar / ramcharan | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733826 — cattle shed ramkishan / foolsahay | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733828 — cattle shed surendra / patiram | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733829 — cattle shed chandrasen / ramsingh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733830 — cattle shed tilak singh / ochhelal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733831 — cattle shed - gurunarayan / harilal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733833 — cattle shed- bedriprasad / tundelal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733834 — cattle shed- santosh / nababprasad | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733835 — cattle shed- shrikrashin / harilal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733837 — cattle shed- ghamandilal / chhotelal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733838 — cattle shed mahaveer / tikaram | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733839 — cattle shed- dayaram / patiram | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733840 — cattle shed- vijay singh / durgpal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733841 — cattle shed- ramswarup / foolsahay | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733842 — cattle shed- ramprakash / karandas | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733843 — cattle shed- gendalal / harilal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733844 — cattle shed- kailash kishor / krashin murari | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733845 — cattle shed- binay / raghuvirprasad | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733846 — cattle shed- ramshankar / ramdyal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733847 — cattle shed- rajendra / murtiram | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733848 — cattle shed- sanjeev shrivas / kailashnarayan | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733850 — cattle shed - ramkumar / shriram | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733853 — cattle shed - rajendra / vishwnath | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733854 — cattle shed - damodar / randhir prasad | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001016/IF/9993733855 — cattle shed - dhoopshri / munnalal | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001016/IF/IAY/134072 — Construction of IAY House -IAY REG. NO. MP-02-001-016-001/48 | Completed | 14310 | 15072 | 2016-11-07 | 2018-06-11
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001016/IF/IAY/199274 — Construction of IAY House -IAY REG. NO. MP-02-001-016-001/43 | Completed | 15030 | 14923.2 | 2016-10-31 | 2018-06-22
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001016/IF/IAY/3678845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107031654 | Completed | 18360 | 17442 | 2022-12-14 | 2024-03-03
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001016/IF/IAY/4326127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114968289 | Completed | 18360 | 17646 | 2023-01-02 | 2024-03-03
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001016/IF/IAY/4336239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113603961 | Completed | 18360 | 17136 | 2022-12-14 | 2024-03-03
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001016/IF/IAY/4379926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113604024 | Completed | 18360 | 18173 | 2022-12-14 | 2024-03-03
BHIND / ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/10 — मेढ बधान गुल्‍लाई/साबधान | Deleted | 9400 | 0 | 2009-01-24
BHIND / ATER | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/11 — मेढ बन्‍धान बुधू बघेल/बटुरी बघेल | Deleted | 9400 | 0 | 2009-01-25
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/12 — मेढ बन्‍धान परशुराम/महादेव | Completed | 5200 | 7500 | 2010-09-20 | 2010-09-26
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/13 — मेड बन्‍धान रामबहादुर/महीपति राठौर | Completed | 9400 | 9650 | 2010-09-20 | 2010-09-26
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/147 — मेढबन्‍धान कलियान / श्‍यामलाल | Completed | 15000 | 15000 | 2010-07-15 | 2010-07-27
BHIND / ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001016/LD/22012034308303 — Shantidham Nirman Nakhlauli | Deleted | 0 | 0 | 2017-01-30
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001016/LD/22012034315980 — Shantidham nirman nakhlauli | Completed | 245000 | 2064 | 2017-06-26 | 2020-05-09
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/275 — मेढबन्‍धान राकेश / कलियान | Completed | 0 | 11650 | 2010-10-22 | 2010-11-08
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/276 — मेढबन्‍धान कैलाशनारायण / आछेलाल | Completed | 0 | 13750 | 2010-10-22 | 2010-10-28
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/277 — मेढबन्‍धान महावीर / टीकाराम | Completed | 0 | 13950 | 2010-10-22 | 2010-10-28
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/319 — मेढबधान चन्‍द्रसेन /रामसिंह | Deleted | 0 | 0 | 2010-08-25
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/320 — मेढबधान चन्‍द्रसेन/रामसिंह | Completed | 0 | 9550 | 2010-12-01 | 2010-12-01
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/321 — मेढबधान वेदरी /डुन्‍डे लाल | Completed | 0 | 13000 | 2010-12-08 | 2010-12-08
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/322 — मेढबधान मायादेवी/आन्‍नद्र | Deleted | 0 | 0 | 2010-01-26
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/323 — मेढबधान मायादेवी / आन्‍नद्र कुमार | Completed | 0 | 0 | 2010-09-20 | 2010-09-26
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/364 — मेढबधान गुरूनारायण/ हरीलाल | Deleted | 0 | 0 | 2011-02-19
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/365 — मेढबधान श्रीकुष्‍ण / हरीलाल | Deleted | 0 | 0 | 2011-02-19
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/367 — मेढबधान पातीराम/गुन्‍दीलाल | Deleted | 0 | 0 | 2011-03-05
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/368 — Earth bunding shrichand/chabbiram | Deleted | 0 | 0 | 2011-03-05
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/369 — मेढबधान भूरेलाल/गेदा लाल | Deleted | 0 | 0 | 2011-03-05
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/372 — मेढबधान रामसिह/विन्‍द्रावन | Deleted | 0 | 0 | 2011-03-12
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/3799394879 — land develoment surendra | Completed | 18700 | 17666 | 2013-06-17 | 2013-07-16
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/3799398385 — land develoment ramkishan | Completed | 18800 | 18396 | 2013-07-02 | 2013-08-13
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/3799400410 — land develoment satish kumar | Completed | 25100 | 24090 | 2013-07-29 | 2013-12-17
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/3799415839 — Land develoment Maju baredha | Completed | 12600 | 11826 | 2013-12-23 | 2014-01-29
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/3799422844 — Land develoment Shri Ram purbanshi | Completed | 12600 | 12556 | 2014-01-27 | 2014-03-15
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/3799424676 — land develoment Deliram | Completed | 18800 | 18396 | 2014-02-03 | 2014-03-15
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/464 — land develoment Ramkumar | Completed | 0 | 11163 | 2011-07-25 | 2011-07-31
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/465 — Land develoment Suresh ojha | Completed | 0 | 13603 | 2011-08-01 | 2011-08-07
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/466 — land develoment Ramprakesh | Completed | 0 | 21899 | 2011-08-08 | 2011-08-14
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/467 — Land develoment Mahadevi | Completed | 0 | 21411 | 2011-08-08 | 2011-08-14
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/468 — Land develoment Nathuram | Completed | 0 | 21411 | 2011-08-15 | 2011-08-21
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/473 — Land develoment Nathuuram | Completed | 0 | 14396 | 2011-06-13 | 2011-07-15
BHIND / ATER | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/562 — Land develoment govind/shiv singh | Completed | 0 | 21350 | 2012-08-15 | 2012-09-15
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/580 — मेडवंधान केहरी लाल | Deleted | 0 | 0 | 2011-04-14
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/582 — मेडवंधान राकेश कुमार जाटव | Deleted | 0 | 0 | 2011-04-14
BHIND / ATER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/583 — मेडवधान नाथूराम | Deleted | 0 | 0 | 2011-04-14
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/7 — मेढ बन्‍धान | Completed | 5200 | 5200 | 2010-10-22 | 2010-10-28
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/8 — मेढ बन्‍धान | Completed | 5200 | 2184 | 2009-11-02 | 2009-01-20
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001016/LD/9 — मेढ बन्‍धान कलियान/श्‍यामलाल | Deleted | 5200 | 0 | 2010-07-21
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034195329 — cc road nathuram mataram mander to kailash purbans | Completed | 147000 | 87537 | 2014-02-17 | 2015-06-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034195331 — cc road g p s Suraj pura to hrijan basti | Completed | 147000 | 140226 | 2014-02-17 | 2015-06-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034195332 — cc road house ramlachin to house ganga visnu | Completed | 147000 | 139482 | 2014-02-10 | 2015-06-20
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034195841 — cc road lala ke remja to purbansi house | Completed | 137000 | 113068 | 2014-02-10 | 2015-08-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034231088 — Gravel road Barua ka pura to nare hanuman mandir t | Completed | 1104500 | 850480.6 | 2014-10-06 | 2016-08-30
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034231096 — gravel road Santosh ke kuan surj pura to School t | Completed | 1104500 | 891282.89 | 2014-10-06 | 2016-08-30
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034231098 — Gravel Road Barua pura kuan to Teli ka pura kalyan | Completed | 667500 | 349734.58 | 2014-10-06 | 2016-10-15
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034231099 — gravel road Nare hanuman minder to harijan basti n | Completed | 667500 | 444518.36 | 2014-10-06 | 2016-10-15
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034231822 — C.C. Road from Abhilash barua house to Govind house | Deleted | 118000 | 0 | 2014-10-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034292102 — CC Road from hanuman mandeer to mata mandeer | Completed | 172000 | 170042 | 2016-01-04 | 2016-07-25
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034293614 — Graval road from Re Nare hanuman mandir to kishupura banda | Completed | 1479000 | 668777 | 2015-12-21 | 2016-07-04
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1702001016/RC/22012034298706 — Const. Of culvert on road of Nare Hanuman mandir to Kishupura bandha ke pass | Completed | 276000 | 261969.1 | 2016-02-22 | 2016-04-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034308839 — Pahuch marg | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309870 — Pahuch marg | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309939 — nakhlauli ke mudare se loke singh ke kua tak pahuch marg | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309941 — loke singh ke kua ke samne se sooraj pura ki puliya tak pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309944 — soorj tirahe se barua ke pura ki or mey puliya ke pahuch marg | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034309946 — si si road madaiya se kehri singh ke khet tak aar si si pilar wali puliya sahit pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309948 — patiram ke khet bhagwan ki thari tak mey puliya ke pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034309949 — bhagwan ki thari se feri wale baba ki or si si pilar wali puliya sahit pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309952 — feribale baba se gulguliyayi khand ke niche tak tin puliya sahit pahuch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309953 — gulyayi khand ke niche se gendalal ke darwaje tak ek rapta tatha ek danda sahit pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309955 — ramdulari ke ghar se lala ke kua tak pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309956 — damodar ke ghar se pathwari ki or pahunch marg nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034309957 — ramkumar ke ghar se bedriprasad ke duwar tak 02 road wali puliya or anganwadi ke pichhe diwalo wale | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034311167 — C C Road ( Govt school surajpura to Umesh sharma ) | Deleted | 0 | 0 | 2015-10-03
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034311168 — C C Road ( Sukh devi house to katare House) | Deleted | 0 | 0 | 2015-10-03
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034311169 — C C Road( Rajesh sharma House to Ramshankar sharma House) | Deleted | 0 | 0 | 2015-10-02
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034314920 — Cc road Rajendra house to thakur house | Completed | 99000 | 98953 | 2016-09-26 | 2016-10-09
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034321474 — C.C.Road Govt. Primary School Surajpura to Rajkumar ke Darwaje Tak | Completed | 178000 | 172968 | 2017-01-23 | 2017-08-20
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034325055 — Sudur Samprak sadak Nirman Donga Ki Puliya Se Pachpeda ke aamo tak | Completed | 1430000 | 1214293.29 | 2017-02-08 | 2018-06-12
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034342349 — c c road kishupura puliya se nare ke hanuman mandir ki or nakhlauli | Deleted | 0 | 0 | 2016-08-15
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034342352 — c c road kishupura puliya se nare ke hanuman mandir ki or nakhlauli | Completed | 140551 | 136984 | 2017-06-28 | 2017-08-20
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034343619 — Sudoor Sampark sadak pachpeda ke aamo se surajpura ki naveen puliya tak surajpura nakhlauli | Completed | 1420000 | 1021974.07 | 2017-09-04 | 2018-06-15
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034347931 — C C Road Lamberdar ke bandha se madainya ki or nakhlauli | Completed | 8850000000 | 65016 | 2017-10-30 | 2018-04-29
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034366728 — C C Road nathuram ke makan se aganbadi bhavan ki or | Completed | 30000 | 29928 | 2017-12-09 | 2018-03-21
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034367716 — C C Road and nali puran ke makan se dilliram ke makan ki or | Completed | 63600 | 55728 | 2017-12-25 | 2018-05-28
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034373303 — cc road | Deleted | 0 | 0 | 2018-01-26
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034381951 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034382479 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034383463 — सी.स्‍ाी. रोड और नाली निर्माण सरनाम के मकान से कलियान के द्वार होते हुए राजेन्‍द्र के मकान की ओर | Completed | 85000 | 67836 | 2018-03-07 | 2018-07-09
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034389084 — सी सी रोड ( नर सिंह के घर से रामविलास के घर की ओर सूरजपुरा ) | Deleted | 0 | 0 | 2017-04-14
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034389085 — सी सी रोड ( नर सिंह के घर से रामविलास के घर की ओर सूरजपुरा ) | Completed | 46500 | 45399 | 2018-05-08 | 2020-05-09
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034442403 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034445540 — सी सी रोड ( राकेश शर्मा के द्वार से दामोदर & घमण्डी के द्वार से गुरूनरायण के द्वार की ओर ) | Completed | 42375 | 41148 | 2019-02-25 | 2020-05-09
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034449188 — सी सी रोड ( रामसेवक शर्मा के द्वार से राम सिया जाटव के घर की ओर ) | Completed | 80512 | 63648 | 2019-03-06 | 2021-03-23
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034473750 — सी सी रोड ( धीर सिंह के मकान से रामेश्वर के मकान होते हुये सरोज देवी के मकान तक ) | Completed | 76500 | 69696 | 2019-10-12 | 2020-05-10
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034514766 — cc road | Deleted | 0 | 0 | 2019-10-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001016/RC/22012034536724 — sudoor road (dayaram ke mandir se banda hote huye pipairiya par puliya sahit surajpura tirahe ke or | Completed | 2300576.93 | 2051241.24 | 2020-09-16 | 2022-10-28
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034561198 — c c road ( Ramprakash katare ke makan se kailashi devi ke makan ke or surajpura) | Deleted | 61200 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/22012034561201 — c c road ( Ramprakash katare ke makan se kailashi devi ke makan ke or surajpura) | Completed | 68850 | 63546 | 2021-03-04 | 2021-10-03
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001016/RC/313 — c.c. nirman soneram ke gate se mahaveer punbansi ke gate tak | Completed | 0 | 47995 | 2012-06-13 | 2012-07-25
BHIND / ATER | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kankar Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001016/RC/33 — पहुॅच मार्ग | Completed | 500000 | 263862 | 2010-09-07 | 2014-01-04
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001016/RS/22012034268018 — Toilet-1. Dayaram, 2. Bitti Devi, 3. Ganesh Kumar, | Completed | 54000 | 53929 | 2014-09-22 | 2014-11-30
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001016/RS/22012034268080 — Toilet- 1. Kamlesh ,2. Nathuram, 3. Gangacharan, 4 | Completed | 54000 | 53929 | 2014-09-29 | 2014-11-30
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001016/RS/22012034268082 — Toilet- 1. Rambaran, 2. Subalal, 3. Arvind Kumar, | Completed | 54000 | 53929 | 2014-09-29 | 2014-11-30
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001016/RS/22012034275843 — Toilet- 1. Damodhar, 2. Lakhpati, 3. Shri prakash, | Completed | 54000 | 53929 | 2014-10-12 | 2014-10-19
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001016/RS/22012034647459 — Nadef- ramniwas sharma / harigyan sharma thok surajpura | Closed | 2000 | 0 | 2022-03-08
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001016/RS/22012034647462 — nadef - badam / sukhdayan jatav thok surajpura | Completed | 2000 | 1836 | 2022-08-20 | 2022-10-07
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001016/RS/22012034647465 — nadef - jayveer singh / chaturi singh thok surajpura | Closed | 2000 | 0 | 2022-03-08
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001016/WC/22012034324159 — NEW TALAV NAKHALAULI | Completed | 49200000000 | 181976 | 2017-05-11 | 2017-09-03
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702001016/WC/22012034355550 — Bori bandhan bade nale par nakhloli | Deleted | 8385500000 | 0 | 2017-10-04
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001016/WC/22012034395011 — नवीन तालाब निर्माण चौवे बन्धा के पास | Completed | 1342000 | 1087664 | 2018-07-14 | 2021-05-20
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034435132 — Naveen dag pond ( joriya bala talab ) | Completed | 200000 | 188640 | 2019-02-12 | 2021-03-17
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034435138 — NAVEEN DAG POND ( SC BALA TALAB ) | Completed | 240000 | 165336 | 2019-02-11 | 2021-03-17
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001016/WC/22012034526326 — dag pond - bahatarkole ke nariya par | Closed | 0 | 0 | 2020-01-26
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001016/WC/22012034526327 — dag pond - kati kandiya ki nariya ke paas nakhloli | Closed | 0 | 0 | 2020-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034619794 — talab nirman - feri bale baba ke pass nakhloli | Completed | 1147588.41 | 981922 | 2021-03-04 | 2021-12-08
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034773624 — talab nirman - khere bali mata ke pass bala purane gao nakhloli me | Physically Completed | 1495508.36 | 1135559.22 | 2021-06-29 | 2026-04-17
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034773628 — talab nirman - madiya gram me ghar bali ke sameep bala | Completed | 1495179.63 | 1065083.72 | 2021-06-29 | 2022-07-22
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1702001016/WC/22012034897717 — 121 | Closed | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034907250 — tala bnirman - ladan bali nariya ke pass madiya | Closed | 0 | 0 | 2022-01-24
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034907256 — tala bnirman - kole ke nariya | Closed | 0 | 0 | 2022-01-24
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034908714 — talab nirman - mahete ka tal ke pass nakhloli | Physically Completed | 1464578.02 | 605508 | 2022-02-25 | 2026-06-10
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034908715 — talab nirman - purane garam surajpura | Ongoing | 1465568.87 | 3672 | 2022-04-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034916593 — Talab nirman - Lotan ke tor ke pass nakhloli | Ongoing | 1349775.27 | 199320 | 2022-03-15
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923425 — sok pit -rameshwar jatav / bhure lal jatav ke thok ke handpamp par | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923426 — sok pit -vishvnath sharma / vidhyaram sharma thok me | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923429 — sok pit -kamlesh / deenanath sharma ke dwar wale handpamp par | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923430 — sok pit -sunita rajendra prasad sharma dwar bale handpamp par | Completed | 4600 | 4488 | 2022-05-09 | 2022-07-22
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923431 — sok pit -ramsiya jatav / chaviram jatav ke thok ke handpamp par | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923432 — sok pit -shri chand / chaviram jatav ke handpamp ke sameep | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923433 — sok pit -Mahesh jatav / bhure lal jatav thok me | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923438 — sok pit -manju baretha / putai baretha thok ke handpamp par | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923439 — sok pit -mukesh sharma / nar singh ke thok me handpamp par | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001016/WC/22012034923834 — Sok pit - govt prathmik vidhalaya surajpura | Closed | 4600 | 0 | 2022-01-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034928482 — talab nirman - Basori bali nariya ke pass | Closed | 0 | 0 | 2022-01-24
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001016/WC/22012034945559 — naveen talab nirman bansori wali nariya ke paas nakhloli | Ongoing | 1405280.95 | 296208 | 2022-04-17
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001016/WC/22012035039638 — Sei ki Nariya Wala Talab Nirman karya Gram Nakhloli | Closed | 0 | 0 | 2022-10-02
BHIND / ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001016/WH/19955525 — Desilting of talab | Deleted | 99000 | 0 | 2016-01-26
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001016/WH/19963982 — Talaw Renovation harjin basti vala nakhlauli | Deleted | 9700000000 | 0 | 2017-05-17
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001016/WH/22012034456589 — talab jiroddar - purana talab narewala | Completed | 31882.73 | 25476 | 2022-03-04 | 2022-07-22
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001016/WH/22012034456590 — talab jiroddar -patwari bale purane talab | Closed | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001016/WH/22012034456591 — talab jiroddar - pokhar wale purane talab | Completed | 37765.13 | 30108 | 2022-02-25 | 2022-07-22
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001016/WH/22012034456683 — Talab jeeroddar - surajpura gram me purane talab | Completed | 24858.6 | 20844 | 2022-02-10 | 2022-07-22