## Work List
Exported on: 2026-10-13 13:01:27
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PAWAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001023/AV/22012034632996 — Shantidham nirman Damaru Bale baba Ke Mandir Ke Pass, Pawai | Ongoing | 488000.18 | 0 | 2023-06-10
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001023/AV/22012034632997 — Shantidham Nirman Mevati Baba Ke Pass, Pawai | Ongoing | 479015.25 | 0 | 2023-06-10
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001023/AV/22012034632998 — Shantidham Nirman Dekhtan Ka Pura, Pawai | Ongoing | 473025.3 | 0 | 2023-06-10
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702001023/FP/22012034369787 — Nala Nirman Nekram Kuswah Ke Makan Se Pawan jain Ke Makan Ki Or, Pawai | Ongoing | 127000 | 0 | 2022-08-26
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035535792 — Khet Talab Nirman Radheshyam/Mahendra Pawai | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035535805 — Khet talab Nirman Ramvaran Singh/Sarnaam Pawai | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035535857 — Khet Talab Nirman Ramjeet/ Sarnaam Pawai | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035535867 — Khet Talab Nirman Mukesh Singh/Mahendra Singh pawai | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035552248 — Khet Talab Nirman Gajraj Singh/Jal Singh Ke Par Pawai | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035650943 — Khet Talab Nirman Purusottam/Harivilas Pawai | Ongoing | 147620.89 | 0 | 2026-05-07
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035650945 — Khet Talab Nirman Ramvaran/Sarnam Pawai | Approved | 0 | 0 | 2025-11-15
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035650952 — Khet Talab Nirman Dhaniram/Gullu Pawai | Ongoing | 147620.89 | 0 | 2026-05-07
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035660874 — Khet Talab Nirman Ramveer/Kriparam Ke Khet Par Pawai | Ongoing | 147620.89 | 0 | 2026-04-30
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035660876 — Khet Talab Nirman Ganga Singh/Kashiram Ke Khet Par Pawai | Approved | 0 | 0 | 2025-10-02
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702001023/IF/22012035660877 — Khet Talab Nirman Surajmukhi/Nathu Singh Ke Khet Par Pawai | Ongoing | 147620.89 | 0 | 2026-04-30
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4518729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106713260 | Ongoing | 27000 | 0 | 2025-04-23
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4521169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115682859 | Ongoing | 27000 | 0 | 2025-04-16
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4521170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115683416 | Ongoing | 27000 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4744160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106486476 | Physically Completed | 23490 | 0 | 2025-06-25 | 2026-08-02
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4754510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118013118 | Physically Completed | 27000 | 0 | 2025-04-16 | 2026-10-04
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4773838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115682525 | Physically Completed | 23490 | 0 | 2025-04-16 | 2026-08-02
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/4773854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115686625 | Physically Completed | 27000 | 0 | 2025-04-15 | 2026-10-04
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/5558183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141458648 | Approved | 27000 | 0 | 2025-04-03
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115685656 | Physically Completed | 27000 | 0 | 2026-06-12 | 2026-09-13
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116056215 | Approved | 27000 | 0 | 2024-09-15
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117653700 | Physically Completed | 27000 | 0 | 2026-06-12 | 2026-10-04
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118302463 | Ongoing | 27000 | 0 | 2026-06-19
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106713010 | Physically Completed | 23490 | 0 | 2026-06-10 | 2026-08-02
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115682980 | Physically Completed | 27000 | 0 | 2026-06-12 | 2026-09-06
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115686143 | Ongoing | 27000 | 0 | 2026-06-12
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115686297 | Physically Completed | 23490 | 0 | 2026-06-19 | 2026-08-02
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115686172 | Approved | 27000 | 0 | 2025-03-05
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113965867 | Ongoing | 27000 | 0 | 2026-06-12
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117656561 | Physically Completed | 27000 | 0 | 2026-06-12 | 2026-10-04
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141458762 | Physically Completed | 23490 | 0 | 2026-06-12 | 2026-08-02
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121351455 | Physically Completed | 23490 | 0 | 2026-06-10 | 2026-08-02
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001023/IF/IAY/6219802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115686195 | Physically Completed | 23490 | 0 | 2026-06-12 | 2026-08-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001023/RC/22012034434879 — C.C.Raod Mai Nali rambaran Gurjar Ke Makan Se Bhagwan Singh Ke Makan Ki Or, Pawai | Ongoing | 116250 | 0 | 2020-09-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001023/RC/22012034434880 — C.C.Road Mai Nali Virendra Gurjar Ke Makan Se Sonveer Yadav Ke Makan Ki Or, Pawai | Ongoing | 139500 | 0 | 2020-09-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001023/RC/22012034434882 — C.C.Road Mai Nali Main Road Se Siddh Baba Ke Mandir Ki Or, Pawai | Ongoing | 139500 | 0 | 2020-09-16
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001023/RC/22012034477656 — सी.सी.रोड निर्माण मेन रोड से आगनवाडी भवन की ओर पावई | Ongoing | 53550 | 0 | 2019-11-25
BHIND / ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001023/RC/22012034833319 — C C Road Nirman Primary School se Mata mandir Ki or Gram Deekhatan ka Pura Pawai | Approved | 61350 | 0 | 2024-10-02
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plug for Community | Boulder Check/Gully Plug | 1702001023/WC/22012035180303 — Earthan Gully Plug Santosh Ke Khet Ke Pass, Pawai | Ongoing | 1492837.05 | 0 | 2024-03-15