## Work List
Exported on: 2026-10-11 10:50:28
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: MUDIYAKHERA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001043/AV/22012034506904 — Gau shala Mudiyakheda | Closed | 0 | 0 | 2019-12-30
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001043/AV/22012034535860 — Samudayak Swacchata Parishar- Mudiyakhera | Completed | 43000 | 42180 | 2020-10-08 | 2020-12-27
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1702001043/DP/22012034594913 — अम्रत बाटिका उचित मूल्य की दुकान के पास एवं शांति धाम मुडियाखेडा | Closed | 55847.4 | 0 | 2023-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001043/FP/22012034625587 — RCC Nala Nirman Ambedkar Nagar Main Road Se Aage Balveer Singh Narvariya Ke Makan Tak, Mudiyakheda | Closed | 217000 | 0 | 2021-06-04
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001043/FP/22012034627337 — RCC Nala Nirman Jardan Singh Narvariya Ke Makan Se Aage Talab Ki or, Baksipura, Mudiyakheda | Completed | 43000 | 41688 | 2021-11-12 | 2023-05-30
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001043/FP/22012034628207 — RCC Nala Nirman Roop Singh Narvariya Ke Makan Se Aage Dheer Singh Ke Makan Ki Or, Mudiyakhera | Completed | 36000 | 35088 | 2022-04-30 | 2023-05-30
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001043/FP/22012034629278 — RCC Nala Nirman Gopal Ke Makan Se Aage Radhe Shyam Ke Makan Ki or, Mudiyakhera | Ongoing | 127950 | 127296 | 2022-08-04
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702001043/FP/22012034631479 — kachha nala nirman - shyam singh ke makan se chote singh ke makan ke or mudiyakheda | Ongoing | 134460 | 106777 | 2023-02-15
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001043/FP/22012034637279 — RCC Nala nirman - mishran ka pura ke hari babu ke handpamp se ange mian road ke or | Ongoing | 230000 | 80886 | 2024-01-14
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water Drain for Community | Works for Flood Control and Protection | 1702001043/FP/22012034638612 — Kaccha Nala Nirman Chote Singh Ke Makan Se Aage Main Road Ki Or, Mudiyakheda | Ongoing | 428450.32 | 13167 | 2024-03-14
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034299957 — Const.ofnadep Composting Bhupsingh | Completed | 12000 | 11072 | 2016-09-24 | 2017-05-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034300030 — Cons Of Compost Pit- Chabiram/ Harvilas | Completed | 12000 | 10404 | 2016-09-24 | 2017-05-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034300031 — Cons. Of Compost Pit- Bhoop Singh/ Ramsahay | Deleted | 12000 | 0 | 2016-09-19
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034300032 — Cons Of Compost Pit- Suresh/ Raghuveer | Completed | 12000 | 11072 | 2016-09-24 | 2017-05-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034300033 — Cons Of Compost Pit- Madho singh/ Lalaram | Completed | 12000 | 11072 | 2016-09-24 | 2017-05-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034305487 — Cons. OF Compost Pit- Bharat Singh/ Vishun Khan | Completed | 12000 | 2672 | 2016-12-03 | 2019-08-18
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001043/IF/22012034352300 — Vriksharopan gram bakshipura avam mudiyakhera pahuch margh par | Completed | 335000 | 9192 | 2017-07-04 | 2020-10-20
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001043/IF/22012034354419 — PLANTATION WORK at ram janki mandir ke paas & govt schoo & swaraj bhawan mudiyakheda | Completed | 335000 | 6192 | 2017-07-04 | 2020-10-20
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001043/IF/22012034354420 — PLANTATION WORK at pahuch marg in baksipura | Closed | 335000 | 0 | 2017-06-20
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771265 — nadef tanka - radheshyam / dhan singh | Completed | 12507.57 | 2316 | 2021-07-01 | 2023-04-18
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771268 — nadef tanka - parmal singh / lalram | Completed | 12507.57 | 1544 | 2021-07-08 | 2023-04-18
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771270 — nadef tanka - Narayan singh / Tikaram | Completed | 12507.57 | 1544 | 2021-07-08 | 2023-04-18
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771274 — nadef tanka - prem singh / bharat singh | Completed | 12507.57 | 1544 | 2021-07-08 | 2023-04-18
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771278 — nadef tanka - pratap singh / ganga singh | Closed | 12507.57 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771284 — nadef tanka - nawal singh / bhoop singh | Closed | 12507.57 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771288 — nadef tanka - surendra singh / kalicharan | Closed | 12507.57 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771294 — nadef tanka - mahesh singh / pooran singh | Closed | 12507.57 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001043/IF/22012034771298 — nadef tanka - lakhan singh / ram hansh | Closed | 12507.57 | 0 | 2021-04-14
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001043/IF/22012035222721 — Khet Talan Nirman- Asharam/ Ramsahay, Mudiyakheda | Closed | 0 | 0 | 2024-01-24
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001043/IF/22012035222724 — Khet Talab Nirman- Hari Babu /Ajan singh, Mudiyakheda | Closed | 0 | 0 | 2024-01-24
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001043/IF/22012035222728 — Khet Talab Nirman- Beti Bai/ Gambheer Singh, Mudiyakheda | Closed | 0 | 0 | 2024-01-24
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001043/IF/22012035638923 — maa ke bagiya maya devi | Ongoing | 257341.57 | 1566 | 2026-01-03
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001043/IF/22012035638926 — maa ke bagiya Babli devi | Ongoing | 257341.57 | 0 | 2026-01-03
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720893 — Cattle Shed Fundilal/Nathuram | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720898 — Cattle Shed Rajendra | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720905 — Cattle Shed Shri krishn | Deleted | 44200 | 0 | 2014-01-26
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720906 — Cattle shed mansingh | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720907 — Cattle shed Bidhaya Ram | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720909 — Cattle Shed Kali charn | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720910 — Cattle Shed Subalal | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720912 — Cattle Shed Janbed | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720914 — Cattle Shed BhanuPratap | Completed | 44200 | 41900 | 2014-02-28 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720917 — Cattle Shed Pramsingh | Completed | 44200 | 41900 | 2014-03-03 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720919 — Cattle Shed Ramshevak | Completed | 44200 | 41900 | 2014-03-03 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720922 — Cattle Shed Suresh | Completed | 44200 | 41900 | 2014-03-03 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720923 — Cattle Shed Gambheer | Completed | 44200 | 41900 | 2014-03-03 | 2014-05-30
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720924 — Cattle Shed Gomta | Completed | 44200 | 39545 | 2014-08-31 | 2014-12-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720925 — Cattle Shed Ramthirth | Completed | 44200 | 41900 | 2014-03-03 | 2014-10-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720926 — Cattle shed Raisingh | Completed | 44200 | 41900 | 2014-03-03 | 2014-05-30
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9926720927 — Cattle Shed Bindraban | Completed | 44200 | 41900 | 2014-03-03 | 2014-05-30
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993656916 — Farm Bunding Ramkishan/Tulsiram | Completed | 22800 | 22608 | 2014-10-04 | 2014-11-25
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993701758 — Farm Bunding- Jitendra Singh/ Mehtab Singh | Deleted | 32000 | 0 | 2016-01-02
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702204 — Farm Bunding- Bharat Singh/ Gyashiram | Deleted | 21300 | 0 | 2016-01-02
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702206 — Farm Bunding- Narayan Singh/ Gyashiram | Deleted | 32000 | 0 | 2015-10-30
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702759 — Farm Bunding- Prem Singh/ Tikaram | Deleted | 37300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702760 — Farm Bunding- Fundilal/ Nathuram | Deleted | 21300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702761 — Farm Bunding- Bharat Singh/ Kishunlal | Deleted | 37300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702762 — Farm Bunding- Suresh/ Raghuveer | Deleted | 37300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702763 — Farm Bunding- Pratap Singh/ Gangaram | Deleted | 37300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702764 — Farm Bunding- Rajendra Singh/ Bhambar Singh | Deleted | 21300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702765 — Farm Bunding- Bhanu Pratap/ Bhagirath | Deleted | 21300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702766 — Farm Bunding-Mahendra Singh/ Maharaj Singh | Deleted | 21300 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702767 — Farm Bunding- Shantilal/ Panna Lal | Deleted | 21300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702768 — Farm Bunding- Mohar Singh/ Babu Singh | Deleted | 37300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702769 — Cattle Shed- Ram Kishan/ Tulashiram | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702770 — Cattle Shed- Shri Gyan Singh/ Jaswant Singh | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702771 — Cattle Shed- Balveer Singh/ Poojaram | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702772 — Cattle Shed- Abhilakh / Chabiram | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702773 — Cattle Shed-Shyam Singh/ Babu Singh | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702774 — Cattle Shed-Pratap Singh/ Ganga Ram | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702775 — Cattle Shed-Madho Singh/ Lalaram | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702817 — Farm Bunding- Parimal / Lalaram | Deleted | 21300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001043/IF/9993702818 — Cattle Shed- Bhoopal Singh/ Ram Sahay | Deleted | 65000 | 0 | 2015-10-29
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993702819 — Farm Bunding- Bhoop Singh/ Ram Sahay | Deleted | 37300 | 0 | 2016-01-06
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993703520 — Farm Funding- Mahendra Singh/ Maharaj Singh | Deleted | 21300 | 0 | 2016-01-08
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001043/IF/9993734777 — Farm bunding kamal keshor | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001043/IF/IAY/134094 — Construction of IAY House -IAY REG. NO. MP-02-001-043-001/18 | Completed | 14310 | 14268 | 2016-08-06 | 2020-12-27
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/3933767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106647430 | Ongoing | 27000 | 17136 | 2022-09-06
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/4924424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106276035 | Approved | 27000 | 0 | 2025-02-18
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/4924445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106644950 | Ongoing | 27000 | 0 | 2025-05-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/4924446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106649598 | Ongoing | 27000 | 0 | 2025-09-25
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/4924455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115214408 | Ongoing | 27000 | 6264 | 2025-05-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/5553292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115215436 | Ongoing | 27000 | 0 | 2025-09-25
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/5553293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115220206 | Ongoing | 27000 | 0 | 2025-09-25
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001043/IF/IAY/5562314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106660606 | Physically Completed | 23490 | 0 | 2025-06-06 | 2026-01-10
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/5765199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106651272 | Ongoing | 27000 | 0 | 2025-09-25
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001043/IF/IAY/6399155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106653090 | Approved | 27000 | 0 | 2024-09-13
BHIND / ATER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001043/LD/140 — मेढबन्‍धान | Completed | 14000 | 4100 | 2010-06-09 | 2010-06-09
BHIND / ATER | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001043/LD/9926713911 — Shanti Dham MudiaKheda | Completed | 340000 | 37680 | 2014-08-16 | 2014-12-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Kitchen shed for NP-MDMS / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1702001043/OP/9425888985 — Boundary ball nirman- Primary School | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034169574 — c.c.road ramshine ke makan se main road takavm sha | Completed | 176000 | 169064.4 | 2013-06-08 | 2014-10-20
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034176394 — C.C. Road Punchayat Bhavan se sunil ke darbaje ki | Completed | 92000 | 90156 | 2013-07-27 | 2013-11-23
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034195116 — C.C.Road Gopal Ke Makan Se Jardan ke makan tak | Completed | 91200 | 90712 | 2013-12-21 | 2014-03-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034201976 — C.C.Road Pashu Hospital se Radha krishna mandir ki | Completed | 172000 | 172008 | 2014-02-01 | 2014-03-31
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034212438 — C.C.Road Sunil Jatav Ke Darwaje se Laxman Jatav Ke | Completed | 68000 | 67456 | 2014-03-08 | 2014-12-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034225297 — Earth work in Internal road | Completed | 60000 | 59895 | 2014-07-19 | 2014-11-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034227225 — CC Road Rambharoshe house to Bikrm master house A | Completed | 91200 | 91050 | 2014-08-16 | 2014-11-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034231115 — cc road Dhirsingh hous to Gh | Completed | 114000 | 113982 | 2014-10-04 | 2014-11-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034231657 — Earthen road from Main road to Jagdesh singh hous etc. | Completed | 129000 | 114896 | 2014-10-18 | 2014-12-22
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034266892 — C.C.Road Kailash narayan jatav ke Makan se manphokhe jatav ke makan ki or | Completed | 218000 | 217698 | 2015-07-04 | 2015-12-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034290319 — C.C.road Prahlad Narwariya Ke Makan Se Amratlal Narwariya Ke Makan Tak | Completed | 167000 | 165970 | 2015-11-28 | 2016-01-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034290325 — C.C.Road Prem Singh Narwariya Ke Makan Se Gram Swaraj Bhawan Ki Or | Completed | 118700 | 117916 | 2016-01-02 | 2016-04-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034297926 — Pahuch Margh Nirman Main Road Se Swaroop Vidhya Niketan School Ke Bagal Se Malkhan Narwariya Ke Maka | Completed | 791000 | 703593.6 | 2016-02-06 | 2017-12-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299815 — Pahuch Margh Nirman Mudiyakhera ki Primary School Se Shrivastava ke khet ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299816 — Pahuch Margh Nirman Mudiyakhera Harijan Chauk se aage mayaram ojha ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299818 — Pahuch Margh Nirman Mudiyakhera pashu hospiyal se aage naveen railway Station ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299819 — Pahuch Margh Nirman Mudiyakhera Jandel singh ke kunya se aage ater road ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299820 — Pahuch Margh Nirman Bakshipura ki primary school se aage main road ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299822 — Pahuch Margh Nirman Bakshipura ke rajaram kotbar ke makan se ramdutt narwariya ke makan tak | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299823 — Pahuch Margh Nirman Main Road Nawal Singh Ke Makan se aage shiv singh narwariya ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299824 — Pahuch Margh Nirman Main Road Balveer ke makan se rajkumar ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299825 — Pahuch Margh Nirman Subhash Jatav Ke Makan Se Mata Charan ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034299826 — Pahuch margh Nirmam Kalyan ke makan se Taar Bind ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299828 — C.C.Road Ramdutt Mastar Ke Makan Se Kashiram ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299829 — C.C.Road Main Road se Madhoram jatav ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299830 — C.C.Road Kadam Singh Ke Makan Se Shri charan Balmik ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299831 — C.C.Raod Ram prakash Fauji ke makan se kamata prasad ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299832 — C.C.Road Amar Singh Ke Makan Se Main Dumbar Raod ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299833 — C.C.Road Prem Singh narwariya ke makan se gram swaraj bhawan ki or avam malkhan narwariya ke makan k | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299834 — C.C.Road Main Raod se Harnarayan narwariya ke makan avam gulab singh ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299835 — C.C.Raod Pahlad Narwariya ke makan se Sikandar narwariya ke makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034299836 — C.C.Road Mahaveer Narwariya ke makan se man singh Patel ke makan makan ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034314588 — Nali Nirman- Haribabu jatav ke makan se main road ki or mishran ka pura | Completed | 155000 | 146970 | 2016-09-03 | 2019-08-18
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034325047 — C.C.Road Main Road Se Aage Gulab Ke Makan Ki Or | Completed | 70000 | 69812 | 2017-03-25 | 2019-08-18
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034325058 — C.C.Raod Shivdayal Jatav Ke Makan Se Rajendra Jatav Ke Makan Ki Or | Completed | 110000 | 99986 | 2017-02-04 | 2019-08-18
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001043/RC/22012034341781 — Sudur Samprak Sadak Vidhyaram Jatav Ke Makan Se Majra Panchseel Nagar Ki Or | Physically Completed | 1100000 | 632621.7 | 2017-06-17 | 2022-01-25
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034348055 — सी.सी.रोड मय नाली मेन रोड से आगे मेवाराम जाटव के माकन की ओर | Completed | 136500 | 126936 | 2017-08-19 | 2019-08-18
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034348056 — सी.सी.रोड श्रीचरण बाल्मिक के माकन से आगे रामकुमार के मकान की ओर | Closed | 104250 | 0 | 2017-07-15
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034348057 — सी.सी.रोड मय नाली कोक सिंह जाटव के मकान से हरी बाबु के मकान से आगे की ओर | Closed | 102375 | 0 | 2017-07-15
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034348058 — सी.सी.रोड मय नाली मेन रोड से आगे माता के मंदिर की ओर | Completed | 136500 | 133128 | 2017-08-26 | 2019-08-18
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034348060 — सी.सी.रोड मय नाली रामस्वरूप मिध्रा के मकान से आगे राम्दुत्त के मकान की ओर | Completed | 84375 | 95976 | 2018-01-20 | 2019-08-18
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034351356 — सी.सी.रोड मय नाली विश्वनाथ पटवारी के मकान से आगे नरेन्द्र कुमार जाटव के मकान की ओर मुडियाखेडा | Closed | 102375 | 0 | 2017-05-03
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034373299 — cc road | Deleted | 0 | 0 | 2018-01-26
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034377310 — C.C.Raod Main Road Se Rambaran Mastar Ke Makan Ke Aage Se Ramdas Jatav Ke Makan Ki or , Mudiyakhera | Completed | 144000 | 142244 | 2017-12-30 | 2019-08-18
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034377312 — C.C.Road Shri Charan Balmik Ke Makan Se Aage Ram kumar Ke Makan Ki Or Mudiyakhera | Completed | 139500 | 141468 | 2018-03-05 | 2019-08-18
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034377313 — C.C.Raod mai naili Kok Singh Ke Makan Se Hari Babu Ke makan Se Aage Komal singh ke makan tak | Completed | 177750 | 194532 | 2018-05-11 | 2019-08-18
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034381953 — cc road | Closed | 0 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034382477 — cc road | Closed | 0 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034384691 — C.C.Road Mai Nali Roop Singh narvariya Ke Makan Ke Aage Dheer Singh Ke Makan Ki Or, Mudiyakhera | Completed | 69750 | 69324 | 2018-03-05 | 2019-08-18
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034394775 — C.C.Road Main Road Se Aage Shiv Singh Master Ke Makan Ki Or, Mudiyakhera | Completed | 54000 | 51156 | 2018-11-01 | 2019-12-16
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034394776 — C.C.Road Karan Singh Jatav Ke Makan Se Aage Rajendra Jatav Me Makan Ki Or, Mudiyakhera | Completed | 59325 | 58812 | 2018-10-03 | 2019-12-16
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034397180 — C.C.Road Mai Nali Nawal Singh Ke Makan Se Aage Hakim Ke Makan Se Aage Radheshyam Ke Makan tak | Completed | 153450 | 137808 | 2019-01-05 | 2019-12-16
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034442401 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034444228 — सी.सी.रोड मय नाली कोमल जाटव के मकान से आगे भान सिंह के मकान की ओर , मुडियाखेडा | Completed | 93600 | 83880 | 2019-03-02 | 2019-12-16
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034444232 — सी.सी.रोड मय नाली मेन रोड बच्चू सिंह के मकान से आगे हीरा सिंह के मकान की ओर , मुडियाखेरा | Completed | 93600 | 69528 | 2019-03-02 | 2019-12-16
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034469344 — सी.सी.रोड निर्माण वासुदेव के मकान से आगे पहलाद के मकान की ओर मुडियाखेरा | Completed | 108600 | 105952 | 2019-11-02 | 2020-06-02
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034469347 — सी.सी.रोड मय नाली मेन रोड से आगे मुन्नालाल फौजी के मकान तक , कबीर कॉलोनी मुडियाखेरा | Completed | 105090 | 104544 | 2019-08-10 | 2019-12-16
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034514764 — cc road | Closed | 0 | 0 | 2019-10-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034527046 — C.C. Road Mai Nali Nirman Main Road Se Swaroop Vidhya Nikedan School Se Aage Bare Khan Ke Makan Ki | Completed | 135600 | 135660 | 2020-07-23 | 2020-11-03
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034539423 — C.C.Road Nirman Mai Nali Raghuveer Mastar Ke Makan Se Aage Kok Singh Ke Makan Ki Or, | Completed | 103455 | 105640 | 2020-10-01 | 2020-12-27
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034539427 — C.C.Raod Nirman Rajkumar Ke Makan Se Aage Lallesh Ke Makan Ki Or, Mudiyakhera | Completed | 89100 | 87210 | 2020-12-17 | 2023-04-29
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034585542 — सी.सी. रोड अंबेडकर नगर के हरप्रसाद जाटव के मकान से आगे शंकर जाटव के मकान की ओर, मुड़ियाखेड़ा | Completed | 64800 | 64269 | 2021-11-12 | 2023-04-29
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034591255 — C.C.Road Nirman Mewaram Jatav Ke Makan Se Aage Shivcharan Ke Makan Ki Or, Mishranpura, Mudiyakheda | Deleted | 0 | 0 | 2021-08-15
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/22012034591256 — C.C.Road Nirman Mewaram Jatav Ke Makan Se Aage Shivcharan Ke Makan Ki Or, Mishranpura, Mudiyakheda | Closed | 105938 | 0 | 2021-08-15
BHIND / ATER | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001043/RC/245 — antric rural conctivity men road se gulab singh ke makan tak | Completed | 0 | 104056 | 2011-08-10 | 2011-12-30
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/285 — c.c. road arjun singh ke makan se mohar singh ke makan tak | Completed | 0 | 188016 | 2012-05-01 | 2012-10-30
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001043/RC/413 — सी0 सी0 रोड मेघ सिह के मकान तक वेजना के मकान से स | Completed | 133000 | 126185 | 2012-12-29 | 2013-11-23
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001043/RC/414 — सी सी रोड रामोतार के मकान से मान सिह के दरवाजे तक | Completed | 0 | 66912 | 2012-11-02 | 2012-12-30
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702001043/RS/22012034528288 — Segrigation Shed Nirman (SLWM)-Mudiyakheda | Ongoing | 45200 | 47202 | 2021-06-24
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702001043/WC/22012034609228 — Talab Saundrikaran Gram Baksipura, Mudiyakhera | Completed | 1153163.43 | 1047275 | 2021-01-28 | 2021-11-15
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749657 — sok pit -bagwan das ke ghar ke pass misharan ka pura | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749668 — sok pit -raghuveer jatav ke ghar ke pass mishran ka pura | Completed | 4600 | 4439 | 2021-08-23 | 2021-08-30
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749678 — sok pit -Ramgopal jatav ke ghar ke pass | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749687 — sok pit -hari babu ke hand pamp ke pass | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749705 — sok pit -ramdhun narwariya ke ghar se samane mudiyakheda | Completed | 4600 | 4439 | 2021-07-08 | 2021-07-20
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749728 — sok pit - pratap singh ke ghar ke pass mudiyakheda | Completed | 4600 | 4439 | 2021-07-08 | 2021-07-20
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749752 — sok pit -jandel singh narwariya ke ghar ke pass | Completed | 4600 | 4439 | 2021-08-23 | 2021-08-30
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034749772 — sok pit -kishori lal ke ghar ke samane | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788898 — sok pit -ramveer narwariya ke ghar ke samane handopamp par | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788921 — sok pit -ramesh bansal ke ghar ke samane | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788927 — sok pit -mahendra singh ke ghar ke samane | Completed | 4600 | 4439 | 2021-07-22 | 2021-08-12
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788934 — sok pit -shukla wear house ke samane bali gali ke samane | Completed | 4600 | 4439 | 2021-08-30 | 2021-10-10
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788937 — sok pit -hanuman ji mandir ke pass handpamp par | Completed | 4600 | 4439 | 2021-07-22 | 2021-08-12
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788945 — sok pit - kok singh narwraiya bali gali me | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788948 — sok pit - padam singh ke ghar wali gali me | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788954 — sok pit -pashu hospital ke pass | Completed | 4600 | 4439 | 2021-07-22 | 2021-08-12
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788962 — sok pit -shrivas ke thok me handpamp par | Completed | 4600 | 4439 | 2021-07-15 | 2021-07-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788979 — sok pit -harijan thok ke handpamp ke pass | Completed | 4600 | 4439 | 2021-07-15 | 2022-11-02
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034788989 — sok pit -kok singh ke ghar ke samane | Completed | 4600 | 4439 | 2021-08-30 | 2021-10-10
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001043/WC/22012034816026 — sok pit - rajendra jatav ke handpamp par mudiyakheda | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003675 — Sok pit -vimla ke makan se samane mudiyakheda | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003677 — Sok pit -maniram ke makan ke samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003681 — Sok pit -ramveer ke makan se samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003684 — Sok pit -main road ke pass mudiyakheda | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003685 — Sok pit -naarayan ke makan ke samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003687 — Sok pit -rajendra ke makan ke samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003688 — Sok pit -pooran wali gali me mudiyakheda | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003689 — Sok pit -anil ke makan se samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003690 — Sok pit -gyadeen ke makan ke samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001043/WC/22012035003691 — Sok pit -ramsiya ke makan ke samane | Closed | 4600 | 0 | 2022-08-16
BHIND / ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001043/WH/19955518 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001043/WH/19956348 — Talab Gaharikaran- Mata Mandir Ke Paas Bakshipura | Deleted | 60000 | 0 | 2016-05-19
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001043/WH/22012034445822 — Rinovation OF Talab Bakshipura, Mudiyakhera | Closed | 0 | 0 | 2020-08-18