## Work List
Exported on: 2026-10-23 07:17:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: TARSOKHAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926711445 — Farmbunding Khunne | Deleted | 23500 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926711454 — Farm bunding Dhnesh kumar | Deleted | 28200 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926711469 — Farmbunding Verendr kumar | Deleted | 21100 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926711532 — Farm bunding Neeraj kumar | Deleted | 18800 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926711539 — Farm bundingTanay Kuamr | Deleted | 23500 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926711549 — Farm bunding Sanjay Kumar | Deleted | 28200 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001005/IF/9926723475 — Farm bunding Bacchu lal | Deleted | 32800 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001015/IF/9926709723 — Farm bunding Jagat singh | Deleted | 16900 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001015/IF/9926709731 — Farm bunding Ajant singh | Deleted | 21100 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001015/IF/9926710637 — Farm bunding Nathu singh | Deleted | 32800 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1702001015/IF/9926710641 — Cattle shed Naresh singh | Deleted | 62000 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001015/IF/9926710645 — Cattle shed Shiv singh | Deleted | 62000 | 0 | 2014-11-22
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001015/IF/9926710648 — Cattle shed Ramveer sigh | Deleted | 62000 | 0 | 2014-11-22
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001046/AV/22012034391781 — Punchayat Bhawan Nirman- Tarsokhar | Completed | 579200 | 578650 | 2019-02-17 | 2020-06-10
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/AV/22012034505154 — शान्तिधाम कार्य- ग्राम नावालिहार | Deleted | 0 | 0 | 2019-10-02
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/AV/22012034505155 — शान्तिधाम कार्य- ग्राम तरसोखर | Deleted | 0 | 0 | 2019-10-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/AV/22012034511482 — Shantidham Work- Tarsokhar | Physically Completed | 283566.25 | 279549.88 | 2020-07-09 | 2026-05-27
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001046/AV/22012034534762 — Samudayak Swacchata Parishar- Tarsokhar | Completed | 43000 | 42940 | 2020-09-14 | 2020-10-15
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/AV/22012034538413 — Shantidham Work-Nawalihar | Ongoing | 285409.48 | 22800 | 2021-01-11
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/AV/22012034538414 — Shantidham Work- Katelan Ka Pura, Tarshokhar | Deleted | 0 | 0 | 2020-08-15
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702001046/AV/22012034551168 — Chabutara Nirman - Tarsokhar | Completed | 802553.42 | 801461 | 2021-02-27 | 2022-04-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001046/AV/22012034562463 — Boundary Ball Nirman Punchayat Bhawan Nirman-Tarsokhar | Completed | 97379 | 97090 | 2021-03-10 | 2021-06-29
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001046/AV/22012034614926 — Maa Ki Bagiya Nirman Karya Govt. Middle School, Tarsokhar | Closed | 7694 | 0 | 2021-11-14
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001046/AV/22012034656422 — Samudayik Bhawan Niraman Karya - Baghelon Ka Pura Me Lok Mata Devi Ahilabai Holkar | Closed | 329000 | 0 | 2023-08-15
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001046/AV/4045 — Anganwadi/Other Rural Infrastructure,ATER | Completed | 330000 | 329607 | 2015-12-12 | 2020-01-16
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001046/AV/5389 — Aaganbadi Bhavan Bajrang gad Tarsokhar | Completed | 330000 | 329976 | 2016-06-18 | 2020-01-16
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1702001046/DP/22012034594385 — Vraksharopan Karya amrit vatika punchayat bhawan ke pass, Tarsokhar | Closed | 55847.4 | 0 | 2023-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001046/FP/22012034625652 — Kaccha Nala Nirman Gram Nawalihar Se Gram Tarsokhar Tak, | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001046/FP/22012034626423 — Kaccha Nala Nirman School Se Baag Bale Hanuman mandir Tak, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001046/FP/22012034626424 — Kaccha Nala Nirman Nawalihar Aganwadi Se Bajranggarh Ki Or, | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001046/FP/22012034626594 — Nali Nirman Karya Hariom Yadav Ke Ghar Se Shivkumar Yadav Ke Ghar Tak, Nawalihar | Completed | 21212 | 18528 | 2021-10-02 | 2021-10-20
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001046/FP/22012034627128 — Nala Nirman Karya Kushwah Mohalla Se Dhanesh Chaturvedi ke Ghar Tak, Tarsokhar | Completed | 46200 | 42846 | 2021-11-11 | 2023-04-29
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001046/FP/22012034633885 — Kaccha Nala Nirman Govt. Primary School Se Khareed Kendra Ki Or, Tarsokhar | Deleted | 51623.81 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001046/FP/22012034633886 — Kaccha Nala Nirman Govt. Primary School Se Khareed Khendra Ke Or, Tarsokhar | Deleted | 0 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001046/FP/22012034635393 — Kaccha Nala Nirman Govt. Primary School Se Kharid Kendra Ki Or, Tarsokhar | Closed | 0 | 0 | 2023-06-08
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702001046/FP/22012034638179 — Kaccha Nala Nirman Govt. Primary School Se Kharid Kendra Ki Or, Tarsokhar | Closed | 0 | 0 | 2024-01-26
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001046/IF/22012034352535 — वृक्षारोपण भिंड पोरसा मेन रोड के किनारे तरसोखर | Completed | 335000 | 5064 | 2017-06-17 | 2020-10-15
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001046/IF/22012034353872 — वृक्षारोपण शंकर जी मंदिर पर नाबालीहार | Completed | 335000 | 14400 | 2017-07-15 | 2020-10-15
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001046/IF/22012034353876 — वृक्षारोपण शरकारी प्राइमरी स्कूल तरसोखर | Completed | 335000 | 3000 | 2017-07-15 | 2020-10-15
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702001046/IF/22012034469044 — khet talab ( bachhu lal / jiwaram ) | Completed | 288000 | 234060 | 2019-03-05 | 2019-09-05
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702001046/IF/22012034469053 — khet talab ( kamlesh / sudama ) | Completed | 288000 | 281732 | 2019-03-05 | 2020-01-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572747 — Med Bandhan Karya- Ramnarayan/ Balwant | Completed | 12687.48 | 10830 | 2020-08-31 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572748 — Med Bandhan Karya- Kunji lal/ Bilandi | Completed | 12342.24 | 10260 | 2020-08-31 | 2020-10-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572749 — Med Bandhan karya- Bacchu lal/ Jiwaram | Completed | 23459.4 | 22800 | 2020-07-20 | 2020-10-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572750 — Med Bandhan Karya- Kamlesh/ Sudama | Completed | 12061.74 | 11400 | 2020-08-31 | 2020-10-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572751 — Med Bandhan Karya- Rambuddh/ Hakim | Completed | 9062.49 | 6840 | 2020-09-14 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572752 — Med Bandhan Karya- Rambharose/ Durjan | Completed | 13444.96 | 11400 | 2020-08-31 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572753 — Med Bandhan Karya-Virendra/ Vishambardayal | Completed | 7249.99 | 5700 | 2020-09-14 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572754 — Med Bandhan karya-Neeraj/ Padam Chand | Completed | 17479.55 | 18240 | 2020-07-23 | 2020-10-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034572755 — Med Bandhan Karya-Sanjay/ Tej Singh | Completed | 17939.54 | 18240 | 2020-07-23 | 2020-08-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012034587582 — Khet Talab Nirman-Rambharose/Durjan Lal, Tarsokhar | Deleted | 0 | 0 | 2020-04-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034603497 — Med Bandhan Karya-Gabde/Tej Singh | Deleted | 0 | 0 | 2020-04-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034603498 — Med Bandhan Karya-Tanay/Padam Chand | Completed | 15859.36 | 13680 | 2020-09-08 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034603988 — Med Bandhan Karya- Gabde/Tej Singh | Completed | 15104.15 | 12540 | 2020-09-14 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034611070 — Med Bandhan Karya- Mahipal/ bhagirath | Closed | 0 | 0 | 2020-05-22
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034611071 — Med Bandhan Karya-Vishvanath/ Maujiram | Closed | 0 | 0 | 2020-05-22
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034611072 — Med Bandhan karya-Subhash/Rajendra Prasad | Deleted | 0 | 0 | 2020-05-22
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034611073 — Med Bandhan Karya-Sughar Singh/Sarnam Singh | Deleted | 0 | 0 | 2020-05-22
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001046/IF/22012034659480 — Pashu Shed Nirman- Bachulal/jiwaram | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001046/IF/22012034659481 — Pashu Shed Nirman-Kamlesh/ Sudama | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001046/IF/22012034659482 — Pashu Shed Nirman- Baikunti/ Ramphal | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731119 — Med Bandhan karya- Danesh Kumar, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731121 — Med Bandhan Karya- Bacchulal, Tarshokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731124 — Med Bandhan Karya- Devi Singh, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731126 — Med Bandhan karya- Ramprakash, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731132 — Med Bandhan Karya- Pappu, Tarshokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731136 — Med Bandhan Karya- Racchapal, Nawalihar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731139 — Med Bandhan Karya- Umesh, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731142 — Med Bandhan Karya- Maidhan, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731147 — Med Bandhan Karya- Vishvanath, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1702001046/IF/22012034731151 — Med Bandhan Kahya- Kamlesh, Tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035017961 — Khet Talab Nirman Khunne Singh Ke Khet Par, Tarshokar | Completed | 358340.1 | 280704 | 2022-09-11 | 2025-01-11
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025336 — Nandep Nirman Karya Rambuddh/ Hakim Singh, Tarsokhar | Completed | 2040 | 1326 | 2023-09-04 | 2023-12-14
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025338 — Nandep Nirman Karya Rajaram/Barelal, Tarsokhar | Completed | 2040 | 1989 | 2023-05-29 | 2023-08-01
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025339 — Nandep Nirman Karya Ramveer/Mahendra, Tarsokhar | Closed | 2040 | 0 | 2022-08-16
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025340 — Nandep Nirman Karya Prakash/Nathuram, Tarsokhar | Completed | 2040 | 1989 | 2023-05-29 | 2023-08-01
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025341 — Nandep Nirman Karya Dharmendra/ Kamta prasad, Nawalihar | Completed | 2040 | 1989 | 2023-05-29 | 2023-08-01
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025342 — Nandep Nirman Karya Dharmendra/Ramphal, Katelan Ka Pura | Completed | 2040 | 1989 | 2023-05-29 | 2023-08-06
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025343 — Nandep Nirman Karya Mahipal/Bhagirath, Nawalihar | Completed | 2040 | 1989 | 2023-05-29 | 2023-08-06
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025347 — Nandep Nirman Karya Suresh/ Buddhe Singh, Katelan ka Pura, Tarsokhar | Completed | 2040 | 1989 | 2023-05-29 | 2023-09-17
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025350 — Nandep Nirman Karya Rambresh/Het Singh, Nawalihar | Completed | 2040 | 1989 | 2023-05-29 | 2023-09-17
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001046/IF/22012035025351 — Nandep Nirman Karya Rambaran/Sovran, Katelan ka Pura | Closed | 2040 | 0 | 2022-08-16
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035041377 — Khet Talab Nirman Rajveer Ke Tubel Ke Pass, Tarsokhar | Closed | 0 | 0 | 2022-10-02
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035086740 — khet Talab Nirman Rashmi Chaturvedi Ke Khet Mai, Tarsokhar | Closed | 0 | 0 | 2023-04-01
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035101624 — Khet Talab Nirman Rashmi Ke Khet Mai, Tarsokhar | Completed | 398061.12 | 343213 | 2023-06-26 | 2023-09-17
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001046/IF/22012035416104 — Khet Talab Nirman Sarita Devi/Surgiv Singh Ke Khet Par Nawalihar | Approved | 147621.16 | 0 | 2025-04-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001046/IF/22012035416125 — khet Talab Nirman Niraj/ Padam Chand Ke Khet Par Tarsokhar | Approved | 147621.16 | 0 | 2025-04-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001046/IF/22012035416137 — Khet talab Nirman dhanesh/Sarju prasad Ke Khet Par Tarsokhar | Approved | 147621.16 | 0 | 2025-04-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035527388 — Khet Talab Nirman Sarita Devi/Surgiv Singh Ke Khet Par Nawalihar | Completed | 147621.16 | 111434.4 | 2025-05-21 | 2026-04-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035527667 — khet Talab Nirman Niraj/ Padam Chand Ke Khet Par Tarsokhar | Completed | 147621.16 | 99406.8 | 2025-05-21 | 2026-04-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001046/IF/22012035527673 — Khet talab Nirman dhanesh/Sarju prasad Ke Khet Par Tarsokhar | Completed | 147621.16 | 110512.2 | 2025-05-21 | 2026-04-11
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001046/IF/9993711069 — Cattle shed Dharmendra/rampal | Completed | 90000 | 90000 | 2016-08-06 | 2017-09-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001046/IF/9993711070 — Cattle shed Gulab singh | Completed | 90000 | 88998 | 2016-08-06 | 2017-09-01
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001046/IF/9993711071 — Cattle shed Ramveer | Deleted | 90000 | 0 | 2015-10-02
BHIND / ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/134097 — Construction of IAY House -IAY REG. NO. MP-02-001-046-002/15 | Completed | 14310 | 14664 | 2019-01-27 | 2019-10-21
BHIND / ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/134098 — Construction of IAY House -IAY REG. NO. MP-02-001-046-002/50 | Completed | 14310 | 14664 | 2019-01-27 | 2019-10-21
BHIND / ATER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/1872964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5608233 | Completed | 15660 | 12528 | 2018-10-29 | 2019-09-05
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/3676262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106479251 | Physically Completed | 18360 | 16320 | 2022-08-16 | 2024-11-21
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/4284682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107186879 | Completed | 18360 | 18241 | 2023-01-29 | 2023-09-16
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/4519454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107044133 | Ongoing | 27000 | 21924 | 2025-04-26
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/4519480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107081930 | Ongoing | 27000 | 18792 | 2025-04-26
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/4519607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107186955 | Ongoing | 27000 | 23229 | 2025-04-18
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/4742006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107051411 | Ongoing | 27000 | 23229 | 2025-04-18
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/4742103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107186633 | Approved | 27000 | 0 | 2024-09-12
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/4742104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107186916 | Ongoing | 27000 | 21924 | 2025-04-18
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702001046/IF/IAY/6219510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120066287 | Ongoing | 27000 | 0 | 2024-09-12
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/79907 — Construction of IAY House -IAY REG. NO. MP-02-001-046-002/57 | Completed | 14310 | 15020 | 2016-07-30 | 2019-10-20
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/80150 — Construction of IAY House -IAY REG. NO. MP-02-001-046-002/20 | Completed | 14310 | 14992 | 2017-05-13 | 2019-10-20
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001046/IF/IAY/80151 — Construction of IAY House -IAY REG. NO. MP-02-001-046-002/18 | Completed | 14310 | 14360 | 2016-07-30 | 2018-09-12
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/LD/22012034316115 — शान्तिधाम कार्य नावलीहार | Deleted | 245000 | 0 | 2017-01-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/LD/22012034316116 — शान्तिधाम कार्य तरसोखर | Deleted | 245000 | 0 | 2017-01-28
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702001046/LD/22012034316117 — शान्तिधाम कार्य कठेलन का पुरा , तरसोखर | Deleted | 245000 | 0 | 2017-01-28
BHIND / ATER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001046/LD/3799394752 — land develoment ramavitar | Completed | 17576 | 16644 | 2013-06-15 | 2013-07-11
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034194835 — cc road ater-porsa road to hrijan basti Bajarang g | Completed | 157000 | 154296 | 2014-01-04 | 2016-05-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034194839 — cc road house of mohar singh towards ramprakash | Completed | 119850 | 65901 | 2014-03-22 | 2017-01-09
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001046/RC/22012034197977 — Pahuch margh nirman harijan basti bajranggarh se k | Deleted | 500000 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001046/RC/22012034197979 — Pahuch marg nirman kharika road se katelan pura ki | Completed | 500000 | 324017.3 | 2014-01-18 | 2014-11-10
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001046/RC/22012034224661 — Pahuch Margh Nirman Kharika Road Se Katelan ka Pur | Completed | 373000 | 200677.5 | 2014-07-19 | 2016-02-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034225680 — GSB Road Kharika road to Kathalen Ka Pura rd 590 to 1000m | Deleted | 0 | 0 | 2014-05-27
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034231969 — C.C. Road from DilliRam house to Ashok House | Completed | 192000 | 88966 | 2014-10-15 | 2016-07-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034282703 — CC Road Gayadeen house To Ramnarayan house | Completed | 118000 | 112586 | 2015-09-05 | 2015-11-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034292096 — CC Road from Main road to Shankarji mandeer | Completed | 136000 | 109970 | 2015-12-19 | 2017-09-01
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001046/RC/22012034292098 — Graval road from Harijan basti to Navali graval road | Completed | 516000 | 223236 | 2015-12-12 | 2017-09-01
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034295529 — cc road Bharat singh house to Ramnarayan house | Completed | 48000 | 47058 | 2016-01-16 | 2017-09-01
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034309868 — cc road main road se nathu jatav ke darwaje ki ore bajranggarh | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034309869 — cc road main road se omprakash choubey ke makan ki ore Tarsokhar | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034310067 — CC ROAD | Deleted | 0 | 0 | 2016-04-01
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034314921 — CC ROAD Kamlesh house to Surendra house Kadelan ka pura | Deleted | 124000 | 0 | 2017-10-29
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034314922 — CC ROAD Shankarji mandir to Rajaram house | Completed | 95000 | 52104 | 2016-10-01 | 2017-09-01
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034343373 — सी.सी.रोड हरिजन मोहल्ला मेन रोड से नाथू जाटव के द्वार तक तरसोखर | Deleted | 70800 | 0 | 2017-06-22
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034353330 — c c road ( main road se nathuram ke ghar ke or bajranggarh ) | Completed | 70800 | 63832 | 2017-09-21 | 2019-09-05
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034353340 — C C ROAD ( MAIN ROAD SE OM PRKASH CHOBE KE MAKAN KE OR ) | Completed | 44250 | 39672 | 2018-10-03 | 2019-09-05
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034373347 — cc road | Deleted | 0 | 0 | 2018-01-26
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034381924 — cc road | Closed | 0 | 0 | 2017-10-02
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034382924 — cc road | Closed | 0 | 0 | 2018-04-01
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034385804 — सी सी रोड ( पंचायत भवन से रामबरन के घर की ओर तरसोखर ) | Completed | 93000 | 92916 | 2018-06-03 | 2019-09-05
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034385811 — सी सी रोड ( वीरेन्द्र के मकान से नीरज के मकान तक तरसोखर ) | Completed | 79050 | 82116 | 2018-03-11 | 2019-09-05
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034386998 — सी सी रोड ( कमल सिंह के घर से राजवीर के घर की ओर कठेलन का पुरा ) | Completed | 89000 | 88332 | 2018-08-18 | 2019-09-05
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034391564 — c c road ( kamlesh ke makan se surendra ke makan ke or gram kathelan ka pura ) | Completed | 124000 | 122580 | 2018-10-03 | 2019-02-02
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034391565 — सी सी रोड ( राजाराम के घर से गनेश के घर की ओर तरसोखर ) | Completed | 65100 | 64728 | 2018-08-03 | 2019-05-15
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034397300 — C.C.Road Devi Singh Ke Makan Se Mahaveer Ke Ghar Ki Or, Tarsokhar | Completed | 69750 | 66816 | 2019-01-08 | 2019-09-05
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034397461 — C.C.Road Mai Nali Ram Sanehi Ke Ghar Se Fojdar Ke Ghar Tak, Tarsokhar | Completed | 23250 | 21924 | 2019-01-27 | 2019-09-05
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034439850 — सी सी रोड ( नाथू जाटव के मकान से पूरन बघेल के घर की ओर ) | Completed | 76500 | 74208 | 2019-02-24 | 2020-01-02
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034442425 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034442426 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034474894 — सी.सी रोड मुन्ना सिंह के घर से पूरन बघेल के घर की ओर , तरसोखर | Completed | 60000 | 60192 | 2019-09-21 | 2020-01-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034524725 — C.C.Raod Damar Road Se Ramsanehi Ke Ghar Ki Or, Tarsokhar | Completed | 57375 | 57000 | 2020-07-17 | 2020-08-12
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034524726 — C.C.Road Fojdar Ke Ghar Se Baghelan pura Road Tak, Tarsokhar | Completed | 21037 | 20520 | 2020-07-16 | 2020-08-12
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001046/RC/22012034540682 — Sudur Samprak Sadak Nawalihar Aaganwadi Se Tarshokhar Tak, Tarshokhar | Closed | 0 | 0 | 2020-08-15
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034540685 — C.C.Raod Nirman Radheshyam Ke Ghar Se NH-552 ki Or, Nawalihar | Completed | 46500 | 46360 | 2020-09-25 | 2021-07-20
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034540688 — C.C.Road Indrajeet Ke Ghar Se Nawalihar School Ki Or, Nawalihar | Completed | 27900 | 28500 | 2020-09-25 | 2020-12-10
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034583254 — C.C.Road Avam Nali Nirman Driver Ke Makan Se Umesh Singh Ke Makan Ki or, Nawalihar | Completed | 51150 | 50952 | 2021-10-02 | 2021-10-20
BHIND / ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034825962 — C C Road Nirman Naveen Panchayat Bhawan Se Rajaram Baghel Ke Ghar Ki or Tarsokhar | Ongoing | 101000 | 100601.34 | 2024-12-30
BHIND / ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702001046/RC/22012034840143 — c c road main road se munna lal baghel ke makan ke or bajranggarh | Approved | 79000 | 0 | 2025-01-24
BHIND / ATER | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001046/RC/23 — पहुॅच मार्ग | Completed | 500000 | 253225 | 2009-03-01 | 2011-11-01
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/359 — 1702001046/RC/359 | Completed | 122006 | 122006 | 2012-06-05 | 2012-08-21
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001046/RC/432 — सीसी रोड रामप्रकाश के दरवाजे से मलथू सिंह के दरवाज | Completed | 130000 | 129959.97 | 2012-12-31 | 2013-03-21
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034668993 — Soak Pit Nirman Harivalas Ke Darwaje Ke Pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-20 | 2023-08-01
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034668995 — Soak Pit Nirman Suresh Ke Darwaje Ke Pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-27 | 2023-08-01
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034668997 — Soak Pit Nirman Banbari lal Ke Darwaje Ke Pass, Nawlihar, Tarsokhar | Completed | 4600 | 4488 | 2022-11-27 | 2023-04-29
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034668998 — Soak Pit Nirman Shankar Ji Ke Mandir par, Nawalihar, Tarsokhar | Completed | 4600 | 4488 | 2022-11-27 | 2023-04-29
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034668999 — Soak Pit Nirman Balmik Thok, Tarsokhar | Completed | 4600 | 4488 | 2022-11-20 | 2023-06-07
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034669000 — Soak Pit Nirman Ayurvedik Hospital ke Pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-20 | 2023-06-07
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034669002 — Soak Pit Nirman Devi Singh ke Darwaje Ke pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-20 | 2023-04-29
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034669003 — Soak Pit Nirman Komal Singh Ke Darwaje Ke pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-20 | 2023-04-29
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034669004 — Soak Pit Nirman Sanjay Chaube Ke Darwaje Ke Pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-27 | 2023-06-07
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034669005 — Soak Pit Nirman Bacchulal Ke Ghar Ke Pass, Tarsokhar | Completed | 4600 | 4488 | 2022-11-27 | 2023-04-29
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705743 — Soak Pit Nirman Kamlesh/ Het Singh Ke Ghar Ke Pass , Nawalihar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705745 — Soak Pit Nirman Alvar/Ganga Singh Ke Ghar ke Pass, Nawalihar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705746 — Soak Pit Nirman Rajendra/Raghunath Ke Ghar ke Pass, Nawalihar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705749 — Soak Pit Nirman Subhash/ Mahaveer Ke Ghar Ke Pass, Nawalihar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705751 — Soak Pit Nirman Sitaram/Sirnam Singh, Nawalihar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705752 — Soak Pit Nirman Sobharam/ Jalim Ke Ghar Ke Pass, Tarsokhar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705753 — Soak Pit Nirman Jagdish/Jaggannath Ke Ghar Ke Pass, Nawalihar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702001046/RS/22012034705754 — Soak Pit Nirman Rakesh Singh/Heeralal, Katelan ka Pura, Tarsokhar | Closed | 4600 | 0 | 2023-06-20
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001046/RS/22012034705755 — Samudayak Nandep Tanka Nirman Vijay Singh/ Atiraj Singh Ke Ghar Ke Pass, Nawalihar | Closed | 2040 | 0 | 2023-06-20
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034426096 — Earthan Bund- Tali Khand Ke Neeche- Tarsokhar | Completed | 143262 | 150336 | 2018-12-17 | 2019-05-29
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034426475 — Earthan Bund- gata Ka siroth, Tarsokhar | Completed | 159200 | 151892 | 2019-01-01 | 2020-03-02
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012034436189 — मिट्टी बन्धान ( पथवारी गता का सोत ) | Completed | 160000 | 155784 | 2019-02-10 | 2019-09-05
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012034443616 — arthan dam ( hardol ke samane ) | Deleted | 195000 | 0 | 2018-12-30
BHIND / ATER | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001046/WC/22012034443624 — parkolation tank ( khand ke niche tarsokhar ) | Deleted | 279000 | 0 | 2018-12-30
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001046/WC/22012034526949 — Naveen Talab Nirman- Hardol Ke Pass, Tarsokhar | Deleted | 0 | 0 | 2020-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001046/WC/22012034543960 — Perculation Tenk Nirman Hardol Ke Pass, Tarsokhar | Completed | 1055497.03 | 579120 | 2020-05-04 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001046/WC/22012034543962 — Perculation Tenk- Punchayat Bhawan Ke Peeche, Tarsokhar | Deleted | 0 | 0 | 2020-04-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034567739 — Earthan Bund Nirman Gyadin Ke Khet Ke Neeche, Tarsokhar | Deleted | 0 | 0 | 2020-04-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034569756 — Mitti Bandh Nirman- Neeraj Ki Tor Ke Pass, Tarsokhar | Completed | 140851.92 | 124260 | 2020-08-17 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034573556 — Mitti Bandh Nirman Subhash Ki Nariya Ke Peeche, Tarsokhar | Completed | 128047.2 | 112860 | 2020-08-31 | 2020-10-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034573557 — Mitti Bandh Nirman Nai Tor Gata Ka Sirot | Deleted | 0 | 0 | 2020-04-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034585762 — Mitti Bandh Nirman Pravesh Ke Khet Ke Neeche, Tarshokhar | Deleted | 0 | 0 | 2020-08-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001046/WC/22012034585763 — Naveen Talab Nirman Shantidham Ke Peeche, Tarshokhar | Completed | 408894.3 | 357996 | 2021-01-18 | 2021-07-22
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034622966 — Naveen mitti bandh nirman khand ke neeche, tarsokhar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034622967 — Naveen mitti bandh nirman subedar ki tor ke pass, Tarsokhar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034622968 — Naveen Mitti bandh nirman nawali ki mod, nawalihar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702001046/WC/22012034622970 — Naveen talab nirman baghelan ka pura ke pass, Tarsokhar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034622971 — Naveen Mitti bandh nirman nawali ki mod, nawalihar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001046/WC/22012034635286 — Parkulation Tenk Nirman Pabuliyai Tarsokhar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702001046/WC/22012034635288 — Mitti Band Nirman Subedar Ki Tor Ke Upar, Tarsokhar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034635290 — Mitti bandh Nirman Pappu Ki Tor Ke Upar, Tarsokhar | Deleted | 0 | 0 | 2021-01-26
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702001046/WC/22012034637423 — Mitti bandh Nirman Pappu Ki Tor Ke Upar, Tarsokhar | Completed | 203315 | 194544 | 2021-06-17 | 2021-07-12
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012034637427 — Mitti Band Nirman Subedar Ki Tor Ke Upar, Tarsokhar | Completed | 218734.11 | 182964 | 2021-06-03 | 2021-07-12
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001046/WC/22012034637430 — Parkulation Tenk Nirman Pabuliyai Tarsokhar | Completed | 1004089.78 | 887028 | 2021-04-08 | 2021-06-03
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001046/WC/22012034765762 — Roof Water Harvesting Punchayat bhawan- tarsokhar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012034963341 — Naveen Mitti Bandh Nirman Fojdar Ke Khet Ke Neeche Tarsokhar | Deleted | 0 | 0 | 2022-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012034963344 — Naveen Mitti Bandh Nirman Fojdar Ke Khet Ke Neeche Tarsokhar | Completed | 205561.8 | 172975 | 2022-05-27 | 2025-01-11
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012034963346 — Naveen Mitti Bandh Nirman Baghelpura Ke Pass, Tarsokhar | Closed | 0 | 0 | 2022-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012034963347 — Naveen Mitti Bandh Nirman Nathu Ke Khet Ke Neeche, Tarsokhar | Closed | 0 | 0 | 2022-04-14
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012035021789 — Mitti Bund Nirman Karya Sudheer Ke Kua Ke Pass, Tarsokhar | Physically Completed | 444908.21 | 375445 | 2023-01-29 | 2026-04-17
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012035064137 — Bund Nirman Subhash Ke Khet Ke Pass, Tarsokhar | Deleted | 0 | 0 | 2023-04-01
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012035073159 — Bund Nirman karya Subhash Ke Khet par, Tarsokhar | Deleted | 0 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012035089405 — Bund Nirman Subhash Ke Khet Ke Pass, Tarsokhar | Deleted | 453690.43 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001046/WC/22012035115486 — Earthan Bund Nirman Subhash Chand Chaturvedi Ke Khet Ke Pass, Tarsokhar | Closed | 0 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702001046/WC/22012035166577 — Bund Nirman Subhash Ke Khet Ke Pass, Tarsokhar | Completed | 453690.43 | 307523 | 2024-03-04 | 2025-01-11
BHIND / ATER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001046/WH/19955507 — Desilting of talab | Deleted | 0 | 0 | 2016-01-26
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001046/WH/19961935 — तालाव जीर्णोध्‍दार कार्य बजरंगगढ तरसोखर | Completed | 97000 | 40936 | 2017-06-03 | 2019-09-05
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001046/WH/19961936 — तालाव जीर्णोध्‍दार कार्य धानुक के दरवाजे के पास नावलीहार | Completed | 99000 | 82560 | 2017-06-15 | 2019-09-05
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034442626 — Renovation Of Talab- Imali Ke Pass, Tarsokhar | Deleted | 0 | 0 | 2020-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034444063 — Renovation Of Pond- Kathelan Ka Pura, Nawalihar | Completed | 273167.36 | 239400 | 2020-06-04 | 2020-08-04
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034444064 — Renovation OF Pond-Bajranggarh | Deleted | 0 | 0 | 2020-04-01
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034445268 — Renovation Of Talab- Emli Ke Pass, Tarshokhar | Deleted | 0 | 0 | 2020-08-15
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034445315 — Renovation Of Talab-Aaganwadi Ke Pass, Bagranjgarh | Completed | 48295.16 | 43130 | 2020-11-19 | 2021-01-03
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034449473 — Renovation Of Pond- Nawalihar | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034450234 — Renovation Of Talab Punchayat Bhawan Ke Peeche, Tarsokhar | Completed | 729523.69 | 416880 | 2022-01-18 | 2022-03-25
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034454862 — Renovation Of Bund, Nawalihar, Tarsokhar | Completed | 500711.95 | 270298 | 2022-03-15 | 2022-04-30
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001046/WH/22012034907329 — Renovation Of Bund Bajranjgarh Tarshokhar | Closed | 0 | 0 | 2022-01-26