## Work List
Exported on: 2026-09-14 11:38:43
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SURPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001069/AV/22012034660508 — Samudayik bhawan mahatma jyotirav fule chidiyapura | Ongoing | 252000 | 0 | 2024-10-25
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001069/DP/22012034546643 — maa ki bagiya ( govt midil school surpura ) | Ongoing | 9283 | 0 | 2023-05-05
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001069/DP/22012034595865 — Basudha bandhan kary govt school surpura | Ongoing | 55847.4 | 0 | 2023-09-03
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702001069/FP/22012034635642 — कच्चा नाला निर्माण कार्य छड़िया पुरा से पचपेड़ा तक क | Ongoing | 1164958.2 | 0 | 2023-10-04
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702001069/FP/22012034635643 — कच्चा नाला निर्माण कार्य बरेठा के आम से सुखपाल के कुआ तक | Ongoing | 775093.8 | 0 | 2023-10-04
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001069/IF/22012035315338 — khet talab vijay singh / dhaniram | Approved | 0 | 0 | 2024-10-02
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001069/IF/22012035315342 — khet talab virendra / tularam | Approved | 0 | 0 | 2024-10-02
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001069/IF/22012035430010 — KHET TALAB SHIVRAM KUSHWAH / MURLI KUSHWAH CHHIDIYAPUA | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001069/IF/22012035430028 — KHET TALAB VIREENDRA SINGH / TULARAM CHHIDIYAPURA | Ongoing | 147621.16 | 0 | 2025-05-12
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001069/IF/22012035430039 — KHET TALAB SATYARAM KUSHWAH / THADHIRAM KUSHWAH CHHIDIYAPURA | Ongoing | 147621.16 | 0 | 2025-05-12
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001069/IF/22012035430048 — KHET TALAB KAMTAPRASHAD / JAGDISHNARAYAN CHHIDIYAPURA | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001069/IF/22012035603049 — EK BAGIYA MAA KE NAAM KESHKALI / RAMLAKHAN | Ongoing | 257341.57 | 0 | 2026-04-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702001069/IF/22012035603070 — EK BAGIYA MAA KE NAAM MEERA / MEGH SINGH | Approved | 0 | 0 | 2025-08-01
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001069/IF/IAY/4924468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146989831 | Ongoing | 27000 | 0 | 2025-08-02
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001069/IF/IAY/5129120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116249367 | Ongoing | 27000 | 0 | 2025-11-21
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001069/IF/IAY/5566420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146989968 | Ongoing | 27000 | 0 | 2025-11-10
BHIND / ATER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001069/IF/IAY/6219737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116275025 | Ongoing | 27000 | 0 | 2026-05-16
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001069/IF/IAY/6219765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146989683 | Approved | 27000 | 0 | 2025-02-13
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001069/WC/22012034870380 — sok pit -anil / rajbahadur | Ongoing | 4600 | 0 | 2022-04-05