## Work List
Exported on: 2026-09-11 16:49:05
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KYARIPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001070/AV/22012034373750 — SAMUDAYAK BHAVAN NIRAMAN GOVT MIDDIL SCHOOL KE PASS | Completed | 150000 | 149136 | 2018-06-23 | 2020-10-20
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001070/AV/22012034373776 — PANCHAYAT BHAVAN NIRMAN KYARIPURA | Suspended | 579200 | 0 | 2019-08-12
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001070/AV/22012034388945 — श्‍ाांंति‍ध्‍ााम माध्‍यमि‍क वि‍द्यालय केे पास कल्‍यानपुुरा | Completed | 245000 | 243991 | 2018-09-25 | 2019-12-10
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001070/AV/22012034389574 — खेल मैदान कल्याणपुरा शा0 मा0 स्कूल के पास | Completed | 187000 | 123856.24 | 2018-09-26 | 2021-03-06
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702001070/AV/22012034535900 — गोशाल निर्माण क्यारीपुरा | Closed | 0 | 0 | 2020-05-09
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702001070/AV/22012034606619 — मिनी स्टेडियम(खेल मैदान) ग्राम पंचायत क्यारीपुरा | Ongoing | 241235.65 | 3474 | 2021-11-13
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001070/AV/22012034607465 — panchayat bhawan - kyaripura | Ongoing | 1000000 | 362709 | 2021-11-13
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702001070/AV/22012034651917 — सामुदायिक भवन अधुर्जपूरा | Ongoing | 252000 | 25013 | 2024-02-22
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702001070/AV/4316 — Anganwadi bhavan Kiyaripura | Completed | 330000 | 345989.34 | 2016-01-06 | 2019-05-28
BHIND / ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702001070/DP/22012034233177 — Plantation work High school campus Kiyaripura | Completed | 236000 | 188566 | 2016-08-27 | 2021-06-13
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001070/DP/22012034548406 — maa ke bagiya - shashkiya high school kyaripura | Ongoing | 9283 | 1158 | 2022-03-14
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001070/DP/22012034594412 — बसुदा बंदन अम्रत बाटिका - प्राथमिक स्कूल , शांति धाम अर्धुजपूरा | Ongoing | 55847.4 | 12155 | 2023-08-23
BHIND / ATER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702001070/DP/22012034594414 — बसुदा बंदन अम्रत बाटिका - प्राथमिक स्कूल , शांति धाम अर्धुजपूरा | Closed | 0 | 0 | 2023-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702001070/FP/22012034624529 — kachh nala - devi mandir se surpura road ke or | Completed | 187090.8 | 92640 | 2021-05-06 | 2022-01-10
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702001070/FP/22012034635017 — कच्चा नाला राजेन्द्र के खेत से अशोक पाराशर के मकान की ओर | Ongoing | 387620.4 | 39559 | 2023-10-06
BHIND / ATER | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702001070/FP/22012034635078 — कच्चा नाला रामवरन के द्वार से भीकम के तालाब की ओर कल्याणपुरा | Ongoing | 387620.4 | 3978 | 2023-10-06
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061543 — Cattle shed Shri chand/ dilasharam | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061649 — Cattle shed Ranveer | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061651 — Cattle shed Gajendra singh | Deleted | 44200 | 0 | 2013-05-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061658 — Cattle shed Govind | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061733 — Cattle shed Satish kumar | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061734 — Cattle shed Puran | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061735 — Cattle shed Sumer singh | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061737 — Cattle shed Ramji lal | Deleted | 44200 | 0 | 2013-08-15
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061740 — Cattle shed Madhoo singh | Deleted | 44200 | 0 | 2013-10-02
BHIND / ATER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/1000061742 — Cattle shed Putten singh | Deleted | 44200 | 0 | 2013-10-02
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034300542 — Const.ofnadep Composting Stendr | Completed | 12000 | 11984 | 2016-11-23 | 2019-09-04
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034300547 — Const.ofnadep Composting Kilash | Deleted | 12000 | 0 | 2016-08-15
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034300551 — Const.ofnadep Composting Bajreg | Suspended | 12000 | 0 | 2019-08-20
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034300552 — Const.ofnadep Composting Chandna | Suspended | 12000 | 0 | 2016-09-29
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034308632 — Nadep taka tejbahadur singh | Completed | 12000 | 11951 | 2016-12-28 | 2017-05-31
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034309027 — Nadep taka surndra/ narpat singh | Completed | 12000 | 11951 | 2016-12-28 | 2017-01-22
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034309030 — nadep taka Kaptan singh/ chhote singh | Completed | 12000 | 11951 | 2016-12-28 | 2017-05-31
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001070/IF/22012034352500 — Vriksharopan shantidham, talab ki paar kyripura | Physically Completed | 335000 | 293996 | 2017-08-02 | 2026-05-15
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001070/IF/22012034354852 — वृक्षारोपण शान्तिधाम शासकीय प्राइमरी स्कूल तालाब के पास अर्धुजपुरा | Deleted | 335000 | 0 | 2017-06-01
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001070/IF/22012034354857 — वृक्षारोपण शान्तिधाम सरकारी प्राइमरी स्कूल एवं तलब पर | Completed | 335000 | 71180 | 2017-07-15 | 2022-07-06
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001070/IF/22012034357518 — वृक्षारोपण सड़क के किनारे मैं रोड सूरपुरा से क्यारिपुरा तक | Completed | 335000 | 19952 | 2017-09-16 | 2022-08-01
BHIND / ATER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702001070/IF/22012034368239 — Vricharopan govt. middle school, shamshaan ghat, kalyanpura | Completed | 335000 | 25800 | 2017-07-15 | 2023-08-14
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034493544 — compost pit - Pramod / shiv raj singh Kyaripura | Deleted | 0 | 0 | 2019-05-27
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034493545 — compost pit - veerpal / chote singh Kyaripura | Deleted | 0 | 0 | 2019-05-27
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034493546 — compost pit - uday singh / vishewshar singh Kyaripura | Deleted | 0 | 0 | 2019-05-27
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034493555 — compost pit - dharmendra / prag singh Kyaripura | Deleted | 0 | 0 | 2019-05-27
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034493556 — compost pit - Jitendra singh / kalandar singh Kyaripura | Deleted | 0 | 0 | 2019-05-27
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034599547 — maid bandan - pramod / sauraj singh | Completed | 18428.96 | 14820 | 2020-09-14 | 2020-11-10
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034599549 — maid bandan - kanhai singh / satavan singh | Completed | 26816.57 | 20520 | 2020-09-14 | 2020-11-10
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034599550 — maid bandan - chote singh / kunji singh | Closed | 0 | 0 | 2020-05-05
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034599551 — maid bandan - mukesh / ram kishan | Closed | 0 | 0 | 2020-05-05
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034599552 — maid bandan - kalyan singh | Completed | 35755.43 | 2280 | 2020-09-14 | 2021-08-20
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034650162 — pashu shed - pramod kumar / sauraj singh | Completed | 101804.91 | 93181.66 | 2021-01-27 | 2021-04-02
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034650163 — pashu shed - shayam pal / malikhan | Completed | 101804.91 | 94411.66 | 2021-01-27 | 2021-05-16
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034650164 — pashu shed - Mukesh / ram kishan | Completed | 101804.91 | 93235.66 | 2021-01-27 | 2021-04-15
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1702001070/IF/22012034651559 — pashu shed sarita w/o sandeep | Completed | 101804.91 | 93325.37 | 2021-01-27 | 2021-04-25
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677583 — pashu shed - kanahi singh /satavan singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677584 — pashu shed - veerpal singh /chote singh | Deleted | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677586 — pashu shed - kandai singh / sarman singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677587 — pashu shed - manish singh / dharm singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677588 — pashu shed - shailendra singh / harbhan singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677589 — pashu shed - ajab singh / samsher singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677592 — pashu shed - kalyan singh /phojdar singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677593 — pashu shed - kishan singh / chote singh | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034677594 — pashu shed - Ravindra kumar / shri krishna | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/22012034680716 — pashu sed - lavkush / shivsingh (diwan singh ) | Closed | 0 | 0 | 2021-01-21
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034704456 — khet talab - jal bihari/ keshav singh | Completed | 337715.44 | 197441.1 | 2021-04-22 | 2022-05-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034704471 — maid bandan - ram het / maniram | Closed | 0 | 0 | 2021-04-01
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034704476 — maid bandan - kashiram / phule | Closed | 0 | 0 | 2021-04-01
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034752522 — maid bandan - shamser / shivraji | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012034752524 — maid bandan - rambahadur / lal singh | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034943826 — nadef tanka - veerpal singh / chote singh | Closed | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034943827 — nadef tanka - suresh / bajrang singh | Closed | 0 | 0 | 2021-10-02
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034943830 — nadef tanka - nisha / sahdev singh | Closed | 0 | 0 | 2021-10-02
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034943831 — nadef tanka - manish / dham singh | Completed | 14006.51 | 11892 | 2022-04-08 | 2023-05-17
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702001070/IF/22012034943836 — nadef tanka - dinesh/ dheer singh | Completed | 14006.51 | 11892 | 2022-04-08 | 2023-05-17
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035075668 — khet talab - meera devi / ramjas | Completed | 385261.22 | 242658 | 2023-05-11 | 2025-05-06
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035130898 — Khet talab - raghuveer / bhonde | Closed | 0 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035130900 — khet talab - matadeen / gobardhan | Closed | 0 | 0 | 2023-04-14
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035132028 — Khet talab veer bhan/ram kishan | Completed | 385305.65 | 148070 | 2023-08-05 | 2026-05-07
BHIND / ATER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035132029 — Khet talab munnedra singh /sobharam | Ongoing | 385305.65 | 164645 | 2023-08-05
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539178 — khet talab Rampal singh ke khet par | New | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539439 — khet talab - sumer singh ke khet par | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539444 — khet talab rampal singh ke khet par | Ongoing | 147621.16 | 31320 | 2025-06-15
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539450 — khet talab sheran singh ke khet par | Closed | 147621.16 | 0 | 2025-06-05
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539476 — khet talab puttana singh ke khet par | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539491 — khet talab pavat singh ke khet par | Approved | 0 | 0 | 2025-04-14
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702001070/IF/22012035539511 — khet talab jagpal singh ke khet par | Ongoing | 147621.16 | 28188 | 2025-06-15
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9926745205 — cattle shed Dalveer singh | Completed | 62000 | 38682 | 2014-07-23 | 2014-12-30
BHIND / ATER | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9926745208 — cattle shed Puttn singh | Completed | 62000 | 37489 | 2014-07-23 | 2014-12-30
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993702176 — Cattle shed Suraj singh | Deleted | 90000 | 0 | 2015-10-02
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993702178 — Cattle shed Attar singh | Deleted | 90000 | 0 | 2015-10-02
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993702179 — Cattle shed Kedar | Deleted | 90000 | 0 | 2015-10-02
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993702180 — Cattle shed Jalbihari singh | Deleted | 90000 | 0 | 2015-10-02
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001070/IF/9993750256 — Form bunding Pramod | Deleted | 19700 | 0 | 2016-04-14
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001070/IF/9993750262 — Form bunding Kalyan singh | Deleted | 29287 | 0 | 2016-07-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001070/IF/9993750264 — Form bunding tejbahadur | Deleted | 29600 | 0 | 2016-07-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702001070/IF/9993750266 — Form bunding Ram bhadur | Deleted | 29600 | 0 | 2016-07-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993750268 — Cattle shed Kalyan shing | Deleted | 90000 | 0 | 2016-07-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993750270 — Cattle shed Uday shing | Deleted | 90000 | 0 | 2016-07-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702001070/IF/9993750272 — Cattle shed Mangla | Deleted | 90000 | 0 | 2016-07-01
BHIND / ATER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/199282 — Construction of IAY House -IAY REG. NO. MP-02-001-070-001/59 | Completed | 15030 | 11356 | 2016-08-03 | 2016-09-13
BHIND / ATER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/199283 — Construction of IAY House -IAY REG. NO. MP-02-001-070-001/9 | Approved | 23490 | 0 | 2016-03-29
BHIND / ATER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/3742492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118763576 | Completed | 18360 | 17136 | 2022-08-24 | 2022-12-24
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4522083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115884935 | Completed | 23490 | 21717 | 2024-10-22 | 2025-06-26
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4915457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120584673 | Completed | 23490 | 23229 | 2025-04-01 | 2026-04-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4915458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120625213 | Ongoing | 23490 | 18531 | 2025-05-06
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4915459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120625742 | Approved | 23490 | 0 | 2025-02-13
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4915499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121697469 | Completed | 23490 | 22842 | 2025-03-16 | 2026-04-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4924472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115887421 | Ongoing | 23490 | 21663 | 2025-04-08
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4924473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115893155 | Ongoing | 23490 | 21663 | 2025-04-29
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/4924507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120588225 | Completed | 23490 | 21924 | 2025-04-01 | 2026-04-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5130394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120624609 | Completed | 23490 | 23229 | 2025-04-08 | 2026-04-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5254296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115882932 | Ongoing | 23490 | 23229 | 2025-04-29
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5282104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115889711 | Ongoing | 23490 | 23229 | 2025-08-13
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5291439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121648276 | Ongoing | 23490 | 23229 | 2025-05-27
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5313908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121644013 | Physically Completed | 23490 | 23229 | 2025-05-27 | 2025-12-13
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5729510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120606107 | Approved | 23490 | 0 | 2025-06-11
BHIND / ATER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/5730805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124296101 | Ongoing | 23490 | 9396 | 2025-09-09
BHIND / ATER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702001070/IF/IAY/6219693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115907952 | Approved | 23490 | 0 | 2025-03-05
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001070/LD/134 — मेढबन्‍धान अखलेश / प्रथ्‍वीपाल | Completed | 9100 | 3822 | 2009-07-01 | 2009-07-07
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001070/LD/135 — मेढबन्‍धान अखिलेश / प्रथ्‍वीपाल | Completed | 7000 | 6962 | 2009-07-01 | 2009-07-07
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001070/LD/136 — मेढबन्‍धान रघुवीर / भोदेलाल | Completed | 5300 | 4641 | 2009-07-08 | 2009-07-14
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001070/LD/137 — मेढबन्‍धान बीरभान / रामकिशन | Completed | 5300 | 0 | 2009-07-08 | 2009-07-14
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001070/LD/138 — मेढबन्‍धान अतिवीर / पुनूराय | Completed | 5300 | 3913 | 2009-07-08 | 2009-07-14
BHIND / ATER | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702001070/LD/139 — मेढबन्‍धान राजाराम/ भोदेलाल | Completed | 5300 | 4368 | 2009-07-01 | 2009-07-07
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001070/LD/22012034296866 — shanti dham kyaripura | Completed | 245000 | 244663.48 | 2017-03-08 | 2019-08-30
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702001070/LD/22012034316036 — शान्तिधाम कंधई सिंह के खेत के पास अर्जुद्धपुरा | Completed | 245000 | 244214.48 | 2017-07-12 | 2018-10-08
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702001070/PG/9425892656 — khel maidan kaliyanpura | Deleted | 186000 | 0 | 2016-12-28
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034168174 — c.c. road harjan basti arjud pura | Deleted | 0 | 0 | 2012-04-14
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034170919 — c.c. raoad harjan basti | Completed | 90000 | 89754 | 2013-06-12 | 2013-12-23
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034189845 — c.c. road Lalman baba ls dharm ke makan tal | Completed | 162400 | 160832 | 2014-09-03 | 2014-12-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034191416 — C.C. Bade lal ke ghar se gulad ke or | Completed | 124500 | 124120 | 2013-12-04 | 2014-03-13
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034223720 — ccroad Main road to katare house | Completed | 144000 | 143750 | 2014-09-03 | 2016-02-20
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034231735 — C.C. Road from main road to Savajeet house part-2 | Completed | 48000 | 5181 | 2014-10-29 | 2016-07-30
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034231757 — C.C. Road from Lalman baba to Dharmsingh house | Completed | 61000 | 2512 | 2014-10-29 | 2016-07-30
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034283475 — cc road Chandrabhan house to Harnamsingh house | Completed | 43200 | 43156 | 2015-08-26 | 2016-04-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034283476 — cc road Udybeer singh house to Jangbhadur house | Completed | 43200 | 43156 | 2015-08-26 | 2016-04-20
BHIND / ATER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034287016 — cc road from Harbance house to Munsi master house | Completed | 69000 | 68936.8 | 2015-10-28 | 2016-04-20
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034309238 — cc road Purohit house to Tej bahadur house | Deleted | 0 | 0 | 2016-04-02
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034309239 — cc road Purohit house to Tej bahadur house | Deleted | 0 | 0 | 2016-04-02
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034311093 — cc road purohit house tejbahadur house | Completed | 51000 | 50775 | 2016-04-20 | 2017-01-06
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034311126 — cc road ramnaresh house toarjudpura | Completed | 76000 | 61189 | 2016-08-10 | 2018-06-29
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034314284 — CC road Sanjay singh house to Aaganbadi bhavan | Deleted | 150000 | 0 | 2017-01-24
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034315042 — C.C.Road Sanjay Singh Ke Darwaje Se Anganwadi bhawan ki or | Completed | 150000 | 149875 | 2016-10-19 | 2018-07-12
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034318758 — CC road main road se Vankhandi shakya ke makan ki ore | Completed | 173219 | 170813.35 | 2016-12-28 | 2018-07-31
BHIND / ATER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034319366 — CC road kaptan singh ke makan sepramod ke dwar ki ore | Completed | 178175 | 179656 | 2017-01-24 | 2017-12-17
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034352195 — सी.सी.रोड निर्माण राजू गोस्वामी के दरवाजे से कैलाश मिर्धा के मकान तक | Deleted | 30975 | 0 | 2017-06-05
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034369588 — C.C.Raod Mai Nali Main Road Se Govt. High School Kyaripura Ki Or Part-1, Kyaripura | Completed | 55800 | 44460 | 2018-01-26 | 2018-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034369606 — C.C.Raod Mai Nali Main Road Se Govt. HighSchool Kyaripura Ki Or, Part-2, Kyaripura | Completed | 32550 | 36120 | 2017-12-23 | 2018-02-15
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034369610 — C.C.Raod Mai Nali Ramveer Barua Ke Darwaje Se Amar Singh Goswami ke darwaje ki or , Ardhujpura | Completed | 81225 | 80696 | 2018-01-26 | 2019-08-11
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001070/RC/22012034369615 — Sudur Samprak Sadak Aganwadi Bhawan Se Govt. High School Kyripura or sarjusingh ke pura - Kyaripura | Closed | 1300000 | 0 | 2017-08-15
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034372720 — C.C.Raod Raju Singh Yadav Ke Dwar Se Primary School Hote Hue Rambaran Ke Dwar Tak, Kalyanpura, | Completed | 83700 | 82950 | 2018-05-14 | 2020-05-07
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034373274 — cc road | Deleted | 0 | 0 | 2018-01-26
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034381949 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / ATER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034382467 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034386331 — सी सी रोड (मशान बाबा के राम किशुन धानुक के द्वार तक ) | Completed | 55800 | 54348 | 2018-09-26 | 2021-03-06
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034390960 — सी सी रोड ( राजबहादुर जाटव के दरवाजे से रघुवीर जाटव के घर की ओर अर्धुजपुरा) | Completed | 32550 | 29232 | 2018-07-11 | 2019-02-06
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034393655 — सी सी रोड ( मेनरोड से मानसिंह के द्वार तक) | Completed | 14000 | 13620 | 2018-10-02 | 2019-06-25
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034393657 — सी सी रोड(रामसेवक चुरारिया के द्वार से मंगल सिंह के द्वार तक क्‍यारीपुरा) | Completed | 28000 | 27912 | 2018-09-25 | 2019-07-03
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034394781 — bhoop singh ke makan se aganwadi bhavan ki or kyaripura | Completed | 49000 | 44328 | 2019-02-25 | 2019-10-09
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034442391 — cc road | Suspended | 0 | 0 | 2019-08-16
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034446936 — सी सी रोड ( धर्म सिंह के दरवाजे से कन्हई सिंह के दरवाजे होते हुये जहान सिंह के द्वार तक ) | Completed | 27900 | 26328 | 2019-03-04 | 2021-03-06
BHIND / ATER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034446938 — सी सी रोड ( कैलास चुरारिया के मकान से भगवान सिंह के मकान की ओर ) | Completed | 58125 | 23196 | 2019-03-04 | 2020-03-02
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034468106 — सी सी रोड ( मैंन रोड से शांती धाम क्यारीपुरा ) | Completed | 16275 | 15840 | 2019-07-28 | 2019-10-16
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034482415 — c c road ( RAMALAKHAN JATAV KE DWAR SE BRAJENDRA YADAV KE DWAR KE OR ) | Completed | 60450 | 55860 | 2020-06-04 | 2020-11-20
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034482417 — C C C ROAD ( RAMESH KE DWAR SE BHURE KE DWAR KE OR ) | Closed | 16275 | 0 | 2019-08-16
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034482418 — C C ROAD ( JURAKHAN SINGH KE MAKAN SE ANIL SINGH KE MAKAN TAK ) | Deleted | 23250 | 0 | 2019-08-15
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034507743 — c c road ( tribhuwan ke darwaje se tej bahadur ke darwaje ke or ) | Closed | 9300 | 0 | 2019-08-15
BHIND / ATER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034514751 — cc road | Deleted | 0 | 0 | 2019-10-02
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001070/RC/22012034523135 — सुदूर सड्क आगनबाडी भवन से शा.हाईस्कूल क्यारीपुरा तक | Completed | 1490729.22 | 897767.38 | 2020-06-04 | 2022-04-20
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034536672 — c c road ( samudyik bhawan se school ke kachh tak kyaripura) | Completed | 19125 | 15960 | 2020-09-25 | 2021-04-07
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702001070/RC/22012034537400 — सुदूर सड़क निर्माण बोरेश्वर सड़क से प्रायमरी स्कूल कलियान होते हुए अजुधपुरा की ओर | Closed | 0 | 0 | 2020-05-09
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034540790 — c c road ( balveer yadav ke dwar se sharan singh ke dwar ke or kaliyanpura ) | Completed | 32550 | 1140 | 2020-09-25 | 2022-02-21
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034562550 — c c road ( govind singh ke darwaje se hanuman mandir ke or ) | Completed | 46500 | 46477 | 2021-03-17 | 2021-09-30
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/22012034578289 — c c road ( shyam pal ke darwaje se anil singh ke darwaje ke or ) | Completed | 52762 | 52110 | 2021-10-13 | 2025-05-06
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702001070/RC/22012034596399 — sudoor sampark sadak - prathamik shala bhawan kalayanpura se ardujjpura ke or | Completed | 1499053.31 | 1033398.25 | 2021-11-17 | 2025-05-06
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/377 — cc road tiwari ke makan se govind singh ke makan tak | Completed | 0 | 105610 | 2012-09-17 | 2012-10-20
BHIND / ATER | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/470 — सी सी रोड छोटे फोजी के दरवाजे से रामराज की ओर | Deleted | 248400 | 0 | 2012-01-26
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702001070/RC/491 — 1702001070/RC/491 | Completed | 0 | 107343.2 | 2013-02-19 | 2013-07-15
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193183 — Maryada abhiyan Santara devi | Deleted | 4500 | 0 | 2012-04-14
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193184 — Maryada abhiyan Bhoop singh | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193196 — Maryda abhiyan Mahindra singh | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-29
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193198 — Maryda abhiyan Satendra singh | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-30
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193203 — Maryda abhiyan Jairam | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193206 — Maryda abhiyan Ramkumar | Completed | 4500 | 4428 | 2014-02-11 | 2017-01-09
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193210 — Maryda abhiyan Dilisharam | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193212 — Maryda abhiyan Bitoli | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193214 — Maryda abhiyan Abdesh singh | Completed | 4500 | 4428 | 2014-02-25 | 2014-05-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034193217 — Maryda abhiyan Ashok | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034200456 — Maryada abhiyan Raju | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034200461 — Maryada abhiyan Arjun singh | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201829 — Maryada abhiyan Bajrang singh | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1702001070/RS/22012034201830 — Maryada abhiyan Rajendra singh | Deleted | 4500 | 0 | 2012-08-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201832 — Maryada abhiyan Gajadher singh | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201850 — Maryada abhiyan Rajendra | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201865 — Maryada abhiyan chote lal | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201869 — Maryada abhiyan Kalyan singh | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201873 — Maryada abhiyan Dasthrath | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201875 — Maryada abhiyan Chote lal | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201878 — Maryada abhiyan Tajbhadhur | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201881 — Maryada abhiyan krishan kumar | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201883 — Maryada abhiyan sanjy | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201885 — Maryada abhiyan govind singh | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201887 — Maryada abhiyan gajendra singh | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034201936 — Maryada abhiyan Rajaram | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1702001070/RS/22012034201941 — Maryada abhiyan Rajaram /sukhan | Deleted | 0 | 0 | 2012-08-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034202050 — Maryada abhiyan Rajaram/sukhan | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034202052 — Maryada abhiyan Satendra | Completed | 4500 | 4428 | 2014-02-05 | 2014-03-24
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034202150 — Maryada abhiyan Anil singh | Completed | 4500 | 4428 | 2014-02-11 | 2014-05-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204445 — Maryada abhiyan Beerendra | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204447 — Maryada abhiyam omprakesh | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204459 — Maryada abhiyam randheer | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204466 — Maryada abhiyam Rajveer | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204482 — Maryada abhiyam satara devi | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204488 — Maryada abhiyam sabajeet | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204489 — Maryada abhiyam Ramlakhan | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204494 — Maryada abhiyam Lal krishan | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204497 — Maryada abhiyam Kalish | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034204503 — Maryada abhiyam Chote lal | Completed | 4500 | 4428 | 2014-02-11 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207126 — Maryada abhiyan Bharat Singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207129 — Maryada abhiyan Samrath Singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207130 — Maryada abhiyan Kuldeep | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-10
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207131 — Maryada abhiyan Pramod | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-10
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207132 — Maryada abhiyan Dharm singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-10
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207133 — Maryada abhiyan Jitendra singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-10
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207134 — Maryada abhiyan Ramkumar | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207135 — Maryada abhiyan Barajbhan singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207137 — Maryada abhiyan Tribhun singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207138 — Maryada abhiyan Raindher singh | Completed | 4500 | 2628 | 2014-02-18 | 2017-01-09
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207140 — Maryada abhiyan Rambhadhur | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207142 — Maryada abhiyan Man singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207144 — Maryada abhiyan Rampal singh | Completed | 4500 | 2628 | 2014-02-18 | 2017-01-09
BHIND / ATER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207146 — Maryada abhiyan Dalveer singh | Deleted | 0 | 0 | 2012-08-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207147 — Maryada abhiyan Dalveer singh | Completed | 4500 | 2628 | 2014-02-18 | 2017-01-09
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207148 — Maryada abhiyan Shri krishan | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207149 — Maryada abhiyan Avnish singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207150 — Maryada abhiyan Goure singh | Completed | 4500 | 4428 | 2014-02-18 | 2017-01-09
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034207152 — Maryada abhiyan Shayam singh | Completed | 4500 | 4428 | 2014-02-18 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210468 — Maryada abhiyan kallu/dulare | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210472 — Maryada abhiyan Randheer/jagmohan | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210488 — Maryada abhiyan Puran singh/chinge lal | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210490 — Maryada abhiyan Man singh/ramlakhan | Completed | 4500 | 4428 | 2014-02-25 | 2017-01-09
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210492 — Maryada abhiyan Anhadh/phaladh | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210493 — Maryada abhiyan Kairan singh/naryan singh | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210496 — Maryada abhiyan Alok singh/krdar singh | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210498 — Maryada abhiyan Rambhorse | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210500 — Maryada abhiyan Putten singh/mulam | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210505 — Maryada abhiyan Jaipal singh/mulam | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034210508 — Maryada abhiyan Vikram singh/ mulam singh | Completed | 4500 | 4428 | 2014-02-25 | 2014-03-15
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034256803 — toilet 1Sarvesh 2 Vipin 3 Rajesh 4 Suman 5 Moharam | Deleted | 54000 | 0 | 2014-08-04
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034256808 — toilet 1 Vidhayabali 2Mupal 3 Vinod 4 Tahasildar 5 | Deleted | 54000 | 0 | 2014-08-04
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034256815 — toilet 1Anujsingh 2 Snjeevsingh 3 parmod 4 Dunamik | Deleted | 54000 | 0 | 2014-08-04
BHIND / ATER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702001070/RS/22012034256820 — toilet 1Sugharati 2 Ramdatt 3 Ramraj | Deleted | 16200 | 0 | 2014-08-04
BHIND / ATER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001070/RS/22012034494833 — commurity Toilet construction gram panchayat kyaripura | Completed | 43000 | 42216 | 2020-09-18 | 2021-04-10
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001070/RS/22012034565260 — Community Toilet construction gram kalyanpura | Closed | 43000 | 0 | 2021-09-13
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702001070/RS/22012034608863 — community senetry complex midil school ke pass kalyanpura | Completed | 43000 | 42264 | 2021-11-13 | 2022-04-24
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001070/RS/22012034646400 — Construction of Nadef - nisha devi / sahdev singh | Completed | 1920 | 1224 | 2022-04-08 | 2023-07-13
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001070/RS/22012034646408 — Nadef- veerpal /chote singh | Completed | 2000 | 1224 | 2022-04-08 | 2023-07-13
BHIND / ATER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001070/RS/22012034647443 — Nadef- veerpal /chote singh | Closed | 0 | 0 | 2022-01-26
BHIND / ATER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702001070/RS/22012034647445 — Nadef - suresh singh / bajrang singh | Completed | 2000 | 1224 | 2022-04-08 | 2023-08-14
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WC/22012034466999 — TALAB JIRODHAR SHANTI DHAM KE PAAS | Suspended | 0 | 0 | 2019-08-16
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WC/22012034467000 — TALAB JIRODDHAR - HARIJAN BASTI KALIYAN PURA | Suspended | 0 | 0 | 2019-08-16
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WC/22012034467001 — TALAB JIRODDHAR - AGANWADI BHAWAN KE PAAS | Suspended | 0 | 0 | 2019-08-16
BHIND / ATER | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001070/WC/22012034546080 — talab niraman - kailas churariya ke khet ke paas | Deleted | 0 | 0 | 2020-01-26
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702001070/WC/22012034547734 — naveen talab nirman kyaripura | Completed | 790100.03 | 351462 | 2020-07-02 | 2021-05-09
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001070/WC/22012034660850 — talab pichhing work - aganwadi bhawan | Deleted | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702001070/WC/22012034683416 — talab aganwadi bhawan ke pass ke rituning wall and pipe puliya sahit nirman | Completed | 986721.32 | 925528 | 2021-05-13 | 2022-07-21
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702001070/WC/22012034769624 — roof water Harvesting work - govt high school kyaripura | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1702001070/WC/22012034780603 — पोषण बाटिका ग्राम पंचायत क्यारीपुरा | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001070/WC/22012034788515 — sok pit - shanti dham kalyanpura par | Closed | 4600 | 0 | 2021-04-14
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001070/WC/22012034788741 — sok pit -govt midil school kalyanpura | Completed | 4600 | 4477 | 2021-12-03 | 2023-02-28
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001070/WC/22012034788754 — sok pit -govt primary school kyaripura | Completed | 4600 | 4632 | 2021-08-30 | 2021-09-07
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001070/WC/22012034788765 — sok pit - govt primary school ardhujpura | Completed | 4600 | 4632 | 2021-09-13 | 2021-09-24
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001070/WC/22012034788767 — sok pit -govt high school kyaripura | Completed | 4600 | 4632 | 2021-08-30 | 2021-09-07
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702001070/WC/22012034798124 — roof water Harvesting work - govt primary school kyaripura | Closed | 0 | 0 | 2021-04-14
BHIND / ATER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001070/WH/19956919 — Talab deepning Ajuddpura kiyaripura | Deleted | 100000 | 0 | 2016-05-25
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001070/WH/19959106 — Renovation of Pond- Lakhan Mirgha ke makan ke pass, Kyaripura | Completed | 96085 | 87000 | 2017-05-10 | 2020-06-06
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001070/WH/19961490 — Renovation of Pond- Primary School Ke Peeche, Kalyan Pura, Kyaripura | Deleted | 96000 | 0 | 2017-05-17
BHIND / ATER | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702001070/WH/19961492 — Renovation Of Pond- Main Road Ke Pass, Kyaripura | Completed | 95000 | 27864 | 2017-05-24 | 2017-07-12
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WH/22012034443644 — तालाब जिण्र्द्वार हरिजन बस्ती कल्यानपुरा | Completed | 199894.05 | 104500 | 2020-06-04 | 2021-03-06
BHIND / ATER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WH/22012034446152 — तालाव सोंदर्यकरण एव मरम्मत कार्य ( शांती धाम के पास क्यारीपुरा ) | Completed | 99514.74 | 99003.54 | 2021-03-05 | 2022-05-20
BHIND / ATER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WH/22012034453861 — तालाब मरम्मत व पार निर्माण (बडा बाला ताल) अधुर्जपुरा | Physically Completed | 975646.16 | 497819.74 | 2022-03-26 | 2026-04-17
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WH/22012034456097 — talab jirnoddar - primary school kalyanpura | Completed | 989828.4 | 582803.4 | 2022-05-14 | 2026-04-09
BHIND / ATER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702001070/WH/22012034933698 — talab jirnoddar-primary school kalyanpura | Closed | 0 | 0 | 2022-04-15