## Work List
Exported on: 2026-09-11 02:41:59
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: VIRDHANPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002001/AV/22012034369003 — SHANTIDHAM NIRMAN BEDIYA BASTI VIRDHANPURA | Completed | 180000 | 179666.66 | 2017-10-16 | 2018-02-02
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702002001/AV/22012034551626 — CHABUTARA NIRMAN SEWA SAHKARI SAMITI VIRTHANPURA | Closed | 802553.42 | 0 | 2021-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702002001/AV/22012034552286 — Returning wall Nirman upswasth kendra ke pichhe | Closed | 0 | 0 | 2021-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1702002001/DP/22012034594802 — AMRIT VATIKA PS/MS SCHOOL PRANGAN ME VIRDHANPURA | Closed | 55847.4 | 0 | 2023-04-14
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Cross Bund / Construction of Earthen graded Bund for Community | Works for Flood Control and Protection | 1702002001/FP/22012034203258 — NALA NIRMAN RAMATAR KE MAKAN SE DAMAR ROAD TAK | Completed | 749000 | 555570.6 | 2015-12-21 | 2016-07-22
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002001/FP/22012034361185 — NALA NIRMAN PAN SINGH KE KHET SE KHEL MAIDAN KI OR | Completed | 111000 | 88740 | 2018-08-27 | 2018-09-29
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002001/FP/22012034364896 — KACHCHA NALA NIRMAN BHUTANI KE GHAR SE CHANDUPURA KI OR | Completed | 283389.93 | 247190 | 2020-05-08 | 2020-06-27
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002001/FP/22012034630173 — KACHCHA NALA NIRMAN AMRATLAL KE KHET SE CHANDUPURA KI OR | Closed | 0 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002001/FP/22012034631138 — NAVEEN KACHA NALLA SATYANARAYAN KE BAGAL SE HANSARAM SAKYA KE GHAR HOTE HUE CHANDUPURA KI AUR | Ongoing | 349562.05 | 23256 | 2022-12-18
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002001/FP/22012034634074 — Kaccha Nala nirmad damodar ke Ghar ke piche se panchayat bhavan ki puliya | Closed | 378871.75 | 0 | 2023-04-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002001/IF/22012034352489 — BRAKSHA ROPAN KARYA SHANTIDHAM VIRDHANPURA | Completed | 335000 | 33192 | 2017-08-01 | 2021-11-23
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002001/IF/22012034352495 — BRAKSHA ROPAN KARYA SHANTIDHAM RAHALA | Closed | 335000 | 0 | 2017-06-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002001/IF/22012034353618 — BRAKSHA ROPAN KARYA TALAB,SCHOOL KE KINARE | Closed | 335000 | 0 | 2017-06-17
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002001/IF/22012034353621 — BRAKSHA ROPAN KARYA SADAK KE KINARE RAHALA | Closed | 335000 | 0 | 2017-06-17
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012034549281 — KHET TALAB DHARAMVEER KE KHET PR GRAM PANCHAYAT VIRDHANPURA | Closed | 332572.21 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012034549284 — KEHT TALAB AVDHESH KE KHET PR GP VIRDHANPURA | Closed | 332572.21 | 0 | 2020-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757062 — MED BANDHAN MAHADEV / TULSIRAM KE KHET PER | Completed | 32716.23 | 23160 | 2021-06-03 | 2021-06-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757065 — MED BANDHAN RAMESH / VIDHYARAM KE KHET PER | Completed | 30681.29 | 25476 | 2021-06-03 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757075 — MED BANDHAN RAMBHAROSE / PIYARAM KE KHET PER | Completed | 30681.29 | 31266 | 2021-06-03 | 2022-04-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757083 — MED BANDHAN RAMPRAKASH / SHRIRAM KE KHET PER | Completed | 30681.29 | 24318 | 2021-06-03 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757090 — MED BANDHAN SANJAY / RAMDULARE KE KHET PER | Completed | 30681.29 | 24318 | 2021-06-03 | 2021-07-03
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757097 — MED BANDHAN KAMLESH / MUKHRAM KE KHET PER | Completed | 31989.2 | 26634 | 2021-06-03 | 2021-06-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002001/IF/22012034757103 — MED BANDHAN VISHAMBHAR / MAHARAJ SINGH KE KHET PER | Completed | 31989.2 | 24318 | 2021-06-03 | 2021-07-02
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/22012034765040 — PASHU SHED NIRMAN ALBELE / MEVARAM | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002001/IF/22012034806353 — MED BANDHAN JAGDAMBA PRASAD / ULFAT KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002001/IF/22012034810591 — MED BANDHAN HARIBALLABH / SHRIRAM KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002001/IF/22012034810596 — MED BANDHAN SUDAMA / SUKHWASI KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012034830843 — KHET TALAB NIRMAN ASHOK / MOHARMAN KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012034830844 — KHET TALAB RAMPRAKASH / SHRIRAM KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012034965965 — KHET TALAB SHER SINGH KE KHET PER | Closed | 0 | 0 | 2022-04-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012034998929 — KHET TALAB NIRMAN MAHESH / MEVARAM KE KHET PER | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012035128477 — khet talab - dadiram / sukhwasi | Ongoing | 386047.53 | 41116.2 | 2023-07-20
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002001/IF/22012035128678 — KHET TALAB NIRMAN SRIKRISHAN BAGHEL / RAMCHARAN KE KHET PER | Ongoing | 386047.53 | 108732 | 2023-07-21
BHIND / BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993655764 — CATTLE SHED RAM NIWAS / JANVED PRASAD | Deleted | 89000 | 0 | 2014-10-20
BHIND / BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993656160 — CATTLE SHED RAM CHARAN / CHETRAM | Deleted | 89000 | 0 | 2014-09-29
BHIND / BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993656161 — CATTLE SHED BRIJESH / SHREE RAM | Deleted | 89000 | 0 | 2014-09-29
BHIND / BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993656163 — CATTLE SHED OMPRAKASH / GADERAM | Deleted | 89000 | 0 | 2014-09-29
BHIND / BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993656178 — CATTLE SHED CUNNI / SARJU | Deleted | 89000 | 0 | 2014-09-29
BHIND / BHIND | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993656181 — CATTLE SHED UGRESEN /BANSIDHAR | Deleted | 89000 | 0 | 2014-10-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993675441 — CATTLE SHED GYADEEN JATAV S/O NAKTU JATAV | Completed | 115900 | 103946.48 | 2015-09-21 | 2015-11-07
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993675443 — CATTLE SHED SULTAN SINGH S/O RAMSWAROOP | Completed | 115900 | 105059.48 | 2015-09-21 | 2015-11-07
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993680107 — CATTLE SHED KAILASH S/O BADRIPRASAD | Completed | 115900 | 117301.54 | 2015-10-11 | 2016-04-12
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993680109 — CATTLE SHED CHHOTE KHAN S/O KAPOOR KHAN | Completed | 115900 | 103946.48 | 2015-10-11 | 2016-01-02
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993682245 — CATTLE SHED VEERENDRA JATAV S/O DEENANATH JATAV VIRDHANPURA | Completed | 115900 | 104582.48 | 2015-10-19 | 2015-12-16
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993682250 — CATTLE SHED PANCHAM S/O SUMER PRAJAPATIVIRDHANPURA | Completed | 115900 | 105536.48 | 2015-10-14 | 2015-12-16
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993682256 — CATTLE SHED PANCHAM LAL S/O RAMGYAN VIRDHANPURA | Completed | 115900 | 107444.48 | 2015-10-14 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993693845 — CATTLE SHED GUDDIBAI /PRALAD | Deleted | 0 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993693849 — cattle shed guddibai /pralad | Completed | 115900 | 107603.48 | 2015-12-07 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993693896 — cattle sead ramsingh/gutnu | Completed | 115900 | 102833.48 | 2015-12-09 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694104 — cattle shed ramsingh/gutnu | Deleted | 11590000000 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694131 — cattle shed chakkilal/baburam | Completed | 115900 | 105218.48 | 2015-12-09 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694141 — CATTLE SHED RAMESWAR/NIRANJAN | Completed | 115900 | 103151.48 | 2015-12-11 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694162 — CATTLE SHED LAJJARAM/RAMFAL | Completed | 115900 | 102197.48 | 2015-12-09 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694166 — CATTLE SHED MAHAVEERSHREERAM | Deleted | 0 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694168 — CATTLE SHED MAHAVEER/SHREERAM | Completed | 115900 | 108398.48 | 2015-12-11 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694171 — CATTLE SHED SURESH/SARMAN | Completed | 115900 | 105536.48 | 2015-12-11 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694174 — CATTLE SHED MAHESH/MEVARAM | Completed | 115900 | 105536.48 | 2015-12-11 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694197 — CATTLE SHED DEENDAYAL/SHRIRAM | Deleted | 0 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694212 — CATTLE SHED DEENDAYAL/SHRIRAM | Completed | 115900 | 107444.48 | 2015-12-12 | 2016-04-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993694215 — CATTLE SHED ASHOK/MULCHAND | Completed | 115900 | 106331.48 | 2015-12-09 | 2016-04-11
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728381 — CATTLE SHED MUKESH / SURESH SHARMA | Completed | 116000 | 102701.88 | 2016-07-19 | 2016-08-17
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728469 — CATTLE SHED SURAJ/TEJPAL | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728472 — CATTLE SHED VILAYAKRAM/VIDYARAM | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728477 — CATTLE SHED AVDESH/KEDARNATH | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728480 — CATTLE SHED AATIRAJ/BADRIPRASAD | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728483 — CATTLE SHED SURESH/DILLIRAM | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728490 — CATTLE SHED NIKET/KRIPARAM | Completed | 116000 | 102868.88 | 2016-07-18 | 2016-08-29
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728493 — CATTLE SHED GANGASHAHAY/MAHIPATI | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728499 — CATTLE SHED KEILAS/SHRIRAM | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728501 — CATTLE SHED RAMNIVAS/KEILAS | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993728503 — CATTLE SHED MAHADEV/TULSIRAM | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002001/IF/9993751424 — Pashu Shed Ramshesh S/o Ramsanehi | Completed | 116000 | 103870.88 | 2016-07-18 | 2016-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/1142414 — Construction of IAY House -IAY REG. NO. MP-02-002-001-001/26 | Approved | 27000 | 0 | 2016-03-31
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/133899 — Construction of IAY House -IAY REG. NO. MP-02-002-001-001/46 | Completed | 14310 | 14028 | 2016-08-08 | 2017-03-25
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/134113 — Construction of IAY House -IAY REG. NO. MP-02-002-001-001/47 | Deleted | 14310 | 0 | 2016-08-08
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/196827 — Construction of IAY House -IAY REG. NO. MP-02-002-001-001/48 | Completed | 14310 | 12921 | 2016-08-08 | 2018-05-10
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/199284 — Construction of IAY House -IAY REG. NO. MP-02-002-001-001/51 | Completed | 15030 | 15030 | 2016-08-08 | 2017-03-06
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/199285 — Construction of IAY House -IAY REG. NO. MP-02-002-001-001/56 | Deleted | 15030 | 0 | 2016-08-08
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/3969415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115081463 | Ongoing | 27000 | 0 | 2023-08-03
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/4518047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103955177 | Ongoing | 27000 | 10962 | 2025-05-29
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/5620604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106451509 | Ongoing | 27000 | 17406 | 2025-09-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002001/IF/IAY/5620627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105994450 | Physically Completed | 23490 | 19836 | 2025-08-11 | 2026-06-07
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/133 — मेढबंधान विरधरनपुरा श्री कष्‍ण / झरगद | Completed | 16000 | 10200 | 2010-06-25 | 2010-07-03
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/135 — मेढबंधान लालसिंह /मोतीराम | Completed | 23000 | 10200 | 2010-06-09 | 2010-06-15
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002001/LD/22012034261943 — SANTIDHAM VIRDANPURA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002001/LD/22012034261945 — SANTIDHAM BEDIABASTI VIRDANPURA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034261950 — BOUNDRIWALL P/S AND M/S VIRDANPURA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034267127 — MUKTIDHAM RAHLA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291892 — MED BANDHAN ALBELE S/O MEVARAM | Completed | 3000000000 | 27722 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291893 — MED BANDHAN ASHARPHILAAL S/O POTHIRAM | Completed | 3110000000 | 29058 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291894 — MED BANDHAN SANJAY S/O KEDEARNATH | Completed | 3220000000 | 30060 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291895 — MED BANDHAN MURARI S/O MAHIPAT | Completed | 3110000000 | 28891 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291896 — MED BANDHAN MAHESH S/O MEVARAM | Completed | 2950000000 | 27054 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291897 — MED BANDHAN DHARMEDRA S/O GULAB CHAND | Completed | 2780000000 | 26052 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034291898 — MED BANDHAN SURSH S/O DILIRAM | Completed | 2890000000 | 26887 | 2016-08-29 | 2016-09-20
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517715 — MED BANDHAN BHAROSHE/PIYARAM KE KHET PER | Completed | 22652.95 | 19380 | 2020-06-26 | 2020-07-14
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517717 — MED BANDHAN RAMLAKHAN / HARIRAM KE KHET PER | Completed | 25673.34 | 20520 | 2020-06-26 | 2020-07-14
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517718 — MED BANDHAN MAHAVEER / MEVARAM KE KHET PER | Completed | 22652.95 | 19380 | 2020-06-26 | 2020-07-14
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517719 — MED BANDHAN ASARFILAL KE KHET PER | Completed | 24163.14 | 23940 | 2020-07-18 | 2020-08-10
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517720 — MED BANDHAN ATAR SINGH / JASHVANT KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517721 — MED BANDHAN SANJAY / KEDARNATH KE KHET PER | Completed | 24163.14 | 20520 | 2020-07-18 | 2020-08-09
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002001/LD/22012034517722 — MED BANDHAN SURESH / DILLIRAM KE KHET PER | Completed | 22652.95 | 18240 | 2020-07-18 | 2020-08-09
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034522547 — MED BANDHAN DADHIRAM / SUKHBASHI KE KHET PER | Completed | 25673.34 | 22800 | 2020-08-28 | 2020-09-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551153 — MED BANDHAN KAILASH / BADRIPRASAD | Completed | 30681.29 | 30108 | 2021-05-03 | 2021-06-17
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551154 — MED BANDHAN JITENDRA/RAMOTAR KE KHET PER | Completed | 30681.29 | 24318 | 2021-05-03 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551155 — MED BANDHAN VASHUDEV/SHRIRAM | Completed | 30681.29 | 25476 | 2021-05-03 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551156 — MED BANDHAN NIRMAN KAMLESH /MOHARMAN | Completed | 32215.35 | 31266 | 2021-05-06 | 2021-06-17
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551157 — MED BANDHAN SARVESH / MOHARMAN | Completed | 37311.48 | 35898 | 2021-05-06 | 2021-06-17
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551158 — MED BANDHAN ASHOK / MOHARMAN | Completed | 30681.29 | 30108 | 2021-05-06 | 2021-06-17
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551159 — MED BANDHAN SHIVDATT / HAJURI | Completed | 27613.16 | 19686 | 2021-05-06 | 2021-06-17
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/LD/22012034551160 — MED BANDHAN SHIVDATT / HAJURI | Closed | 26079.09 | 0 | 2021-01-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034553517 — MED BANDHAN BHAGIRATH / BADRIPRASAD KE KHET PER | Completed | 38351.61 | 28178 | 2021-05-20 | 2021-09-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034553519 — MED BANDHAN KAPTAN / BHOPAT KE KHET PER | Completed | 38351.61 | 27162 | 2021-05-20 | 2025-06-02
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034553521 — MED BANDHAN MAHAVEER / MEVARAM | Completed | 38351.61 | 30108 | 2021-05-20 | 2021-07-07
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034553522 — MED BANDHAN KAILASHI / MEVARAM KE KHET PER | Completed | 38351.61 | 30108 | 2021-05-20 | 2021-07-07
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034553523 — MED BANDHAN DHARAMVEER / ASHARFILAL | Completed | 38351.61 | 30108 | 2021-05-20 | 2021-08-24
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/LD/22012034553524 — MED BANDHAN DEVENDRA / SHIVDATT KE KHET PER | Completed | 38351.61 | 32424 | 2021-05-20 | 2021-09-16
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002001/OP/9425890192 — BOUNDRYWALL P/S SCHOOL RAHALA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002001/OP/9425890194 — PULIYA NIRMAN VEERENDRA JATAV KE MAKAAN KE PASS | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002001/OP/9425890197 — RCC PULIYA NIRMAN SULEMAAN KE MAKAAN KE PASS | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002001/OP/9425890637 — NAVEEN BAUNDRI WALL NIRMAN P/S RAHLA | Deleted | 705000 | 0 | 2016-07-18
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702002001/OP/9425893003 — PANCHAYAT BHAVAN NIRMAN BIRTHANPURA | Completed | 514000 | 511436 | 2017-05-08 | 2018-02-18
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702002001/OP/9425893096 — NALI NIRMAN KARYA VIRDHANPURA | Completed | 131000 | 124100 | 2017-05-22 | 2017-06-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002001/OP/9425893116 — SHANTIDHAM BEDIYA BASTI VIRDHANPURA | Deleted | 180000 | 0 | 2017-01-26
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702002001/OP/9425893117 — NALA NIRMAN KARYA SURESH KE MAKAN SE SHAVIR KE MAKAN KI OR VIRDHANPURA | Completed | 951000 | 450956 | 2017-05-29 | 2017-07-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002001/PG/22012034312838 — KHEL MAIDAN ANGANWADI KE PICHHE VIRDHANPURA | Completed | 186600 | 48504 | 2017-06-19 | 2017-07-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002001/PG/22012034365799 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002001/PG/22012034366319 — Play ground | Closed | 0 | 0 | 2017-10-02
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034173702 — C.C.ROAD CHANDUPURA BAIPAS MAIN ROAD SE SULEMAN KH | Completed | 132508 | 128896.3 | 2013-07-22 | 2014-03-15
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034173704 — C.C.ROAD JAISINGH KE MAKAN SE RAM DULARE KE MAKAN | Completed | 86100 | 67276 | 2013-07-22 | 2013-12-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034182236 — C.C.ROAD MANOJ SHARMA KE MAKAN SE ASHARFILAL KE MA | Completed | 130332 | 125200 | 2014-01-11 | 2016-03-06
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034211179 — C.C.ROAD HARNARAYAN KE MAKAN SE UGRASEN KE MAKAN K | Completed | 75996 | 64365.5 | 2014-03-10 | 2016-01-25
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034211182 — C.C.ROAD BHAGWAT DAYAL KE MAKAN SE MURARI LAL KE M | Completed | 75996 | 57823 | 2014-03-10 | 2016-01-20
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034228402 — C.C.ROAD MUNNA RAWAT KE DWAR SE MAIN ROAD RAHLA KI | Completed | 71387 | 53231 | 2014-09-01 | 2016-06-20
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034285593 — C.C. ROAD NATHURAM KE MAKAN SE JAMADAR KE MAKAN TAK | Completed | 84430 | 69803 | 2015-09-28 | 2015-10-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034287636 — C.C. ROAD SHIV PRASAD KE MAKAN SE BAGHEL MOHALLA TAK VIRADHANPURA | Completed | 169000 | 116423 | 2015-10-21 | 2016-05-15
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034290985 — C.C. ROAD RAMDATT KE MAKAN SE MAHESH KE MAKAN TAK | Completed | 84500 | 42469 | 2015-12-08 | 2016-07-20
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034296729 — VIRDHANPURA MAIN ROAD SE RADHA MOHHAN KE KHET KI OR | Completed | 1126000 | 536799.6 | 2016-01-18 | 2016-06-15
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034305323 — KHETH SADAK VIRDANPURA MAIN ROAD SE SALINGPURA KE OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034305336 — KHETH SADAK P/S SCHOOL SE BIJPURI KE OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034308376 — C.C.ROAD LAVKUS KE MAKAAN SE MANSARAM KE MAKAAN KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034308859 — C.C.ROAD SURESH KE MAKAAN SE HEMANT KE MAKAAN KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034308863 — C.C. ROAD CHAKRAPAN KE MAKAAN SE NATHU BAGEL KE MAKAAN KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034308867 — C.C. MAIN ROAD SE MUKTIDHAM KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034308869 — C.C. ROAD RAMRATAN KE MAKAAN SE SURESH KE MAKAAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034309016 — C.C.ROAD RAMKUMAR KE MAKAAN SE GULAB CHAND KE MAKAAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034309021 — C.C.ROAD MAHAVEER KE MAKAAN SE RAMESHWAR KE MAKAAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034309024 — KHETH SADAK ROAD RAHLA SE CHANDUPURA KE OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034309028 — C.C.ROAD ATAR SINGH KE MAKAAN SE RANVEER KE MAKAAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034309030 — C.C.ROAD RAHLA MAIN ROAD SE VISES KE MAKAAN KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034325875 — C C ROAD RAMKUMAR KE MAKAN SE GULABCHAND KE MAKAN KI OR | Completed | 65000 | 60662 | 2017-02-13 | 2017-05-22
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034339432 — SUDOOR SAMPARK GREVAL ROAD NIRMAN GRAM RAHALA SE CHANDUPURA KI OR | Completed | 1300000 | 1058443.43 | 2017-05-29 | 2018-10-21
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034341960 — SUDOOR SAMPARK SADAK VIRDHANPURA SE SALINGPURA | Completed | 1300000 | 143964 | 2017-06-19 | 2018-10-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034347915 — CC ROAD AND NALI RAHALA MANDIR SE FERAN SINGH KE MAKAN TAK | Completed | 53100 | 43172 | 2017-08-07 | 2017-09-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034347916 — CC ROAD AND NALI NIRMAN JANAK SINGH KE MAKAN SE RANVEER KE MAKAN TAK NARWARIYA THOK | Completed | 44300 | 43000 | 2017-08-07 | 2017-09-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034349346 — CC ROAD AND NALI MAIN ROAD SE MARGHAT KI OR | Completed | 102200 | 56072 | 2017-08-14 | 2018-01-17
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034349347 — CC ROAD AND NALI CHAKRAPAN KE DARWAJE SE NATHU KE MAKAN TAK VIRDHANPURA | Deleted | 362800 | 0 | 2017-02-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034349348 — CC ROAD AND NALI ANTRAM KE DARWAJE SE CHAKRAPAN BAGHEL THOK KI OR VIRDHANPURA | Deleted | 88500 | 0 | 2017-02-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034379475 — CC ROAD KAILASH BALMEEK KE DWAR SE SAVIR KE MAKAN TAK | Deleted | 48000 | 0 | 2017-02-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034379480 — CC ROAD MAHAVEER KE DWAR SE RAMESHWAR KE MAKAN TAK | Deleted | 24000 | 0 | 2017-02-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034379600 — CC ROAD SHANKAR JI KE MANDIR SE PREM KE MAKAN TAK | Deleted | 56000 | 0 | 2017-02-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034380201 — CC ROAD MAHARAJ SINGH KE MAKAN SE MAIN ROAD TAK | Deleted | 51000 | 0 | 2017-02-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034384608 — CC ROAD SURESH KE MAKAN SE MAIN ROAD KI OR RAHALA | Completed | 60000 | 51264 | 2018-03-26 | 2018-10-29
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034384641 — CC ROAD GOVT.PRIMARI SCHOOL RAHALA SE MAIN ROAD CHANDUPURA TAK | Deleted | 149000 | 0 | 2017-02-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034386345 — CC ROAD ANTRAM KE DARWAJE SE SHIVPRASAD KE DARWAJE TAK BAGHEL THOK | Completed | 93000 | 91872 | 2018-03-19 | 2018-10-24
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034396118 — CC ROAD MAHARAJ SINGH KE MAKAN SE MEINROAD TAK VIRDHANPURA | Closed | 51000 | 0 | 2017-02-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034396121 — CC ROAD KELASH BALMIK KE DWAR SE SAVIR KE MAKAN TAK | Completed | 49000 | 48546 | 2018-12-24 | 2019-02-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034435632 — CC ROAD MAHARAJ SINGH KE MAKAN SE MAINROAD TAK | Completed | 51000 | 50982 | 2019-01-14 | 2019-04-02
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034435634 — CC ROAD SHANKAR JI KE MANDIR SE PREM KE MAKAN TAK | Completed | 56000 | 47676 | 2019-01-14 | 2019-02-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034442750 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034443622 — CC ROAD GOVT PRIMARY SCHOOL SE RAHALA MAIN ROAD RAOD CHANDUPURA TAK | Completed | 149000 | 73950 | 2019-02-18 | 2019-04-05
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034443626 — CC ROAD CHAKRAPAN KE DARWAJE SE NATHU KE DARWAJE TAKM BAGHEL THOK | Closed | 57000 | 0 | 2017-02-20
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034518285 — CC ROAD MAIN ROAD SE PANI KI TANKI KI OR EVM NALI RITURNING WALL | Completed | 76000 | 63756 | 2020-02-20 | 2020-05-25
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034519489 — SUDOOR (APROCH) SADAK GULAB KE MAKAN SE GOVT.MIDIL SCHOOL BIRDHANPURA TAK | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034524471 — KHET SADAK GULAB KE KUA SE GOVT PS SCHOOL KI OR | Completed | 1262979.95 | 584714.62 | 2020-06-18 | 2020-08-25
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034556152 — CC ROAD MUKHRAM KE MAKAN SE DADHIRAM KE MAKAN KI OR | Completed | 68000 | 66500 | 2021-01-14 | 2021-03-02
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034612919 — SUDOOR SAMPARK SADAK BIRDHANPURA SE SALINGPURA KI OR | Closed | 0 | 0 | 2022-04-03
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002001/RC/22012034612921 — SUDOOR SAMPARAK SADAK PULIYA SE CHANDARPURA KI OR | Closed | 0 | 0 | 2022-04-03
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/22012034619176 — construction of cc road ajay sharma ke makan se puliya tak nirmaan | Closed | 29250 | 0 | 2022-08-16
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002001/RC/79 — सी0सी0 रोड निर्माण रामचरन बघेल के मकान से रामनाथ बघेल के मकान तक | Completed | 346612 | 65634 | 2012-05-10 | 2012-09-25
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002001/RS/22012034597238 — SAMUDAYAK SWACHCHHATA PARISAR VIRDHANPURA | Completed | 43000 | 39372 | 2021-11-08 | 2022-01-23
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002001/RS/22012034625805 — SAMUDAYAK SWACHCHHATA PARISAR VIRDHANPURA 2 | Closed | 43000 | 0 | 2023-07-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002001/RS/22012034674513 — CONSTRUCTION OF SAMUDAYIK SOAK PIT SUKHWASI KE HAND PUMP VIRDHANPURA | Closed | 10000 | 0 | 2022-08-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002001/RS/22012034674562 — CONSTRUCTION OF SAMUDAYIK SOKHTA NEAR SASKIYA PRATHMIK VIDHYALA RAHALA | Closed | 10000 | 0 | 2022-08-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002001/RS/22012034674573 — CONSTRUCTION OF SAMUDAYIK SOKHTA NEAR VIJAY BAHADUR KE HANDPUMP PAR VIRDHANPURA | Ongoing | 10000 | 9996 | 2022-12-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002001/RS/22012034674600 — CONSTRUCTION OF SAMUDAYIK SOKHTA NEAR JITENDRA KE YHA VIRDHANPURA | Closed | 10000 | 0 | 2022-08-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002001/RS/22012034674829 — CONSTRUCTION OF SAMUDAYIK NADEP NEAR LONGA DEVI KE YHA | Closed | 2000 | 0 | 2022-08-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002001/RS/22012034674867 — CONSTRUCTION OF SAMUDAYIK NADEP NEAR VIJAY BHADUR KE YHA | Closed | 2000 | 0 | 2022-08-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002001/RS/22012034674869 — CONSTRUCTION OF SAMUDAYIK NADEP NEAR MAAN SINGH KE YHA | Closed | 2000 | 0 | 2022-08-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002001/RS/22012034674879 — CONSTRUCTION OF SAMUDAYIK NADEP NEAR BAAL VYASHI KE YHA | Closed | 2000 | 0 | 2022-08-22
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44354 — MARYADA ABHIYAN JAGDAMBA PRASAD / ULPATI | Completed | 4500 | 4427 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44360 — MARYADA ABHIYAN SATENDRA SHARMA / RAM PRAKASH | Completed | 4500 | 1799 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44364 — MARYADA ABHIYAN PANCHAM / SHIV PRASAD | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44367 — MARYADA ABHIYAN RAM BHAROSE / PIYARAM | Completed | 4500 | 4427 | 2014-02-22 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44369 — MARYADA ABHIYAN RAMHET / AADIRAM | Completed | 4500 | 4427 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44406 — MARYADA ABHIYAN SARMAN / GHAMANDI | Completed | 4500 | 2675 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44411 — MARYADA ABHIYAN VISWANATH / MULCHANDRA | Completed | 4500 | 4427 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44415 — MARYADA ABHIYAN JAGDISH PRASAD / ULPHATI | Completed | 4500 | 4427 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44418 — MARYADA ABHIYAN RADHAMOHAN / RAM SWAROOP | Completed | 4500 | 4427 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44420 — MARYADA ABHIYAN MANOJ / BHAGIRATH | Completed | 4500 | 4427 | 2014-02-24 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44423 — MARYADA ABHIYAN PARMANAND / KRIPARAM | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44425 — MARYADA ABHIYAN UGRASEN / VANSHIDHAR | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44433 — MARYADA ABHIYAN HARI PRASAD / MOHAN LAL | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44437 — MARYADA ABHIYAN NABAB | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44438 — MARYADA ABHIYAN CHUNNI GANDHARV | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44440 — MARYADA ABHIYAN BHAGWAN SINGH / LAXMAN | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44443 — MARYADA ABHIYAN RAM NIWAS / JANVED | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-20
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44447 — MARYADA ABHIYAN MAHESWARI / VIJAYRAM | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002001/RS/44449 — MARYADA ABHIYAN KARAN SINGH / JHINGURI | Completed | 4500 | 2669 | 2014-05-12 | 2016-08-11
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/WC/22012034325278 — NAVEEN TALAB NIRMAN MARGHAT KE PASS VIRDHANPURA | Completed | 176000 | 172344 | 2017-05-22 | 2017-07-25
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002001/WC/22012034326278 — DUG TANK MARGHAT KE PASS RAHELA | Completed | 28000 | 25456 | 2017-05-22 | 2017-06-20
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002001/WC/22012034385954 — talaab nirman | Closed | 0 | 0 | 2017-10-02
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/WC/22012034424684 — NAVEEN TALAB (DUG POND )NIRMAN SRVE NO, 405,403,427 | Completed | 254000 | 247096 | 2018-12-26 | 2019-06-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002001/WC/22012034557852 — NAVEEN TALAB NIRMAN MANDIR KE PASS | Completed | 294090.06 | 229278 | 2020-07-03 | 2021-10-15
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002001/WC/22012034610703 — CHECK DAM MANDIR KE PASS BIRDHANPURA | Completed | 714947.28 | 573404 | 2021-03-01 | 2022-12-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002001/WC/22012034617746 — CHECK DAM NIRMAN MANDIR KE PICHHE | Closed | 0 | 0 | 2021-11-22
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702002001/WC/22012034759987 — ROOF WATER HARVESTING PANCHAYAT BHAVAN VIRDHANPURA | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002001/WC/22012035022908 — Talab jirodhar aaganwadi ke pass gram Rahala | Completed | 42500 | 36312 | 2022-12-25 | 2025-06-02