## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Prduction of building material (Comm) / Production of building material for Community | Construction of Other Community Building/Assets | 1702002002/AV/22012034469274 — GAUSHALA NIRMAN KARYA BIJPURI | Completed | 2771628.29 | 2729287.8 | 2019-11-07 - 2020-12-05
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002002/AV/22012034515161 — SHANTIDHAM NIRMAN GRAVAL ROAD KE PAA | Completed | 194312.08 | 175838.4 | 2020-09-19 - 2021-12-28
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1702002002/AV/22012034536775 — PEWAR BLOCK SAMUDAYAK BHAVAN KE SAMNE (KEMP) ME BIJPURI | Closed | 0 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002002/AV/22012034548486 — KHAND KI PULIYA NIRMAN BIJPURI | Closed | 1425000 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002002/AV/22012034550850 — PULIYA NIRMAN KHAND KI PULUYA KE PASS BIJPURI | Completed | 1499000 | 1262320 | 2021-03-01 - 2025-05-09
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702002002/AV/22012034562670 — GEHUN UPARJN KENDRA BIJPURI | Deleted | 0 | 0 | 2021-01-21 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702002002/AV/22012034562673 — GENHU UPARJAN CHAUTRA NIRMAN BIJPURI | Completed | 804741.09 | 693591 | 2021-06-11 - 2022-11-01
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002002/AV/22012034587018 — PARK NIRMAN GALAV RISHI MANDIR KE SAMNE BIJPURI | Completed | 800000 | 701972 | 2021-08-16 - 2024-11-06
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002002/AV/22012034587019 — VENTED CAUSEWAY CONSTRUCTION BISHAMBHAR KE KHET KE PASS | Completed | 99000 | 52368 | 2021-08-16 - 2024-10-23
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002002/AV/22012034597542 — VENTED CAUSEWAY CONSTRUCTION SHANTUN SINGH KE KHET KE PASS | Ongoing | 648000 | 4378 | 2021-09-22 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002002/AV/22012034624127 — SHANTIDHAM NIRMAN KARYA DAHINE THOK KE PASS BIJPURI | Closed | 0 | 0 | 2022-10-02 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002002/AV/4339 — Anganwadi/Other Rural Infrastructure,BIJPURI | Deleted | 330000 | 0 | 2014-10-10 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002002/AV/4340 — Anganwadi/Other Rural Infrastructure,BIJPURI | Deleted | 330000 | 0 | 2014-04-14 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002002/AV/4341 — Anganwadi/Other Rural Infrastructure,BIJPURI | Deleted | 330000 | 0 | 2014-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/130 — निर्मल वाटिका कार्य रामलाल / मनीराम | Completed | 4000 | 5796 | 2011-07-10 - 2011-07-16
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/131 — निर्मल वाटिका कार्य सुरेन्‍द्र सिंह / द्वारिका सिंह | Completed | 4600 | 5796 | 2011-07-10 - 2011-07-16
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/132 — निर्मल वाटिका कार्य जयकुमार सिंह / मुलायम सिह | Completed | 4600 | 5796 | 2011-07-10 - 2011-07-16
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/137 — निर्मल वाटिका कार्य धर्मसिंह / बिन्‍द्रावन सिंह | Completed | 4302 | 5796 | 2011-07-14 - 2011-08-11
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/138 — निर्मल वाटिका कार्य क्रपाल सिंह / कायम सिंह | Completed | 4302 | 5796 | 2011-07-14 - 2011-08-11
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/139 — निर्मल वाटिका कार्य सत्‍यराम / रामजीलाल | Completed | 4302 | 5796 | 2011-07-14 - 2011-08-11
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702002002/DP/22012034580033 — Braksha ropan karay galaw Rishi ashram ke samne bijpuri | Closed | 0 | 0 | 2023-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702002002/DP/22012034598687 — Vasudha Bandhan Amrit Vatika Galav Rishi ashram ke samne bijpuri | Closed | 0 | 0 | 2023-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1702002002/DP/22012034602675 — Vasudha Bandhan Amrit Vatika Galav Rishi Ashram ke pass Bijpuri | Closed | 0 | 0 | 2023-04-14 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002002/FP/22012034369258 — RESECTIONING OF NALA CHECK DAM BIJPURI SE GRAM PANCHAYAT GOARA SEEMA KI OR | Completed | 1408756.83 | 735152 | 2021-03-01 - 2025-04-17
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002002/FP/22012034369309 — NALA NIRMAN RAMVEER KE KHET KE PASS SE GOLE KE PURA KI | Completed | 1458756.83 | 482441 | 2021-03-01 - 2025-05-21
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002002/FP/22012034628454 — NALA NIRMAN GAJENDRA KE MAKAN KE SAMNE SE HOTE HUYE KHAND KI PULIYA KI OR | Ongoing | 500000 | 111588 | 2022-04-25 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702002002/IC/22012034387443 — BAMBA EVM COOL MARAMMAT KARYA BIJPURI MOJA | Closed | 864537.62 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702002002/IC/22012034388539 — BAMBA AVM KOOL MARAMMAT NIRMAN KARYA BIJPURI MOJA | Completed | 1492855.28 | 931394 | 2020-12-25 - 2025-05-08
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/ — KHET TALAB NIRMAN SUNITA / SANTOSH SINGH KE KHET PER | Deleted | 0 | 0 | 2022-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002002/IF/22012034352222 — BRAKSHA ROPAN KARYA GWALA RISHI ASHRAM | Completed | 335000 | 56772 | 2017-06-20 - 2021-11-23
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002002/IF/22012034353998 — braksha ropan karay shantidham , Road ke kinare , Bijpuri | Closed | 335000 | 0 | 2017-06-21 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470201 — KHET TALAB RIPUDAN / PREM SINGH | Completed | 107000 | 94678 | 2019-03-07 - 2019-11-15
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470208 — KHET TALAB RAMVEER SINGH / PREM SINGH | Completed | 107000 | 89388 | 2019-03-07 - 2019-11-15
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470216 — KHET TALAB ARVINDRA SINGH / PREM SINGH | Completed | 107000 | 95910 | 2019-03-07 - 2019-10-05
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470220 — KHAT TALAB SANGEETA DEVI / SHANTANU SINGH | Completed | 107000 | 91148 | 2019-03-07 - 2019-10-22
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470224 — KHET TALAB VISHAMBHAR SINGH / MAHARAJ SINGH | Completed | 107000 | 73290 | 2019-03-07 - 2020-07-15
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034584044 — PASHU SHED RIPUDYAN SINGH / PREM SINGH | Completed | 101273.16 | 92437.5 | 2020-08-06 - 2021-03-27
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034584046 — PASHU SHED DEEPENDRA SINGH / RAMVIR | Completed | 101273.16 | 92437.5 | 2020-08-06 - 2021-03-27
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034584047 — PASHU SHED ARVINDRA SINGH / PREM SINGH | Closed | 0 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034610431 — PASHU SHED NIRMAN RAMVIR SINGH / PREMSINGH | Completed | 101273.16 | 93007.5 | 2020-09-26 - 2021-01-05
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034770417 — KHET TALAB RIPUDHIMAN / PREM SINGH KE KHET PER | Completed | 337715.44 | 252444 | 2021-06-24 - 2022-01-10
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034773551 — MED BANDHAN SURENDRA SINGH KE KHET PER | Closed | 30535.14 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034773552 — MED BANDHAN PUTTU SINGH KE KHET PER | Closed | 32295.36 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034773553 — MED BANDHAN JAYKUMAR/MULAYAM SINGH KE KHET PER | Closed | 33443.25 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034810663 — MED BANDHAN JAGRAM / JWALA KE KHET PER | Closed | 0 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034810667 — MED BANDHAN SUNIL SINGH / SHIVNATH SINGH KE KHET PER | Closed | 30681.29 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034810670 — MED BANDHAN BHAGWAN / DILLIRAM KE KHET PER | Closed | 0 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034810675 — MED BANDHAN RAJESH / CHHOTE KE KHET PER | Closed | 0 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012034810682 — MED BANDHAN GUTTE / MANIRAM KE KHET PER | Closed | 0 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034969845 — KHET TALAB NIRMAN HARIRANDRA KE KHET PER | Closed | 0 | 0 | 2022-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034985461 — KHET TALAB NIRMAN SINNET / AMOL SINGH KE KHET PER | Closed | 356340.1 | 0 | 2022-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034985466 — KHET TALAB NIRMAN RAMNATH / BEERSHAL KE KHET PER | Ongoing | 356340.1 | 2448 | 2022-05-23 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034985473 — KHET TALAB NIRMAN SUNIL / SHIVNATH KE KHET PER | Closed | 356340.1 | 0 | 2022-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034985478 — KHET TALAB NIRMAN SHANTUN SINGH / PREM SINGH KE KHET PER | Ongoing | 356340.1 | 2448 | 2022-05-23 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034985483 — KHET TALAB NIRMAN DIPENDRA SINGH / RAMVEER SINGH KE KHET PER | Physically Completed | 356340.1 | 145215 | 2022-05-23 - 2026-05-07
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034990475 — KHET TALAB NIRMAN SUNITA / SANTOSH SINGH KE KHET PER | Closed | 356340.1 | 0 | 2022-04-14 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1702002002/IF/22012035117039 — KHET TALAB RAJENDRA SINGH KE KHET PAR | Closed | 0 | 0 | 2023-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002002/IF/22012035126345 — KHET TALAB GANESH TOMAR KE KHET PAR | Closed | 0 | 0 | 2023-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002002/IF/22012035137254 — Vasudha Bandhan Amrit Vatika ka Galav Rishi mandir ke samne BIJPURI | Closed | 0 | 0 | 2023-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002002/IF/22012035365209 — KHET TALAB NIRMAN HARNARAYAN SINGH / BHAGIRATH SINGH | Deleted | 0 | 0 | 2025-04-14 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012035405290 — KHET TALAB NIRMAN ARVIND SINGH / PREM SINGH KE KHET PER | Approved | 450885.64 | 0 | 2025-04-15 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012035440117 — KHET TALAB NIRMAN HARNARYAN SINGH / BHAGIRATH KE KHET PER | Ongoing | 450885.64 | 91089 | 2025-05-16 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012035547044 — KHET TALAB NIRMAN SUNITA DEVI / SANTOSH SINGH KE KHET PER | Physically Completed | 147621.16 | 28449 | 2025-06-23 - 2026-04-22
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728057 — CATTLE SHED SHOBHARAM S\O VIRANDAVAN | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728062 — CATTLE SHED RAMHET S\O JAGRAM | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728066 — CATTLE SHED VISHAL SINGH S\O VISHAMBER SINGH | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728077 — CATTLE SHED VISHAL SINGH S\O VISHAMBER SINGH | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728080 — CATTLE SHED PARSURAM S\O BHEEKARAM | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728082 — CATTLE SHED GUTTE S\O MANIRAM | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728083 — CATTLE SHED RAMVEER SINGH S\O PREM SINGH | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/9993728087 — CATTLE SHED KIRPAL SINGH S\O KAYAM SINGH | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/134114 — Construction of IAY House -IAY REG. NO. MP-02-002-002-001/104 | Completed | 14310 | 3006 | 2016-08-02 - 2016-08-15
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/196828 — Construction of IAY House -IAY REG. NO. MP-02-002-002-001/50 | Completed | 14310 | 6012 | 2016-08-09 - 2016-08-24
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/196829 — Construction of IAY House -IAY REG. NO. MP-02-002-002-001/89 | Approved | 23490 | 0 | 2016-03-11 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/3701413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100800894 | Physically Completed | 18360 | 3876 | 2023-01-07 - 2024-11-21
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/4369466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127197832 | Physically Completed | 18360 | 2652 | 2023-10-06 - 2024-11-21
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/4375758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119076439 | Ongoing | 23490 | 2916 | 2025-03-24 -
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/4376698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105978216 | Physically Completed | 18360 | 6426 | 2023-01-07 - 2024-11-21
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/4386109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128129679 | Physically Completed | 18360 | 6426 | 2023-01-07 - 2024-11-21
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/22012034252894 — SHANTIDHAM BADA THOK BIJPURI | Deleted | 1479305 | 0 | 2016-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034261643 — MEDH BANDHAN RAMVEER SINGH S/O PREM SINGH | Completed | 27000 | 24662 | 2016-03-22 - 2016-07-11
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034266354 — MEDH BANDAN VISHAMBER SINGH / MAHARAJ SINGH | Completed | 76243 | 70975 | 2016-07-05 - 2016-08-01
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034268910 — MEDH BANDHAN ARVIND SINGH S/O PREM SINGH | Deleted | 60900 | 0 | 2016-05-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034268914 — MEDH BANDHAN ARVIND SINGH S/O PREM SINGH | Deleted | 60900 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034268916 — MEDH BANDHAN RAMBHADUR SINGH S/O MANRAKHAN SINGH | Completed | 3812100000 | 35070 | 2016-08-16 - 2016-08-29
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034274984 — MEDH BANDHAN SHANTANU SINGH / PREM SINGH | Completed | 27160 | 26052 | 2016-06-07 - 2016-06-21
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034276538 — MEDH BANDHAN RIPUDUMAN SINGH / PREM SINGH | Completed | 27160 | 21042 | 2016-06-21 - 2016-07-04
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034291529 — MEDH BANDHAN PRABHA DEVI S/O PREM SINGH | Completed | 4765200000 | 41416 | 2016-07-19 - 2016-08-08
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034291641 — MEDH BANDHAN ARVIND SINGH / PREM SINGH | Completed | 6099400000 | 58951 | 2016-07-26 - 2016-08-15
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/22012034291804 — BADAH TOK SHANTIDHAM BIJPURI | Completed | 1479000 | 897401.5 | 2016-09-06 - 2017-11-22
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002002/LD/22012034474612 — CHARAHAGAR BIJPURI | Ongoing | 750924.49 | 18456 | 2020-02-03 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002002/LD/22012034533542 — GAU CHARAGAH NIRMAN BIJPURI | Closed | 0 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702002002/LD/22012034543773 — GENHU KHARIDI UPARJAN KENDRA GRAM PANCHAYAT BIJPURI | Deleted | 0 | 0 | 2021-01-26 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/LD/22012034555411 — MEDH BANDAN SUNITA DEVI / SANTOSH SINGH | Closed | 38351.61 | 0 | 2021-01-21 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/LD/22012034555412 — MEDH BANDAN DHRAMVEER SINGH / VIRANDAVAN SINGH | Closed | 0 | 0 | 2021-01-21 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/LD/22012034555413 — MEDH BANDAN DHRAMVEER SINGH / VIRANDAVAN SINGH | Closed | 38351.61 | 0 | 2021-01-21 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/LD/22012034555752 — MED BANDHAN RAMVEER KE KHET PER | Completed | 38351.61 | 12738 | 2021-07-02 - 2021-12-28
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002002/LD/22012034961577 — CHARAGAH GAUSHAK KE PASS BIJPURI | Approved | 0 | 0 | 2025-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/245 — मेड बन्‍धान छोटे / मनीराम | Deleted | 16000 | 0 | 2010-12-29 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/272 — मेड बन्‍धान कार्य सरमन / खुशाल हरिजन | Completed | 19873 | 19764 | 2011-06-18 - 2011-07-08
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/285 — मेड बन्‍धान कार्य शिवप्रताप सिंह / तिलक सिंह | Completed | 10731 | 10370 | 2011-07-20 - 2011-08-03
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/312 — मेड बन्‍धान कार्य सोमता बेबा खुशाल बिजपुरी | Completed | 19873 | 9516 | 2011-10-18 - 2011-10-24
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/313 — मेड बन्‍धान कार्य गुटटे / मनीराम बिजपुरी | Completed | 34777 | 12444 | 2011-10-18 - 2011-10-24
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/33 — मेडबन्‍धान धनीराम/बीरशाय | Completed | 24000 | 17648 | 2009-08-27 - 2009-08-27
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1702002002/OP/9425891565 — NALA NIRMAN HARNAM SINGH KE MAKAN SE PUTTU SINGH KE MAKAN KI OR | Completed | 903000 | 662384 | 2017-01-17 - 2018-07-04
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002002/PG/9425895444 — KHEL MAIDAN KANYA PRATHMIK VIDHYALAY KE PASS | Completed | 353000 | 186863.7 | 2017-03-21 - 2017-08-10
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/17 — सी0सी0 रोड रामगोपाल सिंह के मकान से शिवराज सिंह के मकान तक | Completed | 293571 | 97678 | 2012-03-20 - 2012-10-31
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034158441 — c.c. road gajendra singh ke makan se sinnet singh | Completed | 133300 | 126580.28 | 2013-01-28 - 2013-06-17
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034211841 — C.C.ROAD SHIVSINGH KE MAKAN SE GANPAT KE MAKAN TAK | Completed | 181736 | 102521 | 2014-03-11 - 2015-08-10
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034211843 — C.C.ROAD KHAD WALE KUNWA SE PUTTU SINGH KE MAKAN K | Completed | 215842 | 131121 | 2014-03-11 - 2015-08-10
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034211846 — C.C.ROAD BAKHAR KI CHOUPAL SE DHAN SINGH KE MAKAN | Completed | 58224 | 37408 | 2014-03-11 - 2014-08-10
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034284090 — MAIN ROAD SE SHRIKRISHN KE MAKAN TAK C.C. ROAD NIRMAN | Completed | 126715.9 | 78583 | 2015-09-08 - 2016-01-28
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034288327 — C.C.ROAD NATHU PRAJAPATI KE MAKAN SE MARGHAT TAK | Completed | 204757 | 188134 | 2016-01-12 - 2016-05-09
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307363 — C.C.ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307365 — C.C ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307366 — C.C ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307369 — C.C ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307370 — C.C ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307371 — C.C ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307372 — C.C.ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034307373 — C.C.ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034308964 — C.C. ROAD | Deleted | 0 | 0 | 2016-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034326822 — CC ROAD HARIJAN BASTI SE KHAR KI OR | Deleted | 130700 | 0 | 2017-02-11 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034326904 — CC ROAD HARIZAN BASTI SE KHAR KI OR | Completed | 131000 | 69936 | 2017-02-28 - 2017-05-30
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034347671 — SUDOOR SAMPARK SADAK NIRMAN BIJPURI SE BHATMASPURA KI OR | Completed | 1300000 | 1020079.38 | 2017-08-08 - 2018-09-25
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034348646 — CC ROAD AND NALI DHURUV KE MAKAN SE RAMLAKHAN TOMAR HOTE HUA UTTAM KE GHAR KI OR | Completed | 49000 | 49536 | 2017-08-08 - 2017-09-27
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034349666 — CC ROAD AND NALI NIRMAN NARIYARE SE HARIZAN BASTI KI OR | Completed | 55300 | 53664 | 2017-08-22 - 2017-10-15
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034367837 — CC ROAD HARIZAN BASTI SARMAN KE DAWAJE SE RAMSHAH KE GHAR KI OR | Deleted | 33000 | 0 | 2018-01-23 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034374266 — cc road | Closed | 0 | 0 | 2017-10-02 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034380367 — SUDOOR SAMPARK SADAK BIJPURI SE CHANDUPURA KI OR | Deleted | 1100000 | 0 | 2017-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034381136 — CC ROAD DR. VISHVANATH KE MAKAN SE RANVIJAY KE MAKAN KI OR | Deleted | 69000 | 0 | 2018-01-16 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034381380 — CC ROAD SHIVRAJ PARIHAR KE GHAR SE NARAYAN SINGH KE MAKAN KI OR | Deleted | 23000 | 0 | 2017-02-18 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034381381 — CC ROAD GANESH KE DWAR SE NALA KI OR | Deleted | 23000 | 0 | 2017-02-18 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034386790 — Cc Road Dr. Vishvnath Ke Mkan Se Ranvijay Ke Ghar Ki Aur Bijpuri | Completed | 69000 | 62640 | 2018-04-10 - 2018-05-12
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034388926 — CC ROAD SHIVRAJ PARIHAR KE GHAR SE NARAYAN SINGH KE MAKAN KI OR | Closed | 23000 | 0 | 2017-02-18 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034388927 — CC ROAD SARMAN KE DARWAJE SE RAM SAHAY KE GHAR KI OR HARIZAN BASTI | Completed | 33000 | 28710 | 2019-02-26 - 2019-03-21
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034390614 — CC ROAD RISHI CHAUHAN KE MAKAN SE HARIZAN BASTI KI OR | Completed | 60000 | 60030 | 2018-09-11 - 2018-11-25
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034391716 — CC ROAD GAJENDRA KE MAKAN SE MAHAVEER KE MAKAN KI OR | Completed | 42000 | 30276 | 2018-12-18 - 2019-03-10
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034397765 — Greval Road Satram Ke Makan se puliya ki or | Closed | 150000 | 0 | 2018-04-30 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034436224 — ग्रेवल रोड निर्माण सतराम के मकान से पुलिया की और | Closed | 550000 | 0 | 2018-04-30 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034442695 — cc road | Closed | 0 | 0 | 2019-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034477430 — GRAVAL ROAD BIJPURI SE CHANDUPURA KI OR | Completed | 1282505.16 | 1105988 | 2020-02-03 - 2020-12-15
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034477439 — GRAVAL ROAD GRAVAL RISHI ASHRAM SE CHANDUPURA MOJE KI OR | Closed | 0 | 0 | 2019-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034522132 — GRAVAL ROAD SAHDEV SINGH KE MAKAN SE SHAMSHAN GHAT HOTE HUYE GAUSHALA KI OR | Completed | 2263402.01 | 2023749.88 | 2020-06-02 - 2021-02-05
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034526290 — CC ROAD SIYARAM KE MAKAN SE RAMNARESH SINGH KE GHAR KI OR | Completed | 74000 | 71820 | 2020-09-25 - 2021-01-19
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034526722 — SUDUR SADAK GALAV RISHI MANDIR SE GOPALPURA DONCHARA PAHUCH MARG EVM VISHAMBAR SINGH KE KUA KI OR | Completed | 2478480.13 | 2394252.23 | 2020-07-23 - 2021-03-15
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034528337 — KHET SADAK NIRMAN GWALAB RISHI MANDIR SE VISHAL SINGH KE KUA KI OR | Closed | 0 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034528339 — KHET SADAK NIRMAN NAVIN TALAB SE RAMBAHADUR SINGH KE KUA KI OR | Closed | 0 | 0 | 2020-01-26 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034561205 — SUDOOR SAMPARK SADAK NIRMAN BISHAMBHAR KE KUA SE GOPALPURA DHONCHARA MARG KI OR | Ongoing | 1461517.34 | 1141069.92 | 2021-03-11 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034603953 — PEVAR BLOCK GALAV RISHI PARK EVM SAMUDAYAK BHAVAN KE SAMNE | Closed | 0 | 0 | 2021-10-02 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677944 — CONSTRUCTION OF SOKHTA SANGRAM SINGH KE MAKAN KE SAMNE | Completed | 10000 | 7344 | 2022-12-22 - 2025-04-17
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677957 — CONSTRUCTION OF SOKHTA HARNARAYAN SINGH KE DWAR PER | Completed | 10000 | 8568 | 2022-12-22 - 2024-11-06
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677968 — CONSTRUCTION OF SAMUDAYAK SOKHTA DURGA SINGH / RAMCHARAN SINGH KE DWAR PER | Completed | 10000 | 6120 | 2022-12-22 - 2023-05-02
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677969 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMSANEHI KE DWAR PER | Completed | 10000 | 6120 | 2022-12-22 - 2023-05-01
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034678983 — CONSTRUCTION OF SAMUDAYAK SOKHTA KANCHAN SINGH / BADRI SINGH KE GHAR KE PASS | Completed | 10000 | 8160 | 2022-12-22 - 2023-05-01
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034678989 — CONSTRUCTION OF SAMUDAYAK SOKHTA PRABHU SINGH / NATHU SINGH DWAR KE PASS | Closed | 10000 | 0 | 2022-11-22 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679709 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAJESH SINGH / RAMSWAROOP SINGH KE MAKAN KE PASS | Closed | 10000 | 0 | 2022-11-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679713 — CONSTRUCTION OF SAMUDAYAK SOKHTA RANVEER KE DWAR PER | Closed | 10000 | 0 | 2022-11-11 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679718 — CONSTRUCTION OF SAMUDAYAK SOKHTA JALEV SINGH KE PASHUVASA PER | Closed | 10000 | 0 | 2022-11-22 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679725 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMCHANDRA KE DWAR PER | Completed | 10000 | 9792 | 2022-12-30 - 2023-05-01
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679808 — CONSTRUCTION OF SAMUDAYAK SOKHTA JOGENDRA SINGH / MAHESH SINGH KE MAKAN KE PASS | Completed | 10000 | 8568 | 2022-12-30 - 2023-05-01
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034682054 — CNSTRUCTION OF SAMUDAYAK SOKHTA RAJESH SINGH KE MAKAN KE PASS | Closed | 10000 | 0 | 2022-11-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034682056 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMVEER KE DWAR PER | Closed | 10000 | 0 | 2022-11-22 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44793 — MARYADA ABHIYAN PARASURAM SINGH / ATIBAL SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44796 — MARYADA ABHIYAN MEERA DEVI / SATYARAM SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44801 — MARYADA ABHIYAN BHARAT SINGH / RAJENDRA SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44803 — MARYADA ABHIYAN SHIVRAM SINGH / KADAR SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44832 — MARYADA ABHIYAN MUNNI DEVI / BRIJRAJ SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44900 — MARYADA ABHIYAN DIGAMBAR / MAJBOOT SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44903 — MARYADA ABHIYAN ANANT SINGH / AHIVARAN SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44905 — MARYADA ABHIYAN CHOTE SINGH / HARNAM SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44908 — MARYADA ABHIYAN RAM PRATAP SINGH / RAJENDRA SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44910 — MARYADA ABHIYAN NARESH SINGH / MOHKAM SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44913 — MARYADA ABHIYAN RAM KUMAR SINGH / HARI SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44915 — MARYADA ABHIYAN SHIVRAJ SINGH / RAGHUVEER SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44918 — MARYADA ABHIYAN PRAYAG SINGH / RAM PRASAD SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002002/RS/44920 — MARYADA ABHIYAN BHAGWAN SINGH / PHOOL SINGH | Deleted | 4500 | 0 | 2012-08-15 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002002/WC/22 — सोख्‍ता गडडा निर्माण | Completed | 0 | 14763 | 2009-07-10 - 2009-07-12
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/WC/22012034294161 — TALAB GAHARIKARAN | Deleted | 98000 | 0 | 2016-05-24 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/WC/22012034324322 — NAVIN TALAB NIRMAN MARGHAT KE PASS BIJPURI | Completed | 188000 | 148608 | 2017-05-16 - 2017-08-12
BHIND / BHIND / BIJPURI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/WC/22012034387740 — तालाब जीर्णोद्धार बिजपुरी | Completed | 418000 | 383039.54 | 2018-05-01 - 2019-08-05
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034389893 — नवीन तालाब निर्माण बिजपुरी | Completed | 2446000 | 2225900 | 2018-07-03 - 2020-08-16
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034557577 — CHECK DEM KHARAUA PER SHANTUN SINGH KE KHET KE PASS | Completed | 1422379.56 | 1377920 | 2020-06-26 - 2021-04-15
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034603525 — TALAB SOUNDRIKARAN GAUSHALA KE PASS BIJPURI | Completed | 1459893.21 | 1056230 | 2021-02-22 - 2023-04-27
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034616000 — NAVEEN TALAB NIRMAN SARAVJANIK SHAUCHALAY KE PASS | Deleted | 0 | 0 | 2021-02-15 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034617943 — CHEK DAM NIRMAN RAMVEER KE KHET KE PASS | Deleted | 1181137.17 | 0 | 2021-02-15 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034624180 — CHEK DAM NIRMAN RAMVEER KE KHET KE PAS | Completed | 1330722.07 | 974402 | 2021-04-15 - 2023-04-27
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034624239 — CHECK DEM NIRMAN REPUDHAMAN SINGH KE KHET KE PASS | Deleted | 0 | 0 | 2021-01-26 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034728388 — TALAB NIRMAN GALAB RISHI ASHRAM KE SAMNE BIJPURI | Completed | 1156795 | 962992 | 2021-08-14 - 2023-04-27
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702002002/WC/22012034759994 — ROOF WATER HARVESTING SAMUDAYAK BHAVAN BIJPURI | Closed | 32079.25 | 0 | 2021-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034805197 — CHECK DAM NIRMAN ARVIND KE KHET KE PASS | Completed | 221000 | 100852 | 2021-10-14 - 2023-07-07
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034842081 — CHECK DAM NIRMAN YOGRAM KE KHET KE SAMNE | Closed | 0 | 0 | 2021-08-15 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034863261 — CHECK DAM NIRMAN BADE TALAB KE ANGE BIJPURI | Deleted | 1124670 | 0 | 2021-10-02 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034897157 — NAVEEN TALAB JIRDODHAR KARYA BIJPURI | Deleted | 0 | 0 | 2021-10-02 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002002/WC/22012034910369 — NAVEEN TALAB NIRMAN RAMVEER KE KHET KE PASS | Deleted | 0 | 0 | 2021-10-02 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034913706 — NAVEEN TALAB NIRMAN RAMVEER KE KHET KE PASS | Deleted | 0 | 0 | 2022-01-24 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034917012 — TALAB JIRDODDHAR KARYA BIJPURI | Closed | 0 | 0 | 2022-01-24 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034917013 — NAVEEN TALAB NIRMAN RAMVEER KE KHET KE PASS | Closed | 1497595.89 | 0 | 2022-01-24 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034934492 — CHECK DAM NIRMAN TALAB KE PASS | Completed | 152000 | 79152 | 2022-04-25 - 2025-05-08
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/WC/22012034953681 — AMRAT SAROVER NIRMAN RAMVEER KE KHET KE PASS | Completed | 2492407.95 | 1097842.94 | 2022-04-29 - 2025-05-13
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034955676 — CONSTRUCTION OF CC CHECK DAM FOR COMMUNITY RAMBAHADUR KE KHET KE PASS | Closed | 0 | 0 | 2022-04-14 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/WC/22012035030370 — NAVEEN TALAB NIRMAN JALEV SINGH KE KHET KE PASS | Closed | 0 | 0 | 2022-10-02 -
BHIND / BHIND / BIJPURI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012035049550 — CHEAK DEM NIRMAN JALEW SINGH KE KHET KE PASS | Ongoing | 1483456.14 | 1327164 | 2023-06-13 -