## Work List
Exported on: 2026-10-07 14:25:20
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BIJPURI
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Prduction of building material (Comm) / Production of building material for Community | Construction of Other Community Building/Assets | 1702002002/AV/22012034469274 — GAUSHALA NIRMAN KARYA BIJPURI | Completed | 2771628.29 | 2729287.8 | 2019-11-07 | 2020-12-05
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002002/AV/22012034515161 — SHANTIDHAM NIRMAN GRAVAL ROAD KE PAA | Completed | 194312.08 | 175838.4 | 2020-09-19 | 2021-12-28
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002002/AV/22012034550850 — PULIYA NIRMAN KHAND KI PULUYA KE PASS BIJPURI | Completed | 1499000 | 1262320 | 2021-03-01 | 2025-05-09
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702002002/AV/22012034562673 — GENHU UPARJAN CHAUTRA NIRMAN BIJPURI | Completed | 804741.09 | 693591 | 2021-06-11 | 2022-11-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002002/AV/22012034587018 — PARK NIRMAN GALAV RISHI MANDIR KE SAMNE BIJPURI | Completed | 800000 | 701972 | 2021-08-16 | 2024-11-06
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002002/AV/22012034587019 — VENTED CAUSEWAY CONSTRUCTION BISHAMBHAR KE KHET KE PASS | Completed | 99000 | 52368 | 2021-08-16 | 2024-10-23
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/130 — निर्मल वाटिका कार्य रामलाल / मनीराम | Completed | 4000 | 5796 | 2011-07-10 | 2011-07-16
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/131 — निर्मल वाटिका कार्य सुरेन्‍द्र सिंह / द्वारिका सिंह | Completed | 4600 | 5796 | 2011-07-10 | 2011-07-16
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/132 — निर्मल वाटिका कार्य जयकुमार सिंह / मुलायम सिह | Completed | 4600 | 5796 | 2011-07-10 | 2011-07-16
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/137 — निर्मल वाटिका कार्य धर्मसिंह / बिन्‍द्रावन सिंह | Completed | 4302 | 5796 | 2011-07-14 | 2011-08-11
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/138 — निर्मल वाटिका कार्य क्रपाल सिंह / कायम सिंह | Completed | 4302 | 5796 | 2011-07-14 | 2011-08-11
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002002/DP/139 — निर्मल वाटिका कार्य सत्‍यराम / रामजीलाल | Completed | 4302 | 5796 | 2011-07-14 | 2011-08-11
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002002/FP/22012034369258 — RESECTIONING OF NALA CHECK DAM BIJPURI SE GRAM PANCHAYAT GOARA SEEMA KI OR | Completed | 1408756.83 | 735152 | 2021-03-01 | 2025-04-17
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002002/FP/22012034369309 — NALA NIRMAN RAMVEER KE KHET KE PASS SE GOLE KE PURA KI | Completed | 1458756.83 | 482441 | 2021-03-01 | 2025-05-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702002002/IC/22012034388539 — BAMBA AVM KOOL MARAMMAT NIRMAN KARYA BIJPURI MOJA | Completed | 1492855.28 | 931394 | 2020-12-25 | 2025-05-08
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002002/IF/22012034352222 — BRAKSHA ROPAN KARYA GWALA RISHI ASHRAM | Completed | 335000 | 56772 | 2017-06-20 | 2021-11-23
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470201 — KHET TALAB RIPUDAN / PREM SINGH | Completed | 107000 | 94678 | 2019-03-07 | 2019-11-15
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470208 — KHET TALAB RAMVEER SINGH / PREM SINGH | Completed | 107000 | 89388 | 2019-03-07 | 2019-11-15
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470216 — KHET TALAB ARVINDRA SINGH / PREM SINGH | Completed | 107000 | 95910 | 2019-03-07 | 2019-10-05
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470220 — KHAT TALAB SANGEETA DEVI / SHANTANU SINGH | Completed | 107000 | 91148 | 2019-03-07 | 2019-10-22
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034470224 — KHET TALAB VISHAMBHAR SINGH / MAHARAJ SINGH | Completed | 107000 | 73290 | 2019-03-07 | 2020-07-15
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034584044 — PASHU SHED RIPUDYAN SINGH / PREM SINGH | Completed | 101273.16 | 92437.5 | 2020-08-06 | 2021-03-27
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034584046 — PASHU SHED DEEPENDRA SINGH / RAMVIR | Completed | 101273.16 | 92437.5 | 2020-08-06 | 2021-03-27
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002002/IF/22012034610431 — PASHU SHED NIRMAN RAMVIR SINGH / PREMSINGH | Completed | 101273.16 | 93007.5 | 2020-09-26 | 2021-01-05
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/IF/22012034770417 — KHET TALAB RIPUDHIMAN / PREM SINGH KE KHET PER | Completed | 337715.44 | 252444 | 2021-06-24 | 2022-01-10
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/134114 — Construction of IAY House -IAY REG. NO. MP-02-002-002-001/104 | Completed | 14310 | 3006 | 2016-08-02 | 2016-08-15
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002002/IF/IAY/196828 — Construction of IAY House -IAY REG. NO. MP-02-002-002-001/50 | Completed | 14310 | 6012 | 2016-08-09 | 2016-08-24
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034261643 — MEDH BANDHAN RAMVEER SINGH S/O PREM SINGH | Completed | 27000 | 24662 | 2016-03-22 | 2016-07-11
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034266354 — MEDH BANDAN VISHAMBER SINGH / MAHARAJ SINGH | Completed | 76243 | 70975 | 2016-07-05 | 2016-08-01
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034268916 — MEDH BANDHAN RAMBHADUR SINGH S/O MANRAKHAN SINGH | Completed | 3812100000 | 35070 | 2016-08-16 | 2016-08-29
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034274984 — MEDH BANDHAN SHANTANU SINGH / PREM SINGH | Completed | 27160 | 26052 | 2016-06-07 | 2016-06-21
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034276538 — MEDH BANDHAN RIPUDUMAN SINGH / PREM SINGH | Completed | 27160 | 21042 | 2016-06-21 | 2016-07-04
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034291529 — MEDH BANDHAN PRABHA DEVI S/O PREM SINGH | Completed | 4765200000 | 41416 | 2016-07-19 | 2016-08-08
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002002/LD/22012034291641 — MEDH BANDHAN ARVIND SINGH / PREM SINGH | Completed | 6099400000 | 58951 | 2016-07-26 | 2016-08-15
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/22012034291804 — BADAH TOK SHANTIDHAM BIJPURI | Completed | 1479000 | 897401.5 | 2016-09-06 | 2017-11-22
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/LD/22012034555752 — MED BANDHAN RAMVEER KE KHET PER | Completed | 38351.61 | 12738 | 2021-07-02 | 2021-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/272 — मेड बन्‍धान कार्य सरमन / खुशाल हरिजन | Completed | 19873 | 19764 | 2011-06-18 | 2011-07-08
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/285 — मेड बन्‍धान कार्य शिवप्रताप सिंह / तिलक सिंह | Completed | 10731 | 10370 | 2011-07-20 | 2011-08-03
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/312 — मेड बन्‍धान कार्य सोमता बेबा खुशाल बिजपुरी | Completed | 19873 | 9516 | 2011-10-18 | 2011-10-24
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/313 — मेड बन्‍धान कार्य गुटटे / मनीराम बिजपुरी | Completed | 34777 | 12444 | 2011-10-18 | 2011-10-24
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002002/LD/33 — मेडबन्‍धान धनीराम/बीरशाय | Completed | 24000 | 17648 | 2009-08-27 | 2009-08-27
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Gully Plug / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1702002002/OP/9425891565 — NALA NIRMAN HARNAM SINGH KE MAKAN SE PUTTU SINGH KE MAKAN KI OR | Completed | 903000 | 662384 | 2017-01-17 | 2018-07-04
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002002/PG/9425895444 — KHEL MAIDAN KANYA PRATHMIK VIDHYALAY KE PASS | Completed | 353000 | 186863.7 | 2017-03-21 | 2017-08-10
BHIND / BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/17 — सी0सी0 रोड रामगोपाल सिंह के मकान से शिवराज सिंह के मकान तक | Completed | 293571 | 97678 | 2012-03-20 | 2012-10-31
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034158441 — c.c. road gajendra singh ke makan se sinnet singh | Completed | 133300 | 126580.28 | 2013-01-28 | 2013-06-17
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034211841 — C.C.ROAD SHIVSINGH KE MAKAN SE GANPAT KE MAKAN TAK | Completed | 181736 | 102521 | 2014-03-11 | 2015-08-10
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034211843 — C.C.ROAD KHAD WALE KUNWA SE PUTTU SINGH KE MAKAN K | Completed | 215842 | 131121 | 2014-03-11 | 2015-08-10
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034211846 — C.C.ROAD BAKHAR KI CHOUPAL SE DHAN SINGH KE MAKAN | Completed | 58224 | 37408 | 2014-03-11 | 2014-08-10
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034284090 — MAIN ROAD SE SHRIKRISHN KE MAKAN TAK C.C. ROAD NIRMAN | Completed | 126715.9 | 78583 | 2015-09-08 | 2016-01-28
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034288327 — C.C.ROAD NATHU PRAJAPATI KE MAKAN SE MARGHAT TAK | Completed | 204757 | 188134 | 2016-01-12 | 2016-05-09
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034326904 — CC ROAD HARIZAN BASTI SE KHAR KI OR | Completed | 131000 | 69936 | 2017-02-28 | 2017-05-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034347671 — SUDOOR SAMPARK SADAK NIRMAN BIJPURI SE BHATMASPURA KI OR | Completed | 1300000 | 1020079.38 | 2017-08-08 | 2018-09-25
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034348646 — CC ROAD AND NALI DHURUV KE MAKAN SE RAMLAKHAN TOMAR HOTE HUA UTTAM KE GHAR KI OR | Completed | 49000 | 49536 | 2017-08-08 | 2017-09-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034349666 — CC ROAD AND NALI NIRMAN NARIYARE SE HARIZAN BASTI KI OR | Completed | 55300 | 53664 | 2017-08-22 | 2017-10-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034386790 — Cc Road Dr. Vishvnath Ke Mkan Se Ranvijay Ke Ghar Ki Aur Bijpuri | Completed | 69000 | 62640 | 2018-04-10 | 2018-05-12
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034388927 — CC ROAD SARMAN KE DARWAJE SE RAM SAHAY KE GHAR KI OR HARIZAN BASTI | Completed | 33000 | 28710 | 2019-02-26 | 2019-03-21
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034390614 — CC ROAD RISHI CHAUHAN KE MAKAN SE HARIZAN BASTI KI OR | Completed | 60000 | 60030 | 2018-09-11 | 2018-11-25
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034391716 — CC ROAD GAJENDRA KE MAKAN SE MAHAVEER KE MAKAN KI OR | Completed | 42000 | 30276 | 2018-12-18 | 2019-03-10
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034477430 — GRAVAL ROAD BIJPURI SE CHANDUPURA KI OR | Completed | 1282505.16 | 1105988 | 2020-02-03 | 2020-12-15
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034522132 — GRAVAL ROAD SAHDEV SINGH KE MAKAN SE SHAMSHAN GHAT HOTE HUYE GAUSHALA KI OR | Completed | 2263402.01 | 2023749.88 | 2020-06-02 | 2021-02-05
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002002/RC/22012034526290 — CC ROAD SIYARAM KE MAKAN SE RAMNARESH SINGH KE GHAR KI OR | Completed | 74000 | 71820 | 2020-09-25 | 2021-01-19
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002002/RC/22012034526722 — SUDUR SADAK GALAV RISHI MANDIR SE GOPALPURA DONCHARA PAHUCH MARG EVM VISHAMBAR SINGH KE KUA KI OR | Completed | 2478480.13 | 2394252.23 | 2020-07-23 | 2021-03-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677944 — CONSTRUCTION OF SOKHTA SANGRAM SINGH KE MAKAN KE SAMNE | Completed | 10000 | 7344 | 2022-12-22 | 2025-04-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677957 — CONSTRUCTION OF SOKHTA HARNARAYAN SINGH KE DWAR PER | Completed | 10000 | 8568 | 2022-12-22 | 2024-11-06
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677968 — CONSTRUCTION OF SAMUDAYAK SOKHTA DURGA SINGH / RAMCHARAN SINGH KE DWAR PER | Completed | 10000 | 6120 | 2022-12-22 | 2023-05-02
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034677969 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMSANEHI KE DWAR PER | Completed | 10000 | 6120 | 2022-12-22 | 2023-05-01
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034678983 — CONSTRUCTION OF SAMUDAYAK SOKHTA KANCHAN SINGH / BADRI SINGH KE GHAR KE PASS | Completed | 10000 | 8160 | 2022-12-22 | 2023-05-01
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679725 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMCHANDRA KE DWAR PER | Completed | 10000 | 9792 | 2022-12-30 | 2023-05-01
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002002/RS/22012034679808 — CONSTRUCTION OF SAMUDAYAK SOKHTA JOGENDRA SINGH / MAHESH SINGH KE MAKAN KE PASS | Completed | 10000 | 8568 | 2022-12-30 | 2023-05-01
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002002/WC/22 — सोख्‍ता गडडा निर्माण | Completed | 0 | 14763 | 2009-07-10 | 2009-07-12
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/WC/22012034324322 — NAVIN TALAB NIRMAN MARGHAT KE PASS BIJPURI | Completed | 188000 | 148608 | 2017-05-16 | 2017-08-12
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002002/WC/22012034387740 — तालाब जीर्णोद्धार बिजपुरी | Completed | 418000 | 383039.54 | 2018-05-01 | 2019-08-05
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034389893 — नवीन तालाब निर्माण बिजपुरी | Completed | 2446000 | 2225900 | 2018-07-03 | 2020-08-16
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034557577 — CHECK DEM KHARAUA PER SHANTUN SINGH KE KHET KE PASS | Completed | 1422379.56 | 1377920 | 2020-06-26 | 2021-04-15
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034603525 — TALAB SOUNDRIKARAN GAUSHALA KE PASS BIJPURI | Completed | 1459893.21 | 1056230 | 2021-02-22 | 2023-04-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034624180 — CHEK DAM NIRMAN RAMVEER KE KHET KE PAS | Completed | 1330722.07 | 974402 | 2021-04-15 | 2023-04-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002002/WC/22012034728388 — TALAB NIRMAN GALAB RISHI ASHRAM KE SAMNE BIJPURI | Completed | 1156795 | 962992 | 2021-08-14 | 2023-04-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034805197 — CHECK DAM NIRMAN ARVIND KE KHET KE PASS | Completed | 221000 | 100852 | 2021-10-14 | 2023-07-07
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002002/WC/22012034934492 — CHECK DAM NIRMAN TALAB KE PASS | Completed | 152000 | 79152 | 2022-04-25 | 2025-05-08
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002002/WC/22012034953681 — AMRAT SAROVER NIRMAN RAMVEER KE KHET KE PASS | Completed | 2492407.95 | 1097842.94 | 2022-04-29 | 2025-05-13