## Work List
Exported on: 2026-10-13 13:28:22
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: MANPURA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002011/AV/22012034371018 — SHANTIDHAM NIRMAN MANPURA | Completed | 245000 | 240046.28 | 2017-12-29 | 2018-02-25
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/100 — निर्मल वाटिका कार्य अमित / रामचन्‍द्र | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/101 — निर्मल वाटिका कार्य मातादीन / मिजाजी | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/102 — निर्मल वाटिका कार्य मुनेन्‍द्र / मंगल | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/103 — निर्मल वाटिका कार्य नरेश / अजुद्वी | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/104 — निर्मल वाटिका कार्य छोटेलाल / दुजू | Completed | 0 | 3591 | 2011-09-24 | 2011-12-21
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/85 — निर्मल वाटिका कार्य रामचरन / बच्‍छीलाल | Completed | 0 | 3686 | 2011-09-24 | 2012-01-04
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/86 — निर्मल वाटिका कार्य सूधरी / लाखन | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/87 — निर्मल वाटिका कार्य रामचरन / सुल्‍तान | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/88 — निर्मल वाटिका कार्य सुखराम / बुन्‍डन | Completed | 0 | 1398 | 2011-09-24 | 2011-12-21
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/89 — निर्मल वाटिका कार्य श्रीक्रष्‍ण / भजनलाल | Completed | 0 | 1398 | 2011-09-24 | 2011-12-21
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/90 — निर्मल वाटिका कार्य अमर सिंह / रतिभान | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/91 — निर्मल वाटिका कार्य रामचरन/ घमण्‍डी | Completed | 0 | 3591 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/92 — निर्मल वाटिका कार्य गिरेन्‍द्र / भजनलाल | Completed | 0 | 1398 | 2011-09-24 | 2011-12-21
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/93 — निर्मल वाटिका कार्य काशीप्रसाद / श्रीराम | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/94 — निर्मल वाटिका कार्य नाथू / जोहरी | Completed | 0 | 1398 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/95 — निर्मल वाटिका कार्य मोहनमन / सरमन | Completed | 0 | 1398 | 2011-09-24 | 2011-12-28
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/96 — निर्मल वाटिका कार्य कीरत / श्रीराम | Completed | 0 | 3591 | 2011-09-04 | 2011-12-21
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/97 — निर्मल वाटिका कार्य सतेन्‍द्र / तेहसीलदार | Completed | 0 | 3591 | 2011-09-24 | 2011-12-21
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/98 — निर्मल वाटिका कार्य जगदीश / झुण्‍डन | Completed | 0 | 3591 | 2011-09-24 | 2012-01-04
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702002011/DP/99 — निर्मल वाटिका कार्य अशोक / ग्‍याराम | Completed | 0 | 3591 | 2011-09-24 | 2011-12-21
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002011/FP/22012034363601 — NALI NIRMAN SCHOOL WALW TALAB KE PASS SE PANCHAYAT BHAVAN KI OR | Completed | 172000 | 52800 | 2019-09-21 | 2020-07-23
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002011/IF/22012034338528 — NADEP TANKA RAJENDRA SINGH NARWARIYA S/O JAGMOHAN | Completed | 118000 | 3096 | 2017-05-12 | 2017-06-15
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002011/IF/22012034352218 — BRAKSHAROPAN KARYA MUKTIDHAM MANPURA | Completed | 335000 | 41104 | 2017-06-23 | 2017-12-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034980635 — INDIVIDUAL SOAK PIT LAL SINGH / AMRAT SINGH | Completed | 1100 | 1020 | 2022-09-05 | 2022-11-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002011/IF/22012034980638 — INDIVIDUAL SOAK PIT DHARMENDRA / RANJEET SINGH | Completed | 1100 | 1020 | 2022-05-25 | 2024-11-07
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993673420 — pashu shed keshav singh s/o jaychandra singh | Completed | 115900 | 98251 | 2015-09-04 | 2016-02-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993674300 — pashu shed suresh singh s/o indal singh | Completed | 115900 | 90937 | 2015-09-11 | 2016-02-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993680545 — CATTLE SHED DHEER SINGH/ GYA SINGH | Completed | 115900 | 96161 | 2015-10-16 | 2016-02-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993680548 — CATTLE SHED LALVEER SINGH/ MALKHAN SINGH | Completed | 115900 | 97981 | 2015-10-16 | 2017-03-30
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993680549 — CATTLE SHED UMMED SINGH/ GYAN SINGH | Completed | 115900 | 99483.25 | 2015-10-16 | 2017-03-30
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700776 — Pashu Shed Rajveer singh S/o Homsingh | Completed | 116000 | 3816 | 2016-01-01 | 2016-04-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993700777 — Pashu Shed Sumendra Singh S/o Sughar Singh | Completed | 116000 | 3816 | 2016-01-01 | 2016-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701123 — Pashu Shed Jaymangal singh S/o Kanchan Singh | Completed | 116000 | 6678 | 2016-01-01 | 2016-04-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701166 — Pashu Shed Shivnath Singh S/O Bachchu Singh | Completed | 116000 | 3816 | 2016-01-08 | 2016-04-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701188 — Pashu Shed Radhamohan Sharma S/o Shyam Bihari Sharma | Completed | 116000 | 3816 | 2016-01-01 | 2016-08-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701190 — Pashu Shed Harendra Singh S/o Dev Singh Narwariya | Completed | 115900 | 6678 | 2016-01-01 | 2016-04-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002011/IF/9993701196 — Pashu Shed Sardar Singh S/o Sultan Singh | Completed | 116000 | 5724 | 2016-01-01 | 2016-04-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4326052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121345976 | Completed | 18360 | 18343 | 2022-08-10 | 2023-06-17
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4371361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142076179 | Completed | 18360 | 17136 | 2022-11-24 | 2023-09-06
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002011/IF/IAY/4384321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117870938 | Completed | 18360 | 17340 | 2022-12-15 | 2023-09-06
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/104 — मेढबन्‍धान कीरत / श्रीराम | Completed | 0 | 10596 | 2010-05-07 | 2010-05-07
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/105 — मेढबन्‍धान अशोक / रामसहाय | Completed | 0 | 3500 | 2010-08-18 | 2010-08-18
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002011/LD/3799395453 — MADBANDHAN RAJARAM / RAMSAHAY KE KHET MEIN | Completed | 18900 | 9782 | 2013-06-14 | 2013-07-20
BHIND / BHIND | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/9926709949 — MAD BANDHAN SURESH SINGH BHADOURIYA KE KHET PAR | Completed | 43300 | 30144 | 2014-06-27 | 2016-01-20
BHIND / BHIND | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002011/LD/9926709950 — MAD BANDHAN DHEER SINGH CHAUHAN KE KHET ME | Completed | 43300 | 28260 | 2014-06-20 | 2016-01-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034194860 — C.C.ROAD PURAN SINGH KE MAKAN SE BHOJRAJ KE MAKAN | Completed | 71268 | 68164 | 2013-12-20 | 2014-04-05
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034196532 — C.C.ROAD RAMBIHARI KE MAKAN SE HARIVILAS KE MAKAN | Completed | 85522 | 80896 | 2014-01-10 | 2014-05-20
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034219112 — C.C.RAOD BHOJRAJ KE MAKAN SE NAHAR SINGH KE MAKAN | Completed | 49545 | 49283 | 2014-05-30 | 2015-06-05
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002011/RC/22012034292430 — KHET SADAK YOJANA MAIN ROAD SE RAJENDRA KE GHAR TAK | Completed | 817867 | 59148 | 2016-01-08 | 2016-08-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034365826 — CC ROADASHOK GHAR SE SATENDRA GHAR TAK | Completed | 5700000000 | 59856 | 2017-11-03 | 2018-01-13
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034382735 — CC ROD SAROJ JOSHI GHAR SE SURESH GHAR TAK | Completed | 93000 | 92988 | 2018-02-23 | 2019-04-19
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034389598 — CC ROAD MEN ROAD SE BALMIK GHAR KI AUR | Completed | 93000 | 90828 | 2018-05-25 | 2018-12-29
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034432546 — cc rod prathmik shala manpura | Completed | 59000 | 59856 | 2018-12-18 | 2019-04-08
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034521949 — C C ROAD MANOJ SHARMA KE GHAR SE KULDEEP RAJAWAT KE GHAR KI AUR | Completed | 100000 | 88086 | 2020-05-25 | 2022-11-22
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034566805 — c.c.road nirman rathor mohalla me manpura | Completed | 81900 | 63690 | 2021-04-29 | 2022-11-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034608988 — CC ROAD SANJU KE MAKAN SE SITAMBER KE GHAR TAK SAMEER NAGAR | Completed | 17000 | 12240 | 2022-04-22 | 2022-11-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/22012034608989 — CC ROAD SHANTIDHAM ME MANPURA | Completed | 32000 | 33048 | 2022-06-03 | 2022-11-22
BHIND / BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002011/RC/45 — सी0सी0 रोड निर्माण बैजन्‍ती के मकान से रामबिहारी के मकान तक | Completed | 293308 | 72629 | 2012-03-22 | 2012-10-04
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002011/RS/22012034503067 — Samudayak Swachhta Toilatr Work Manpura | Completed | 43000 | 41184 | 2020-12-17 | 2022-11-22
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002011/RS/22012034525048 — SEGREGATION SHED NIRMAN MANPURA | Completed | 37000 | 27792 | 2021-06-17 | 2022-11-22
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of Panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002011/SK/9993649491 — Bharat Nirman Rajeev Gandhi Sewa Kendra,MANPURA | Completed | 200000 | 60888 | 2018-01-05 | 2018-02-15
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002011/WC/21 — सौकपिट निर्माण कार्य रामवरन नाई के हैण्‍डपम्‍प के पास | Completed | 14950 | 14565 | 2009-07-25 | 2009-07-25
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002011/WC/22012034325349 — TALAB MARAMMAT KARYA HAR KA LAT | Completed | 51000 | 16512 | 2017-05-19 | 2017-07-06
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002011/WC/22012034444215 — NAVEEN TALAB TARI KA PURA | Completed | 1068000 | 427680 | 2019-03-06 | 2019-12-23
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034934661 — talav jinudhar dhongada bala talav manpura | Completed | 42500 | 34272 | 2022-05-26 | 2024-08-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002011/WH/22012034934669 — TALAB JIRDODDHAR MARGHATI KA TALAB MANPURA | Completed | 42500 | 27234 | 2022-05-26 | 2025-05-13