## Work List
Exported on: 2026-10-01 05:29:18
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BILHORA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002016/AV/22012034370555 — SHANTIDHAM MOHAR SINGH KA PURA | Completed | 180000 | 179863.22 | 2018-02-15 | 2018-04-10
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002016/AV/4149 — Aanganbadi/Other Rural Infrastructure,BILHORA | Completed | 330000 | 329824 | 2015-12-10 | 2017-04-15
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1702002016/DP/22012034594892 — अमृत ​​वाटिका कार्य धूमगिर माता मंदिर के पास | Completed | 55847.4 | 26520 | 2023-08-20 | 2025-06-06
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002016/FP/22012034367515 — KACHCHA NALA NIRMAN KHAND KE NICHE SE BILHORA | Completed | 147617.91 | 142793 | 2020-10-06 | 2021-05-30
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Fisheries | Excavation of Pond / Construction of Community Water Harvesting Ponds | Fish Culture | 1702002016/FR/9993648848 — TALAB NIRMAN BILOHARA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002016/IF/22012034352838 — BARAKSHA ROPAN KARYA BILHORA | Deleted | 335000 | 0 | 2017-06-18
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002016/IF/22012034354169 — BRAKSHA ROPAN KARYA DHOOMAR GIRI MANDIR KE PASS BILHORA | Completed | 335000 | 80286 | 2017-07-06 | 2021-11-17
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002016/IF/22012034388459 — nadep tanka | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002016/IF/22012034980716 — KHET TALAB VIJAY KUMAR / DAMBARDAS KE KHET PER | Completed | 356340.1 | 227460 | 2022-05-26 | 2023-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002016/IF/22012034980723 — KHET TALAB KASTURI DEVI / VIJAY KUMAR KE KHET PER | Completed | 356340.1 | 218688 | 2022-05-26 | 2023-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002016/IF/22012035512445 — खेत तालाब निर्माण विजय कुमारके खेत पर बिल्होरा | New | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002016/IF/22012035512452 — खेत तालाब निर्माण विजय कुमारके खेत पर बिल्होरा | Ongoing | 450885.64 | 78300 | 2025-07-03
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725358 — PASHU SHED NIRMAN GUMAN | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725359 — PASHU SHED NIRMAN RAJESH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725360 — PASHU SHED NIRMAN RAJESH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725361 — PASHU SHED NIRMAN CHAKRAPAN SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725362 — PASHU SHED NIRMAN SARNAME SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725363 — PASHU SHED NIRMAN RAMCHARAN SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725364 — PASHU SHED NIRMAN SIYARAM SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725365 — PASHU SHED NIRMAN BHAWAR SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725366 — PASHU SHED NIRMAN BHAWAR SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725367 — PASHU SHED NIRMAN HARDAYAL | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725368 — PASHU SHED NIRMAN KEDAR SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725369 — PASHU SHED NIRMAN JAGMOHAN | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725370 — PASHU SHED NIRMAN NARENDRA SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725371 — PASHU SHED NIRMAN SUBED SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725372 — PASHU SHED NIRMAN KAPATAN SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725373 — PASHU SHED NIRMAN KESHAV SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725374 — PASHU SHED NIRMAN DWARIKA SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725375 — PASHU SHED NIRMAN JAYRAM SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725376 — PASHU SHED NIRMAN GAVALE | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725377 — PASHU SHED NIRMAN RAMPRAKASH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725378 — PASHU SHED NIRMAN RAJVEER SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725379 — PASHU SHED NIRMAN RAMLAKHAN | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725380 — PASHU SHED NIRMAN YATENDRA SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725381 — PASHU SHED NIRMAN SUBEDAR SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725382 — PASHU SHED NIRMAN RAJENDRA SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725383 — PASHU SHED NIRMAN JAMADAR SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725384 — PASHU SHED NIRMAN LOKMAN SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725385 — PASHU SHED NIRMAN RAGHUVEER SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725386 — PASHU SHED NIRMAN JANDEL SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725387 — PASHU SHED NIRMAN SINNTE SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002016/IF/9993725388 — PASHU SHED NIRMAN MAHESH SINGH | Closed | 0 | 0 | 2016-01-27
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002016/IF/IAY/1872859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5385220 | Completed | 15660 | 14616 | 2018-08-23 | 2019-01-15
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002016/IF/IAY/202955 — Construction of IAY House -IAY REG. NO. MP-02-002-016-001/44 | Completed | 15030 | 12692 | 2016-10-20 | 2018-08-23
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002016/IF/IAY/263566 — Construction of IAY House -IAY REG. NO. MP3216949 | Completed | 15030 | 15100 | 2017-01-26 | 2018-05-24
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002016/IF/IAY/4369764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105480350 | Completed | 18360 | 17901 | 2023-10-16 | 2024-07-18
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002016/IF/IAY/4380053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105480272 | Completed | 18360 | 18037 | 2023-01-05 | 2024-02-14
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002016/IF/IAY/4396012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106003352 | Completed | 19890 | 18564 | 2023-10-16 | 2025-06-06
BHIND / BHIND | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/1 — Earthen Bunding Hare Lal | Completed | 18000 | 16653 | 2009-02-02 | 2008-01-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/10 — मेड् बन्‍धान कार्य का नाम राजेश सिंह | Completed | 80000 | 0 | 2009-09-19 | 2009-06-15
BHIND / BHIND | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/11 — मेड् बन्‍धान कार्य का नाम बलराम जाटव | Completed | 0 | 0 | 2009-01-26 | 2009-01-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/12 — मेड् बंधान कार्य का नाम सियाराम चतुरी | Completed | 31000 | 4368 | 2009-07-24 | 2009-01-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/13 — मेड् बंधान कार्य का नाम वलराम / डिब्‍बे जाटव | Completed | 14000 | 8548 | 2009-06-26 | 2009-06-15
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/134 — मेढबंधान बिल्‍हारा मेवाराम / कुजी आदि | Completed | 55000 | 45900 | 2010-08-12 | 2010-08-12
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/14 — मेड् बंधान कार्य का नाम मुन्‍नीलाल/ दोलतराम | Completed | 16000 | 12558 | 2009-07-17 | 2008-01-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/15 — मेड बंधान बलराम मूगाराम का पुरा | Completed | 14000 | 8372 | 2009-08-19 | 2009-01-26
BHIND / BHIND | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/2 — मेढ् बंधान | Completed | 26000 | 5369 | 2009-02-27 | 2008-01-24
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/200 — मेड बन्‍धान कार्य सीयाराम / चतुरी | Completed | 19400 | 3000 | 2010-07-12 | 2010-07-12
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/208 — मेड बन्‍धान कार्य सुधामालाल | Completed | 24200 | 6500 | 2010-08-04 | 2010-08-04
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263568 — MED BANDHAN NIRMAN RAMSEVAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263569 — MED BANDHAN NIRMAN HARELAL | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263570 — MED BANDHAN NIRMAN BHAWAR SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263571 — MED BANDHAN NIRMAN GANGA SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263572 — MED BANDHAN NIRMAN CHAKRAPAN | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263573 — MED BANDHAN NIRMAN RAMCHARAN | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263574 — MED BANDHAN NIRMAN MANIRAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263575 — MED BANDHAN NIRMAN RAMLAKHAN | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263576 — MED BANDHAN NIRMAN BABURAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263577 — MED BANDHAN NIRMAN RAMKARAN | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263578 — MED BANDHAN NIRMAN RAMPRAKASH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263579 — MED BANDHAN NIRMAN BHAWAR SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263580 — MED BANDHAN NIRMAN RAMPRAKASH SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263581 — MED BANDHAN NIRMAN RAJVEER | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263582 — MED BANDHAN NIRMAN KEDAR | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263583 — MED BANDHAN NIRMAN SIYARAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263584 — MED BANDHAN NIRMAN KESHAV | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263585 — MED BANDHAN NIRMAN ITENDRA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263586 — MED BANDHAN NIRMAN LAKHAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263587 — MED BANDHAN NIRMAN RAJESH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263588 — MED BANDHAN NIRMAN HARDAYAL | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263589 — MED BANDHAN NIRMAN SUBEDAR SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263590 — MED BANDHAN NIRMAN MUNNA SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263591 — MED BANDHAN NIRMAN VIRENDRA SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263592 — MED BANDHAN NIRMAN GYAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263593 — MED BANDHAN NIRMAN ARJUN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263594 — MED BANDHAN NIRMAN DIBAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263595 — MED BANDHAN NIRMAN JAGDISH SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263596 — MED BANDHAN NIRMAN SUBED SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263597 — MED BANDHAN NIRMAN RADHESHYAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263598 — MED BANDHAN NIRMAN BABURAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263599 — MED BANDHAN NIRMAN HARIRAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263600 — MED BANDHAN NIRMAN PATIRAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263601 — MED BANDHAN NIRMAN BADELAL | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263602 — MED BANDHAN NIRMAN RADHAKRISHAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263603 — MED BANDHAN NIRMAN SINNET | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263604 — MED BANDHAN NIRMAN MURALI | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263605 — MED BANDHAN NIRMAN HUKUM SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263606 — MED BANDHAN NIRMAN JANDEL SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263607 — MED BANDHAN NIRMAN AMAR SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263608 — MED BANDHAN NIRMAN JAGRAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263609 — MED BANDHAN NIRMAN RAM SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263610 — MED BANDHAN NIRMAN BALRAM | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263611 — MED BANDHAN NIRMAN VINOD SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034263612 — MED BANDHAN NIRMAN RAJKUNWAR | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265302 — MED BANDHAN NIRMAN HAKIM SIGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265303 — MED BANDHAN NIRMAN BHAGWANT | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265304 — MED BANDHAN NIRMAN MUNSHI | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265305 — MED BANDHAN NIRMAN JANDEL SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265306 — MED BANDHAN NIRMAN NATHOO SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265307 — MED BANDHAN NIRMAN JAYRAM SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265308 — MED BANDHAN NIRMAN RAMHET SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265309 — MED BANDHAN NIRMAN YADUNATH SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265310 — MED BANDHAN NIRMAN DHAN SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/22012034265311 — MED BANDHAN NIRMAN RAMSWAROOP | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002016/LD/22012034316179 — SHANTIDHAM NIRMAN BILHORA | Completed | 180000 | 179003.22 | 2017-07-06 | 2017-09-30
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/231 — मेड बन्‍धान कार्य राधेश्‍याम / रामनाथ्‍ा | Completed | 17700 | 4800 | 2010-07-19 | 2010-07-19
BHIND / BHIND | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/3 — मेढ् बंधान रामशंकर सिंह | Completed | 26000 | 2912 | 2009-02-25 | 2008-01-24
BHIND / BHIND | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/4 — मेढ् बंधान मुन्‍नीलाल | Completed | 16500 | 546 | 2009-03-01 | 2008-01-24
BHIND / BHIND | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/5 — मेढ् बंधान मानपाल | Completed | 17000 | 6097 | 2009-03-01 | 2008-01-24
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/51 — मेड बन्‍धान रामलखन / लोकमन | Completed | 21266 | 13900 | 2010-06-28 | 2010-06-28
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/52 — मेड बन्‍धान चक्रपान बघेल | Completed | 24000 | 22600 | 2010-06-28 | 2010-06-28
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/53 — मेड बन्‍धान श्‍यामसिंह / जबर सिंह | Completed | 28483 | 20000 | 2010-07-24 | 2010-07-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002016/LD/9 — मेड् बंधान कार्य का नाम राम कुवंर , बलराम | Completed | 15000 | 6734 | 2009-08-04 | 2008-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002016/OP/9425889605 — NALA NIRMAN JAGDISH KE DWAR SE MEWARAM KE DWAR TAK OCHHAI PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002016/OP/9425889606 — NALA NIRMAN HARIJAN THOK MOHAR SINGH KA PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002016/OP/9425889607 — NALA NIRMAN MUGARAM KA PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002016/OP/9425889609 — SOKHHATA GADDA SCHOOL PAR HAEDPUMP KE PASS MUGARAM PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002016/OP/9425889796 — SOKHATA GADDA NIRMAN HEAD PUMP KE PASS | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002016/OP/9425889797 — BAUINDRI WALL NIRMAN SCHOOL PAR | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002016/OP/9425892881 — SHANTIDHAM MOHAR SINGH KA PURA | Deleted | 180000 | 0 | 2017-04-13
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002016/PG/9425888462 — KHEL MAIDAN BILOHARA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034158564 — c.c. road main road se amar ke darwaje tak | Completed | 46465 | 44778 | 2013-03-01 | 2013-07-17
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034158568 — c.c.raod subedar singh ke darwaje se sudama ke dar | Completed | 79658 | 72502 | 2013-03-01 | 2013-07-17
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034197946 — C.C.ROAD VIKESH SINGH KE DARWAJE SE RAGHUNATH SING | Completed | 85635 | 77352 | 2014-01-16 | 2015-08-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034206200 — C.C.ROAD MAIN ROAD SE GYAN SINGH KE DARWAJE TAK | Completed | 50408 | 45955 | 2014-03-13 | 2014-11-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034206202 — C.C.ROAD JILEDAR SINGH KE DWAR SE MAIN ROAD TAK | Completed | 92416 | 79083 | 2014-02-20 | 2016-01-28
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034220257 — C.C.ROAD BALRAM KE DWAR SE SHAUCHALAYA TAK | Completed | 50408 | 33622 | 2014-06-05 | 2016-01-28
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034224400 — C.C.ROAD MAIN ROAD SE VIRENDRA SINGH KE DWAR KI TARAF | Completed | 68755 | 61540 | 2014-07-17 | 2016-01-28
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034224403 — C.C.ROAD KASHIRAM KE MAKAN SE RAMRATAN KE GHAR TAK | Completed | 101821 | 57793 | 2014-07-17 | 2016-10-25
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034286191 — C.C.ROAD RAJESH SINGH KE MAKAN SE KUNWA KI AUR BILHORA | Completed | 84258 | 75056 | 2015-10-20 | 2016-06-05
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034286192 — C.C.ROAD DHAN SINGH KE DAREWAJE SE KUNWA KI AUR MUNGARAM KA PURA | Completed | 147450 | 144635 | 2015-10-22 | 2016-06-05
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306597 — CC ROAD NIRMAN GANGA SINGH KE GODA SE SCHOOL TAK MUGARAMPURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306598 — CC ROAD NIRMAN RAJESH KE GHAR KE PICHE SE BAIJANATH KE GHAR TAK MUGARAM PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306599 — CC ROAD NIRMAN KAMALESH KE GHAR KE SAMANE SE BHAWAR KE GHAR KE PICHHE TAK MUGARAMPURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306600 — CC ROAD NIRMAN RAGHUVEER KE GHAR KE SAMANE SE BHAWAR KE GHAR KE PICHE TAK KANHIPURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306601 — CC ROAD NIRMAN RAMPRAKASH KE DWAR SE SURENDRA KE DWAR TAK TAL KA PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306602 — CC ROAD NIRMAN SIRNAME KE DWAR SE CHAKRAPAN KE DWAR TAK MUGARAMPURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306603 — CC ROAD NIRMAN SUBEDAR KE MAKAN SE GODA TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306604 — CC ROAD NIRMAN MAIN ROAD SE SURESH KE MAKAN TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034306605 — CC ROAD NIRMAN JANDEL KE KUWA SE LAKHAN KE MAKAN KE AUR RAGHUVEER PURA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034306606 — MITTI SADAK NIRMAN MUKHHYA MARG SE MUGARAM PURA TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034306607 — MITTI SADAK NIRMAN KANAHI PURA SE GUDUPURA PAHUCH MARD TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034306608 — MITTI SADAK NIRMAN DHOOMGIRI SE MADAIYAN TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034306609 — MITTI SADAK NIRMAN GYAN SINGH KE KHET SE JASRAM KE KHET TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034306610 — MITTI SADAK NIRMAN JASRAM KE KHET SE RAMSEVAK KE KHET TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034306611 — MITTI SADAK NIRMAN MOHAR SINGH KE PURA SE CHATHAR TAK | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034307598 — CC ROAD NIRMAN RAMSIYA KE DWAR SE SCHOOL KI AUR MADAIYA | Deleted | 0 | 0 | 2016-01-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034333360 — CC ROAD SARNAM KE MAKAN SE TEEKARAM KE MAKAN TAK MUNGARAM PURA | Completed | 22200 | 22016 | 2017-11-02 | 2018-01-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034345276 — SUDOOR SAMPARK SADAK PM MAIN ROAD SE MOONGA RAM KA PURA KI OR | Completed | 750000 | 497806.19 | 2017-08-17 | 2017-12-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034352625 — CC ROAD BRAJMOHAHAN KE MAKAN SE DULARE KE MAKAN KI OR | Completed | 79700 | 76884 | 2017-11-02 | 2018-02-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034365607 — CC ROAD DHARMENDRA KE MAKAN SE KAMLESH KE MAKAN TAK MOONGARAM KA PURA | Completed | 55800 | 52288 | 2017-11-02 | 2018-01-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034378791 — CC ROAD RAMDAS / UDAYBHAN KE MAKAN SE MAIN ROAD TAK MOHAR SINGH KA PURA | Completed | 69000 | 69660 | 2018-02-15 | 2018-04-02
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034381777 — CC ROAD RAMCHARAN KE MAKAN SE KUA TAK | Completed | 51000 | 50634 | 2018-04-19 | 2018-06-15
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034383168 — SUDOOR SAMPARK SADAK GADDUPURA SE KANDHAIPURA TAK | Deleted | 750000 | 0 | 2017-03-27
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034387264 — CC ROAD SUBEDAR KE MAKAN SE KESHAV KE MAKAN KI OR | Completed | 47000 | 39324 | 2018-04-19 | 2018-05-25
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034387295 — CC ROAD RAMCHARAN KE MAKAN SE KUA TAK | Closed | 51000 | 0 | 2017-01-29
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034387304 — CC ROAD MAIN ROAD SE ANGANWADI BHAVAN TAK | Completed | 47000 | 39324 | 2018-04-19 | 2018-06-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034391571 — CC ROAD BALIRAM KE MAKAN SE RAMLAKHAN KE MAKAN TAK | Completed | 60000 | 59508 | 2018-08-09 | 2018-09-27
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034392264 — CC ROAD BHEEKAM KE MAKAN SE SCHOOL KI OR | Completed | 64000 | 21228 | 2018-08-16 | 2018-09-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034435240 — CC ROAD CHETRAM EVM GOVT PRI. SCHOOL SE BHAMAR EVM RADHESHYAM KE MAKAN KI OR MADAIYA | Completed | 93000 | 82080 | 2019-01-31 | 2019-04-25
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034435246 — CC ROAD HARI KE MAKAN SE RAMNARESH EVM SCHOOL KI OR PACHPENDA | Completed | 70000 | 68976 | 2019-02-07 | 2019-05-25
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034436510 — CC ROAD MAIN ROAD SE SUGHAR EVM PHULSAHAY KE MAKAN KI OR BHURE SINGH KA PURA | Completed | 56000 | 55780 | 2019-01-31 | 2019-05-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034442699 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034475929 — SUDOOR SAMPARK SADAK HAJURIPURA SE OJHAI KA PURA BILHORA | Completed | 1076399.22 | 932812.67 | 2020-01-11 | 2020-08-29
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002016/RC/22012034535457 — SUDOOR GRAM SAMPARK SADAK MOHAR SINGH KA PURA SE GOVT PRIMARI SCHOOL TAL KA PURA (PACHPENDA) TAK | Completed | 660771.01 | 594749.26 | 2020-09-03 | 2021-03-29
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034540782 — CC ROAD DHANIRAM SHAKYA KE MAKAN SE BAJRANG BALI MANDIR KI OR MOHAR SINGH KA PURA | Completed | 61000 | 51300 | 2020-10-06 | 2021-01-03
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034541428 — CC ROAD MAIN ROAD SE MEWATI BABA MANDIR KI OR BILHORA | Completed | 61000 | 51300 | 2020-10-06 | 2021-02-09
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034541434 — CC ROAD GOVT MS SCHOOL MUNGARAM KA PURA PARISAR ME GRAM MOONGARAM KA PURA | Completed | 77000 | 70680 | 2020-10-06 | 2021-03-03
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/22012034584981 — CC ROAD DHUMAVATI MATA MANDIR PARISAR ME | Ongoing | 119000 | 35126 | 2021-10-05
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002016/RC/63 — सी0सी0 रोड निर्माण मैन रोड से सुदामा के घर की तरफ | Completed | 79552 | 66424 | 2012-06-10 | 2013-02-28
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034670995 — CONSTRUCTION OF SAMUDAYAK SOKHTA LAKHA SINGH / JORDAR SINGH RAGHUVEER SINGH KA PURA | Completed | 10000 | 9792 | 2022-12-24 | 2023-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034678045 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAVINDRA SINGH RAGHUVEER SINGH KA PURA | Completed | 10000 | 8568 | 2022-12-24 | 2023-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034679792 — CONSTRUCTION OF SAMUDAYAK SOKHTA BASANT SINGH / RAMSWAROOP SINGH TAK KA PURA | Completed | 10000 | 9792 | 2022-12-19 | 2023-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034679796 — CONSTRUCTION OF SAMUDAYAK SOKHTA SHIVRATAN SINGH / RAJARAM TAL KA PURA | Completed | 10000 | 9792 | 2022-12-15 | 2023-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034679798 — CONSTRUCTION OF SAMUDAYAK SOKHTA SHYAMBALI SINGH / RAMESHWAR SINGH TAL KA PURA | Completed | 10000 | 9792 | 2022-12-19 | 2023-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034679802 — CONSTRUCTION OF SAMUDAYAK SOKHTA BEBA RAJKUMARI / KEDAR SINGH TAL KA PURA | Completed | 10000 | 8568 | 2022-12-26 | 2023-04-14
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002016/RS/22012034681568 — community toilet nirman karya bilohara | Completed | 43000 | 42908 | 2023-05-16 | 2024-10-23
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002016/RS/22012034681759 — COMMUNITY NADEP ARJUN SINGH BHADAURIYA S/O DEVI SINGH BHADAURIYA | Closed | 2000 | 0 | 2022-12-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685716 — community sokpit hardyal singh s/o nandram mogarampura | Closed | 10000 | 0 | 2023-07-04
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685730 — COMMUNITY SOKPIT NIRMAN PUSHPA DEVI W/O RAMSHARAN MOGARAMPURA | Completed | 10000 | 9945 | 2023-05-06 | 2023-07-11
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685734 — COMMUNITY SOKPIT NIRMAN RAGHUNATH SINGH S/O BABURAM | Completed | 10000 | 9945 | 2023-05-06 | 2023-07-11
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685738 — COMMUNITY SOKPIT NIRMAN TULARAM S/O RAMSANEHI MOHAR SINGH KA PURA | Completed | 10000 | 9945 | 2023-05-06 | 2023-07-11
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685739 — COMMUNITY SOKPIT NIRMAN MANISH S/O VINOD SINGH MOHAR SINGH KA PURA | Completed | 10000 | 9945 | 2023-07-11 | 2023-09-06
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685967 — COMMUNITY SOKPIT NIRMAN VITTI DEVI W/O LAKHAN SINGH MOHAR SINGH KA PURA | Completed | 10000 | 9945 | 2023-04-29 | 2023-07-11
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685969 — COMMUNITY SOKPIT NIRMAN YATENDRA SINGH S/O JASWANT SINGH MOHAR SINGH KA PURA | Completed | 10000 | 9945 | 2023-04-29 | 2023-07-11
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685972 — COMMUNITY SOKPIT NIRMAN JITENDRA SINGH S/O KESHAV SINGH MOHAR SINGH KA PURA | Completed | 10000 | 9945 | 2023-04-29 | 2023-07-11
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685975 — COMMUNITY SOKPIT NIRMAN ASHOK SINGH S/O PRAHALAD SINGH TAL KA PURA | Completed | 10000 | 9792 | 2023-02-15 | 2023-04-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002016/RS/22012034685978 — COMMUNITY SOKPIT NIRMAN UGRAPAL SINGH S/O RAJARAM SINGH TAL KA PURA | Completed | 10000 | 8568 | 2023-02-15 | 2023-10-16
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002016/WC/22012034394899 — NAVEEN TALAB NIRMAN MAIN ROAD KE PASS BILHORA | Completed | 690000 | 336505.64 | 2019-01-10 | 2019-04-03
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002016/WC/22012034474839 — TALAB GAHRIKARAN MANDIR KE PASS | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002016/WC/22012034551544 — TALAB GAHRIKARAN ROAD KE PASS | Completed | 211281.82 | 185637.93 | 2020-06-02 | 2020-08-29
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002016/WC/22012034585936 — TALAB GAHEIKARAN SHANTIDHAM KE PASS MOHAR SINGH KA PURA BILHORA | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002016/WC/22012034643090 — TALAB GAHRIKARAN SHANTIDHAM KE PASS | Completed | 172726.96 | 160962 | 2021-05-13 | 2021-10-15
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002016/WC/22012035037842 — TALAV NIRMAN KARY DHUMGIR MATA MANDIR KE PASS | Physically Completed | 1610883 | 815932 | 2023-07-30 | 2026-04-17
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002016/WC/33 — सोकपिट निर्माण शिक्षा गारंटी केन्‍द्र तालकापुरा | Completed | 5000 | 1092 | 2009-12-12 | 2009-12-12
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702/DP/9926690068 — Plantation | Completed | 204900 | 37987 | 2010-08-09 | 2016-08-24