## Work List
Exported on: 2026-10-25 18:56:26
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BHADAKUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702002021/AV/22012034504088 — KHEL MAIDAN MARGHAT KE PASS BHADAKUR | Completed | 215276.77 | 103740 | 2020-06-12 | 2021-11-10
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002021/AV/22012034548197 — SHANTIDHAM NIRMAN GADIYA BHADAKUR | Ongoing | 195535.43 | 14820 | 2021-03-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002021/AV/22012034653382 — naveen samudhyik bhavan nirman karya bhadakur | Closed | 0 | 0 | 2023-08-15
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002021/AV/22012034653432 — naveen samudhyik bhavan nirman karya bhadakur | Closed | 0 | 0 | 2023-08-15
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1702002021/AV/22012034653433 — naveen samudhyik bhavan nirman karya bhadakur | Ongoing | 200000 | 147003.12 | 2024-03-12
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002021/AV/3964 — Aanganbadi/Other Rural Infrastructure,BHADAKUR | Completed | 330000 | 323486 | 2015-11-18 | 2017-11-28
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002021/AV/4408 — ANGANWADI BHAWAN MARGHAT KE PASS | Completed | 330000 | 333288 | 2016-01-27 | 2017-11-28
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002021/AV/4409 — ANGANWADI BHAWAN GOPAL SINGH KE MAKAN KE PASS | Completed | 330000 | 304220 | 2016-01-27 | 2017-11-28
BHIND / BHIND | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1702002021/DP/22012034622256 — BRAKSHAROPAN KARYA ANGANWADI BHAVAN KE PASS | Approved | 0 | 0 | 2024-06-10
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1702002021/FP/1 — नाला निर्माण भदाकुर | Completed | 0 | 48922 | 2011-09-16 | 2016-08-24
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002021/IF/22012034300429 — NADEP COMPOST PIT RAJENDRA / SOBRAN | Completed | 11800 | 11206 | 2016-09-25 | 2016-10-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002021/IF/22012034300434 — NADEP COMPOST PIT VIJAY SINGH / NATHI SINGH | Completed | 11800 | 11006 | 2016-09-25 | 2016-10-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002021/IF/22012034300436 — NADEP COMPOST PIT RAM SINGH / ATIVAL | Completed | 11800 | 11206 | 2016-09-25 | 2016-10-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002021/IF/22012034300438 — NADEP COMPOST PIT DIVAKAR / RAJARAM | Completed | 11800 | 11006 | 2016-09-25 | 2016-10-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002021/IF/22012034300439 — NADEP COMPOST PIT MANOJ / AMAR SINGH | Completed | 11800 | 11006 | 2016-09-25 | 2016-10-20
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002021/IF/22012034352352 — VRIKSHAROPAN SHANTIDHAM KE PAS BHADAKUR | Completed | 335000 | 91332 | 2017-06-21 | 2021-11-23
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002021/IF/22012034352361 — VRIKSHAROPAN KARAY ANGANVADI BHAVAN KE PAS BHADAKUR | Completed | 335000 | 65896 | 2017-07-19 | 2021-11-23
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012034567310 — KHET TALAB RAJO DEVI KE KHET PER | Completed | 108814.67 | 84550 | 2020-06-27 | 2020-10-18
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012034642103 — KHET TALAB NIRMAN VRANDAWAN KE KHET PER | Completed | 110516.06 | 63690 | 2021-05-19 | 2025-07-24
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002021/IF/22012034773543 — MED BANDHAN PRATAP SINGH KE KHET PER | Closed | 30681.29 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002021/IF/22012034773544 — MED BANDHAN SADHU SINGH KE KHET PER | Closed | 30681.29 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002021/IF/22012034773547 — MED BANDHAN ASHOK SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002021/IF/22012035062119 — NAVEEN KHET TALAB NIRMAN KARYA BUDH SINGH S/O FOOL SINGH BHADAKUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002021/IF/22012035123798 — khet talab nirman karya basant singh ke khet par | Closed | 0 | 0 | 2023-04-14
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002021/IF/22012035123799 — khet talab nirman karya kok singh ke khet par bhadakur | Closed | 0 | 0 | 2023-04-14
BHIND / BHIND | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002021/IF/22012035123802 — khet talab nirman karya rani devi ke khet par | Completed | 386461.22 | 177207 | 2025-02-27 | 2026-03-03
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002021/IF/22012035300105 — NAVIN KHET TALAB DEVENDRA KE KHET PAR | Approved | 0 | 0 | 2024-06-08
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035319504 — Naveen khet talab kalyaan singh ke khet par | Completed | 450885.64 | 299106 | 2025-08-08 | 2026-04-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035369409 — नवीन खेत तालाब अजयपाल के खेत पर | Completed | 147621.16 | 104922 | 2025-04-30 | 2025-07-31
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035369500 — नवीन खेत तालाब विशुन पाल के खेत पर | Completed | 147621.16 | 103356 | 2025-04-30 | 2025-08-21
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035369552 — नवीन खेत तालाब विश्राम सिंह के खेत पर | Completed | 147621.16 | 104922 | 2025-04-30 | 2025-07-31
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035470422 — Naveen khet talab shyam singh ke khet par | Completed | 450885.64 | 303282 | 2025-05-12 | 2025-08-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035470470 — Naveen khet talab manoj singh ke khet par | Completed | 450885.64 | 300150 | 2025-05-12 | 2025-10-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035470987 — Naveen khet talab munni devi ke khet par | Completed | 450885.64 | 272484 | 2025-05-12 | 2026-04-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035471038 — Naveen khet talab Mahendra singh ke khet par | Completed | 450885.64 | 317376 | 2025-05-12 | 2025-08-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035471070 — Naveen khet talab parmal singh ke khet par | Completed | 450885.64 | 297540 | 2025-05-12 | 2025-08-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035471088 — Naveen khet talab arvind singh ke khet par | Completed | 450885.64 | 301977 | 2025-05-12 | 2026-04-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035566507 — Naveen khet talab buddh singh ke khet par | Completed | 450885.64 | 274050 | 2025-08-08 | 2026-04-23
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035566509 — Naveen khet talab Prahlad singh ke khet par | Completed | 450885.64 | 269874 | 2025-07-08 | 2026-04-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035566516 — Naveen khet talab satyaprakash singh ke khet par | Completed | 450885.64 | 301194 | 2025-07-02 | 2025-08-21
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035566524 — Naveen khet talab shivpal singh ke khet par | Completed | 450885.64 | 292842 | 2025-07-02 | 2025-10-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035566526 — Naveen khet talab dragpal singh ke khet par | Completed | 450885.64 | 302238 | 2025-07-08 | 2026-04-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035566528 — Naveen khet talab Shailesh singh ke khet par | Completed | 450885.64 | 288144 | 2025-07-02 | 2025-08-21
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035596304 — Naveen khet talab vratha devi ke khet par | Completed | 450885.64 | 241164 | 2025-08-26 | 2026-05-08
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035596309 — Naveen khet talab shyam ke khet par | Completed | 450885.64 | 294408 | 2025-08-26 | 2026-05-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002021/IF/22012035596311 — Naveen khet talab vinayk ke khet ke paas | Completed | 450885.64 | 227070 | 2025-09-19 | 2026-05-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993686483 — CATTLE SHED JABARSINGH/BASHANTSINGH | Completed | 115900 | 97023.01 | 2015-11-11 | 2016-08-31
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993686490 — CATTLE SHED SUNITA/RAMSARUP | Completed | 115900 | 99451.01 | 2015-11-11 | 2016-09-30
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993686493 — CATTLE SHED GAJENDRA/RAMBHAJAN | Completed | 115900 | 95602.01 | 2015-11-11 | 2016-09-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993691656 — CATTEL SHED SEETARAM/SHANKAR | Completed | 115900 | 101436.01 | 2015-12-16 | 2016-08-31
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993691660 — CATTEL SHED RAKSHAPAL/SAHDEV SINGH | Completed | 115900 | 86728.01 | 2015-11-23 | 2016-09-30
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993712430 — CATTEL SHED RADHESHYAM/RAMPRASAD | Completed | 115900 | 101030.01 | 2016-06-29 | 2016-09-30
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993715805 — CATTEL SHED AJAY SINGH / RAMNARESH SINGH | Deleted | 115900 | 0 | 2016-06-29
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993727812 — CATTEL SHED DIWAKAR / RAJARAM | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993727815 — CATTEL SHED SADAN / CHHOTE | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002021/IF/9993727816 — CATTEL SHED RAJENDRA / DEV SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002021/IF/IAY/199286 — Construction of IAY House -IAY REG. NO. MP-02-002-021-001/12 | Completed | 15030 | 4008 | 2016-07-19 | 2016-08-20
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002021/IF/IAY/3692999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105322687 | Physically Completed | 18360 | 17196 | 2022-11-24 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002021/IF/IAY/3693002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105322905 | Physically Completed | 18360 | 18084 | 2022-11-09 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002021/IF/IAY/3777731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125053623 | Physically Completed | 18360 | 17880 | 2022-11-09 | 2024-11-21
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/4518570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105297569 | Ongoing | 27000 | 22842 | 2025-02-21
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/4873679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125053246 | Physically Completed | 23490 | 18360 | 2025-02-12 | 2026-08-02
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/4874398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105297681 | Ongoing | 27000 | 18144 | 2025-01-31
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002021/IF/IAY/5620697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119637153 | Physically Completed | 23490 | 15660 | 2025-06-15 | 2026-02-28
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5620771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105985101 | Physically Completed | 23490 | 7830 | 2025-06-16 | 2026-08-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5620835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119637103 | Ongoing | 27000 | 9396 | 2025-08-12
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141337421 | Ongoing | 27000 | 12528 | 2025-07-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141342303 | Physically Completed | 27000 | 18792 | 2025-08-12 | 2026-10-04
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106186721 | Ongoing | 27000 | 17226 | 2025-06-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141345051 | Ongoing | 27000 | 9396 | 2025-08-12
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141338033 | Ongoing | 27000 | 14877 | 2025-06-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128062098 | Physically Completed | 23490 | 12528 | 2025-06-14 | 2026-08-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141342647 | Ongoing | 27000 | 10962 | 2025-06-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106194776 | Ongoing | 27000 | 12528 | 2025-07-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341608 | Ongoing | 27000 | 14094 | 2025-06-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124809313 | Ongoing | 27000 | 9396 | 2025-08-12
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141347794 | Physically Completed | 23490 | 15660 | 2025-08-12 | 2026-08-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5621760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141337034 | Ongoing | 27000 | 15660 | 2025-06-15
BHIND / BHIND | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5669882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105297364 | Ongoing | 27000 | 0 | 2026-05-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5682012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141344869 | Ongoing | 27000 | 14094 | 2025-08-12
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002021/IF/IAY/5688084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141343304 | Ongoing | 27000 | 7830 | 2025-09-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002021/LD/211 — मेड बन्‍धान कार्य श्री ग्‍याप्रसाद काछी भदाकुर | Deleted | 23000 | 0 | 2010-03-08
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002021/LD/22012034266084 — MED BANDHAN KRAPAL/PRSHURAM | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002021/LD/22012034266756 — MED BANDHAN MUNNI / TEJ SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002021/LD/22012034266758 — MED BANDHAN GOPAL / ENDAL SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002021/LD/22012034266760 — MED BANDHAN JOGENDRA / DEVENDRA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522200 — MED BANDHAN NIRMAN KISHUN SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522201 — MED BANDHAN NIRMAN BHAMAR SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522202 — MED BANDHAN NIRMAN VIRENDRA SINGH BAGHEL KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522203 — MED BANDHAN NIRMAN GANGA SINGH BAGHEL KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522204 — MED BANDHAN NIRMAN PRADEEP SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522205 — MED BANDHAN NIRMAN AJMER SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522206 — MED BANDHAN NIRMAN AJAY TOMAR KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034522207 — MED BANDHAN NIRMAN DARSHAN SINGH KE KHET PER | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552727 — MED BANDHAN KISHUN SINGH KE KHET PER | Completed | 30681.29 | 18528 | 2021-05-12 | 2021-12-03
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552729 — MED BANDHAN BHAMAR SINGH KE KHET PER | Completed | 30681.29 | 18528 | 2021-05-24 | 2021-12-03
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552730 — MED BANDHAN VIRENDRA SINGH BAGHEL KE KHET PER | Completed | 30681.29 | 25476 | 2021-05-12 | 2021-12-03
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552731 — MED BANDHAN GANGA SINGH BAGHEL KE KHET ER | Completed | 31448.32 | 27792 | 2021-08-28 | 2021-12-03
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552732 — MED BANDHAN PRADEEP SINGH KE KHET PER | Closed | 0 | 0 | 2021-01-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552733 — MED BANDHAN NIRMAN AJMER SINGH KE KHET PER | Closed | 30681.29 | 0 | 2021-01-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552735 — MED BANDHAN AJAY TOMAR KE KHET PER | Closed | 29849.18 | 0 | 2021-01-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034552736 — MED BANDHAN DARSHAN SINGH KE KHET PER | Deleted | 0 | 0 | 2021-01-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/LD/22012034556420 — मेड़ बंधान कार्य साधू सिंह के खेत पर | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1702002021/LD/22012034576397 — ma ki bagiya nirman kary | Closed | 0 | 0 | 2022-01-24
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1702002021/LD/22012034576398 — ma ki bagiya nirman kary | Closed | 9000 | 0 | 2022-01-24
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1702002021/LD/22012034576400 — ma ki bagiya nirman kary anganwadi bhadakur | Closed | 9000 | 0 | 2022-01-24
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002021/LD/22012034584527 — KACCHA NALA NIRMAN MAIN ROAD SE KODAR KI AUR | Completed | 553642 | 323476 | 2023-04-15 | 2025-05-12
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/LD/22012034591667 — naveen kachha nala nirman puliya se kasa ki aur bhadakur | Completed | 532520.4 | 446862 | 2023-09-29 | 2024-03-10
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1702002021/LD/22012034593742 — MERI MATI MERA GWAN BRAKSHAROPAN KARAY MANDIR EVAM PANCHAYAT BHAVAN KE PASS BHADAKUR | Completed | 55847.4 | 18564 | 2023-08-27 | 2025-05-08
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Infrastructure for Berkley composting / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/OP/9425891409 — SHANTI DHAM | Completed | 245000 | 206568.5 | 2017-01-25 | 2017-11-28
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002021/PG/22012034365774 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002021/PG/22012034366337 — play ground | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034206468 — C.C.ROAD PASHU ASHPATAL SE JAI SINGH KI MAKAN KI A | Completed | 124065 | 53292 | 2014-02-26 | 2014-05-26
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034206471 — C.C.ROAD KUNWAR SINGH KE MAKAN SE TALKI BAGHEL KE | Completed | 140606 | 95550 | 2014-02-26 | 2014-08-09
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034206474 — C.C.ROAD JAI SINGH KE MAKAN SE DHEER KE MAKAN KI A | Completed | 124065 | 47371 | 2014-02-26 | 2016-01-15
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034211780 — C.C.ROAD BHURE KE MAKAN SE CHOTI MATA MANDIR KI A | Completed | 66237 | 28598 | 2014-03-05 | 2014-06-19
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034211786 — C.C.ROAD LAJJARAM KE MAKAN SE RAJENDRA SINGH KE MA | Completed | 82796 | 16565 | 2014-03-05 | 2014-06-30
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034211790 — C.C.ROAD DINESH KE MAKAN SE MATHURI KE MAKAN KI AU | Completed | 82796 | 17733 | 2014-03-05 | 2014-06-30
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034211797 — C.C.ROAD PARVAT KE MAKAN SE BASUDEV KE MAKAN KI AU | Completed | 66237 | 17733 | 2014-03-05 | 2014-06-30
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034211802 — C.C.ROAD KUNWA SE DASHRATH KE MAKAN KI AUR | Completed | 82796 | 55731 | 2014-03-05 | 2015-12-22
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034288329 — C.C.ROAD BUDDHE KE MAKAN SE HANUMANT KI AUR | Completed | 127093 | 125946 | 2015-11-04 | 2016-08-31
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034298438 — C.C.ROAD NIRMAN RAVINDRA KE MAKAN SE RANCHHOR KE MAKAN KI OR | Completed | 211621 | 194153 | 2016-02-17 | 2016-09-30
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034308199 — C.C.ROAD NIRMAN KUAA SE JAWAR SINGH KE MAKAN KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034308205 — C.C.ROAD NIRMAN MAYA SINGH KE DWAR SE PULIYA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034308207 — MITTI BAJRIKARAN MIDDIL SCHOOL SE DAGA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034308210 — MITTI BAJRIKARAN UMARI ROAD SE POORAN KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034308212 — MITTI BAJRIKARAN GAMBHIR KE KUA SE PATHA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034308215 — MITTI BAJRIKARAN P/S PATHA SE KHAR KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034313539 — KHET SADAK YOJNA MIDIL SCHOOL SE DAGA KE SHER KI AUR | Deleted | 1435100 | 0 | 2016-06-08
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034316117 — c.c.road nirnan harijan basti dilliram balmik ke makan se ramsnehi | Completed | 75634 | 73698 | 2016-11-09 | 2017-01-31
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034316190 — c.c.road nirnan harijan basti surendra ke makan se ram singh ki or | Completed | 50976 | 50364 | 2016-11-23 | 2017-01-31
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034316192 — c.c.road nirnan harijan basti kallu ke dwar se sai baba ki or | Completed | 50976 | 48067 | 2016-11-23 | 2017-04-19
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034339474 — सुदूर सम्पर्क सड़क मुख्य मार्ग से भदाकुर गांव तक | Closed | 1080000 | 0 | 2017-05-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034339477 — सुदूर सम्पर्क सड़क शाला भवन से सुल्तान पूरा तक | Completed | 660000 | 195010 | 2017-06-06 | 2018-09-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034350265 — C. C ROAD sankar ji ke mandir se nagre baba tak | Completed | 48675 | 49536 | 2017-08-30 | 2017-10-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034350352 — c.c road ramgopal kushawah se beta master ke yeha tak | Completed | 39825 | 37152 | 2017-11-01 | 2018-01-23
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034350354 — c.c road sunil bhagel ke makan se rajkumar bhagel tak | Completed | 89828 | 88752 | 2017-11-01 | 2018-02-04
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034350363 — c.c road man singh bhagel se rameshvar bhagel tak | Completed | 39825 | 39216 | 2017-08-30 | 2017-10-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034350365 — c.c road gopal wali aangan wadi se kunaa tak | Completed | 31838 | 33024 | 2017-10-11 | 2019-03-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034350367 — c.c road gopal ke yeha se dashrath ki aur | Completed | 39825 | 40248 | 2017-11-01 | 2018-02-12
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034373928 — C C ROAD RAMPRASAD BAGHEL SE NEECHE KI OR | Completed | 56000 | 35088 | 2017-12-13 | 2018-03-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034373974 — C C ROAD GOPAL KE YANHA SE SANTOSH TAK | Completed | 295000 | 43344 | 2017-12-20 | 2024-03-04
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034388778 — C C ROAD PULIYA SE MAYARAM KI OR | Deleted | 70000 | 0 | 2018-05-09
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034389020 — C C ROAD RAVINDRA SE KOMAL KE GHAR KI OR | Completed | 28000 | 26100 | 2018-08-15 | 2024-03-04
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034389021 — C C ROAD SHYAMSUNDAR SE MAHESH KE GHAR KI OR | Completed | 11500 | 11484 | 2018-08-15 | 2024-03-04
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034389022 — C C ROAD PRATAP KE GHAR SE HANUMAN KI OR | Completed | 13000 | 12528 | 2018-10-10 | 2018-10-23
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034393521 — C C ROAD BALVEER SE VEERBHAN TAK | Completed | 39000 | 39672 | 2018-10-03 | 2021-10-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034393557 — C C ROAD JAIPRAKASH SE SUSHEELA KI OR | Completed | 18000 | 16704 | 2018-10-17 | 2018-11-01
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034394645 — C C ROAD PULIYA SE MAYARAM KI OR | Completed | 69000 | 54984 | 2018-12-07 | 2019-02-03
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034397673 — C C ROAD PULIYA SE MUNNA KHAN TAK | Completed | 140000 | 126672 | 2018-12-19 | 2019-02-23
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034433532 — C C ROAD MAIN ROAD SE MANOHAR KI OR | Completed | 28000 | 28800 | 2019-08-07 | 2021-03-07
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034442691 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034447761 — C C ROAD BAJRANGBALEE MANDIR SE PUSHKAL TAK | Ongoing | 70000 | 522 | 2019-03-09
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034447768 — C C ROAD POORAN KE DUAR SE SWASTHYA KENDRA KI OR | Closed | 84000 | 0 | 2017-04-16
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034447778 — C C CHITRA KUAA SE DHEER SINGH KE TAK | Completed | 95000 | 92214 | 2019-03-09 | 2021-07-03
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034463202 — C C ROAD SURJAN KE DUAR SE KANJU KE MAKAN TAK | Closed | 19000 | 0 | 2017-04-16
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702002021/RC/22012034530538 — SUDOOR SAMPARK SADAK UMARI ROAD SE PRIMARI SCHOOL KI OR | Ongoing | 394428.05 | 68400 | 2020-08-22
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034535141 — CC ROAD VEERENDRA SINGH KE YAHA SE PAHALWAN KE DWAR KI OR MAHIMA THOK | Completed | 62000 | 49020 | 2020-12-24 | 2021-03-10
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002021/RC/22012034541339 — SUDOOR SAMPARK SADAK UMARI ROAD PULIYA SE RAMAUTAR KE GHAR KI OR | Completed | 1954610.66 | 1065849 | 2020-09-29 | 2022-07-15
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034552866 — CC ROAD RAMSEWAK KUSHWAH SE HANDPUMP KI OR PATHA | Completed | 78000 | 72954 | 2021-04-01 | 2021-05-06
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034596080 — CC ROAD PRAKASH BALMIK SE GOPAL KE GHAR KI OR | Completed | 131000 | 130914 | 2021-11-25 | 2023-09-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/22012034596095 — CC ROAD MAIN ROAD SE BADI MATA KI OR | Closed | 40000 | 0 | 2021-08-15
BHIND / BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/24 — सी0सी0 रोड छविराम के द्वार से किशुन सिंह के घर की ओर | Completed | 299230 | 101544 | 2012-03-22 | 2012-08-30
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/87 — सी0सी0 रोड निर्माण मुन्‍ना के द्वार से रामपाल सिंह | Completed | 112565 | 90810 | 2013-02-10 | 2014-02-05
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002021/RC/88 — सी0सी0 रोड निर्माण रामपाल सिंह के द्वार से रामेश्‍ | Completed | 112500 | 94158 | 2013-02-17 | 2014-02-05
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034525864 — SEGREGATION SHED NIRAMN BHADAKUR | Completed | 37000 | 32424 | 2021-09-14 | 2022-10-29
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034538338 — nadep kishun singh ke ghar par | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034538339 — nadep kishun singh ke ghar par | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034538352 — NADEP KISHUN SINGH KE GHAR PAR | Completed | 3000 | 2856 | 2022-07-19 | 2022-10-20
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034538355 — Samudayik nadep marghat ke pass | Closed | 5000 | 0 | 2021-07-10
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034538402 — sokhta gadda ram singh ke ynha farsh thok | Closed | 1100 | 0 | 2021-07-10
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034539175 — samudayik sokhta marghat ke pass | Completed | 6600 | 5790 | 2021-09-24 | 2021-12-03
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034541511 — samudayik sokhta ripudman singh ke ynha | Completed | 6600 | 6120 | 2022-07-19 | 2022-10-20
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034541514 — Hitgrahi sokhta prakash balmik ke hendpump par | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034541516 — Hitgrahi sokhta prakash balmik ke hendpump par | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034541517 — Hitgrahi sokhta raju kha ghar par | Closed | 1100 | 0 | 2021-07-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034569708 — nadep bharat singh ke ynha | Completed | 3000 | 2856 | 2022-07-19 | 2022-08-25
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034569717 — nadep anantram jatav ke ynha | Completed | 3000 | 2856 | 2022-08-04 | 2022-10-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034569720 — nadep balakram joshi ke ghar par | Completed | 3000 | 2856 | 2022-07-19 | 2022-08-25
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034569727 — Nadep ramashankar singh ke ghar par | Closed | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034569730 — Nadep chandrabhan singh ke ghar par | Closed | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702002021/RS/22012034570789 — SAMUDAYAK SWACHCHHTA PARISAR BHADAKUR | Completed | 43000 | 42846 | 2021-11-17 | 2022-10-20
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034571398 — Hitgrahi sokhta meharavan singh ke ynha | Closed | 1100 | 0 | 2021-09-24
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002021/RS/22012034659731 — nadep nirman bheekam joshi ke ynha | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674851 — samudayik sokhta bharat kumar ke ghar ke pass | Closed | 10000 | 0 | 2022-11-05
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674871 — samudayik sokhta ramesh ke ghar ke pass | Completed | 10000 | 7973 | 2022-11-23 | 2023-07-12
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674882 — samudayik sokhta srikrishna ke pass | Closed | 10000 | 0 | 2022-11-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674885 — samudayik sokhta ramesh patel ke pas | Completed | 10000 | 7973 | 2022-11-23 | 2023-07-12
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674891 — Samudayik soak pit munna kha ke ghar ke pass | Closed | 10000 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674892 — Samudayik soak pit sultan singh ke ghar ke pass | Completed | 10000 | 6868 | 2022-11-23 | 2023-07-12
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674895 — samudyik sokhta virendra chouhan ke ghar ke pass | Completed | 10000 | 7973 | 2022-11-23 | 2025-05-08
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674897 — samudyik sokhta upswasth kendrake pass | Completed | 10000 | 2448 | 2022-12-01 | 2024-03-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674907 — samudyik soak pit rachhipal ke ghar ke pass | Closed | 10000 | 0 | 2022-11-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674909 — Samudayik soak pit munni devi ke ghar ke pass | Closed | 10000 | 0 | 2022-11-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002021/RS/22012034674915 — Samudayik soak pit bharat kumar ke ghar ke pass | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1702002021/RS/22012034696227 — COMMUNITY TOILET NIRMAN bhadakur | Ongoing | 43000 | 27846 | 2023-06-11
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of Panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002021/SK/9993649274 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BHADAKUR | Completed | 1078000 | 502504 | 2017-07-19 | 2024-02-23
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/WC/22012034293674 — TALAB GAHRIKARAN MANDIR KE PAS BHADAKUR | Deleted | 99000 | 0 | 2016-05-25
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/WC/22012034325446 — TALAB MARMMAT KARY BHUJRYA BALA BHADAKUR | Completed | 97000 | 86688 | 2017-05-24 | 2017-07-10
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/WC/22012034325447 — TALAB MARMMAT KARY SEVLA BALA BHADAKUR | Completed | 88000 | 87720 | 2017-05-24 | 2017-07-10
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702002021/WC/22012034519758 — talab nirman karya khemraj ke khet ke pass | Deleted | 0 | 0 | 2019-10-02
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012034687016 — NAVEEN TALAB NIRMAN BABHAUKAR WALA TAL | Deleted | 0 | 0 | 2021-01-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002021/WC/22012034732962 — NAVEEN TALAB NIRMAN KARYA PATHA | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702002021/WC/22012034767101 — ROOF WATER HARVESTING MIDIL SCHOOL BHADAKUR | Completed | 32079.25 | 3474 | 2021-09-24 | 2024-03-02
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702002021/WC/22012034767108 — ROOF WATER HARVESTING PANCHAYAT BHAVAN BHADAKUR | Closed | 32079.25 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702002021/WC/22012034767118 — ROOF WATER HARVESTING ANGANWADI BHAVAN BHADAKUR | Closed | 32024.05 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002021/WC/22012034910868 — talab ka jirnodhar | Closed | 0 | 0 | 2022-01-24
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002021/WC/22012034910869 — talab ka jirnodhar | Closed | 0 | 0 | 2022-01-24
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012034945036 — CHECK DAM BARBAI PATHA BHADHAKUR | Closed | 0 | 0 | 2022-04-03
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012034945042 — TALAB GAHRIKARAN RAMTALA BHADAKUR | Closed | 0 | 0 | 2022-04-03
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/WC/22012034945047 — TALAB JIRDODDHAR RAMGADA BHADAKUR | Closed | 0 | 0 | 2022-04-03
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/WC/22012034983423 — TALAB JIDODDHAR KARYA PREM GAD TAL | Closed | 42500 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012034983438 — TALAB JIRDODDHAR KARYA BHABHOKAR KA TAL | Closed | 42500 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012034983447 — TALAB JIDODDHAR KARYA RAMTALA KA TAL | Closed | 42500 | 0 | 2022-04-14
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035017631 — NAVEEN ARDDAN DAM NARIYA KE PASS | Completed | 1481086.95 | 682601 | 2023-04-15 | 2025-05-12
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702002021/WC/22012035042348 — TALAB VISTARIKARAN EVAM PITCHING NIRAMN BHUJARIYA KA TAL BHADAKUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012035042355 — TALAB VISTARIKARAN EVAM PITCHING NIRAMN SHIROLA WALA HAR TAL BHADAKUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012035042360 — TALAB VISTARIKARAN EVAM PITCHING NIRAMN BHABHOKHAR BALA TAL TAL BHADAKUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012035042363 — TALAB VISTARIKARAN EVAM PITCHING NIRAMN PREMGADA BALA TAL BHADAKUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035042368 — NAVEEN ARDAN DEAM BEL KI NARI KE PAAS BHADAKUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035068216 — NAVEEN ARDAN BAND NALE KE PASS | Completed | 910557.85 | 635375 | 2023-07-13 | 2025-05-12
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035087425 — NAVEEN ARDAN BUND kiriy nariya ke pass | Completed | 910557.85 | 688636 | 2023-07-10 | 2025-05-12
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035087427 — NAVEEN ARDAN BUND sison bali ke pass bhadakur | Completed | 1323751.47 | 1007760 | 2023-09-29 | 2024-03-03
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012035092635 — NAVEEN ARDAN BAND NARIYA KE PASS | Completed | 1497851.99 | 776373 | 2023-09-06 | 2025-07-24
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012035092636 — NAVEEN ARDAN BAND ROAD KE PASS | Completed | 1495634.32 | 699244 | 2023-09-06 | 2024-03-03
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035166641 — NAVEEN ARDAN BANDHA NALE KE PASS | Completed | 1295483.26 | 679375 | 2024-03-02 | 2025-08-06
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035166643 — NAVEEN ARDAN TILIYA KE PASS | Closed | 0 | 0 | 2024-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035166644 — NAVEEN ARDAN TILIYA KE PASS | Closed | 0 | 0 | 2024-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035166645 — NAVEEN ARDAN TILIYA KE PASS | Completed | 1333998.19 | 692658 | 2024-03-12 | 2026-04-22
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035166647 — NAVEEN ARDAN KHAR KE PASS | Closed | 0 | 0 | 2024-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002021/WC/22012035166651 — NAVEEN ARDAN DHAR KE PASS | Closed | 0 | 0 | 2024-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002021/WC/22012035168607 — NAVEEN ARDAN BUND PULIYA KE PASS | Completed | 975108.41 | 656640 | 2024-03-12 | 2025-10-15
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702002021/WC/22012035301090 — डगवैल रीचार्ज पिट बाग वाले कुआ पर ग्राम पंचायत भदाकुर | Physically Completed | 25899.46 | 22909 | 2025-05-12 | 2026-04-22
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702002021/WC/22012035313417 — Arthan chek band nirman kary dande ke paas bhadakur | Ongoing | 983750.22 | 408465 | 2025-12-06
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702002021/WC/22012035313418 — Arthan chek band nirman kary pakke bandh ke paas bhadakur | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702002021/WC/22012035319051 — Naveen arthan chek dem pilua ke paas bhadakur | Approved | 0 | 0 | 2025-06-30
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1702002021/WC/24 — सोखता गढढा मजरा पठा भदाकुर | Completed | 0 | 14475 | 2009-07-07 | 2009-07-07
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002021/WC/30 — सोख्‍ता गडडा अमर सिंह के पास गुरैया थोक भदाकुर | Completed | 5900 | 14435 | 2009-07-07 | 2009-07-07
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002021/WC/31 — सोख्‍ता गडडा बंधा (गडिया) भदाकुर | Completed | 5500 | 14475 | 2009-07-07 | 2009-07-07
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002021/WC/32 — सोख्‍ता गडडा जमादार वस्‍ती भदाकुर | Completed | 5500 | 14475 | 2009-07-07 | 2009-07-07