## Work List
Exported on: 2026-10-21 15:03:09
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: NEHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002028/AV/22012034507632 — Gaushala Nirman Nahara | Closed | 0 | 0 | 2019-10-02
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002028/AV/22012034511386 — SHANTIDHAM NIRMAN KHERE KE PASS NAHARA | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002028/AV/22012034537424 — naveen anganwadi bhavan nirman nahara | Completed | 180000 | 178980 | 2020-09-29 | 2021-04-20
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002028/AV/22012034547678 — BOUNDARI WALL NIRMAN MIDIL SCHOOL NAHARA | Ongoing | 1126238.31 | 62856 | 2021-02-18
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002028/IF/22012034308487 — munesh singh /naresh | Deleted | 36240 | 0 | 2016-12-22
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002028/IF/22012034308542 — Nadep, Bajrag/amar singh | Suspended | 1188000000 | 0 | 2016-12-29
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034354027 — paudh ropan karya khere bale hanuman ji mandir parisar nehra | Suspended | 335000 | 0 | 2017-06-29
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034354039 — paudh ropan karya mata mandir parisar safedpura | Completed | 335000 | 102552 | 2017-07-27 | 2018-11-03
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034366632 — PAUDHA ROPAN KARYA MIDDLE SCHOOL NAHARA | Completed | 335000 | 173392 | 2017-07-27 | 2018-11-03
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034366638 — PAUDHA ROPAN KARYA ANGANVADI PARISAR SAFEDPURA | Completed | 335000 | 68370 | 2017-07-27 | 2018-11-03
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034368453 — PAUDHA ROPAN KARYA SADAK KINARE JAVAI | Suspended | 335000 | 0 | 2020-02-07
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002028/IF/22012034883072 — INDIVIDUAL NADEP NIRMAN HARIOM SHARMA / RAMLAKHAN SHARMA | Completed | 3000 | 2856 | 2022-05-06 | 2022-05-23
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002028/IF/22012034883077 — INDIVIDUAL NADEP NIRMAN OMPRAKASH SHARMA / GENDALAL | Completed | 3000 | 2448 | 2022-05-06 | 2022-05-23
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002028/IF/22012034883078 — INDIVIDUAL NADEP NIRMAN SANJEEV KUMAR / PRUSHOTTAM | Completed | 3000 | 2448 | 2022-05-06 | 2022-05-23
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002028/IF/22012034883083 — INDIVIDUAL NADEP NIRMAN RAMSHANKAR SHAMRA / SHYAMLAL | Closed | 3000 | 0 | 2021-08-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034996315 — KHET TALAB BEBA POOJA KE KHET PR 2629/4 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034996324 — KHET TALAB NIRMAAN RAKESH SINGH KE KHET PR2632/3 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034996333 — KHET TALAB NIRMAAN RAKESH SINGH/BRAJPAT KE KHET PR 2629/4/3 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012034996348 — KHET TALAB NIRMAAN RAKESH SINGH/BRAJPAT KE KHET PR 2629/4/3 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702002028/IF/22012034996354 — KHET TALAB BRAJPAT SINGH KE KHET PR 2638 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702002028/IF/22012034996357 — KHET TALAB BRAJPAT SINGH KE KHET PR 2638 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702002028/IF/22012034996360 — KHET TALAB BRAJPAT SINGH KE KHET PR 2638 | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702002028/IF/22012034996364 — KHET TALAB NIRMAAN BIRSINGH KE KHET PR | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702002028/IF/22012034996365 — KHET TALAB NIRMAAN BIRSINGH KE KHET PR | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035001205 — KHET TALAB NIRMAAN BHABHOOTI SINGH KHUAWLI | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035001206 — KHET TALAB NIRMAAN BHABHOOTI SINGH KHUAWLI | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002028/IF/22012035476149 — KHET TALAB ANIL/HAKIM KE KHET PR GRAM PANCHYAT NEHRA | Completed | 439568.13 | 199143 | 2025-05-16 | 2026-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002028/IF/22012035476177 — KHET TALAB MUKESH KUMAR KE KHET PR GRAM PANCHYAT NEHRA | Completed | 439568.13 | 163125 | 2025-05-16 | 2026-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002028/IF/22012035487607 — KHET TALAB AJAD SINGH/RAMSEVAK KE KHET PR GRAM PANCHYAT NEHRA | Completed | 147621.16 | 100485 | 2025-05-16 | 2026-03-13
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1702002028/IF/22012035627173 — EK BAGIYA MA KE NAM SARVESHA KE KHET PR NEHRA | Deleted | 0 | 0 | 2025-08-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Coast) - horti-trees (Individuals) / Along the coast Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002028/IF/22012035627175 — EK BAGIYA MA KE NAM RANI DEVI KE KHET PR NEHRA | Deleted | 0 | 0 | 2025-08-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035627177 — EK BAGIYA MA KE NAM GUPTA DEVI KE KHET PR NEHRA | Ongoing | 187841.53 | 0 | 2026-01-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035627278 — EK BAGIYA MA KE NAM SARVESHA KE KHET PR GP NEHARA | New | 0 | 0 | 2025-08-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035627301 — EK BAGIYA MA KE NAM SARVESHA KE KHET PR NEHRA | New | 0 | 0 | 2025-08-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035627307 — EK BAGIYA MA KE NAM SARVESHA KE KHET PR NEHRA | New | 0 | 0 | 2025-08-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035627418 — EK BAGIYA MA KE NAM SARVESHA KE KHET PR GP NEHARA | Ongoing | 187841.53 | 1566 | 2026-01-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035627420 — EK BAGIYA MA KE NAM RANEE DEVI KE KHET PR GP NEHARA | Ongoing | 187894.48 | 0 | 2026-01-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035633430 — EK BAGIYA MA KE NAM RAMKANTI DEVI KE KHET PR NEHRA | Deleted | 0 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035638147 — EK BAGIYA MA KE NAM SARVESHA KE KHET PR NEHRA | New | 0 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035638955 — EK BAGIYA MA KE NAM RAMKANTI KE KHET PR NEHRA | Ongoing | 266578.64 | 1566 | 2026-01-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002028/IF/22012035641788 — EK BAGIYA MA KE NAM PATVARI KE KHET PR NEHRA | Ongoing | 266578.64 | 0 | 2026-01-10
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993684622 — CATTLE SHED JASMANT/ DILSUKH | Completed | 115900 | 2544 | 2015-10-29 | 2017-12-09
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993684623 — CATTLE SHED RAMANAND/PREMDAS | Completed | 115900 | 2544 | 2015-10-29 | 2017-12-09
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724630 — CATTLE SHED DEVENDRA SINGH/BHAGIRATH SINGH | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724632 — CATTLE SHED SURESH/RAMSINGH | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724634 — CATTLE SHED KOTVAL/HAVALDAR SINGH | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724635 — CATTLE SHED BAJRANG SINGH /AMAR SINGH | Suspended | 115900 | 0 | 2021-01-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724636 — CATTLE SHED DILEEP SINGH /CHOTE SINGH | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724637 — CATTLE SHED JAMADAR /ANGAD SINGH | Closed | 115900 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724638 — CATTLE SHED BHEEM SINGH/MAHESHVAR | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724639 — CATTLE SHED NAVAB SINGH /CHATUR SINGH | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724640 — CATTLE SHED SHIVKUMAR/RAMBAHADUR | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724643 — CATTLE SHED JAMADAR/JAYSHRIRAM | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724646 — CATTLE SHED OMPRAKASH/GEDALAL | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724647 — CATTLE SHED RAMMOHAN SHARMA/SULLAN | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724648 — CATTLE SHED SANJEET/PURUSHOTTAM | Deleted | 115900 | 0 | 2016-01-26
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724649 — CATTLE SHED RANI DEVI / PAVAN SINGH | Suspended | 115900 | 0 | 2020-02-10
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724650 — CATTLE SHED DHEER SINGH / KALYAN SINGH | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724651 — CATTLE SHED RAKHI DEVI / RAVINDRA | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724652 — CATTLE SHED MANJU / KAMVOD | Closed | 115900 | 0 | 2015-08-15
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993724653 — CATTLE SHED PUTULAL / DHANIRAM | Suspended | 115900 | 0 | 2020-02-10
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993726969 — CATTLE SHED RATAN SINGH | Suspended | 0 | 0 | 2020-05-01
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993733491 — CATTLE SHAD SHIVRAJ SINGH/DEEL SINGH | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002028/IF/9993733492 — CATTLE SHED SHIVRAM SINGH/DEEL SINGH | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002028/IF/IAY/3846996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128162018 | Completed | 18360 | 17952 | 2022-11-12 | 2024-08-12
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002028/IF/IAY/4178999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123657441 | Completed | 18360 | 17544 | 2022-11-12 | 2023-04-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002028/IF/IAY/4528944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142775188 | Ongoing | 23490 | 20358 | 2025-04-19
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002028/IF/IAY/484460 — Construction of IAY House -IAY REG. NO. MP2051894 | Suspended | 17100 | 0 | 2020-09-10
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002028/IF/IAY/484727 — Construction of IAY House -IAY REG. NO. MP2056070 | Suspended | 17100 | 0 | 2020-02-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002028/IF/IAY/5669374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150751705 | Ongoing | 23490 | 7830 | 2025-08-04
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/173 — मेढबंधान रतन सिंह पुत्र जबर सिंह | Completed | 18000 | 2300 | 2010-08-28 | 2010-08-28
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/174 — मेढबंधान बाबू राम पुत्र बद्री | Completed | 21000 | 9000 | 2010-10-15 | 2010-10-15
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/175 — मेढबंधान राजकुमार पुत्र नाथू | Completed | 24000 | 18000 | 2010-11-08 | 2010-11-08
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034266263 — MEDBANDHAN RAJVEER SINGH NEHARA | Suspended | 0 | 0 | 2020-09-09
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034266264 — MEDBANDHAN ANGAD SINGH NEHRA | Suspended | 0 | 0 | 2020-08-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034266265 — MEDBANDHAN ANGAD SINGH NEHRA | Suspended | 0 | 0 | 2020-09-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034266266 — MEDBANDHAN RATAN SINGH | Suspended | 0 | 0 | 2020-09-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034269788 — MED BANDHAN SHIVRAJ SINGH/DEEL SINGH | Completed | 30695.36 | 26220 | 2020-10-06 | 2020-11-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034269789 — MED BANDHAN SHIVRAM SINGH/DEEL SINGH | Completed | 31791.62 | 27612 | 2020-10-27 | 2023-03-06
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034518357 — MED BANDHAN NIRMAN RAMBHUAN SINGH / MEGH SINGH KE KHET PER | Completed | 31769.58 | 34200 | 2020-09-29 | 2020-11-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034518358 — MED BANDHAN NIRMAN RAKESH SINGH / BRAJPAL SINGH KE KHET PER | Completed | 37064.5 | 35340 | 2020-08-24 | 2020-10-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/22012034518359 — MED BANDHAN POOJA DEV / RAGHVENDRA SINGH KE KHET PER | Completed | 32828.55 | 27360 | 2020-09-03 | 2020-12-11
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702002028/LD/22012034520564 — med bandhan rambhuban singh ke khet par | Completed | 30590.36 | 30780 | 2020-10-10 | 2020-11-21
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702002028/LD/22012034520569 — med bandhan kuber singh ke khet par | Completed | 30590.36 | 26220 | 2020-10-27 | 2021-03-07
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034525663 — MED BANDHAN NIRMAN BRAJPAT SINGH/DHURANDHAR SINGH | Completed | 33984.16 | 31920 | 2021-01-05 | 2021-02-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034525879 — med bandhan rakesh ke khet pr | Completed | 34870.42 | 30780 | 2021-01-12 | 2021-02-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034525880 — med bandhan rakes/brajpat ke khet pr | Completed | 29599.11 | 28500 | 2021-01-26 | 2021-02-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034525881 — med bandhan rakesh singh ke khet pr | Completed | 30695.36 | 29640 | 2021-01-26 | 2021-02-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034526442 — dam nirman karan singh/darkhasi ke khet pr nahara. | Closed | 0 | 0 | 2020-09-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034551730 — Med bandhan nathu singh ke khet pr | Completed | 38351.61 | 35898 | 2021-06-03 | 2021-10-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555639 — MED BANDHAN MAHARAJ SINGH KE KHET PR | Completed | 38351.61 | 33775 | 2021-06-03 | 2021-10-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555640 — MED BANDHAN HARISARAN KE KHET PR. | Completed | 38351.61 | 35898 | 2021-05-20 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555641 — MED BANDHAN SUKHPAL SINGH KE KHET PR. | Completed | 38351.61 | 35898 | 2021-07-10 | 2021-11-05
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034555643 — MED BANDHAN SUKHPAL SINGH KE KHET PRNAHARA | Completed | 38351.61 | 26827 | 2021-07-10 | 2021-10-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555645 — MED BANDHAN BHOLA SINGH KE KHET PR | Completed | 38351.61 | 36284 | 2021-05-20 | 2021-09-12
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555646 — MED BANDHAN PREMLATA KE KHET PR | Completed | 38351.61 | 31266 | 2021-05-20 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555648 — MED BANDHAN SAURABH KE KHET PR | Completed | 36817.55 | 33582 | 2021-05-20 | 2021-07-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034555649 — MED BANDHAN DALIPSINGH/CHHOTESINGH KE KHET PR | Completed | 35283.48 | 35898 | 2021-08-08 | 2021-10-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034555650 — Med bandhan bhoore singh ke khet pr | Completed | 38351.61 | 35898 | 2021-09-23 | 2021-11-19
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034555651 — Med bandhan Arvind ke khet pr | Completed | 38351.61 | 34740 | 2021-10-01 | 2021-10-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/LD/22012034555652 — Med bandhan dilipsingh ke khet pr | Completed | 37584.58 | 35898 | 2021-09-08 | 2021-11-05
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034574661 — MA KI BAGIYA GOV. P S SAFEDPURA | Closed | 0 | 0 | 2021-10-02
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702002028/LD/22012034593807 — अमृत वाटिका खेरावाले हनुमान जी मंदिर नाहरा | Closed | 55847.4 | 0 | 2023-04-14
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/247 — मेड बन्‍धान राकेश सिंह / ब्रजपत सिंह | Deleted | 0 | 0 | 2011-02-02
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/248 — मेड बन्‍धान कार्य राजवीर सिंह/ गुनसिंह | Deleted | 0 | 0 | 2011-01-08
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/249 — मेड बन्‍धान कार्य रतनसिह / जबर सिंह | Deleted | 18000 | 0 | 2011-01-01
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/259 — मेड बन्‍धान कार्य जसमन्‍त नेहरा | Completed | 19500 | 0 | 2010-11-15 | 2010-11-22
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/260 — मेड बन्‍धान कार्य लक्ष्‍मण / दिलसुख | Completed | 19500 | 0 | 2010-12-08 | 2010-12-14
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/286 — मेड बन्‍धान कार्य राकेश सिंह / ब्रजपत सिंह | Completed | 41526 | 18788 | 2011-07-01 | 2014-10-30
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002028/LD/287 — मेड बन्‍धान कार्य गंगाराम / कल्‍याण | Completed | 49679 | 26230 | 2011-07-01 | 2014-11-11
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002028/PG/22012034365792 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002028/PG/22012034366332 — play ground | Suspended | 0 | 0 | 2020-02-01
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002028/PG/9425891829 — KHEL MAIDAN M/S SCHOOL NEHRA | Deleted | 149000 | 0 | 2017-01-05
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034160220 — C.C.ROAD MAIN ROAD SE ANUSUCHIT VASTI TAK | Completed | 184000 | 148145 | 2013-06-20 | 2014-05-02
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034161500 — C.C.ROAD BHAGWAN SINGH KE MAKAN SE JAMADAR SINGH K | Completed | 155000 | 130297 | 2013-09-19 | 2014-05-18
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034186721 — C.C.ROAD SHIV SINGH KE MAKAN SE KHAY MOHALLA KI AU | Completed | 150000 | 114832 | 2013-10-10 | 2014-05-26
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034224302 — C.C.ROAD PRAJAPATI THOK SE NAHAR SINGH KI AUR | Completed | 72997 | 42692 | 2014-10-23 | 2016-03-06
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034224305 — C.C.ROAD SHANKAR JI KE MANDIR SE VIRENDRA TRIPATHI KI AUR | Deleted | 93700 | 0 | 2014-04-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034224309 — C.C.ROAD SHANKAR JI KE MANDIR SE VIRENDRA TRIPATHI | Completed | 93700 | 88736 | 2014-08-14 | 2016-03-06
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034227095 — C.C.ROAD RAMSHARAN KI AUR SE HARIJAN VASTI KI AUR | Deleted | 0 | 0 | 2014-04-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034232008 — C.C.ROAD RAMSHARAN KI AUR SE HARIJAN THOK KI AUR | Completed | 52295 | 18840 | 2014-10-23 | 2017-01-09
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034308361 — C.C. ROAD RAMSARUP KE YHA SE RAMESH BALMIK KI OR NEHRA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034308363 — C.C. ROAD UDAY KE YHA SE SURAJ KI OR NEHRA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034308364 — C.C. ROAD GANGADEEN KE YHA SE GURJAN KE MAKAN KI OR NEHRA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034308365 — C.C. ROAD MUKHAY MARG SE PRATHMIK VIDHYALAY KI OR SAPHED PURA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034308367 — C.C. ROAD SURENDRA KE YHA SE GODAM TAK JAVAI | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034329954 — cc road shivdatt ke eha se kedar singh ki or | Completed | 6637500000 | 66048 | 2017-11-02 | 2018-03-18
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034339410 — CC ROAD RAM SINGH KE EHA SE BRAJRAJ SINGH KI OR | Completed | 4425000000 | 51600 | 2017-05-25 | 2018-03-18
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034360536 — CC ROAD SUKHRAM KE YHA SE KHASE KI OR | Completed | 6637500000 | 66048 | 2017-09-21 | 2018-03-18
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034365829 — सी.सी.रोड जलसिंह के यहाँ से मोहन सिंह की और | Completed | 8850000000 | 65700 | 2017-11-02 | 2019-03-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034365830 — सी.सी.रोड कल्लू के यहाँ से सुरेन्द्र की ओर | Completed | 89000 | 79320 | 2017-11-02 | 2019-03-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034365831 — सी.सी.रोड मुनुआ के यहाँ से माता मंदिर की ओर | Completed | 47000 | 44184 | 2017-11-02 | 2019-08-14
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034365832 — CC ROAD GANGADEEN KE YAHA SE DURJAN KI OR | Completed | 47000 | 3132 | 2017-11-02 | 2018-11-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034436222 — सी सी रोड शिव सिंह के यहाँ से कुइया की और नेहरा | Completed | 31000 | 30600 | 2019-03-07 | 2019-07-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034436223 — सी सी रोड मुनुआ के यहाँ से माता मंदिर की और नेहरा | Deleted | 47000 | 0 | 2017-01-26
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034439809 — जगदम्बा के बड़े से पप्पू शर्मा की और | Deleted | 9300000000 | 0 | 2017-04-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034442731 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034446026 — सी.सी.रोड जगदम्बा के बड़े से पप्पू शर्मा की और | Completed | 93000 | 92928 | 2019-03-07 | 2019-09-18
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034446315 — सी सी रोड अभिलाख के यहाँ से प्राथमिक विद्यालय की ओर | Completed | 23000 | 25320 | 2019-03-07 | 2019-09-18
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034446319 — सी .सी रोड अनिल शर्मा के यहाँ से संतोष शर्मा की ओर | Completed | 47000 | 46464 | 2019-03-07 | 2019-09-18
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034447698 — सी.सी.रोड मेन रोड से भंवर सिंह की ओर देह | Completed | 70000 | 69540 | 2020-06-10 | 2020-08-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034447757 — सी.सी.रोड मैंन रोड से राजवीर की ओर | Deleted | 23000 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448250 — सी.सी.रोड तहर के गोंडा से सुखदेव की और | Completed | 33000 | 32016 | 2019-03-07 | 2019-09-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448254 — सी.सी.रोड मेन रोड से भीमसेन की ओर | Deleted | 0 | 0 | 2019-01-26
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448257 — सी.सी.रोड नबाव के कुआँ से ददेल सिंह की ओर | Completed | 47000 | 45912 | 2020-01-02 | 2020-05-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448265 — सी.सी.रोड लखपत के यहाँ से कुअंर सिंह की ओर | Completed | 44000 | 43320 | 2021-01-27 | 2021-03-09
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448267 — सी.सी.रोड उदल के यहाँ से सुरेन्द्र सिंह की ओर | Completed | 47000 | 46368 | 2019-03-07 | 2020-05-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448268 — सी.सी.रोड गंगादीन के यहाँ से दुर्जनलाल की ओर | Completed | 47000 | 5280 | 2019-03-07 | 2020-02-29
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034448270 — सी.सी.रोड पुत्तु सिग के यहाँ से रामसेवक की ओर | Deleted | 70000 | 0 | 2019-03-07
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034514526 — Cc Road Shankar Ji Ke Mandir Se Hakim Ki Aur Nahra | Completed | 55000 | 54720 | 2020-06-10 | 2020-09-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034514528 — Cc Road Ramesh Ke Yaha Se Durjan Ki Aur Nahara | Completed | 92000 | 90324 | 2021-10-17 | 2022-04-01
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034518688 — सी सी रोड राम सहाय के यहाँ से राम स्वरुप के घर की और नेहरा | Completed | 37000 | 36480 | 2020-06-30 | 2020-09-10
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034553002 — Cc Road Mata Ke Mandir Se Surendra Ki Aur Nahra | Completed | 32000 | 35898 | 2021-04-01 | 2021-10-12
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034553006 — CC ROAD RAMESH KE YAHA SE BRAJPAT KI OR | Completed | 74000 | 72960 | 2020-12-22 | 2021-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/22012034553008 — CC ROAD GANGA PRASAD KE YAHA SE PUTTULAL KI OR | Completed | 42000 | 41040 | 2020-12-22 | 2021-01-26
BHIND / BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002028/RC/39 — सी0सी0 रोड निर्माण कार्य मैन रोड से जमादार के मकान की ओर | Completed | 299222 | 100500 | 2012-03-22 | 2012-08-30
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702002028/RS/22012034585491 — SAMUDAYAK SWACHCHHATA PARISAR NEHARA | Completed | 43000 | 41688 | 2021-11-07 | 2022-04-11
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002028/RS/22012034586746 — COMUNITY NADEP NIRMAN GOVT MIDDIL SCHOOL NEHARA | Closed | 5000 | 0 | 2021-08-15
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1702002028/RS/22012034586772 — COMMUNITY SOAK PIT NIRMAN KHAD GODAM KE PASS JAVAI | Closed | 6600 | 0 | 2021-10-08
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002028/RS/22012034588519 — COMMUNITY SOAK PIT NRIMAN PS SCHOOL SAPHEDPURA | Closed | 6600 | 0 | 2021-10-09
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002028/RS/22012034588527 — COMMUNITY SOAK PIT MIDDIL SCHOOL KE PASS | Closed | 6600 | 0 | 2021-08-15
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002028/RS/22012034588537 — COMMUNITY NADEP NIRMAN KHAD GODAM KE PASS JAVAI | Completed | 5000 | 5018 | 2021-11-08 | 2021-12-08
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702002028/RS/22012034643858 — SAMUDAYAK SWACHCHHATA PARISAR SAPHEDPURA | Completed | 43000 | 42840 | 2022-05-06 | 2022-05-24
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002028/WC/22012034327235 — TALAB MARAMMAT KARYA KHERE KE PASS NEHARA | Completed | 98000 | 96836 | 2017-06-01 | 2017-08-20
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002028/WC/22012034327324 — TALAB MARAMMAT KARY MANDIR KE PAS SAFEDPURA | Completed | 5712400000 | 56760 | 2017-06-22 | 2017-08-27
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002028/WC/22012034446814 — DUG POND HANUMAN JI KE MANDIR KE PASS | Completed | 417000 | 416592 | 2019-03-07 | 2020-07-17
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002028/WC/22012034446818 — NAVEEN TALAB NIRMAN MATA MANDIR BADI JHOR PER | Completed | 1052000 | 710272 | 2019-03-07 | 2020-10-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002028/WC/22012034585212 — NAVEEN TALAB NIRMAN BUDH SINGH KE KHET KE PASS | Completed | 571619.5 | 422286 | 2020-09-28 | 2021-05-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034586919 — chek dem nirman mahua ke pass nahara | Closed | 0 | 0 | 2020-09-24
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002028/WC/22012034586921 — naveen dam nirman ramsingh ke pass nahra. | Completed | 711726.7 | 513864 | 2020-09-29 | 2021-05-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002028/WC/22012034587215 — NAVEEN TALAB NIRMAN RAMSINGH KE BAGAL SE NAHRA | Closed | 0 | 0 | 2020-09-25
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002028/WC/22012034587357 — naveen talab nirman mahua ke pas nahara. | Closed | 0 | 0 | 2020-09-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002028/WC/22012034608072 — TALAB GAHRIKARAN KARYA MIDIL SCHOOL KE PASS NAHARA | Completed | 1089323.69 | 864114 | 2021-02-23 | 2021-09-10
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034680115 — Talab ghari karan mata madiri safedpura | Completed | 47153.88 | 39168 | 2022-11-08 | 2023-02-20
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034801272 — NAVEEN TALAB NIRMAN MAHUAA KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034801275 — NAVEEN TALAB NIRMAN HANUMAN YADAV NAVEEN TALAB NIRMAN MAHUAA KE PASS KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034801276 — CHEK DAM NIRMAN MOHAN SINGH KE PASS | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034812742 — NAVEEN TALAB NIRMAN HANUMAN YADAV KE KHET KE PASS | Physically Completed | 1485215.02 | 1322182 | 2021-11-21 | 2026-04-17
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034812743 — NAVEEN TALAB NIRMAN HANUMAN YADAV KE KHET KE PASS | Closed | 0 | 0 | 2021-08-16
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034812744 — NAVEEN TALAB NIRMAN HARISARAN KE KHET KE PASS | Closed | 0 | 0 | 2021-08-16
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1702002028/WC/22012034812745 — NAVEEN TALAB NIRMAN RAKESH SINGH KE KHET KE PAS | Closed | 0 | 0 | 2021-08-16
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034812746 — NAVEEN TALAB NIRMAN BHABHOOTI KE KHET KE PAS | Closed | 0 | 0 | 2021-08-16
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002028/WC/22012034945236 — AMRAT SAROVAR TALAB MAHUA KE PASS NEHRA | Physically Completed | 2079000 | 1584704.44 | 2022-05-27 | 2026-04-17
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034983724 — NAVEEN TALAB NIRMAN VINOD KE KHET KE PASS. | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034995231 — NAVEEN TALAB NIRMAN BHABHOOTI KE KHET KE PAS | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002028/WC/22012034995232 — NAVEEN TALAB NIRMAN SEMARAVALI NARI | Completed | 1116531.03 | 1033794.36 | 2022-10-05 | 2025-05-10
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012034995233 — NAVEEN TALAB NIRMAN LAMSOOTA KHAR | Physically Completed | 1420714.54 | 1412387.56 | 2022-12-31 | 2026-04-17
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012035065571 — ARDAN DEM SYAWLI | Ongoing | 1353113.39 | 232050 | 2024-01-09
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002028/WC/22012035065572 — NAVEEN TALAB NIRMAN POOJA KE KHET KE PAS | Physically Completed | 1492662.5 | 790244 | 2023-10-13 | 2026-04-17
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702002028/WC/22012035300178 — डग बेल रिचार्ज पिट ओमप्रकाश शर्मा के घर के पास सफेदपुरा GP नेहरा | Physically Completed | 25899.46 | 22354 | 2025-05-14 | 2026-04-16
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702002028/WC/22012035300690 — डगवैल रीचार्ज पिट खासे वाला कुआ पर ग्राम पंचायत नेहरा | Physically Completed | 25899.46 | 22354 | 2025-05-14 | 2026-04-16
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702002028/WC/22012035300693 — डगवैल रीचार्ज पिट बड़ा वाला कुआ पर ग्राम पंचायत नेहरा | Approved | 25899.46 | 0 | 2025-04-14
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002028/WC/38 — सोख्‍ता गडडा सुरेन्‍द्र सिंह के समीप हैण्‍डपम्‍प पर | Completed | 4500 | 14315 | 2009-06-23 | 2009-06-23
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002028/WC/39 — सोख्‍ता गडडा बीरेन्‍द्र कुमार के समीप हैण्‍डपम्‍प पर | Completed | 4500 | 14315 | 2009-06-28 | 2009-06-28
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034449096 — Talab gahrikaran khere ke pass | Completed | 49511.57 | 41916 | 2023-05-03 | 2023-05-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034449097 — Talab ghari karan mata madiri safedpura | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034454398 — TALAB JIRNODHAR KHEREVALE HANUMAN JI KE PAS. | Closed | 0 | 0 | 2021-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034932797 — AMRIT SAROVAR NIRMAN SARVE NO. 598 RAKESH/BRAJPAT SINGH KE KHET KE PASS GRAM PANCHAYAT NEHRA | Closed | 0 | 0 | 2022-04-24
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034932799 — AMRIT SAROVAR ANTARGAT CHECK DEM NIRMAN SARVE NO. 598 RAKESH/BRAJPAT SINGH KE KHET KE PASS NAHRA | Closed | 0 | 0 | 2022-04-24
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034935985 — NAVEEN TALAB NIRMAN SEMARA VALI NARI | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002028/WH/22012034935986 — NAVEEN TALAB NIRMAN LAMSOOTA KHAR | Closed | 0 | 0 | 2022-08-15