## Work List
Exported on: 2026-10-24 17:53:33
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: UMRAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034506514 — shantidham nirman umari | Deleted | 0 | 0 | 2019-10-02
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034512116 — Shantidham nirman motipura | Closed | 283566.25 | 0 | 2020-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034621687 — naveen shantidham nirman motipura | Deleted | 0 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034621688 — naveen shantidham nirman gehbat | Ongoing | 290458.68 | 107213.86 | 2022-11-24
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034622823 — naveen shantidham nirman motipura1 | Ongoing | 280230.45 | 101244.56 | 2022-11-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034622825 — naveen shantidham nirman devgad | Deleted | 0 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034629793 — naveen shantidham nirman devgadUMARI | Deleted | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034629794 — naveen shantidham nirman kanawar road umari | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034629795 — naveen shantidham nirman pandri road umari | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034639495 — naveen shantidham nirman devgad umari | Deleted | 0 | 0 | 2023-04-14
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034639496 — naveen shantidham nirman umari | Ongoing | 322408.11 | 288456 | 2024-11-06
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034642951 — shantidham nirman pandari road umari | Closed | 330286.99 | 0 | 2023-08-15
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034658522 — SHANTIDHAM NIRMAN KARYA DEVGAD UMARI | New | 0 | 0 | 2024-06-14
BHIND / BHIND | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034669315 — SHANTI DHAM NIRMAN PANDRI ROAD UMARI | New | 0 | 0 | 2026-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/3796 — Anganwadi/Other Rural Infrastructure,UMRAI | Deleted | 330000 | 0 | 2015-10-03
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/3797 — Aanganbadi/Other Rural Infrastructure,BHIND | Deleted | 330000 | 0 | 2015-10-03
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/3798 — Anganwadi/Other Rural Infrastructure,UMRAI | Completed | 330000 | 243148 | 2016-01-02 | 2022-11-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/3799 — Aanganbadi/Other Rural Infrastructure,BHIND | Completed | 330000 | 78152 | 2017-07-29 | 2022-11-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/3800 — Anganwadi/Other Rural Infrastructure,UMRAI | Completed | 330000 | 307566 | 2016-01-02 | 2022-11-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/3801 — Aanganbadi/Other Rural Infrastructure,UMRAI | Completed | 330000 | 350177 | 2015-11-14 | 2022-11-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002036/AV/7532 — Anganwadi/Other Rural Infrastructure, MOTIPURA UMRAI | Completed | 330000 | 227220 | 2017-06-24 | 2024-03-07
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1702002036/DP/22012034597686 — meri mati mera desh amrit vatika nirman govt kanya school umari | Ongoing | 56725.4 | 13481 | 2023-09-04
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002036/DP/22012034597695 — meri mati mera desh amrit vatika nirman mandir motipura umari | Closed | 0 | 0 | 2023-07-01
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002036/DP/22012034597704 — meri mati mera desh amrit vatika nirman post office umari | Closed | 56725.4 | 0 | 2023-07-01
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002036/DP/22012034607460 — vraksharopan nirman gahiyar baba devgad | Closed | 0 | 0 | 2023-08-15
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002036/FP/22012034628368 — नाला निर्माण कार्य बॉद से गाव की ओर उमरी | Closed | 133800 | 0 | 2021-10-02
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002036/FP/22012034628380 — NALA NIRMAN RAMSWAROOP KE MAKAN SE VANKHANDESHWAR MANDIR KI OR | Deleted | 750000 | 0 | 2021-09-19
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702002036/FP/22012034638006 — Kachha nala nirman motipura gram se talav ki or | Physically Completed | 123052.25 | 63648 | 2024-03-08 | 2026-04-17
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002036/IF/22012034352300 — BIRACHA ROPAN KARYA MANDIR AUR SCHOOL KE PASS | Completed | 335000 | 12976 | 2017-06-17 | 2020-05-19
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002036/IF/22012034352313 — BIRACHA ROPAN KARYA TALAB SCHOOL MANDIR | Completed | 335000 | 9020 | 2017-06-17 | 2020-05-19
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761176 — MED BANDHAN RASNVEER SINGH / VIDHYARAM SINGH KHET PAR | Completed | 26079.09 | 13896 | 2021-05-24 | 2023-04-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761180 — MED BANDHAN RADHESHYAM SINGH / LAKSHMINARAYAN SINGH KHET PAR | Completed | 26385.91 | 6948 | 2021-05-24 | 2022-05-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761184 — MED BANDHAN RAJENDRA SINGH / GIRDABAL SINGH KHET PAR | Completed | 25772.28 | 6948 | 2021-05-24 | 2022-05-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761186 — MED BANDHAN MAHAVEER SINGH / PRAG SINGH KHET PAR | Completed | 25465.47 | 6948 | 2021-05-24 | 2022-05-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761190 — MED BANDHAN SURESH SINGH / HARNATH SINGH KHET PAR | Completed | 25158.65 | 6948 | 2021-05-24 | 2022-05-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761194 — MED BANDHAN DILEEP SINGH / GOVIND SINGH KHET PAR | Completed | 24851.85 | 9264 | 2021-05-24 | 2022-05-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761199 — MED BANDHAN SATYAVEER SINGH / VIDHYARAM SINGH KHET PAR | Completed | 24851.85 | 6948 | 2021-05-24 | 2023-04-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002036/IF/22012034761202 — MED BANDHAN RAMVEER SINGH / VIDHYARAM SINGH KHET PAR | Completed | 23991.9 | 5790 | 2021-05-24 | 2022-05-04
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002036/IF/22012034826222 — BENEFICIARY SOKPIT SONVEER KE GHAR KE PAAS | Deleted | 1100 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1702002036/IF/22012034826230 — BENEFICIARY SOKPIT MANOJ KE GHAR KE PAAS | Deleted | 1100 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002036/IF/22012034826241 — BENEFICIARY NADEP MAHAVEER KE DWAR KE PAAS | Deleted | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002036/IF/22012034826359 — BENEFICIARY NADEP ANIL KE DWAR KE PAAS | Deleted | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002036/IF/22012034826369 — BENEFICIARY NADEP DINESH KE DWAR KE PAAS | Deleted | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002036/IF/22012034826382 — BENEFICIARY NADEP RAKESH KE DWAR KE PAAS | Deleted | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002036/IF/22012034826395 — BENEFICIARY NADEP MITHALESH KE DWAR KE PAAS | Deleted | 3000 | 0 | 2021-04-14
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002036/IF/22012035190387 — Khet talav nirman munni devi / jay Narayan Singh ke khet par | Closed | 0 | 0 | 2023-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002036/IF/22012035511181 — KHET TALAB NIRMAN KARYA RAMLAKHAN / RATIRAM KE KHET PER | Physically Completed | 450885.64 | 289971 | 2025-05-17 | 2026-04-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002036/IF/22012035553638 — KHET TALAB NIRMAN DATARAM / GYAPRASAD KE KHET PER | Physically Completed | 147621.16 | 43848 | 2025-07-18 | 2026-04-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002036/IF/22012035582492 — खेत तालाब निर्माण कार्य ग्राम पंचायत umari | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1702002036/IF/22012035582494 — kapil dhara kup work gp umari | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678360 — CATTLE SHED MANOJ/ GULAB SINGH | Completed | 115900 | 94159 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678361 — CATTLE SHED SACHIN BABU/ DHARAM SINGH | Completed | 115900 | 95908 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678469 — CATTLE SHED ANIL SHRIVASTAVA/ RAM SHANKAR | Completed | 115900 | 93364 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678473 — CATTLE SHED KAMLESH/ NARESH SINGH | Completed | 115900 | 96544 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678476 — CATTLE SHED ABHILAKH SINGH / NATHU SINGH | Completed | 115900 | 94159 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678478 — CATTLE SHED LAKHAN SINGH/ INDRAJEET SINGH | Completed | 115900 | 94000 | 2015-10-24 | 2016-06-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678486 — CATTLE SHED SONVEER/ RADHESHYAM SINGH | Completed | 115900 | 91933 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678488 — CATTLE SHED MITHLESH SINGH / RAMESWAR | Completed | 115900 | 86996.5 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678489 — CATTLE SHED ANIL SINGH /MULAYAM SINGH | Completed | 115900 | 97975 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993678491 — CATTLE SHED RANVEER SINGH/ VIDHYARAM | Completed | 115900 | 88594 | 2015-10-24 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700731 — CATTEL SHED PRAHLAD/RAMBHAROSE | Closed | 115900 | 0 | 2015-12-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700732 — CATTEL SHED MAHAVEER/PRAYAG SINGH | Completed | 115900 | 76505.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700734 — CATTEL SHED RAMBHAROSE/JEERAKHAN | Completed | 115900 | 82865.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700735 — CATTEL SHED RADHESHYAM/ LAJJARAM | Completed | 115900 | 79208.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700737 — CATTEL SHED VISHNATH/LAJJARAM | Completed | 115900 | 87158.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700739 — CATTEL SHED ABHILAKH/JAGRAM GEHVAD | Completed | 115900 | 80003.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700741 — CATTLE SHED SURESH SINGH / HARNATH SINGH | Completed | 115900 | 82229.9 | 2016-01-16 | 2016-06-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993700744 — CATTLE SHED GANGA SINGH/MADHO SINGH GEHVAD | Completed | 115900 | 78413.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993701370 — CATTLE SHED RAMCHARANLAL/SUNDARLAL | Closed | 115900 | 0 | 2015-12-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993701371 — CATTEL SHED RINKU / SHRIGOVINDRA | Closed | 115900 | 0 | 2015-12-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702063 — CATTLE SHED DASHRATH/RAMESHWAR | Completed | 115900 | 83183.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702064 — CATTEL SHED SANJAY/SHRIKRISHAN | Completed | 115900 | 87476.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702065 — CATTEL SHED VIPIN/JAMUNAPRASAD | Completed | 115900 | 82865.9 | 2016-01-16 | 2016-06-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702066 — CATTEL SHED RAKESH/SATYRAM SINGH | Completed | 115900 | 82229.9 | 2016-01-16 | 2016-06-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702067 — CATTEL SHED DEVENDRA/NATHU | Completed | 115900 | 85091.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702068 — CATTEL SHED DEVENDRA/MAHADEV | Completed | 115900 | 82070.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702072 — CATTEL SHED CHHOTELAL/LAUA | Completed | 115900 | 75710.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002036/IF/9993702074 — CATTEL SHED PRAMOD/JAGDEESH | Completed | 115900 | 78413.9 | 2016-01-16 | 2016-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133966 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/114 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133967 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/145 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133968 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/207 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133969 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/254 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133970 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/504 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133972 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/227 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199289 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/148 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199290 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/219 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199291 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/521 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199292 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/532 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/212291 — Construction of IAY House -IAY REG. NO. MP1101649 | Completed | 15030 | 12234 | 2017-01-28 | 2018-07-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/261750 — Construction of IAY House -IAY REG. NO. MP2631297 | Completed | 15030 | 12354 | 2017-01-28 | 2018-09-16
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/263573 — Construction of IAY House -IAY REG. NO. MP3219303 | Completed | 15030 | 14616 | 2017-01-28 | 2018-09-16
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/264308 — Construction of IAY House -IAY REG. NO. MP3595861 | Completed | 15030 | 15030 | 2017-01-28 | 2017-12-10
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/277290 — Construction of IAY House -IAY REG. NO. MP3588435 | Completed | 15030 | 14178 | 2017-01-28 | 2017-08-30
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/277304 — Construction of IAY House -IAY REG. NO. MP3590216 | Completed | 15030 | 12264 | 2017-01-28 | 2018-07-18
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/4379737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106851054 | Completed | 18360 | 17136 | 2022-12-15 | 2024-03-03
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5608932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126465428 | Approved | 27000 | 0 | 2025-05-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5614343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146779137 | Physically Completed | 27000 | 14094 | 2025-06-02 | 2026-08-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5615050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118019887 | Ongoing | 27000 | 6264 | 2025-07-28
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5615235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146843620 | Ongoing | 27000 | 14094 | 2025-06-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5615935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113655253 | Ongoing | 27000 | 12528 | 2025-06-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5616548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129964908 | Ongoing | 27000 | 12528 | 2025-06-02
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002036/IF/IAY/686323 — Construction of IAY House -IAY REG. NO. MP2611690 | Completed | 15030 | 14568 | 2017-08-12 | 2018-09-16
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/202 — मेड बन्‍धान कार्य शरद / हाकिम के खेत पर | Completed | 20000 | 19900 | 2010-08-26 | 2010-08-26
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/203 — मेड बन्‍धान कार्य रूस्‍तम / उमराम | Completed | 20500 | 20000 | 2010-08-26 | 2010-08-26
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/206 — मेड बन्‍धान कार्य मजनू / सहनाद के खेत पर | Completed | 18000 | 17500 | 2010-09-03 | 2010-09-03
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/207 — मेड बन्‍धान कार्य सर्वेश / गंगाराम | Completed | 21700 | 21700 | 2010-09-11 | 2010-09-11
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239210 — MAD BANDHAN RADHAVAR/BACCHU | Completed | 35400 | 33867 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239214 — MAD BANDHAN MITHLESH/RAMESWAR | Completed | 35400 | 34980 | 2015-12-12 | 2017-03-30
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239215 — MAD BANDHAN RAKESH/ SHANKAR SINGH | Completed | 47200 | 41817 | 2015-12-12 | 2016-03-30
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239216 — MAD BANDHAN SOMNATH/BACHHU | Completed | 44800 | 41340 | 2015-12-12 | 2016-03-30
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239217 — MAD BANDHAN BRIJENDRA SINGH/ GULJHARI | Completed | 35400 | 34662 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239218 — MAD BANDHAN DILASHRAM/ SHRIPAL | Completed | 44800 | 38637 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239219 — MAD BANDHAN HARVILAS/ BACHHU | Completed | 35400 | 33708 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239220 — MAD BANDHAN JAGDISH/ RAM DAYAL | Completed | 44800 | 44520 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239221 — MAD BANDHAN DEVENDRA/SHIVCHARAN | Completed | 44800 | 40863 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034239222 — MAD BANDHAN JAGDISH/ INDRAJEET | Completed | 35400 | 29892 | 2015-12-12 | 2017-05-25
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/22012034259959 — MITTI BHARAV NIRMAN GOVT.HIGH.SCHOOL UMARI | Completed | 835000 | 710466 | 2016-05-28 | 2017-10-09
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1702002036/LD/22012034542542 — uparjan kendra umari chabutra nirman | Completed | 802553.42 | 792596 | 2021-03-14 | 2021-12-01
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/336 — शमशान घाट मुक्तिधाम उमरी | Completed | 545000 | 68484 | 2011-12-14 | 2015-08-20
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002036/LD/338 — खेल मैदान क्रीडागन उमरी | Completed | 85845 | 17544 | 2012-01-13 | 2015-08-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002036/PG/22012034365798 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002036/PG/22012034366327 — play ground | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034189380 — CC ROAD GYAN CHANDRA K GHAR SAI NAHARA WALE KI OR | Completed | 107000 | 94191.8 | 2013-12-14 | 2014-02-11
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034189446 — CC ROAD MUSTHAK KHA K GHAR SAI RAM SWAROOP K DWAR | Completed | 124800 | 104794.9 | 2013-12-14 | 2015-01-12
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034189447 — CC ROAD K DWAR SAI MAHAVEER K DWAR KI OR | Completed | 107000 | 97683.78 | 2013-12-14 | 2015-06-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034189448 — CC ROAD KESHAV K DWAR SAI AAHIWARAN K DWAR KI OR | Completed | 71300 | 65145.9 | 2013-12-14 | 2014-03-27
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034189449 — CC ROAD KALLU K BHAWAN SAI RAM JANKI MANDIR KI OR | Completed | 71300 | 67191 | 2013-12-14 | 2014-03-27
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034189500 — CC ROAD IMAM KHA K DWAR SAI KHAREEM MOHALLA KI OR | Deleted | 124900 | 0 | 2013-08-15
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034194090 — C.C.ROAD IMAN KHAN KE DWAR SE KHATIK MOHALLA KI AU | Completed | 124856 | 118226.9 | 2013-12-17 | 2016-06-05
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034227640 — C.C.ROAD BHUTANI KE GHAR SE AYUB KHAN KE GHAR KI A | Completed | 184178 | 155265 | 2014-08-30 | 2015-07-27
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034227641 — C.C.ROAD LAHAR ROAD MUKHYA SADAK SE JAIN MANDIR KI | Completed | 97776 | 82479.7 | 2014-08-30 | 2015-07-27
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034227643 — C.C.ROAD PHOOL SINGH KE MAKAN SE LALLU KHAN KE DWA | Completed | 97776 | 84363.7 | 2014-08-30 | 2015-07-27
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034227645 — C.C.ROAD TEHANGUR ROAD SE KAMLESH KE DWAR KI AUR | Deleted | 0 | 0 | 2014-04-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034227647 — C.C.ROAD TEHANGUR SADAK SE KAMLESH KE DWAR KI AUR | Completed | 97776 | 84363.9 | 2014-08-30 | 2015-07-27
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034227648 — C.C.ROAD PANDARI ROAD SE ARJUN KE GHAR KI AUR | Completed | 97776 | 80752.7 | 2014-08-30 | 2015-07-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034285940 — C.C.ROAD HOM SINGH KE DWAR SE BABA KE KUNWA KI AUR UMARI | Completed | 172988 | 140288 | 2015-10-24 | 2017-10-10
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034285941 — C.C.ROAD NARAYAN KE DWAR SE NAYAB SHAB KI BAGIA KI AUR UMARI | Completed | 172988 | 137585 | 2015-10-24 | 2017-10-10
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034303582 — C.C.ROAD NIRMAN RAMSHANKAR KE DWAR SE JAIN MANDIR KI OR | Completed | 145589 | 60053 | 2016-03-19 | 2020-07-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034304276 — C.C.ROAD NIRMAN VAHALIYA BABA SE SHYAM SINGH KE GHAR KI OR | Completed | 139112 | 87156 | 2016-03-19 | 2020-07-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034304286 — C.C.ROAD NIRMAN LAHAR ROAD SE LALA KA PURA KI OR | Completed | 139112 | 129570 | 2016-03-19 | 2021-12-01
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034304288 — C.C.ROAD NIRMAN SHILLU KE DWAR SE RAM SINGH DWAR TAK | Completed | 139112 | 4770 | 2016-03-19 | 2016-05-15
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034304292 — C.C.ROAD NIRMAN JAGDEESH KE GHAR SE ATAR SINGH KE GHAR KI OR | Completed | 139112 | 117168 | 2016-03-19 | 2020-05-19
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034304295 — C.C.ROAD NIRMAN MUKHY MARG RADHESYAM KE DWAR SE KISHOR SINGH KA PURA KI OR | Completed | 139112 | 81619 | 2016-03-19 | 2018-01-25
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034310632 — C.C.ROAD NIRMAN DILEEP SINGH KE DWAR SE TARA SINGH KE DWAR TAK DEVGAD | Deleted | 140750 | 0 | 2016-03-19
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034310634 — C.C.ROAD NIRMAN TEHNGUR ROAD SE SHALA BHAVAN KI OR GEHVAD | Deleted | 140750 | 0 | 2016-03-19
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034310635 — C.C.ROAD NIRMAN SATI CHAURAH SE NARESH RATHOR KI DWAR KI OR | Deleted | 140750 | 0 | 2015-04-14
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034366058 — Cc Road Nirman Singpura Road Se Raghurajan Yadav Ke Mkan Ki Aur | Completed | 77550 | 76176 | 2021-03-17 | 2021-12-01
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034366064 — C.C.ROAD NIRMAN PANCHAYAT BHAVAN SE ABHILAKH KE DWAR KI OR | Deleted | 132750 | 0 | 2020-06-01
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034386110 — C.C.ROAD NIRMAN PHOOL SINGH KE DWAR SE PANDARI ROAD KI OR | Completed | 132750 | 131526 | 2018-03-17 | 2020-07-27
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034387160 — C.C.ROAD NIRMAN MUKHAY SER SE PARSHOTAM KE DWAR KI OR | Deleted | 79050 | 0 | 2020-06-01
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034434034 — c.c.road nirman hariram ke dwar se ujagar ke dwar ki or motipura | Completed | 83700 | 55332 | 2019-01-12 | 2020-07-27
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034434038 — c.c.road nirman jal singh ke dwar se kamle ke dwar ki or | Completed | 93000 | 97962 | 2019-01-05 | 2020-05-19
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034442749 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034449028 — c.c.road nirman dileep ke dwar se shyambabu ki or devgad | Closed | 46500 | 0 | 2018-04-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034449032 — c.c.road nirman lala ke dwar se kaptan ke dwar ki or motipura | Deleted | 32550 | 0 | 2019-03-09
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034469863 — C.C.Road nirman pan singh ke dur se ujagar ki or | Ongoing | 57375 | 55032 | 2019-08-04
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034469864 — C.C.Road Nirman mukesh dwar se ballu ke dwar ki or devgar | Completed | 32550 | 34484 | 2019-08-04 | 2022-10-31
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034469865 — C.C.Road Nirman hanuman andir se atar singh ke gonda ki or | Ongoing | 32550 | 31888 | 2019-08-04
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034514501 — c.c.road nirman shealendra nai ke dwar se sanju bande ke dwar ki or | Completed | 116250 | 115272 | 2020-02-14 | 2021-12-01
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034514502 — c.c.road nirman devendra ke dwar se ramswaroop ke dwar ki or foji moholla | Completed | 93000 | 95892 | 2020-02-14 | 2021-12-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034523820 — सी सी रोड बज्रसेन के द्वार से गुलाब के द्वार की ओर उमरी | Completed | 34875 | 37056 | 2021-04-15 | 2021-12-01
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034523821 — सी सी रोड पप्पू महाते के द्वार से मुन्नी यादव के द्वार की और | Completed | 37200 | 36480 | 2021-02-24 | 2021-12-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034523822 — सी सी रोड दुजा के द्वार से केदारनाथ के द्वार की ओर | Completed | 84000 | 86850 | 2021-05-20 | 2022-10-31
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034523823 — सी सी रोड भूप सिंह जाटव के द्वार से सेवाराम कुम्हार की और | Completed | 93000 | 114000 | 2021-01-13 | 2021-12-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034568576 — Cc Road Janved Ke Dwar Se Mithalesh Ke Dwar Ki Aur Umari | Completed | 132000 | 132012 | 2021-04-22 | 2021-12-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034570565 — c.c. road | Deleted | 0 | 0 | 2021-04-22
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034570939 — सी सी रोड कनावर रोड से उमदेश्वर मदिर की ओर | Completed | 102000 | 120432 | 2021-05-20 | 2022-05-04
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034570987 — सी 0 सी0 रॉड एव नाली निमार्ण अरविंद आरोन बाले के हार से कल्लू सिकरिया की ओर | Completed | 93000 | 100746 | 2021-05-27 | 2022-05-04
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034578381 — kanawar road se manshingh chiteriya ke mkan tak | Closed | 93000 | 0 | 2021-04-15
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034597783 — c.c.road suresh ke dwar se kua ki or gehvat | Deleted | 144300 | 0 | 2021-10-02
BHIND / BHIND | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034846857 — CC Road Work GP Umari | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002036/RC/50 — सी0सी0 रोड निर्माण जगदीश के घर से कोमल के द्वार की ओर | Completed | 299231 | 91957 | 2012-06-07 | 2013-06-21
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002036/RS/22012034497170 — Saamudaayik Svachhata Parisar Umari | Completed | 43000 | 36480 | 2021-02-03 | 2021-12-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034524919 — seggreshan shed nirman umari | Ongoing | 37000 | 33582 | 2021-08-23
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034535637 — COMMUNITY NADEP DINESH KE GHAR KE SAMANE | Closed | 5000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034535648 — COMMUNITY NADEP VISHRAM KE GHAR KE SAMANE | Closed | 5000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034535659 — COMMUNITY NADEP FOJI NAGAR KE GHAR KE SAMANE | Closed | 5000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034535670 — COMMUNITY NADEP LOHA PIS MEDAN KE SAMANE | Closed | 5000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034535687 — COMMUNITY NADEP JAIN MANDIR KE PICHHE | Closed | 5000 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034535711 — COMMUNITY SOKPIT HIGH SCHOOL UMARI | Closed | 6600 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034535723 — COMMUNITY SOKPIT MIDDIL SCHOOL UMARI | Closed | 6600 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034535738 — COMMUNITY SOKPIT PRIMARY SCHOOL UMARI | Closed | 6600 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034535756 — COMMUNITY SOKPIT KANYA SHALA PRIMARY SCHOOL UMARI | Deleted | 6600 | 0 | 2021-07-03
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034535761 — COMMUNITY SOKPIT KANYA SHALA MIDDIL SCHOOL UMARI | Closed | 6600 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034536178 — SOKPIT NIRMAN POLICE THANE KE PASS | Deleted | 1100 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034536181 — SOKPIT NIRMAN JAIN KI BAGIYA KE PASS | Deleted | 1100 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034536184 — SOKPIT NIRMAN AGANWADI KE PASS | Deleted | 1100 | 0 | 2021-04-14
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002036/RS/22012034649893 — Constr of Community sanitary complex umari | Completed | 43000 | 24310 | 2023-04-27 | 2024-03-06
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034678151 — CONSTRUCTION OF SAMUDAYAK SOKHTA CHHATRAWAS KE SAMNE HANDPUMP KE PASS | Completed | 10000 | 6630 | 2023-07-17 | 2023-09-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034680007 — CONSTRUCTION OF SAMUDAYAK SOKHTA MAHARAJ SINGH KE GHAR KE PASS | Completed | 10000 | 7956 | 2023-07-16 | 2023-09-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034682145 — CONSTRUCTION OF SAMUDAYAK SOKHTA SHYAMSUNDAR OJHA LAHAR ROAD | Ongoing | 10000 | 6630 | 2023-09-11
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034682148 — CONSTRUCTION OF SAMUDAYAK SOKHTA VINOD MEMBER KE GHAR KE PASS | Closed | 10000 | 0 | 2022-11-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689601 — samudayak shokpit HANSE KE GHAR KE PASS UMARI | Completed | 10000 | 6630 | 2023-07-17 | 2023-09-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689605 — samudayak shokpit ENDAL SINGH KE MAKAN KE PASS UMARI | Completed | 10000 | 6630 | 2023-09-11 | 2024-10-17
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689606 — samudayak shokpit GAIYHAR WALE BABA PER DEVGAD | Ongoing | 10000 | 6630 | 2023-07-17
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689624 — samudayak shokpit RAMRATAN SINGH KE GHAR KE PASS UMARI | Physically Completed | 10000 | 7956 | 2023-09-11 | 2026-04-17
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689625 — samudayak shokpit BRAJESH BAGHEL KE GHAR KE PASS UMARI | Ongoing | 10000 | 7956 | 2023-07-16
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689628 — samudayak shokpit KULDEEP SINGH LAHAR ROAD UMARI | Physically Completed | 10000 | 6630 | 2023-09-11 | 2026-04-17
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689629 — samudayak shokpit DHEERENDRA SINGH KE GHAR KE PASSMOTIPURA UMARI | Completed | 10000 | 6630 | 2023-07-17 | 2024-03-21
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689630 — samudayak shokpit VEERENDRA KE GHAR KE PASS MOTIPURA UMARI | Completed | 10000 | 6630 | 2023-09-11 | 2024-10-16
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689631 — samudayak shokpit SOMNATH KE GHAR KE SAMNE MOTIPURA UMARI | Physically Completed | 10000 | 6630 | 2023-07-17 | 2026-04-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689643 — SAMUDAYIK NADEP RAMJANKI MANDIR KE PASS | Closed | 2000 | 0 | 2023-02-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689647 — SAMUDAYIK NADEP GAIYHAR WALE BABA PER UMARI | Closed | 2000 | 0 | 2023-02-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689649 — SAMUDAYIK NADEP MANDI KE PASS UMARI | Closed | 2000 | 0 | 2023-02-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689650 — SAMUDAYIK NADEP SHANKARJI MANDIR KE PASS | Closed | 2000 | 0 | 2023-02-15
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123218 — SAMUDAYAK SHOKPIT NIRMAD THANE KE BAGAL SE UMARI | Deleted | 10000 | 0 | 2024-02-14
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123546 — SAMUDAYAK SHOKPIT DEVENDRA NARAWALE KE DWAR PER | Deleted | 10000 | 0 | 2024-02-14
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123548 — SAMUDAYAK SHOKPIT RAMHET ROOR WALE KE DWAR PER | Deleted | 0 | 0 | 2023-08-16
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123549 — SAMUDAYAK SHOKPIT RAMHET ROOR WALE KE DWAR PER | Closed | 10000 | 0 | 2024-02-14
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123552 — SAMUDAYAK SHOKPIT RAGHVENDRA PATRAKAR KE DWAR PER | Closed | 10000 | 0 | 2024-02-14
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123917 — samudayak shokpitraghvendra patrakar ke dwar per | Ongoing | 10000 | 7290 | 2024-04-01
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123923 — SAMUDAYAK SHOKPITJITENDRA SHARMA LAHAR ROAD PER | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123926 — SAMUDAYAK SHOKPIT PAWAN SINGH MARKET KE YAHA SOKTA | Physically Completed | 10000 | 7290 | 2024-04-01 | 2026-04-17
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123927 — SAMUDAYAK SHOKPIT RAMVEER KE DWAR PER | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123931 — SAMUDAYAK SHOKPIT POORAN SINGH KE DWAR PER SOKHTA | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123933 — SAMUDAYAK SHOKPIT PAPPU MONUSINGH KE DWAR PER SOKHTA | Ongoing | 10000 | 7290 | 2024-04-01
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123934 — SAMUDAYAK SHOKPIT HOM SINGH KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123935 — SAMUDAYAK SHOKPIT LAKHAN SINGH KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123948 — SAMUDAYAK SHOKPIT GOVIND SINGH KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123949 — SAMUDAYAK SHOKPIT SANTOSH SINGH KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123952 — SAMUDAYAK SHOKPIT POORAN SINGH KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123953 — SAMUDAYAK SHOKPIT MINTU KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123954 — SAMUDAYAK SHOKPIT DR DASHRATH SINGH KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035124038 — SAMUDAYAK SHOKPIT SUGHAR SINGH BADHOLIYA KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035124042 — SAMUDAYAK SHOKPIT AHIVAR DR KE DWARSOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035124044 — SAMUDAYAK SHOKPIT RAMESH MODI KE DWAR PER SOKHTA GEHWAT | Closed | 10000 | 0 | 2024-02-20
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43391 — MARYADA ABHIYAN CHOTE / LAU | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43394 — MARYADA ABHIYAN AHIVARAN / RAMNARAYAN | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43399 — MARYADA ABHIYAN HARDAYAL / MATHURA PARASAD | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43402 — MARYADA ABHIYAN RAJKUMAR / CHOTELAL | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43411 — MARYADA ABHIYAN SURENDRA / DEVI | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43414 — MARYADA ABHIYAN JAKIR HUSSAIN / AMRUDDIN KHAN | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43417 — MARYADA ABHIYAN DILLIRAM / HARNARAYAN | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43421 — MARYADA ABHIYAN JABAR SINGH / GIRDAWAL | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43424 — MARYADA ABHIYAN SOVRAN / PAN SINGH | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43427 — MARYADA ABHIYAN LALU KHAN / AMJAD KHAN | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43473 — MARYADA ABHIYAN RAJESH / RAMESWAR | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43480 — MARYADA ABHIYAN SURENDRA / DHARMA SINGH | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43483 — MARYADA ABHIYAN BHARAT SINGH / CHOTE SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43485 — MARYADA ABHIYAN SHIROMAN / JAIRAM | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43488 — MARYADA ABHIYAN SANTOSH / SHARANLAL | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43491 — MARYADA ABHIYAN BASARAT KHAN / BUDHU KHAN | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43494 — MARYADA ABHIYAN MUSTAP KHAN / PUTTU KHAN | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43497 — MARYADA ABHIYAN MAHARAJ SINGH / RAGHUNATH SINGH | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43502 — MARYADA ABHIYAN VIRENDRA / AHIVARAN SINGH | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43555 — MARYADA ABHIYAN DALVEER / VIJAY SINGH | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43559 — MARYADA ABHIYAN SANTOSH / GIRDAWAL | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43561 — MARYADA ABHIYAN RAMAVTAR | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43564 — MARYADA ABHIYAN SWAROOPNAND | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43566 — MARYADA ABHIYAN KRISHNA BIHARI / NANDRAM | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43569 — MARYADA ABHIYAN MAHAVEER / JIYALAL | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43572 — MARYADA ABHIYAN SUNDAR BAI / CHANDAN | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43575 — MARYADA ABHIYAN MAHENDRA SINGH / RAGHUNATH SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43577 — MARYADA ABHIYAN RAMESWAR / MADHO SINGH | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43579 — MARYADA ABHIYAN UDAYVEER / MUNSHI | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43581 — MARYADA ABHIYAN LAKHAN SINGH / MANSHARAM | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43585 — MARYADA ABHIYAN SOVRAN / CHOTELAL | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43587 — MARYADA ABHIYAN SUBHASH CHANDRA / BHAGCHANDRA | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43588 — MARYADA ABHIYAN CHOTE KHAN / BABU KHAN | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43592 — MARYADA ABHIYAN KARU / JAGDEESH | Completed | 4500 | 4626 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43594 — MARYADA ABHIYAN JAGDESH / BADRI | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43597 — MARYADA ABHIYAN AGYARAM / HARIVILAS | Completed | 4500 | 4469 | 2014-08-02 | 2014-08-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43599 — MARYADA ABHIYAN ARVIND / MEVARAM | Completed | 4500 | 2669 | 2014-08-02 | 2016-08-11
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43601 — MARYADA ABHIYAN NARESH / NATHU | Deleted | 4500 | 0 | 2012-08-15
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002036/RS/43603 — MARYADA ABHIYAN JASMANT / RAM DEEN | Completed | 4500 | 4469 | 2014-07-05 | 2014-07-11
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002036/WC/22012034325441 — TALAB MARMAT KARY UMARI | Completed | 79600 | 83764 | 2017-05-20 | 2017-10-09
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012034705811 — talav gaharikaran nirman hanuman mandir ke pas | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002036/WC/22012034770669 — water harvesting tank school parisar umari | Completed | 38864.3 | 6948 | 2021-06-24 | 2023-04-22
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035002573 — khet talav padam singh | Deleted | 0 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035002574 — khet talav padam singh | Completed | 356340.1 | 194276 | 2022-12-23 | 2024-10-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1702002036/WC/22012035039990 — marmmat kary kool and nahar motipura umari | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002036/WC/22012035087768 — Khet talav Nirman sanjeev ke khet par | Completed | 350433.91 | 270283 | 2023-08-07 | 2024-10-17
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035092962 — khet talav nirman parmal singh khet par | Completed | 383083.54 | 204867 | 2023-10-07 | 2025-06-11
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702002036/WC/22012035103544 — khet talav nirman parmal singh khet par | Deleted | 0 | 0 | 2023-08-15
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035107394 — khet talav nirman ramsevak singh khet par | Completed | 383083.54 | 169728 | 2023-09-23 | 2025-06-11
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035187110 — talav nirman dolaya bala umari | Deleted | 0 | 0 | 2024-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035187137 — talav nirman dolaya bala umari | Deleted | 0 | 0 | 2024-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002036/WC/22012035187141 — talav nirman dolaya bala umari | Closed | 985140.02 | 0 | 2024-01-26
BHIND / BHIND | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002036/WC/43 — तालाब विस्‍तारीकरण उमरी | Completed | 82225 | 79332 | 2012-06-21 | 2012-07-05