## Work List
Exported on: 2026-10-19 08:29:37
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: UMRAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034621688 — naveen shantidham nirman gehbat | Ongoing | 290458.68 | 0 | 2022-11-24
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034622823 — naveen shantidham nirman motipura1 | Ongoing | 280230.45 | 0 | 2022-11-16
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034639496 — naveen shantidham nirman umari | Ongoing | 322408.11 | 0 | 2024-11-06
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034658522 — SHANTIDHAM NIRMAN KARYA DEVGAD UMARI | New | 0 | 0 | 2024-06-14
BHIND / BHIND | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002036/AV/22012034669315 — SHANTI DHAM NIRMAN PANDRI ROAD UMARI | New | 0 | 0 | 2026-01-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1702002036/DP/22012034597686 — meri mati mera desh amrit vatika nirman govt kanya school umari | Ongoing | 56725.4 | 0 | 2023-09-04
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002036/IF/22012035582492 — खेत तालाब निर्माण कार्य ग्राम पंचायत umari | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1702002036/IF/22012035582494 — kapil dhara kup work gp umari | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133966 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/114 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133967 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/145 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133968 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/207 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133969 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/254 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133970 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/504 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/133972 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/227 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199289 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/148 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199290 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/219 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199291 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/521 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/199292 — Construction of IAY House -IAY REG. NO. MP-02-002-036-001/532 | Approved | 27000 | 0 | 2016-03-26
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5608932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126465428 | Approved | 27000 | 0 | 2025-05-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5614343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146779137 | Physically Completed | 27000 | 0 | 2025-06-02 | 2026-08-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5615050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118019887 | Ongoing | 27000 | 0 | 2025-07-28
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5615235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146843620 | Ongoing | 27000 | 0 | 2025-06-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5615935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113655253 | Ongoing | 27000 | 0 | 2025-06-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002036/IF/IAY/5616548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129964908 | Ongoing | 27000 | 0 | 2025-06-02
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034469863 — C.C.Road nirman pan singh ke dur se ujagar ki or | Ongoing | 57375 | 0 | 2019-08-04
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034469865 — C.C.Road Nirman hanuman andir se atar singh ke gonda ki or | Ongoing | 32550 | 0 | 2019-08-04
BHIND / BHIND | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002036/RC/22012034846857 — CC Road Work GP Umari | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034524919 — seggreshan shed nirman umari | Ongoing | 37000 | 0 | 2021-08-23
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012034682145 — CONSTRUCTION OF SAMUDAYAK SOKHTA SHYAMSUNDAR OJHA LAHAR ROAD | Ongoing | 10000 | 0 | 2023-09-11
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689606 — samudayak shokpit GAIYHAR WALE BABA PER DEVGAD | Ongoing | 10000 | 0 | 2023-07-17
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702002036/RS/22012034689625 — samudayak shokpit BRAJESH BAGHEL KE GHAR KE PASS UMARI | Ongoing | 10000 | 0 | 2023-07-16
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123917 — samudayak shokpitraghvendra patrakar ke dwar per | Ongoing | 10000 | 0 | 2024-04-01
BHIND / BHIND | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002036/RS/22012035123933 — SAMUDAYAK SHOKPIT PAPPU MONUSINGH KE DWAR PER SOKHTA | Ongoing | 10000 | 0 | 2024-04-01