## Work List
Exported on: 2026-09-28 16:44:22
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BILAV
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1702002037/DP/22012034595050 — Amart Vatika kachar sarovar k pas BILAW | Ongoing | 55847.4 | 0 | 2023-09-18
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002037/IF/22012035518076 — KHET TALAB NARAYAN KE KHET PER | Ongoing | 147621.16 | 0 | 2025-05-18
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002037/IF/22012035518118 — KHET TALAB LAKSHAI K KHET K PAS | Ongoing | 147621.16 | 0 | 2025-05-18
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002037/IF/22012035532949 — KHET TALAB RAJESH K KHET PR | Ongoing | 147621.16 | 0 | 2025-05-24
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002037/IF/22012035532996 — KHET TALAB PREMNARAYAN K KHET PR | Ongoing | 147621.16 | 0 | 2025-05-24
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002037/IF/22012035533074 — KHET TALAB KISHAN SINGH K KHET PR | Ongoing | 147621.16 | 0 | 2025-05-24
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002037/IF/22012035533110 — KHET TALAB AWADH NARAYAN K KHET PR | Ongoing | 147621.16 | 0 | 2025-05-24
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002037/IF/22012035626972 — EK BAGIYA MA K NAM NEETA/BHEEM SINGH | Approved | 187949.48 | 0 | 2025-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/133974 — Construction of IAY House -IAY REG. NO. MP-02-002-037-001/100 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/133976 — Construction of IAY House -IAY REG. NO. MP-02-002-037-001/94 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/133978 — Construction of IAY House -IAY REG. NO. MP-02-002-037-001/98 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/134122 — Construction of IAY House -IAY REG. NO. MP-02-002-037-001/95 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/3825537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119974734 | Approved | 27000 | 0 | 2022-05-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4881685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150053579 | Ongoing | 27000 | 0 | 2025-05-18
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4882194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149622137 | Ongoing | 27000 | 0 | 2025-02-13
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4882253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147245894 | Ongoing | 27000 | 0 | 2025-04-09
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4882261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147281692 | Ongoing | 27000 | 0 | 2025-08-26
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4882263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147281760 | Ongoing | 27000 | 0 | 2025-04-21
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4882264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147281804 | Ongoing | 27000 | 0 | 2025-02-24
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4915401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147242227 | Ongoing | 27000 | 0 | 2025-03-24
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/4915413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147293269 | Ongoing | 27000 | 0 | 2025-04-09
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5616221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149670300 | Physically Completed | 23490 | 0 | 2025-06-17 | 2026-08-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5616811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122777455 | Ongoing | 27000 | 0 | 2025-07-28
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5616872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147666883 | Ongoing | 27000 | 0 | 2025-07-28
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5616949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127714092 | Approved | 27000 | 0 | 2025-03-31
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5616962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119596018 | Ongoing | 27000 | 0 | 2025-08-04
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5720977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120924137 | Ongoing | 27000 | 3600 | 2026-02-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5852802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146963623 | Ongoing | 27000 | 0 | 2025-12-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5852875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147234342 | Ongoing | 27000 | 0 | 2025-12-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5852939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146913297 | Physically Completed | 23490 | 0 | 2025-12-30 | 2026-08-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5852962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147265866 | Ongoing | 27000 | 3600 | 2025-12-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5852964 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118336099 | Ongoing | 27000 | 0 | 2025-12-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5852965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118339114 | Ongoing | 27000 | 0 | 2026-02-25
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002037/IF/IAY/5853094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147273335 | Ongoing | 27000 | 0 | 2025-12-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Horticulture Trees for Community | Plantation | 1702002037/LD/22012034474882 — charagah nirmad bilaw | Ongoing | 811270.93 | 0 | 2021-06-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002037/RC/22012034613145 — Sudur road bilaw se yadavpura ki pura ki or | Ongoing | 2478126.76 | 0 | 2022-05-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002037/RS/22012034665781 — Samudayak NADEP Laxminarayan gr k pas | Ongoing | 2000 | 0 | 2023-01-18
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002037/WC/22012034981485 — BANDHA NIRMAD KATAN WALI NARIYA K PAS | Ongoing | 980786.91 | 0 | 2022-05-29
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002037/WC/22012035063226 — Naveen talab Gadrayi wala talab kachar | Ongoing | 2291759.36 | 0 | 2023-11-27