## Work List
Exported on: 2026-10-25 11:29:27
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KHARIKA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002041/AV/22012034375084 — SHANTI DHAM NIRMAN DHAJEKAPURA (KHARIKA) | Completed | 245000 | 238714 | 2018-08-18 | 2021-04-23
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002041/AV/22012034508564 — GAUSHALA NIRMAN KHARIKA | Closed | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1702002041/AV/22012034510253 — KICHAN SHED NIRMAN GOVT. P.S. DHAJEKA PURA | Ongoing | 425000 | 63270 | 2020-07-06
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1702002041/AV/22012034534020 — Construction Of Pavor Blaock Near High School Kharika | Completed | 90000 | 86640 | 2020-09-26 | 2021-02-28
BHIND / BHIND | 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1702002041/AV/22012034535545 — Gau Shala nirman kharika | Ongoing | 3784582.21 | 1140 | 2020-09-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002041/AV/22012034537620 — contraction of pevar block middil school kharika | Completed | 83100 | 80270 | 2020-09-26 | 2021-06-14
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002041/AV/22012034546318 — Katan nirman shankar ji mandir ke pas | Completed | 410703.52 | 382144 | 2021-03-27 | 2022-10-28
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1702002041/AV/22012034546319 — Katan nirman sati mata mandir ke pas | Closed | 0 | 0 | 2020-11-18
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1702002041/AV/22012034562715 — pavar block nirman pramary school kharika | Completed | 75000 | 71688 | 2021-03-19 | 2021-05-05
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002041/AV/4868 — AGANBADI BHAVAN NIRMAN KHARIKA | Completed | 330000 | 329986 | 2017-08-04 | 2020-04-30
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002041/AV/5111 — AGANBADI BHAVAN DHAJE KA PURA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1702002041/DP/22012034541280 — maa ki bagiya nirman govt,school,kharika | Closed | 0 | 0 | 2021-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702002041/DP/22012034547893 — maa ki bagiya nirman govt.p,s,kharika | Ongoing | 9000 | 8976 | 2022-10-29
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702002041/DP/22012034547894 — maa ki bagiya nirman govt.h,s,kharika | Completed | 9000 | 8976 | 2022-06-05 | 2022-11-30
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002041/DP/22012034594577 — meri mati mera desh amrit vatika nirman shantidham kharika | Closed | 56725.4 | 0 | 2023-06-30
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002041/DP/22012034594599 — meri mati mera desh amrit vatika nirman govt high school kharika | Closed | 56725.4 | 0 | 2023-06-30
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002041/FP/22012034624756 — kachha nala nirman jhanda ke tal se bamba ki or | Completed | 202620.01 | 61200 | 2022-12-05 | 2023-07-07
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002041/FP/22012034627361 — nala nirman rajesh ke dwar se dhara singh ke dwar ki or | Completed | 34500 | 25704 | 2022-05-27 | 2023-03-13
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002041/FP/22012034630723 — kachcha nala nirman ranvijay ke dwar se chhotelal ke dwar ki or | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002041/IF/22012034352174 — vrIksharopan shantidham me kharika | Completed | 335000 | 30072 | 2017-06-16 | 2018-11-06
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002041/IF/22012034352334 — VRIKSHAROPAN KARAY SCHOOL,TALAB KHARIKA | Completed | 335000 | 29136 | 2017-06-16 | 2019-06-19
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702002041/IF/22012034440831 — sochalay nirman kary kushma/mukhram | Deleted | 12000 | 0 | 2018-04-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034593068 — CATTEL SHED LAKSHMAN / PAN SINGH | Closed | 0 | 0 | 2020-04-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034593071 — CATTEL SHED AYODHYA / DHEER SINGH | Ongoing | 101273.16 | 4560 | 2020-09-11
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034593072 — CATTEL SHED HARNATH / ROOPSAHAY | Completed | 101804.91 | 92836.88 | 2020-09-30 | 2022-05-10
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034593073 — CATTEL SHED HOM SINGH / MAHARAJ SINGH | Ongoing | 101273.16 | 2280 | 2020-09-25
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594549 — CATTAL SHED RAKESH / NARENDRA | Completed | 101273.16 | 91696.88 | 2020-09-25 | 2021-08-30
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594550 — CATTAL SHED SURENDRA / RAMBARAN | Completed | 101273.16 | 92836.88 | 2020-09-25 | 2022-05-10
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594551 — CATTAL SHED DEVENDRA / BALIRAM | Completed | 101273.16 | 82576.88 | 2020-09-14 | 2022-05-10
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594552 — CATTAL SHED AMAR SINGH / RAMHET | Completed | 101273.16 | 92872.88 | 2020-09-25 | 2022-05-10
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594553 — CATTAL SHED VISHWNATH / ROOPSAHAY | Ongoing | 101273.16 | 3420 | 2020-09-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594556 — CATTAL SHED PRADEEP / RAMBHAROSE | Completed | 101273.16 | 90556.88 | 2020-09-30 | 2021-10-25
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594557 — CATTAL SHED BRAJESH / DWARIKA | Ongoing | 101273.16 | 3420 | 2020-09-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594558 — CATTAL SHED UPENDRA / VASDEV | Completed | 101273.16 | 92076.88 | 2020-09-25 | 2021-05-05
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594559 — CATTAL SHED LAKHAN / LAKSHMAN | Completed | 101273.16 | 91886.88 | 2020-09-14 | 2021-03-13
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594563 — CATTALE SHED HET SINGH / BALVEER | Ongoing | 101273.16 | 3420 | 2020-09-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594564 — CATTAL SHED SHYAM SINGH / NARAYAN | Completed | 101273.16 | 92890.88 | 2020-09-14 | 2021-05-05
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594565 — CATTAL SHED MUNNA / KASHIRAM | Completed | 101273.16 | 92836.88 | 2020-10-03 | 2021-03-13
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034594567 — cattal shed gajendra / rambharose | Closed | 0 | 0 | 2020-04-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034598558 — CATTEL SHED ramu singh / narhari | Closed | 101273.16 | 0 | 2020-10-03
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034598559 — CATTEL SHED rajaveti / mathura prasad | Ongoing | 101273.16 | 2280 | 2020-09-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034598899 — CATTEL SHED janesh singh / rukum singh | Ongoing | 101273.16 | 3420 | 2020-09-14
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034607062 — CATTEL SHED vijay singh / nathu | Completed | 101273.16 | 90556.88 | 2020-10-03 | 2021-10-25
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034607063 — CATTEL SHED kamlesh / lakhan | Closed | 101273.16 | 0 | 2020-10-03
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034609779 — CATTEL SHED MANSHARAM / MANIRMA | Closed | 101273.16 | 0 | 2020-10-03
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034609780 — CATTEL SHED CHANDRAPRATAP / AHIVARAN | Suspended | 101273.16 | 0 | 2020-10-03
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034647928 — CATTEL SHED RAJNARAYAN SHUKLA / JAGNNATH | Closed | 0 | 0 | 2020-11-18
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/22012034647932 — CATTEL SHED NIRMAN PRAGATI KUMAR / RAMPRAKASH | Closed | 0 | 0 | 2020-11-18
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002041/IF/22012035131723 — khet talav nirman ramvihari/bannelal khet pa | Closed | 0 | 0 | 2023-06-28
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002041/IF/22012035131780 — naveen khet talav nirman mahendrapal/sultan singh khet par | Physically Completed | 383083.54 | 190502 | 2023-09-18 | 2026-04-17
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002041/IF/22012035131793 — naveen khet talav nirman darsan/kanai khet par | Physically Completed | 383083.54 | 191828 | 2023-08-14 | 2026-04-17
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002041/IF/22012035491939 — naveen khet talav nirman vishnath singh / hari singh khet par | Deleted | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002041/IF/22012035493825 — KHET TALAB NIRMAN VISHNATH SINGH / HARI SINGH KE KHET PER | Closed | 450885.64 | 522 | 2025-05-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993673650 — CATTLE SHED RAJKUMAR/RAMBHAROSE | Completed | 115900 | 94928 | 2015-09-11 | 2017-05-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993674141 — cattle shed raghvendra singh / surendra singh | Completed | 115900 | 92066 | 2015-09-18 | 2017-05-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993674154 — CATTLE SHED MADHURAJ SINGH / RAN SINGH | Completed | 115900 | 94133 | 2015-09-18 | 2017-04-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993674157 — CATTEL SHED BHANUPRATAP / JANAK SINGH | Completed | 115900 | 94928 | 2015-09-18 | 2017-02-12
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993674159 — CATTEL SHED BASUDEV SINGH / BHAVAR SINGH | Completed | 115900 | 90953 | 2015-09-18 | 2016-12-12
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993698936 — CATTEL SHED RAMVARAN/PATIRAM | Completed | 115900 | 96630.97 | 2015-12-25 | 2017-04-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993698940 — CATTEL SHED ASHOK KUMAR/AJJUDHI | Completed | 115900 | 94588.08 | 2015-12-25 | 2017-04-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993703902 — CATTEL SHED MUKHRAM / KHYALI | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993703904 — CATTEL SHED RAMHET / HARBHAJAN | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993703906 — CATTEL SHED ASHOK SINGH / BRAHMA SINGH | Completed | 115900 | 104176.97 | 2016-05-13 | 2016-12-12
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993703907 — CATTEL SHED VIKRAM / KAMMOD | Completed | 115900 | 101504.97 | 2016-05-13 | 2017-04-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993703908 — CATTEL SHED LAKSHMAN / PAN SINGH | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993703909 — CATTEL SHED ARVINDRA / PATOKHI | Deleted | 115900 | 0 | 2015-10-02
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993716220 — CATTEL SHED MAHESH SINGH / BRAJVIHARI | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993716221 — CATTEL SHED VIMLESH / SATENDRA | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993716222 — CATTEL SHED SOKIRAM / BALDU | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993716223 — CATTEL SHED LAKHAN / LAKSHAMAN | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718340 — CATTEL SHED MUNNA SINGH / JHIGURI | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718341 — CATTEL SHED DATARAM / KEDAR | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718342 — CATTEL SHED KELASH / HIMANCHAL | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718343 — CATTEL SHED KUAR SINGH / RAJARAM | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718344 — CATTEL SHED BALKISHAN / ARJUN | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718345 — CATTEL SHED AMAR SINGH / RAMSNEHI | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993718346 — CATTEL SHED VISHNATH / ROOPSAHAY | Deleted | 115900 | 0 | 2015-12-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993727762 — CATTEL SHED PREM SINGH / BRAJENDRA | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993727766 — CATTEL SHED JAYPAL / BHOLA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993727768 — CATTEL SHED HOM SINGH / MAHARAJ SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002041/IF/9993727770 — CATTEL SHED VEER SINGH / VANNE SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/134035 — Construction of IAY House -IAY REG. NO. MP-02-002-041-001/156 | Completed | 14310 | 13861 | 2016-06-03 | 2017-05-25
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/134036 — Construction of IAY House -IAY REG. NO. MP-02-002-041-001/35 | Completed | 14310 | 13724 | 2016-07-22 | 2018-04-13
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/199295 — Construction of IAY House -IAY REG. NO. MP-02-002-041-001/27 | Completed | 15030 | 14088 | 2016-07-22 | 2017-06-25
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/255946 — Construction of IAY House -IAY REG. NO. MP2144323 | Completed | 15030 | 15120 | 2017-01-20 | 2018-02-10
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/273035 — Construction of IAY House -IAY REG. NO. MP2999202 | Completed | 15030 | 16092 | 2017-01-20 | 2017-07-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/3792961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106495182 | Completed | 18360 | 17425 | 2022-09-06 | 2024-03-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/3823888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120578278 | Completed | 18360 | 17340 | 2022-09-13 | 2024-03-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/3837255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123805391 | Physically Completed | 18360 | 8772 | 2022-10-29 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4230257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123801883 | Completed | 18360 | 17323 | 2022-09-14 | 2024-03-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4326231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120575968 | Physically Completed | 18360 | 7548 | 2022-11-28 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4326316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120607268 | Physically Completed | 18360 | 16813 | 2022-11-05 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4369664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123810534 | Completed | 18360 | 18156 | 2022-11-05 | 2024-03-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4376263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120588432 | Completed | 18360 | 17833 | 2022-11-05 | 2024-03-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4376265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120602785 | Physically Completed | 18360 | 2550 | 2022-12-05 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4379103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120607697 | Completed | 18360 | 18156 | 2022-11-05 | 2024-03-03
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4386016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120605409 | Physically Completed | 18360 | 6528 | 2023-01-20 | 2024-11-21
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/4394135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120589896 | Physically Completed | 19890 | 1326 | 2023-05-03 | 2024-11-21
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/465850 — Construction of IAY House -IAY REG. NO. MP1769370 | Completed | 15030 | 14792 | 2017-01-27 | 2018-04-09
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5620517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120585009 | Physically Completed | 23490 | 0 | 2025-07-30 | 2026-06-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5620655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120585413 | Physically Completed | 23490 | 4698 | 2025-07-30 | 2026-02-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5620883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120582729 | Ongoing | 23490 | 4698 | 2025-07-31
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5621038 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123799481 | Physically Completed | 23490 | 4698 | 2025-07-31 | 2026-06-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5621688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120608498 | Ongoing | 23490 | 4698 | 2025-07-31
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5621859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120579434 | Physically Completed | 23490 | 4698 | 2025-07-31 | 2026-06-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/5621990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120580221 | Ongoing | 23490 | 3132 | 2025-07-31
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002041/IF/IAY/566597 — Construction of IAY House -IAY REG. NO. MP3925363 | Completed | 15030 | 14990 | 2017-01-27 | 2018-07-19
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/149 — मेढबंधान सामंत पुत्र मुरली | Completed | 13000 | 11971 | 2009-07-29 | 2011-07-12
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/150 — मेढबंधान रामसखी वेवा शोभाराम | Completed | 16000 | 13700 | 2010-07-23 | 2010-07-23
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/151 — मेढबंधान भूरे / रामेश्‍वर | Completed | 14000 | 9600 | 2010-08-05 | 2010-08-05
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002041/LD/22012034241191 — SHANTIDHAM NIRMAD KHARIKA | Completed | 1479300 | 1425078 | 2015-12-11 | 2017-11-30
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034255120 — MED BANDHAN BRAHMA SINGH/RISHIKESH | Completed | 41600 | 37832 | 2016-02-19 | 2016-12-12
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034255129 — MED BANDHAN ARVIND/PATOKHI | Completed | 40000 | 36775 | 2016-02-19 | 2016-12-12
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034255137 — MED BANDHAN VIKRAM SINGH/ KAMMOD | Completed | 47600 | 43551 | 2016-02-19 | 2016-12-12
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034255141 — MED BANDHAN RAMA DEVI/BRAHMA | Completed | 59500 | 44004 | 2016-02-19 | 2016-12-12
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034256845 — MED BANDHAN PAN SINGH / CHOTE SINGH | Completed | 35700 | 31529 | 2016-03-18 | 2016-12-12
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262965 — MED BANDHAN VEERENDRA / UMRAV SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262968 — MED BANDHAN JAYPAL / BHOLA SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262969 — MED BANDHAN KALIKA / UMRAV SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262970 — MED BANDHAN DHEER SINGH / KAMMOD | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262971 — MED BANDHAN GODAN / KEDAR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262972 — MED BANDHAN PREMKISHOR / CHETRAM | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262973 — MED BANDHAN PRAYAG SINGH / BHAVAR SINGH | Deleted | 35400 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002041/LD/22012034262974 — MED BANDHAN KAUR SINGH / BHAVAR SINGH | Completed | 35400 | 18203 | 2016-08-19 | 2016-12-12
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002041/LD/22012034262975 — MED BANDHAN HOM SINGH / MAHARAJ SINGH | Completed | 35400 | 25384 | 2016-08-19 | 2016-12-12
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262976 — MED BANDHAN RAGHUVEER / BHARAT SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262977 — MED BANDHAN VIJAY SINGH / SHRILAL | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262978 — MED BANDHAN MAJBUT / BHAGIRATH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262979 — MED BANDHAN BANBARI / MITHAE LAL | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262980 — MED BANDHAN SHIVCHARAN / REVATIRAM | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262981 — MED BANDHAN RAMVARAN / PATIRAM | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262982 — MED BANDHAN RAMBHAJAN / RAMBHAJAN | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262983 — MED BANDHAN BANKAT / RAGHUVEER | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262984 — MED BANDHAN DHURANDAR / KADORE | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262985 — MED BANDHAN SAMAR SINGH / BADURI | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002041/LD/22012034262986 — MED BANDHAN MADHURAJ / RAN SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002041/LD/22012034291872 — MED BANDHAN VASDEV / BHAVAR SINGH | Completed | 35400 | 25050 | 2016-08-19 | 2016-12-12
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002041/LD/22012034291873 — MED BADHAN JAESEERAM / HARVANSH | Deleted | 35400 | 0 | 2016-08-12
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002041/LD/22012034291874 — MED BANDHAN RAMOTAR / SURAJPAL | Deleted | 35400 | 0 | 2016-08-12
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702002041/LD/22012034291875 — MED BANDHAN ROOPNARAYAN / SURAJPAL | Deleted | 35400 | 0 | 2016-08-12
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034517886 — MED BANDHAN NIRMAN NARENDRA / BHAVAR KHET PAR | Completed | 30042.19 | 24700 | 2020-07-28 | 2020-09-25
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034517889 — MED BANDHAN NIRMAN PREMKISHOR / CHETRAM KHET PAR | Completed | 30042.19 | 23940 | 2020-07-28 | 2020-12-13
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034517890 — MED BANDHAN NIRMAN SHIVCHARAN / REVATIRAM KHET PAR | Completed | 25591.49 | 20520 | 2020-07-28 | 2020-10-25
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034517891 — MED BANDHAN NIRMAN RAMBARAN /PATIRAM KHET PAR | Completed | 24478.82 | 20140 | 2020-07-28 | 2020-11-06
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034517894 — MED BANDHAN NIRMAN VITTI DEVI /SURENDRA KHET PAR | Completed | 28929.51 | 23940 | 2020-07-28 | 2020-11-06
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034517895 — MED BANDHAN NIRMAN VASDEV / BHAVAR KHET PAR | Completed | 27816.84 | 22800 | 2020-07-28 | 2020-08-30
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034518105 — MED BANDHAN NIRMAN PAN SINGH / CHHOTE SINGH KHET PAR | Completed | 31154.86 | 26220 | 2020-07-28 | 2020-10-25
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034518106 — MED BANDHAN NIRMAN GODAN / KEDAR KHET PAR | Completed | 31154.86 | 25080 | 2020-07-28 | 2020-08-30
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034519194 — MED BANDHAN NIRMAN RAMSEVA / KHYALI KHET PAR | Closed | 0 | 0 | 2020-04-14
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524954 — MED BANDHAN HOM SINGH / MAHARAJ SINGH KHET PAR | Completed | 28693.73 | 22800 | 2020-09-25 | 2020-11-20
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524955 — MED BANDHAN VIKRAM SINGH / KAMMOD KHET PAR | Completed | 27183.53 | 23940 | 2020-09-25 | 2021-03-13
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524956 — MED BANDHAN AYODHYA / DHEER SINGH KHET PAR | Completed | 24163.14 | 20520 | 2020-09-25 | 2021-02-28
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524957 — MED BANDHAN ENDAL / RAGHUVEER KHET PAR | Completed | 31714.13 | 27360 | 2020-09-25 | 2021-03-13
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524958 — MED BANDHAN SAMAR SINGH / BADRI SINGH KHET PAR | Completed | 31714.13 | 27360 | 2020-09-25 | 2021-03-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524959 — MED BANDHAN JASRATH / MAHARAJ SINGH KHET PAR | Completed | 27183.53 | 23932 | 2021-05-20 | 2021-06-14
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524960 — MED BANDHAN SURESH SINGH / BHARAT SINGH KHET PAR | Completed | 30959.03 | 26220 | 2020-09-25 | 2021-03-30
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524961 — MED BANDHAN DHURAV SINGH / DHEER SINGH KHET PAR | Completed | 27183.53 | 22800 | 2020-09-25 | 2021-03-30
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524962 — MED BANDHAN VIJAY SINGH / SHRILAL KHET PAR | Completed | 30203.93 | 25080 | 2020-09-25 | 2021-03-13
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034524963 — MED BANDHAN GAMBHIR SINGH / BHARAT SINGH KHET PAR | Completed | 31714.13 | 26220 | 2020-09-25 | 2021-03-13
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702002041/LD/22012034542530 — uparjan kendra kharika (motipura) chabutra nirman | Closed | 0 | 0 | 2021-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702002041/LD/22012034542839 — uparjan kendra kharika (motipura) chabutra nirman | Suspended | 802553.42 | 0 | 2021-03-31
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034550588 — Med bandhan nirman rajesh singh khet par | Completed | 23010.96 | 19686 | 2021-05-13 | 2021-06-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034550589 — Med bandhan nirman santosh singh khet par | Completed | 27613.16 | 19686 | 2021-05-13 | 2021-08-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034551232 — med bandhan nirman ashok khet par | Completed | 29147.22 | 20072 | 2021-05-27 | 2021-10-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034551233 — med bandhan nirman arvindra khet par | Completed | 25312.06 | 21616 | 2021-05-13 | 2021-07-13
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034551234 — med bandhan nirman dharmendra khet par | Completed | 24851.85 | 20844 | 2021-05-13 | 2021-07-13
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034551236 — med bandhan nirman avadesh khet par | Completed | 23010.96 | 20265 | 2021-05-13 | 2021-06-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034551237 — med bandhan nirman badshah khet par | Completed | 24238.22 | 17370 | 2021-05-20 | 2021-08-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/LD/22012034551238 — med bandhan nirman santosh khet par | Completed | 28380.19 | 24318 | 2021-05-13 | 2021-07-13
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002041/OP/9425889374 — CATTEL PROTECTION WALL GOVT. M. SCHOOL KHARIKA | Deleted | 0 | 0 | 2015-10-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002041/OP/9425889375 — CATTEL PROTECTION WALL GOVT. P/S. SCHOOL DHAJEKA PURA | Deleted | 0 | 0 | 2015-10-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702002041/OP/9425890018 — NAL BANDHAN NIRMAN DEVI KE MAKAN SE HANUMAN MANDIR KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702002041/OP/9425890019 — TALAB NIRMAN HANUMAN MANDIR KE PASS | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002041/PG/9425888430 — KHEL MAEDAN NIRMAN KHARIKA | Completed | 153600 | 136076 | 2017-03-24 | 2018-04-09
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034202569 — C.C.ROAD PAPPU KE DWAR SE BAJRANG VALI KE MANDIR T | Completed | 39258 | 31324 | 2014-04-24 | 2014-08-09
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034202580 — C.C.ROAD VINOD KE DWAR SE DILSUKHRAM KE DWAR KI AU | Completed | 124217 | 85761 | 2014-05-09 | 2015-05-08
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034202581 — C.C.ROAD DEVI SINGH KE DWAR SE BAJRANG VALI KE MAN | Completed | 124217 | 110881 | 2014-04-24 | 2014-10-10
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034202582 — C.C.ROAD NAVEEN HANDPUMP SE DILSUKHRAM KE DWAR KI | Completed | 39258 | 29127 | 2014-08-22 | 2015-09-18
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034296165 — MITTI BAJARIKARAN NIRMAN HANUMAN JI KE MANDIR SE NARENDRA KE MAKAN TAK | Completed | 1446900 | 811199 | 2016-01-15 | 2016-12-12
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034305721 — C.C.ROAD NIRMAN PREMKISHOR KE DWAR SE SONPAL KE DWRA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034305722 — C.C.ROAD NIRMAN GUPAL KE DWAR SE GOVT.P/S KI OR DHAJEKA PURA | Deleted | 0 | 0 | 2015-10-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034305968 — C.C.ROAD NIRMAN RAMVAKSH KE DWAR SE AJMER KE DWAR KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034306019 — C.C.ROAD NIRMAN PREM SINGH KE DWAR SE RAMESH KE DWAR KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034306020 — MITTI BAJRIKARAN KHARIKA SE MOTIPURA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034306021 — MITTI BAJRIKARAN CHANDI MATA KE MANDIR SE LACHHIRAM PURA KI OR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034318297 — HARIJAN BASTI C.C. ROAD NIRMAN TALAB SE RAMHET DWAR KI OR | Deleted | 194000 | 0 | 2016-10-02
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034318447 — harijan basti c.c.road nirman talab se rahet ke dwar ki or | Completed | 194000 | 194302 | 2016-12-23 | 2019-12-31
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034349704 — C.C,ROAD NIRMAN JAYKAM KE DWAR SE CHANDI MATA KE MANDIR KI OR | Completed | 88500 | 86688 | 2017-08-18 | 2018-05-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034353270 — C.C.ROAD NIRMAN PANCHAYAT BHAVAN SE DEVI SINGH KE DWAR KI OR | Completed | 132750 | 132494 | 2017-09-29 | 2019-04-04
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034365832 — C.C.ROAD NIRMAN CHANDI MATA KE MANDIR SE LAKSHIRAM KA PURA KI OR | Completed | 132750 | 132726 | 2017-11-03 | 2019-01-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034374282 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034436850 — c.c.road nirman man singh ke dwar se ajeet singh ke dwar tak | Completed | 69750 | 75870 | 2019-02-08 | 2019-09-30
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034442721 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034527221 — c.c.road nirman indal ke darvaje se madhvendra ke darvaje tak | Completed | 26370 | 23940 | 2020-10-03 | 2020-12-03
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034530297 — khet sadak nirman arvindra ke khet se narendra khet ki or | Completed | 1100792.11 | 993815.4 | 2020-08-19 | 2023-03-30
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034531006 — pewar block nirman govt high school kharika | Closed | 0 | 0 | 2020-04-14
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034560410 — PAHUCH MARG MAIN TEHANGUR ROAD SE SHANTIDHAM DHAJEKAPURA KI OR | Completed | 118105.74 | 113635.47 | 2021-03-14 | 2023-03-30
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/22012034560927 — c.c.road nirman barunendra ke dwar se vijay singh ke dwar ki or | Completed | 26400 | 25476 | 2021-05-06 | 2021-06-25
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034611873 — Sudoor sadak nirman kharika se nabalpura ki or | Closed | 0 | 0 | 2022-01-26
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002041/RC/22012034613954 — Sudoor road nirman kharika se gusing ki or | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002041/RC/77 — सी0सी0 रोड निर्माण जनक सिंह के मकान से बाबू सिंह के मकान तक | Completed | 382108 | 75067 | 2012-06-05 | 2013-07-22
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002041/RS/22012034570307 — Saamudaayik Svachchhata Parisar kharika | Completed | 43000 | 40916 | 2021-10-06 | 2022-04-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034669748 — Construction Of Samudayik Sokhta Near Govt.P.S.Lakshirampura | Completed | 10000 | 8160 | 2022-11-26 | 2023-04-30
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034669749 — Construction Of Samudayik Sokhta Near Vishwanath Ke Dwar Ke Pas | Ongoing | 10000 | 9792 | 2022-11-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034669751 — Construction Of Samudayik Sokhta Near Munnalal Ke Dwar Ke Pas | Completed | 10000 | 9792 | 2022-11-17 | 2023-04-30
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034672479 — Construction Of Samudayik Sokhta Near Gambhir Thok | Completed | 10000 | 9792 | 2022-11-10 | 2023-07-07
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034672832 — Construction Of Samudayik Sokhta Near Ranvijay Ke Dwar Ke Pas | Completed | 10000 | 8109 | 2022-11-25 | 2024-03-03
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034677334 — Construction Of Samudayik Sokhta Near Govt.P.S.Kharika | Ongoing | 10000 | 9792 | 2022-12-21
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034677335 — Construction Of Samudayik Sokhta Near Govt.P.S.Dhajekapura | Ongoing | 10000 | 7735 | 2023-08-03
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034677336 — Construction Of Samudayik Sokhta Near Lakhan Thok | Ongoing | 10000 | 9792 | 2022-12-21
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034677337 — Construction Of Samudayik Sokhta Near Kamlesh Thok | Completed | 10000 | 7735 | 2023-08-03 | 2023-09-14
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002041/RS/22012034677338 — Construction Of Samudayik Sokhta Near Mansharam Ke Dwar Ke Pas | Ongoing | 10000 | 8840 | 2023-04-26
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002041/WC/22012034293633 — TALAB GAHRIKARAN KHARIKA | Deleted | 99000 | 0 | 2016-05-20
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002041/WC/22012034325101 — TALAB NIRMAN BAJRANG MANDIR KE PASS KHARIKA | Completed | 98000 | 85140 | 2017-05-19 | 2017-09-25
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002041/WC/22012034331026 — talab gahrikaran school ke pas kharika | Completed | 279000 | 154112 | 2017-07-21 | 2017-10-20
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002041/WC/22012034331027 — talab gahrikaran shankar ji mandir ke pas kharika | Completed | 189000 | 128484 | 2017-07-21 | 2018-05-20
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002041/WC/22012034331028 — naveen talab nirman bhikari baba ke pas kharika | Deleted | 174000 | 0 | 2017-05-30
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002041/WC/22012034430440 — naveen talab nirman vikram ke khet ke pas | Completed | 610500 | 373412 | 2019-01-04 | 2019-10-02
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/WC/22012034444320 — नवीन अर्थन बंड निर्माण नबलपुरा | Closed | 311000 | 0 | 2018-10-02
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/WC/22012034444326 — नवीन अर्थन बंड निर्माण धजेकापुरा | Suspended | 311000 | 156714 | 2019-03-07
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702002041/WC/22012034520290 — TALAB SAUNDRIKARAN HANUMAN JI MANDIR KE PASS KHARIKA | Deleted | 0 | 0 | 2020-04-01
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702002041/WC/22012034550523 — TALAB SAUDARIKARAN NIRMAN KHARIKA | Completed | 1469845.65 | 1460348 | 2020-06-01 | 2022-05-15
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/WC/22012034623131 — talav gaharikaran nirman khariak | Completed | 451768.32 | 160836 | 2021-04-29 | 2022-05-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002041/WC/22012034676736 — samudayik shok pit tank kharika | Completed | 14467.3 | 9264 | 2021-06-24 | 2023-07-07
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002041/WC/22012034770678 — water harvesting tank samudayik bhavan parisar kharika | Completed | 39279.27 | 9264 | 2021-06-24 | 2022-10-28
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002041/WC/22012034939416 — Naveen talav nirman khel maedan ke pas | Ongoing | 1343596.5 | 53856 | 2022-05-05
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002041/WC/22012034943792 — talav saundrikaran nirman shankar ji pas kharika | Completed | 1487382.9 | 1267117 | 2022-05-19 | 2025-05-13
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002041/WC/22012034992417 — Talav saundrikarn nirman lakshirampura | Ongoing | 643411.23 | 161551 | 2023-05-16
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002041/WC/22012035004214 — naveen khet talav nirman indrapal/bashant singh | Physically Completed | 356188.41 | 234396 | 2022-11-01 | 2026-04-17
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002041/WC/22012035011058 — Naveen khet talav nirman chandni /parmal singh khet par | Closed | 325610.42 | 0 | 2022-10-02
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702002041/WC/22012035301714 — DUGWELL NIRMAN KARYA PS SCHOOL KHARIKA KE PASS | Physically Completed | 25899.46 | 14355 | 2025-05-30 | 2026-04-20
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1702002041/WC/23 — सोखपिट अनुसूचित जाति वस्‍ती नवलपुरा | Completed | 16000 | 1092 | 2009-07-29 | 2014-11-11
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002041/WH/22012034442115 — TALAV MARAMMAT KARYA NAWALPURA | Completed | 407727.69 | 166476 | 2020-01-28 | 2020-08-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002041/WH/22012034448018 — talav gahrikaran arvind khet ke pas | Completed | 470592 | 250752 | 2021-05-27 | 2022-05-15
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002041/WH/22012034455557 — talav marmmat kary heera singh khet ke pas | Completed | 49823.26 | 34272 | 2022-05-26 | 2022-08-30
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002041/WH/22012034938161 — Talav safai karya Hanuman mandir kharika | Closed | 0 | 0 | 2023-08-15