## Work List
Exported on: 2026-10-21 15:03:14
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KOT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002046/AV/22012034506322 — NAVEEN GAOSHALA NIRMAN GRAM KOT | Completed | 2949264.21 | 2699867.55 | 2020-02-13 | 2022-06-10
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002046/AV/22012034512384 — CONSTRUCTION WORK OF BOUNDARY WALL GP KOT | Completed | 106000 | 101460 | 2020-08-28 | 2021-11-23
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002046/AV/22012034534283 — NAVEEN ANGANWADI BHAWAN NIRMAN GP KOT | Closed | 180000 | 0 | 2016-10-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002046/AV/4203 — Aanganbadi/Other Rural Infrastructure,KOT | Completed | 330000 | 325479 | 2015-12-17 | 2018-10-10
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002046/DP/153 — निर्मल वाटिका रामचिन्‍नी / मुलू | Completed | 0 | 488 | 2011-12-26 | 2016-08-11
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002046/DP/154 — निर्मल वाटिका कार्य झण्‍डन / पोखन | Completed | 0 | 488 | 2011-12-26 | 2016-08-11
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002046/DP/155 — निर्मल वाटिका कार्य कटोरी /रामभरोसे | Completed | 0 | 488 | 2011-12-26 | 2016-08-11
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002046/DP/156 — निर्मल वाटिका कार्य वासुदेव / मातादीन | Completed | 0 | 488 | 2012-01-02 | 2016-08-11
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002046/FP/22012034626051 — CONSTRUCTION WORK OF NALA WORK MAHENDRA KE MAKAN SE SHANKAR JI THAN KI OR | Completed | 98000 | 40530 | 2021-08-27 | 2022-08-08
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012034352404 — BRAKSHA ROPAN KARYA SADAK KE KINARE | Completed | 335000 | 34396 | 2017-06-22 | 2018-02-05
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012034359987 — BRAKSHA ROPAN KARYA SARVJANIK STHAL PER | Completed | 335000 | 6096 | 2017-08-01 | 2019-07-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002046/IF/22012034388472 — nadep tanka | Closed | 0 | 0 | 2017-10-02
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034750259 — KHET TALAB SHYAMSUNDAR | Deleted | 337715.44 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034750263 — KHET TALAB GANGASINGH | Deleted | 337715.44 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034750267 — KHET TALAB KALICHARAN | Deleted | 337715.44 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034751919 — KHET TALAB NIRMAN SHYAMSUNDAR KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034751924 — KHET TALAB NIRMAN GANGA SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034751928 — KHET TALAB KALICHARAN KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012034751932 — KHET TALAB NIRMAN BADSHAH SINGH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752896 — Med bandhan Kary lokendra putr sadhu ke khet par kot | Completed | 20058.98 | 17370 | 2021-06-04 | 2021-06-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752901 — Med bandhan Kary Sugar putr Devi ke khet par kot | Completed | 20058.98 | 15054 | 2021-05-28 | 2021-06-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752914 — Medbandan Kary ramnarayan putr raghuveer ke khet par kot | Completed | 18235.45 | 17370 | 2021-06-04 | 2021-06-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752917 — Med bandhan Kary sarla Devi pati Sonu me khet par | Completed | 16411.89 | 17370 | 2021-06-04 | 2021-06-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752936 — Medbandan Kary narsingh ke let par kot | Closed | 18235.45 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752966 — Medbandan Kary Shanti veva done ke khet par kot | Completed | 18235.45 | 17370 | 2021-06-04 | 2021-06-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752983 — Med bandhan Kary jagdeesh ke khet par kot | Completed | 21882.53 | 16212 | 2021-06-04 | 2021-10-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752987 — Med bandhan Kary ramdas ke khet or kot | Completed | 20970.75 | 17370 | 2021-05-28 | 2021-06-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034752994 — Med bandhan Kary Ramnath ke khet par kot | Completed | 21882.53 | 17370 | 2021-05-28 | 2021-06-15
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753002 — Med bandhan Kary Charan ke khet par kot | Completed | 22794.3 | 14475 | 2021-06-20 | 2021-06-28
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753008 — Med bandhan Kary kailash ke khet par kot | Completed | 18235.45 | 14475 | 2021-06-20 | 2021-06-28
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753018 — Med bandhan Kary Dharmendra ke khet par kot | Completed | 18235.45 | 17370 | 2021-06-04 | 2021-06-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753022 — Med bandhan Kary NAthu Singh ke khet par kot | Completed | 21882.53 | 18528 | 2021-06-04 | 2021-06-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753027 — Medbandan Kary Indraveer ke khet par kot | Completed | 22794.3 | 15826 | 2021-06-11 | 2021-06-28
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753034 — Med bandhan Kary kalicharan ke khet par kot | Completed | 18235.45 | 17370 | 2021-06-04 | 2021-06-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753053 — Medbandhan Kary brajkisor ke kHey par kot | Completed | 18235.45 | 15440 | 2021-06-04 | 2021-06-28
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753062 — Medbandhan Kary harisingh ke khet par | Completed | 18235.45 | 14475 | 2021-06-20 | 2021-06-28
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753074 — Medbandhan Kary rameswar putr makarandh ke kkhet par kot | Completed | 20058.98 | 17370 | 2021-05-28 | 2021-06-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753086 — Medbandhan Kary sukhveer putr girandra ke kkhet par kot | Completed | 20058.98 | 15440 | 2021-06-04 | 2021-06-28
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753095 — Medbandhan Kary Rajesh ke khet par kot | Completed | 18235.45 | 15054 | 2021-06-04 | 2021-06-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753101 — Med bandhan Kary rambaran ke khet par kot | Completed | 22794.3 | 10422 | 2021-06-04 | 2021-06-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002046/IF/22012034753103 — Med bandhan Kary syamsundar ke khet par kot | Completed | 18235.45 | 17370 | 2021-05-28 | 2021-06-20
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802390 — MED BANDHAN KALLE / RAJAN KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802393 — MED BANDHAN RAGHURAJ / YADUNATH KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802398 — MED BANDHAN MAHENDRA / FOJDAR KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802401 — MED BANDHAN JAL SINGH / TUNDE KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802404 — MED BANDHAN LALLU / BHIRAI KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802406 — MED BANDHAN KARAN SINGH / BHIRAI KE KHET PER | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802493 — medbandan kary sunil / lalsingh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802508 — medbandan kary muni/ramlakhan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802511 — medbandan kary muni/ramlakhan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802513 — medbandan kary muni/ramlakhan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802614 — medbandan kary urmila/bechu ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802633 — medbhandan kary hotam jatav ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802649 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802654 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802658 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802660 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802666 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802669 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802672 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802676 — madbandan kary shivratan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802845 — medbandan kary ramnare ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802861 — medbandhan kary sardev/rampal ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802878 — medbandan kary ramendra/muktyar ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802898 — medbandan kary surabhan/lakhan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802915 — medbandan kary chatury/bhirai ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802924 — medbandan kary gunsingh /ramotar ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802934 — medbandan kary sivsingh/malkhan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802946 — medbandan kary dasrath/kursingh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802962 — medbandan kary shivratan/muni ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802971 — medbandan kary rampraka khatikn ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034802992 — medbandan kary ramdas/gyaden ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034803009 — madbandan kary dharmsingh /harenarayan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034803019 — medbandan kary mahaver/matru ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034803031 — medbandan kary manoj/jagdev ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Gabion Anicut for Individuals / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1702002046/IF/22012034803042 — medbandan kary rames/angad ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034803059 — medbandan kary suneel/gendalal ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002046/IF/22012034803070 — medban amit/ramsajivan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002046/IF/22012034976938 — Khet talab nirman kary kalicharan/chhidi k khet pr | Ongoing | 356340.1 | 117504 | 2022-05-17
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002046/IF/22012034976942 — खेत तालाब निर्माण कार्य रामप्रकाश पुत्र टुंडे के खेत पर | Ongoing | 356340.1 | 53856 | 2022-05-17
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002046/IF/22012034976944 — खेत तालाब निर्माण कार्य श्याम सुंदर पुत्र मलखान सिंह के खेत पर | Closed | 0 | 0 | 2022-04-18
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012035042249 — NAVEEN KHET TALAB NIRMAN BADAN / ARJUN KE KHET PER | Physically Completed | 356188.41 | 118014 | 2023-07-22 | 2026-04-15
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012035124620 — KHET TALAB NIRMAN SANDEEP KE KHET PER | Physically Completed | 383083.54 | 72930 | 2023-10-08 | 2026-06-10
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012035124621 — KHET TALAB NIRMAN RAJENDRA KE KHET PER | Ongoing | 383083.54 | 41106 | 2024-01-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012035545776 — KHET TALAB NIRMAN MOTIBABA KE KHET PER | Physically Completed | 450885.64 | 169911 | 2025-06-30 | 2026-04-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002046/IF/22012035545784 — KHET TALAB NIRMAN NATHU KE KHET PER | Ongoing | 450885.64 | 0 | 2025-07-28
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035614222 — EK BAGIYA MAA KE NAAM SUNITA DEVI / MANOJ | Ongoing | 266577.25 | 0 | 2026-01-08
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035642378 — EK BAGIYA MAA KE NAAM ADESH DEVI / NISHANT | Deleted | 0 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035642383 — EK BAGIYA MAA KE NAAM HIRANKUMARI / RAVINDRA | Deleted | 188139.36 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035642386 — EK BAGIYA MAA KE NAAM PRITI / KULDEEP | Deleted | 187842.03 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035644402 — EK BAGIYA MAA KE NAAM HIRANKUMARI/RAVINDRA | Ongoing | 266578.64 | 0 | 2026-01-08
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035651738 — EK BAGIYA MAA KE NAAM ADESH DEVI / NISHANT | Ongoing | 266578.64 | 27754.02 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002046/IF/22012035651744 — EK BAGIYA MAA KE NAAM PRITI / KULDEEP | Ongoing | 266578.64 | 0 | 2026-01-08
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993690245 — CATTLE SHED UPASHNA/ANIL SINGH | Completed | 115900 | 68829.15 | 2015-12-11 | 2017-12-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993690246 — CATTLE SHED MAHESH SINGH/ RAJENDRA SINGH | Completed | 115900 | 8586 | 2015-12-03 | 2017-12-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993690247 — CATTLE SHED MUKUT SINGH/ SUBA SINGH | Completed | 115900 | 60362.15 | 2015-12-11 | 2017-12-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993690248 — CATTLE SHED MAHVEER SINGH/MATARU SINGH | Completed | 115900 | 45564.15 | 2015-12-11 | 2017-12-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993690249 — CATTLE SHED MUNNALAL/ RAJARAM | Completed | 115900 | 45564.15 | 2015-12-11 | 2017-12-25
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727039 — cattle shed het singh bhaghel | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727042 — cattle shed rajaram bhaghel | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727044 — cattle shed dyal singh | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727046 — cattle shed ajeet singh /homsingh | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727047 — cattle shed ramnaresh singh | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727049 — cattle shed keshri | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727050 — cattle shed janved | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727052 — cattle shed rajrndra singh | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727053 — cattle shed ramotar/raghuveer | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727054 — cattle shed ravindra | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002046/IF/9993727055 — cattle shed chatur/puttu | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/134019 — Construction of IAY House -IAY REG. NO. MP-02-002-046-001/05 | Completed | 14310 | 12908 | 2016-07-28 | 2019-07-20
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/134020 — Construction of IAY House -IAY REG. NO. MP-02-002-046-001/12 | Completed | 14310 | 14195 | 2016-07-28 | 2017-02-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/134022 — Construction of IAY House -IAY REG. NO. MP-02-002-046-001/53 | Approved | 23490 | 0 | 2016-02-14
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/1871373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4550972 | Completed | 15660 | 15336 | 2018-08-02 | 2019-06-10
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/1871489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4645029 | Completed | 15660 | 15558 | 2018-08-16 | 2019-07-20
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/1872920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5491658 | Completed | 15660 | 15222 | 2018-08-02 | 2019-07-20
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/1872936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5532544 | Completed | 15660 | 14268 | 2018-08-23 | 2019-03-10
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/3807193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113575629 | Physically Completed | 18360 | 8768 | 2023-01-10 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/3807197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576663 | Physically Completed | 18360 | 11220 | 2022-11-09 | 2024-11-21
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/3807202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113578756 | Physically Completed | 18360 | 1458 | 2024-04-18 | 2024-11-26
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/4176810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576492 | Physically Completed | 18360 | 0 | 2024-11-04 | 2025-03-01
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/4221883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576465 | Physically Completed | 18360 | 0 | 2024-04-18 | 2024-11-21
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/444840 — Construction of IAY House -IAY REG. NO. MP1504238 | Completed | 15030 | 15090 | 2017-02-02 | 2018-01-01
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/450758 — Construction of IAY House -IAY REG. NO. MP1572939 | Completed | 15030 | 15166 | 2017-02-02 | 2018-06-10
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/4872572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106349356 | Ongoing | 23490 | 7506 | 2025-02-05
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/4872661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576689 | Ongoing | 23490 | 5832 | 2025-02-05
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/532454 — Construction of IAY House -IAY REG. NO. MP2861359 | Completed | 15030 | 15090 | 2017-02-02 | 2017-10-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106349461 | Ongoing | 23490 | 9396 | 2025-10-07
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113577158 | Ongoing | 23490 | 12528 | 2025-10-07
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106349103 | Ongoing | 23490 | 14094 | 2025-10-07
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576577 | Ongoing | 23490 | 10962 | 2025-10-07
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113575741 | Ongoing | 23490 | 8874 | 2025-06-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576388 | Physically Completed | 23490 | 14094 | 2025-09-09 | 2026-05-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576510 | Physically Completed | 23490 | 10962 | 2025-10-07 | 2026-01-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5621958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113575826 | Ongoing | 23490 | 0 | 2025-11-28
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/562501 — Construction of IAY House -IAY REG. NO. MP3752358 | Completed | 15030 | 15198 | 2017-02-23 | 2018-06-06
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5669340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576819 | Approved | 23490 | 0 | 2025-04-13
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5669880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113576564 | Ongoing | 23490 | 10962 | 2025-10-07
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/5681796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114817888 | Ongoing | 23490 | 7830 | 2025-10-07
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/6048201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106349231 | Approved | 23490 | 0 | 2025-04-07
BHIND / BHIND | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/6219676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114818080 | Ongoing | 23490 | 6264 | 2026-05-21
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/684098 — Construction of IAY House -IAY REG. NO. MP1533272 | Completed | 15030 | 15486 | 2017-09-14 | 2018-06-10
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/684113 — Construction of IAY House -IAY REG. NO. MP1537698 | Completed | 15030 | 15480 | 2017-09-14 | 2018-06-10
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/684125 — Construction of IAY House -IAY REG. NO. MP1541564 | Completed | 15030 | 15308 | 2017-11-02 | 2018-05-05
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/684214 — Construction of IAY House -IAY REG. NO. MP1582896 | Completed | 15030 | 15498 | 2017-09-14 | 2018-06-06
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/686476 — Construction of IAY House -IAY REG. NO. MP2714314 | Completed | 15030 | 15480 | 2017-10-12 | 2018-02-02
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002046/IF/IAY/686716 — Construction of IAY House -IAY REG. NO. MP2861282 | Completed | 15030 | 15480 | 2017-09-14 | 2018-08-06
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034269207 — CHARAN SINGH KE KHET PAR | Closed | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034291854 — RAMESHVAR KE KHET PAR | Completed | 35700 | 33066 | 2016-08-11 | 2018-12-12
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034291855 — NATHU SINGH / KARAN SINGH KE KHET PAR | Completed | 41600 | 38076 | 2016-08-11 | 2018-12-12
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034291923 — MED BANDHAN RAMVEER KE KHET PAR | Deleted | 26200 | 0 | 2016-04-16
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034291924 — MED BANDAN CHHUTKAN SINGH KE KHET PAR | Deleted | 35700 | 0 | 2016-08-24
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034292027 — MED BANDAN KARY TULAI S/O JHARGADI KE KHET PAR | Deleted | 14295 | 0 | 2016-09-02
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034292028 — MED BANDAN RAMDAS S/O SUKHU KE KHET PAR | Deleted | 0 | 0 | 2016-04-16
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/LD/22012034292029 — MED BANDAN RAMDAS S/O SUKHU KE KHET PAR | Deleted | 0 | 0 | 2016-04-16
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034535426 — NAVEEN CHARAGAH GP KOT | Completed | 929307.69 | 472920 | 2021-01-21 | 2022-06-10
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555714 — med bandhan kalicharan/chhiddi | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555715 — med bandhan brajkishor/tulai | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555716 — med bandhan harisingh/diman | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555717 — med bandhan shyamsunar/malkhan | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555719 — med bandhan rameswar/makrand | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555721 — med bandhan sukhveer singh/girendra | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555722 — med bandhan rajesh/chhaviram | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555723 — med bandhan ramvaran/gudal | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555724 — med bandhan jagdish/kashiram | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555725 — med bandhan ramdas / sukhu | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555726 — med bandhan ramnath / sukhu | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555727 — med bandhan charan singh/ atarsingh | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555729 — med bandhan kailash/girdawal | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555730 — med bandhan gangasingh/pryag singh | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555732 — med bandhan pooran/bade | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555733 — med bandhan lokendra/sadhu | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555734 — med bandhan sughar singh/ devi | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555735 — med bandhan ramnarayan/raghuveer | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555736 — med bandhan sarla/sonu | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555737 — med bandhan narsingh/navav singh | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555738 — med bandhan indraveer | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555739 — med bandhan nathusingh / karan singh | Closed | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555740 — med bandhan dharmendra/jandel | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/22012034555741 — med bandhan shantidevi/shivve | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002046/LD/22012034950631 — CHARAGAR NIRMAN KARYA GAUSHALA KE PASS KOT | Approved | 0 | 0 | 2025-01-26
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/36 — mad bandhan karya judavan \ kasari jatav | Deleted | 0 | 0 | 2009-04-14
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/37 — mad bandhan karya suresh \ malle jatav | Completed | 8200 | 12400 | 2010-04-30 | 2010-04-30
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/38 — mad bandhan karya ramvaran \ bansi jatav | Completed | 7000 | 10000 | 2010-04-30 | 2010-04-30
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/39 — mad bandhan karya jagat singh \ badhole jatav | Completed | 3200 | 4500 | 2010-05-06 | 2010-05-06
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/40 — mad bandhan karya chote lal \ badhole jatav | Completed | 1100 | 1100 | 2010-04-30 | 2010-04-30
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/41 — mad bandhan ransiya \ kanhai jatav | Deleted | 0 | 0 | 2010-03-08
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002046/LD/87 — मेढबन्‍धान पुनू / पुन्‍ने | Completed | 0 | 1500 | 2010-09-01 | 2010-09-01
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002046/OP/9425890917 — SHANTI DHAM KA NIRMAN KARY NAVAL PURA | Completed | 245000 | 240715.68 | 2016-12-01 | 2017-12-23
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002046/OP/9425890919 — SHANTI DHAM NIRMAN KOT | Completed | 245000 | 241520.68 | 2016-12-01 | 2017-12-24
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002046/PG/22012034304435 — KHEL MAEDAN KOT | Completed | 353000 | 8256 | 2017-04-13 | 2018-12-12
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034199254 — C.C.ROAD RAMHET KE DWAR SE PUSHPENDRA KE DWAR TAK | Completed | 124823 | 94422 | 2014-01-16 | 2014-05-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034218452 — C.C.ROAD JAGMOHAN KE DWAR SE SULTAN KE DWAR TAK | Completed | 126175 | 63108 | 2014-05-22 | 2016-09-29
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034287739 — C.C.ROAD RAJJAK KHAN KE DWAR SE SHALA BHAWAN KI AUR | Completed | 135343 | 110066 | 2015-10-29 | 2016-04-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034287873 — C.C.ROAD LAKHAN KE DWAR SE MANDIR TAK | Completed | 148032 | 130805 | 2015-12-28 | 2016-07-28
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034297054 — C.C.ROAD GIRENDRA SINGH KE DWAR SE MAHENDRA SINGH KE DWAR TAK | Deleted | 85813 | 0 | 2016-01-14
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034297055 — C.C.ROAD ASHARAM HARIJAN KE DWAR SE BHAJU HARIJAN KE DWAR TAK | Deleted | 85813 | 0 | 2016-01-14
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034298970 — RAMSEVA JATAV KE MAKAN SE JAGNNATH JATAV KE MAKAN KEE OR | Deleted | 120000 | 0 | 2016-02-19
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034314652 — C.C.ROD NIRMAN RAMSEWA JATAV KE MAKAN SE JAGANNATH KE MAKAN KEE OR NAVAL PURA | Completed | 120000 | 110432 | 2016-09-08 | 2016-10-10
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034316387 — C C ROD NIRMAN ASHARAM HARIJAN KE MKAN SE BHAJU HARIJAN KE MKAN TAK KOT | Completed | 86000 | 81164 | 2016-11-17 | 2017-03-22
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034316389 — C C ROD NIRMAN MUNNALAL JATAV KE MKAN SE KHERA PATI KE MANDIR TAK | Completed | 163000 | 159315 | 2016-11-17 | 2017-05-30
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034318149 — C C ROD HARIJAN VASTI GAEDALAL JATAV KE MKAN SE SVARAJ BHAVAN KEE OR | Completed | 101000 | 100221 | 2017-02-16 | 2017-05-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002046/RC/22012034339136 — SUDUR SAMPARK SADAK KOT SE SARSAI PRADHAN MANTRI SADAK TAK | Completed | 2428000 | 2116037.94 | 2017-05-25 | 2019-12-24
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034353187 — C C ROD KALEECHARAN KE MAKAN SE LAXMAN KE MAKAN TAK | Completed | 17700 | 9288 | 2017-09-28 | 2019-05-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034353189 — C C ROD RAMJIT KE MAKAN SE RAJARAM KE MAKAN OR MEVATI MANDIR TAK | Completed | 79650 | 73960 | 2017-09-28 | 2018-12-10
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034353190 — C C ROD INDAL KE MAKAN SE RAGHURAJ KE MAKAN OR RAJU KE MAKAN TAK | Completed | 44250 | 44376 | 2017-09-28 | 2018-04-25
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034364719 — CC ROAD HARI NARAYAN KE MAKAN SE SURESH KE MAKAN TAK | Completed | 35800 | 37368 | 2017-10-26 | 2018-05-10
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034364786 — CC ROAD MUNNI KE MAKAN SE SHRI GOVIND KE MAKAN TAK | Completed | 45000 | 46416 | 2017-10-26 | 2019-12-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034365083 — CC ROAD PRAMOD KE MAKAN SE RAJHANSH KE MAKAN TAK | Completed | 25600 | 19608 | 2017-10-26 | 2018-06-10
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034380222 — CC ROAD MAHENDRA KE MAKAN SE RAMPRAKASH KE MAKAN TAK | Completed | 56000 | 46620 | 2018-01-11 | 2018-10-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034385518 — सी सी रोड आगनबाड़ी भवन से शाशकीय प्राथमिक विद्यालय तक ज्ञान थोक | Completed | 88000 | 68036 | 2018-03-16 | 2019-09-24
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034385569 — CC ROAD UDAL KE MAKAN SE MOONGARAM KE MAKAN EVM RAMJILAL KE MAKAN TAK | Completed | 70000 | 68036 | 2018-03-16 | 2018-12-12
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034442722 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034463252 — C C ROAD KALICHARAN KE MAKAN SE VIRENDRA KE MAKAN TAK GRAM NABALPURA | Completed | 56000 | 50130 | 2019-03-10 | 2019-11-04
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034463284 — C C ROAD RAJESH KE MAKAN SE SURESH KE MAKAN TAK NABALPURA | Completed | 45000 | 36936 | 2019-03-10 | 2019-11-04
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034471859 — C C ROAD PAKKE CHABUTRA SE JAWAHAR KE MAKAN TAK | Completed | 109000 | 106656 | 2019-08-08 | 2019-11-04
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034474788 — C C ROAD GOVT SCHOOL SE JIND BABA KE THAN TAK | Closed | 140000 | 0 | 2017-04-01
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034477935 — C C ROAD HOTAM KE MAKAN SE KALICHARAN KE MAKAN KI OR | Completed | 55000 | 40128 | 2019-11-06 | 2019-12-24
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034482025 — Cc Road Hotam Ke Mkan Se Kali Charan Ke Mkan Tak Kot | Closed | 56000 | 0 | 2017-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002046/RC/22012034522944 — SUDUR SADAK KOT SE RAORA KABRISTHAN PAHUCHMARG TAK | Completed | 3069841.3 | 1766327.08 | 2020-07-23 | 2025-07-24
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034529465 — C C ROAD PINKU KE GODA SE SHANTIDHAM TAK | Closed | 93000 | 0 | 2020-12-23
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002046/RC/22012034531863 — SUDUR SADAK PM SADAK SE PEWALI PM SADAK TAK | Ongoing | 2443992.86 | 1789904.28 | 2020-10-08
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034555533 — CC ROAD JIND BABA KE THAN SE GOVT MIDIL SCHOOL KI OR | Completed | 126000 | 112146 | 2021-01-21 | 2021-10-29
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/22012034555534 — CC ROAD MAIN ROAD SE SAMUDAYAK SWACHCHHATA SHAUCHALAY KI OR | Completed | 50000 | 38528 | 2021-03-04 | 2022-04-10
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002046/RC/85 — सी0सी0 रोड मुख्‍य सडक से पाल सिंह के घर तक | Completed | 134173 | 105504 | 2012-09-15 | 2014-06-15
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702002046/RS/22012034494021 — CONSTRUCTION OF COMMUNITY TOILET GP KOT | Completed | 43000 | 43392 | 2020-12-23 | 2021-11-23
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669389 — CONSTRUCTION OF SAMUDAYAK SOKHTA BADAN SINGH KE GHAR KE PASS | Closed | 10000 | 0 | 2022-09-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669393 — CONSTRUCTION OF SAMUDAYAK SOKHTA PUSHPENDRA SINGH KE GHAR KE PASS | Closed | 10000 | 0 | 2022-09-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669397 — CONSTRUCTION OF SAMUDAYAK SOKHTA CHHOTELAL JATAV THOK | Closed | 10000 | 0 | 2022-09-20
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669401 — CONSTRUCTION OF SAMUDYAK SOKHTA RAMNARESH KE GHAR KE PASS | Ongoing | 10000 | 6120 | 2022-10-31
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669429 — CONSTRUCTION OF SAMUDAYAK SOKHTA KALIMATA MANDIR KE PASS | Closed | 10000 | 0 | 2023-07-08
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669436 — CONSTRUCTION OF SAMUDAYAK SOKHTA SANDEEP KE GHAR KE PASS | Ongoing | 10000 | 9792 | 2022-11-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669439 — CONSTRUCTION OF SAMUDAYAK SOKHTA SUKHVEER THOK | Ongoing | 10000 | 7344 | 2022-10-31
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669451 — CONSTRUCTION OF SAMUDAYAK SOKHTA NAL JAL YOJNA KE PASS | Closed | 10000 | 0 | 2023-06-30
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669457 — CONSTRUCTION OF SAMUDAYAK SOKHTA PS SCHOOL BHAVAN KOT | Ongoing | 10000 | 3672 | 2022-11-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669458 — CONSTRUCTION OF SAMUDAYAK SOKHTA MIDIL SCHOOL KOT | Ongoing | 10000 | 3672 | 2022-11-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002046/RS/22012034669459 — CONSTRUCTION OF SAMUDAYAK SOKHTA UPSWASTHYA KENDRA KOT | Ongoing | 10000 | 9792 | 2022-10-31
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002046/WC/22012034293685 — तालाब गहरीकरण कार्य नवल पुरा | Deleted | 97400 | 0 | 2016-05-18
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/WC/22012034324154 — TALAB MARAMMAT KARYA NAWALPURA | Completed | 93000 | 69144 | 2017-05-11 | 2017-07-20
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/WC/22012034325120 — TALAB MARAMMAT RAJENDRA KE KUA KE PASS KOT | Completed | 425000 | 244756 | 2017-05-18 | 2017-08-29
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/WC/22012034357210 — BORI BANDHAN NSLE PER MATA MADIR KE PASS | Deleted | 83000 | 0 | 2017-10-05
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/WC/22012034357211 — BORI BANDHAN NALE PER SHANKAR JI MANDIR KE PASS | Deleted | 78000 | 0 | 2017-10-05
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002046/WC/22012034389945 — नवीन तालाब निर्माण माता के मंदिर के पास | Ongoing | 1073000 | 252267.39 | 2018-07-05
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002046/WC/22012034432204 — NAVEEN TALAB NIRMAN RAMTALAIYA KHAR KOT | Completed | 1031000 | 598748 | 2019-08-04 | 2022-04-10
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002046/WC/22012034445283 — DUG POND SHANKAR JI KE THAN KE PASS | Completed | 243000 | 120792 | 2019-08-04 | 2020-08-30
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002046/WC/22012034607612 — NAVEEN TALAB NIRMAN SIDDHBABA KE PASS | Closed | 0 | 0 | 2020-11-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002046/WC/22012034623780 — Naveen talav Nirman khar ke pass kot | Closed | 0 | 0 | 2021-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002046/WC/22012034642902 — TALAB NIRMAN KHAR KE PASS | Ongoing | 1075714.04 | 173578 | 2021-04-24
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002046/WC/22012034642906 — NAVEEN TALAB NIRMAN PATHAN BABA KE PASS | Closed | 0 | 0 | 2021-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002046/WC/22012034642907 — NAVEEN TALAB SIDHBABA KE PASS | Closed | 0 | 0 | 2021-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002046/WC/22012034642911 — NAVEEN TALAB PUKHARIYA KE PASS | Completed | 295625.89 | 197246 | 2021-04-22 | 2022-08-08
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002046/WC/22012034642912 — TALAB NAVEEN BRAHMMAN TALAIYA | Completed | 392638.43 | 220406 | 2021-04-22 | 2021-08-16
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002046/WC/22012034963121 — Amrat sarowar talab raju ki kudaria ke pass | Closed | 0 | 0 | 2022-04-21
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble contour Bund for Community / Construction of Pebble contour Bund for Community | Construction of Bund | 1702002046/WC/22012034981014 — NAVEEN TALAB NIRMAN GANGA SINGH KE KUDARIYA KE PASS | Closed | 0 | 0 | 2022-04-14
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/WC/22012035072559 — NAVEEN TALAB NIRMAN ROAD WALI TALAIYA WALA KOT | Physically Completed | 1210208.21 | 167297 | 2023-12-23 | 2026-06-10
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002046/WC/22012035072560 — TALAB NIRMAN PATHAN BABA KE PASS | Physically Completed | 1469973.71 | 339014 | 2024-01-29 | 2026-06-10
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002046/WH/22012034935074 — talab jirnoudhar karya navalpura | Closed | 41000 | 0 | 2022-04-24
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002046/WH/22012034935075 — talab jirodhar karya rajendra ke kuwa ke pass | Closed | 41000 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002046/WH/22012034935077 — talab jirodhar mahesh ke khet | Closed | 41000 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702002046/WH/22012034935078 — talab jirodhar sankar ji ke than ke pass | Closed | 41000 | 0 | 2022-04-14