## Work List
Exported on: 2026-10-20 05:14:54
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: PEWALEE
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002047/AV/22012034390469 — aganbadi nirmand karya pewali | Completed | 330000 | 295103.12 | 2018-12-28 | 2021-10-10
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002047/AV/22012034513336 — Goshala nirmad karya pewali | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002047/DP/146 — व्रक्षारोंपण कार्य देवी माता मन्दिर के पास पेवली | Completed | 187431 | 2562 | 2011-08-18 | 2016-12-26
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002047/DP/22012034242997 — BRAKSHAROPAN MATA MANDIR PEWALI | Deleted | 335000 | 0 | 2017-05-26
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002047/DP/22012034604315 — मेरी माटी मेरा देश वशुधा वंदन अमृत बाटिका ब्रक्षारोपण कार्य माता मंदिर पेवली | Closed | 56725.4 | 0 | 2023-04-14
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002047/FP/22012034362515 — nali nirman ramdatt ke makan se jagjish ke makan tak | Completed | 10000 | 16860 | 2019-03-08 | 2020-10-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002047/FP/22012034362525 — nali nirman bholaram ke makan se jagdees ke makan tak | Suspended | 3100 | 0 | 2019-02-20
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702002047/FP/22012034362526 — nali nirman ashok ke makan se prahlad ke makan tak | Suspended | 12300 | 0 | 2019-02-20
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702002047/IF/22012034342945 — VRAKSHAROPAD KARYA MATA MANDIR PEWALI | Deleted | 33500000000 | 0 | 2017-05-25
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002047/IF/22012034348317 — KHET TALAV RAMSWARUP/BACHCHI | Completed | 70300 | 41280 | 2017-06-09 | 2017-07-28
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002047/IF/22012034348322 — KHET TALAV RAMVARAN/HUBBY | Completed | 70300 | 41280 | 2017-06-09 | 2017-07-28
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002047/IF/22012034352104 — brakshropad karya mata mandir pewali | Completed | 335000 | 38180 | 2017-07-22 | 2018-08-20
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002047/IF/22012034358887 — VRAKSHROPAD KARYA TALAV HARBALA PEWALI | Deleted | 335000 | 0 | 2017-07-22
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1702002047/IF/22012034388473 — nadep tanka | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034469540 — khet talb devidayal | Deleted | 251000 | 0 | 2019-01-26
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034558119 — khet talab pewali pura | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002047/IF/22012034558130 — khet talab balram | Completed | 332572.21 | 292980 | 2020-05-31 | 2020-08-28
BHIND / BHIND | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034558143 — khet talab ganga singh/patiram | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702002047/IF/22012034558146 — khet talab manbhoop | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1702002047/IF/22012034559181 — khet talav devidayal /motiram | Completed | 332572.21 | 190380 | 2020-05-31 | 2020-11-10
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034721719 — khet talav nirman ashok/devideen | Closed | 369663.53 | 0 | 2021-01-16
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Line Plantation of Forestry Trees for Individual | Plantation | 1702002047/IF/22012034721809 — khet talv nirman karya ganga singh /patiram | Ongoing | 338902.57 | 59976 | 2022-04-01
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034721814 — men bandhan vishunlal/ramhet | Suspended | 23789.95 | 0 | 2021-04-01
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bondry Block - Coastal Shelter Belt-Individuals / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Other Works | 1702002047/IF/22012034721827 — med bandhan vishunlal/ramhet | Deleted | 0 | 0 | 2021-01-16
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034721830 — med bandhan raju/ hariram | Suspended | 22537.84 | 0 | 2021-04-01
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034721835 — med bandhan mahendra/ | Suspended | 21716.2 | 0 | 2021-05-01
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002047/IF/22012034721839 — med bandhan harnam/prathivi pal | Suspended | 24040.37 | 0 | 2021-05-01
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1702002047/IF/22012034721842 — men bandhan sukhram/ harvilas | Suspended | 23789.95 | 0 | 2021-05-01
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813852 — med bandhan mangla devi /vijaram | Deleted | 0 | 0 | 2021-01-16
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813853 — med bandhan mangla devi /vijaram | Deleted | 0 | 0 | 2021-06-16
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813924 — med bandhan karya chhaviram/sukhbasi | Deleted | 0 | 0 | 2021-04-16
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813929 — med bandhan karya ramswarup/prathvipal | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813940 — med bandhan karya harvilash/maniram | Suspended | 27546.26 | 0 | 2021-06-01
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813944 — med bandhan karya rupsingh/vijayram | Closed | 31552.98 | 0 | 2021-06-18
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813947 — med bandhan karya bahadur /ramsanehi | Closed | 32554.66 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813950 — med bandhan karya urmila devi/atarsingh | Closed | 27546.26 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813957 — med bandhan karya laxminarayan/gopal | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813959 — med bandhan karya ramshankar/ lajjaram | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813962 — med bandhan karya ramfal/hulasi | Closed | 32867.68 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813965 — med bandhan karya indrajeet/ramsah | Closed | 31302.56 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813971 — med bandhan karya mukesh/visram | Deleted | 0 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813974 — khet talav mangladevi/vijaram | Closed | 338902.57 | 0 | 2021-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012034813982 — khet talav vishunlal/ramhet | Closed | 338902.57 | 0 | 2021-04-14
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002047/IF/22012035031112 — Khet talav Nirman karya Ajmer s/o Gopal singh | Physically Completed | 356188.41 | 145538 | 2023-12-06 | 2026-06-09
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002047/IF/22012035031113 — Khet talav Nirman karya dilliram /ganesh | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702002047/IF/22012035031115 — Khet talav Nirman karya raja Singh /mulu | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002047/IF/22012035031116 — Med Bandhan karya Hira Singh /punu | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002047/IF/22012035031117 — Med Bandhan karya manbhoop /punu | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1702002047/IF/22012035031398 — Khet talav Nirman karya Parvati /khagidam | Closed | 356188.41 | 0 | 2023-09-21
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of stone peripheral bund for indiv / Construction of Stone peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012035457480 — Khet talav karya maniram ke khet par | Closed | 147621.16 | 0 | 2025-07-10
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002047/IF/22012035457529 — Khet talav karya narottam ke khet par | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702002047/IF/22012035636580 — एक बगिया मां के नाम श्री राम आजीविका समूह पेवली | New | 0 | 0 | 2025-10-27
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702002047/IF/22012035636853 — एक बगिया मां के नाम श्री राम आजीविका समूह पेवली | Approved | 0 | 0 | 2025-10-27
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702002047/IF/22012035636866 — एक बगिया मां के नाम जय झांकुरिया आजीविक समूह पेवली | Approved | 0 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702002047/IF/22012035636881 — एक बगिया मां के नाम श्री कृष्ण आजीविका समूह पेवली | Approved | 0 | 0 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035637145 — एक बगिया मां के नाम श्री राम आजीविका समूह पेवली | Ongoing | 266578.64 | 1566 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035637146 — एक बगिया मां के नाम जय झांकुरिया आजीविक समूह पेवली | Ongoing | 266578.64 | 1566 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035637148 — एक बगिया मां के नाम श्री कृष्ण आजीविका समूह पेवली | Ongoing | 266578.64 | 0 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035638968 — एक बगिया मां के नाम श्री कृष्ण आजीविका समूह पेवली पूजा बघेल | Ongoing | 266578.64 | 1566 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035640032 — एक बगिया मां के नाम सावित्री पेवली | Ongoing | 266578.64 | 1566 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035640036 — एक बगिया मां के नाम श्री राम आजीविका समूह पेवली केशवती | Ongoing | 266578.64 | 1566 | 2025-12-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002047/IF/22012035640040 — एक बगिया मां के नाम मां पदमावाती आजीविका समूह पेवली बेबी | Ongoing | 266578.64 | 1566 | 2025-12-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002047/IF/9993673833 — CATTLE SHED RAMDATT/PATIRAM | Completed | 115900 | 108901.96 | 2015-09-18 | 2016-12-01
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/1873015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5732610 | Completed | 15660 | 15312 | 2018-07-27 | 2018-12-29
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/256618 — Construction of IAY House -IAY REG. NO. MP2160984 | Completed | 15030 | 15110 | 2017-01-20 | 2017-10-23
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/3796467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100872182 | Physically Completed | 18360 | 16602 | 2023-01-15 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002047/IF/IAY/4326099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100871934 | Ongoing | 27000 | 12318 | 2022-09-09
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002047/IF/IAY/4518517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100872073 | Ongoing | 27000 | 19251 | 2024-11-07
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/490155 — Construction of IAY House -IAY REG. NO. MP2131850 | Completed | 15030 | 15424 | 2017-02-17 | 2017-08-15
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/684580 — Construction of IAY House -IAY REG. NO. MP1761571 | Completed | 15030 | 15488 | 2017-05-05 | 2018-05-10
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/687971 — Construction of IAY House -IAY REG. NO. MP3687708 | Completed | 15030 | 15308 | 2017-05-05 | 2018-02-24
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/687976 — Construction of IAY House -IAY REG. NO. MP3689879 | Completed | 15030 | 15480 | 2017-05-12 | 2018-03-08
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002047/IF/IAY/687990 — Construction of IAY House -IAY REG. NO. MP3708362 | Completed | 15030 | 15480 | 2017-05-05 | 2017-10-27
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002047/LD/140 — मेढबंधान मुन्‍नी सिंह /करन सिंह | Completed | 20000 | 4300 | 2010-08-05 | 2010-08-05
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002047/LD/22012034228790 — MED BANDHAN AJMER/GOPAL | Completed | 27868 | 20670 | 2015-09-11 | 2015-09-17
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002047/LD/22012034232080 — med bandhn mahadev /patiram | Completed | 2360000000 | 18126 | 2015-10-30 | 2015-11-05
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034517617 — med bandhan karya ashok s/o jagat singh | Completed | 31154.86 | 29260 | 2020-06-25 | 2020-09-03
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034517618 — med bandhan karya ganga singh | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034517619 — med bandhan bitty devi | Completed | 27816.84 | 18240 | 2020-06-28 | 2020-09-09
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034517620 — manbhoop singh med bandhan karya | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034517621 — med bandhan karya meena devi /jay singh | Completed | 26704.17 | 22800 | 2020-06-28 | 2020-07-30
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034518335 — med bandhan ganga singh/patiram | Completed | 31154.86 | 29640 | 2020-06-25 | 2020-09-03
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034518336 — men bandhan manbhoop/punnilal | Completed | 33380.21 | 28500 | 2020-06-25 | 2020-08-25
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520118 — med bandhan karya ashok/ devidin | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520119 — med bandhan karya mahendra /tularam | Closed | 31862.99 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520120 — med bandhan karya raju /hariram | Closed | 20392.32 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520121 — med bandhan karya parmeshri/pankshilal | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520122 — med bandhan karya sukhram / | Closed | 22588.41 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520123 — med bandhan karya | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520124 — med bandhan karya indrajit/ ramsahh | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002047/LD/22012034520125 — bed bandhan karya man singh /rambharose | Deleted | 0 | 0 | 2020-07-07
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002047/OP/9425891235 — SHANTI DHAM PEWALI | Completed | 245000 | 239087.78 | 2016-12-16 | 2018-08-25
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002047/PG/22012034303830 — PLAY GROUND PEWALI | Deleted | 186600 | 0 | 2017-04-06
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034160435 — C.C.ROAD KESHAV KE DWAR SE TEJPAL KE DWAR KI TARAF | Completed | 98300 | 96514.79 | 2013-03-31 | 2013-11-07
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034198015 — C.C.ROAD PUTTULAL KE DWAR SE MAIN ROAD TAK | Completed | 68380 | 66125.9 | 2014-01-17 | 2014-06-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034206411 — C.C.ROAD POTHIRAM KE DWAR SE MATA MANDIR KI AUR | Completed | 151160 | 149375 | 2014-02-21 | 2014-06-20
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034225822 — C.C.ROAD HOM SINGH KE DARWAJE SE GOV. PRIMARY SCHOOL KI AUR | Deleted | 0 | 0 | 2014-04-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034225825 — C.C.ROAD HOM SINGH KE DARWAJE SE GOV. PRIMARY SCHOOL KI AUR | Deleted | 88858 | 0 | 2014-04-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034225828 — C.C.ROAD HOM SINGH KE DARWAJE SE GOV. PRIMARY SCHO | Completed | 88858 | 82595 | 2014-07-25 | 2015-06-20
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034225829 — C.C.ROAD BAHADUR KE DWAR SE DEVIDIN KI DWAR KI AUR | Deleted | 133300 | 0 | 2014-04-14
BHIND / BHIND | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034225830 — C.C.ROAD BAHADUR KE DWAR SE DEVIDIN KE DWAR KI AUR | Completed | 133300 | 117988 | 2014-07-25 | 2015-06-20
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034288057 — C.C.ROAD YADUNATH SINGH JATAV KE MAKAN SE BENIRAM KE MAKAN KI AUR | Completed | 101538 | 100614 | 2015-11-06 | 2017-03-28
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034292470 — C.C.ROAD SANKAR JI MANDIR SE PAAN SINGH KE DWAR KI OR | Deleted | 0 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034292499 — C.C ROAD SANKAR JI MANDIR SE PAAN SINGH KE DWAR KI OR | Completed | 107839 | 107712 | 2015-12-11 | 2017-04-03
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002047/RC/22012034337666 — SUDUR SAMPARK ROAD NIRMAD PEWALI SE PEWALI PURA | Completed | 695000 | 492873.04 | 2017-05-12 | 2019-01-01
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034345014 — C.C.ROAD NIRMAD PAPPU KE MAKAN SE MUNNI KE MAKAN TAK | Completed | 26550 | 23564 | 2017-07-28 | 2018-01-01
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034345017 — C.C.ROAD NIRMAD PAN SINGH KE MAKAN SE MUNNI KE MAKAN KI OR | Completed | 53100 | 53492 | 2017-08-04 | 2018-02-24
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034364918 — cc road sovran ke makan se ramdayal ke makan tak | Completed | 53100 | 54756 | 2017-10-27 | 2018-07-16
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1702002047/RC/22012034378977 — C C Road mata mandir se santosh ke makan tak | Closed | 22500 | 0 | 2017-04-19
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034381599 — CC ROAD NIRMAD KRIPASHANKAR KE MAKAN SE LAXMINARAYAN KE MAKAN TAK | Completed | 35400 | 35328 | 2018-02-09 | 2018-07-28
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034383001 — C C ROAD | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034384127 — CC ROAD NIRMAD MAIN ROAD SE MAHATE KE MAKAN TAK | Completed | 69750 | 66528 | 2018-02-23 | 2018-07-16
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034384177 — CC ROAD NIRMAD LAJJU BALMIK KE MAKAN SE MATA MANDIR TAK | Completed | 32550 | 33408 | 2018-06-22 | 2018-09-10
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034384184 — CC ROAD NIRMAD VISHRAM KE MAKAN SE ELAYAT KHAN KE MAKAN TAK | Ongoing | 23250 | 22610 | 2020-09-17
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1702002047/RC/22012034442736 — C C Road shivdayal ke makan se gyan singh ke makan ki or | Closed | 23000 | 0 | 2019-01-26
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034444807 — cc road main raod se darulala ke makanki or | Completed | 74400 | 77310 | 2019-03-08 | 2020-06-10
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002047/RC/22012034444951 — cc road sudama ke makan se school ki or | Closed | 51000 | 0 | 2018-04-14
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034444952 — cc road vishunlal ke makan se padam ke makan ki or | Completed | 37200 | 41112 | 2019-03-08 | 2019-11-10
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034469444 — C C ROAD RATAN SINGH KE MAKAN SE JANVED KE MAKAN TAK | Closed | 50000 | 0 | 2017-04-01
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034470053 — C C ROAD SHIVDAYAL KE MAKAN SE GHYAN SINGH KE MAKAN TAK | Closed | 23000 | 0 | 2017-04-01
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034470056 — C C ROAD SUDAMA KE MAKAN SE SCHOOL KI OR | Closed | 51000 | 0 | 2017-04-01
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034503606 — C C ROAD JITENDRA KE MAKAN SE MUNNI KE GHAR KI ARU | Completed | 52000 | 53712 | 2019-11-18 | 2020-06-10
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034503906 — C C ROAD RAKESH SINGH SE PANCHAYAT BHAVAN KI AUR | Completed | 52000 | 52116 | 2019-11-18 | 2020-06-10
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034508322 — C C ROAD POORAN SINGH KE MAKAN SE MOHAN SINGH KE MAKAN KI OR | Completed | 66000 | 66924 | 2019-12-12 | 2020-09-25
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002047/RC/22012034525587 — sudur sampark road pewali pura se gusing ki or | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034534970 — cc road nirmad karya mata mandir se rajkumar ke makan ki or pewali pura | Closed | 0 | 0 | 2020-04-14
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034536130 — CC ROAD MATA MANDIR SE RAJKUMAR KE MAKAN KI OR PEWALI | Completed | 34000 | 35340 | 2020-09-17 | 2021-04-30
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034540672 — cc road kishun singh ke makan se sukhdeen ke makan ki or | Ongoing | 77400 | 2850 | 2020-09-27
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034540679 — cc road jagdish ke makan se godilal ke makan ki or | Completed | 25800 | 17860 | 2020-09-27 | 2022-03-10
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034541020 — cc road mahesh ke makan se beniram ke makan ki or | Completed | 84450 | 88008 | 2021-04-24 | 2021-05-18
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/22012034569855 — cc road ramfal ke dwar se mahaveer ke dwar ki or pura | Completed | 57600 | 57528 | 2022-04-08 | 2022-10-10
BHIND / BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002047/RC/23 — सी0सी0 रोड जगदीश बघेल के द्वार से अजान बघेल के मका | Completed | 102322 | 85221 | 2012-03-24 | 2013-03-23
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1702002047/RS/22012034580082 — SAMUDAYAK SWACHCHHATA PARISAR PEWALI | Completed | 43000 | 52746 | 2022-03-01 | 2022-09-10
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1702002047/RS/22012034591330 — samudayak swachhta parisar pewali | Deleted | 43000 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002047/RS/22012034672482 — SOAKPIT Nirman mata mandir ke pass pewali | Deleted | 0 | 0 | 2022-08-15
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002047/RS/22012034672483 — Gov.middale school pewali | Closed | 10000 | 0 | 2022-10-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002047/RS/22012034673877 — soakpit nirman karya mata mandir pewali | Closed | 10000 | 0 | 2022-10-25
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1702002047/RS/22012034674071 — Soakpit nirman karya sachivalay ke pass | Closed | 10000 | 0 | 2022-10-25
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002047/RS/22012034674109 — soakpit gov primary school ke pass pewali pura | Closed | 10000 | 0 | 2022-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002047/RS/22012034674110 — soakpit nirman karya indal singh ke dwar ke pass | Closed | 10000 | 0 | 2022-10-25
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002047/RS/22012034681317 — samudayik soakpit nirman swachhta parisar ke pass | Closed | 10000 | 0 | 2022-12-17
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002047/WC/22012034324190 — TALAV NIRMAN PEWALI HARWALA | Completed | 9900000000 | 79120 | 2017-05-12 | 2018-02-18
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002047/WC/22012034561402 — talab gaharikaran pewali pura | Completed | 82568.57 | 72200 | 2020-08-19 | 2021-03-25
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1702002047/WC/22012034637463 — naveen talav gaharikaran shantidham ke paas | Ongoing | 645885.98 | 125886 | 2021-04-24
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1702002047/WC/22012034644172 — Harfan dam nirmaf karya jagram ke khet ke pass | Suspended | 881640.93 | 2316 | 2021-05-15
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002047/WC/22012035171973 — EARTHEN BUND NIRMAN DILYAI KE PAS PEWALEE | Physically Completed | 1460094.75 | 904078.36 | 2024-03-04 | 2026-06-11
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002047/WC/22012035171976 — EARTHEN BUND NIRMAN RATNU VALI KE PAS PEWALEE | Physically Completed | 1421692.23 | 1063492.26 | 2024-03-04 | 2026-06-11
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002047/WC/22012035171980 — EARTHEN BUND NIRMAN BADARI KE PAS PEWALEE | Physically Completed | 1480381.5 | 1082768.48 | 2024-03-04 | 2026-06-11
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002047/WC/22012035171982 — EARTHEN BUND NIRMAN MAHADEV KE PAS PEWALEE | Physically Completed | 1421692.23 | 848360.3 | 2024-03-04 | 2026-06-11
BHIND / BHIND | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002047/WC/22012035321562 — NAVEEN TALAB NIRMAN KUDARIYA KE PAS PEVLI | Closed | 1482247.95 | 0 | 2026-04-06
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702002047/WC/22012035321563 — NAVEEN TALAB NIRMAN MATA KE MANDIR KE PAS PEVLI | Ongoing | 1482747.95 | 379233 | 2026-01-05