## Work List
Exported on: 2026-10-25 17:03:58
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: HARKIJAMEH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002050/AV/22012034400918 — SHANTIDHAM NIRMAN KARYA GRAM DHANUK PURA | Deleted | 0 | 0 | 2018-04-01
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002050/AV/22012034400922 — SHANTIDHAM NIRMAN KARYA GRAM DHANUK PURA | Ongoing | 180000 | 5700 | 2021-03-14
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen Shed for Government School for Community | Constr of Kitchen Shed | 1702002050/AV/22012034534077 — KITCHIN SHED NIRMAN M/S SCHOOL HARKIJAMEH | Ongoing | 425000 | 397827 | 2020-08-28
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702002050/AV/22012034537368 — BOUNDARY WALL NIRMAN GOVT. MS/PS SCHOOL PARISAR ME DHANUKPURA | Completed | 35000 | 22800 | 2020-12-16 | 2022-04-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002050/AV/22012034624911 — SHANTIDHAM NIRMAN KARYA DHANUK KA PURA | Closed | 0 | 0 | 2022-04-01
BHIND / BHIND | 2025-2026 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1702002050/AV/22012034667440 — ek bagia maa ke nam chhaya devi ke khet per gram rora | Approved | 271093.25 | 0 | 2025-08-27
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002050/AV/4183 — Aanganbadi/Other Rural Infrastructure,HARKIJAMEH | Completed | 330000 | 330950 | 2015-12-15 | 2020-02-25
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002050/AV/8304 — SHANTIDHAM NIRMAN KARYA GRAM RORA | Completed | 180000 | 6192 | 2017-04-04 | 2022-11-04
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1702002050/DP/22012034601716 — meri mati mera desh amrat batika govt ps school dhanukpra | Closed | 0 | 0 | 2023-04-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002050/IF/22012034352341 — PODHAROPAN KARYA MANDIR OR SHALABHAVAN HARKIJAMEH | Closed | 335000 | 0 | 2017-06-20
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002050/IF/22012034357342 — PODHAROPAN KARYA SCHOOL MANDIR HARKIJAMEH | Closed | 335000 | 0 | 2017-05-12
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002050/IF/22012034357348 — PODHAROPAN KARYA AGANWADI RORA | Closed | 335000 | 0 | 2017-05-12
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002050/IF/22012034357350 — PODHAROPAN KARYA SCHOOL RORA | Closed | 335000 | 0 | 2017-05-12
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002050/IF/22012034653851 — KHET TALAB NIRMAN ARVINDRA/MEHARBAN SINGH | Deleted | 0 | 0 | 2020-11-26
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002050/IF/22012034669954 — KHET TALAB NIRMAN ARVIND SINGH /MEHARBAN SINGH | Physically Completed | 332962.02 | 214788 | 2021-03-17 | 2026-04-15
BHIND / BHIND | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702002050/IF/22012035482061 — khet talabnirman arvind singh ke khet per gram rora | New | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002050/IF/22012035483090 — NAVEEN KHET TALAB NIRMAN ARVIND KE KHET PAR | Ongoing | 147621.16 | 2871 | 2025-05-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702002050/IF/22012035614522 — ek bagiya maa ke name chhaya devi ke khet par | Ongoing | 266577.25 | 56409.36 | 2025-12-19
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993676560 — CATTLE SHED AMAR SINGH / MAKRAND SINGH | Completed | 115900 | 108626.76 | 2015-09-29 | 2017-09-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993676561 — CATTLE SHED UMESH SINGH / JAGDISH SINGH | Completed | 115900 | 108626.76 | 2015-09-29 | 2017-09-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993676562 — CATTLE SHED RAMVEER SINGH / NARESH | Completed | 115900 | 109679.58 | 2015-12-15 | 2017-09-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718836 — NARENDRA S/O HIMAT SINGH | Completed | 115900 | 110579.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718837 — TAHSEELDAR SINGH S/O SADHU SINGH | Completed | 115900 | 110497.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718844 — MATHURA SINGH S/O DARSHAN SINGH | Completed | 115900 | 110154.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718849 — nathu singh s/o hotam singh | Completed | 115900 | 110154.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718852 — avdesh s/o bhagvan singh | Completed | 115900 | 105641.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718855 — amar singh s/o ajay singh | Completed | 115900 | 92786 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718858 — narendra singh s/o makhan singh | Completed | 115900 | 110154.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718861 — yadunath singh s/o raguveer singh | Closed | 115900 | 0 | 2016-02-20
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718865 — shatrughan singh s/o dashrath singh | Completed | 115900 | 110475.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002050/IF/9993718869 — govindra singh s/o jasram singh | Completed | 115900 | 109229.5 | 2016-03-22 | 2017-07-05
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002050/IF/IAY/134025 — Construction of IAY House -IAY REG. NO. MP-02-002-050-001/59 | Completed | 14310 | 8684 | 2016-08-09 | 2016-09-27
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002050/IF/IAY/261217 — Construction of IAY House -IAY REG. NO. MP2541624 | Completed | 15030 | 9916 | 2017-03-07 | 2017-12-14
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002050/IF/IAY/261476 — Construction of IAY House -IAY REG. NO. MP2588696 | Completed | 15030 | 15938 | 2017-01-31 | 2017-10-15
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002050/IF/IAY/3685715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115132480 | Physically Completed | 18360 | 5304 | 2023-06-06 | 2024-11-21
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002050/IF/IAY/500729 — Construction of IAY House -IAY REG. NO. MP2260919 | Completed | 15030 | 14188 | 2017-01-31 | 2017-10-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5227177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115149078 | Ongoing | 27000 | 0 | 2026-02-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5620980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115137347 | Ongoing | 27000 | 0 | 2026-02-24
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5621066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115142549 | Physically Completed | 27000 | 6525 | 2025-09-29 | 2026-09-13
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5621113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115151965 | Ongoing | 27000 | 1566 | 2026-02-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5621247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115142573 | Physically Completed | 27000 | 6525 | 2025-09-29 | 2026-09-13
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5621779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115155054 | Physically Completed | 27000 | 4698 | 2026-02-16 | 2026-09-13
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002050/IF/IAY/5726627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145528 | Ongoing | 27000 | 0 | 2026-02-16
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034230187 — MAD BANDHAN RAMENDRA SINGH / BACCHI SINGH | Completed | 31300 | 28143 | 2015-09-29 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034233020 — MED BANDHAN KALICHARAN/CHHAVIRAM | Completed | 41400 | 38376 | 2015-10-13 | 2017-07-10
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034241079 — MAD BANDHAN VIRENDRA SINGH/ SURENDRA SINGH | Completed | 34700 | 29892 | 2015-12-01 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251142 — MED BANDAN MAHIPAT S/O SARMAN DHANUK PURA | Completed | 27900 | 25760 | 2016-01-19 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251145 — MED BANDAN RADHA DEVI W/O LAL SINGH | Completed | 25300 | 15900 | 2016-01-19 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251148 — MED BANDAN SHATRUGHAN SINGH S/O DASHRATH SINGH | Completed | 17800 | 15694 | 2016-01-19 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251150 — MED BANDAN GOVIND SINGH S/O JASRATH SINGH | Completed | 17800 | 16059 | 2016-01-19 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251152 — MAD BANDAN BEERENDRA SINGH S/O BABU SINGH | Completed | 21200 | 18444 | 2016-01-19 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251155 — MED BANDAN NARENDRA SINGH S/O MAKHAN SINGH | Completed | 21200 | 18963 | 2016-01-20 | 2016-06-28
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034251157 — MED BANDAN RAMJILAL S/O ACHHELAL | Completed | 41400 | 38166 | 2016-01-19 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/22012034260310 — MED BANDHAN RAJESH SINGH S/O VIJAY SINGH | Completed | 41400 | 38410 | 2016-06-14 | 2017-07-10
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291422 — MED BANDAN JITENDAR SINGH KE KHET PAR | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291549 — MED BANDAN JITENDRA SINGH KE KHET PAR | Completed | 31000 | 29893 | 2016-07-26 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291550 — MED BANDAN NATHU SINGH KE KHET PAR | Completed | 32000 | 30895 | 2016-07-26 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291551 — MMED BANDAN HIMMAT SINGH KE KHET PAR | Completed | 39000 | 36907 | 2016-08-16 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291552 — MED BANDAN RAMBHADUR KE KHET PAR | Completed | 32000 | 29893 | 2016-08-02 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291553 — MED BANDAN MATHURA SINGH KE KHET PAR | Completed | 32000 | 30895 | 2016-08-02 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291554 — MED BANDAN GAJENDRA SINGH KE KHET PAR | Completed | 43300 | 42084 | 2016-08-09 | 2017-07-10
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034291555 — MED BANDAN PRAHALAD SINGH KE KHET PAR | Completed | 41000 | 39579 | 2016-08-23 | 2017-07-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034551365 — MED BANDHAN VIRENDRA / SURENDRA SINGH | Closed | 29147.22 | 0 | 2021-01-21
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034551366 — MED BANDHAN RAJENDRA SINGH / VIJAY SINGH | Closed | 29147.22 | 0 | 2021-05-31
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034551367 — MED BANDHAN RAMENDRA SINGH / BACHCHI SINGH | Ongoing | 29914.25 | 12738 | 2021-08-27
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034551369 — MED BANDHAN VIRENDRA SINGH / MAHENDRA SINGH | Closed | 30681.29 | 0 | 2021-05-31
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034551370 — MED BANDHAN DEVENDRA SINGH / RANJEET SINGH | Closed | 29914.25 | 0 | 2021-05-31
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002050/LD/22012034551371 — MED BANDHAN RAMPRAKASH / BALAKRAM | Closed | 32215.35 | 0 | 2021-05-31
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002050/LD/227 — मेडबन्‍धान कार्य सुखराम / नारायण जाटव | Completed | 26000 | 13300 | 2010-09-23 | 2010-09-23
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002050/PG/9425895273 — KHEL MAIDAN RORA | Deleted | 186600 | 0 | 2017-03-21
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002050/PG/9425895275 — KHEL MAIDAN HARKIJAMEH | Completed | 186600 | 90612 | 2017-04-04 | 2023-03-25
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034283993 — C.C.ROAD NIRMAN KARYA SCHOOL SE LEKAR PURAN SINGH KE MAKAN KI AUR | Deleted | 0 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034283994 — C.C.ROAD NIRMAN KARYA SCHOOL SE LEKAR PURAN SINGH KE MAKAN KI AUR | Completed | 360201 | 318017 | 2015-09-08 | 2018-04-14
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034295848 — C.C.ROD NIRMAN SCHOOL SE LEKAR RAJU SINGH KE MAKAN TAK | Completed | 154589 | 152311 | 2016-01-12 | 2016-09-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002050/RC/22012034350547 — GRAVEL SADAK NIRMAN KARYA DHANUK PURA SE NAYAGWAN KI AUR | Completed | 1634000 | 631239.78 | 2017-10-03 | 2021-11-23
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034353451 — CC ROAD NIRMAN KARYA DIVOLE KE MAKAN SE PANDIT KE MAKAN TAK RORA | Completed | 59737 | 56760 | 2017-09-12 | 2018-03-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034353461 — CC ROAD NIRMAN RAMRATAN SE MUGARAM UMRAW SE SCHOOL TAK RORA | Completed | 31860 | 47472 | 2017-09-12 | 2018-04-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034353465 — CC ROAD NIRMAN RAJESH KE DARWAJE SE MATA TAK RORA | Completed | 53100 | 49880 | 2017-10-11 | 2018-04-17
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034353467 — CC ROAD NIRMAN BAGIYA SE MATA KE THAN TAK RORA | Completed | 50445 | 46620 | 2017-10-11 | 2018-04-22
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034365386 — CC ROAD SCHOOL SE SUMER KE MAKAN TAK DHANUK KA PURA | Completed | 50900 | 55776 | 2017-10-29 | 2018-10-07
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034365387 — CC ROAD SHIVNATH KE DWAR SE YOGENDRA KE DARWAJE KI OR | Completed | 71700 | 65944 | 2017-10-29 | 2018-05-27
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034365390 — CC ROAD ATUL KE GHAR SE SHIVNATH KE GHAR TAK | Completed | 13600 | 16512 | 2017-10-29 | 2022-11-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034374420 — CC ROAD | Closed | 0 | 0 | 2017-10-02
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034386178 — CC ROAD AMRATLAL SE LOTAL KE GHAR TAK | Completed | 36000 | 42630 | 2018-06-26 | 2018-10-28
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034386179 — CC ROAD SHEETAL KE MAKAN SE SAHUKAR KE MAKAN TAK | Completed | 24000 | 17226 | 2018-05-18 | 2018-10-28
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034386180 — CC ROAD RAMAUTAR SINGH SE JANDEL KE MAKAN TAK | Completed | 60000 | 33408 | 2018-05-18 | 2022-11-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034386181 — CC ROAD JASMANT SE MATA KE MANDIR TAK RORA KA PURA | Closed | 16000 | 0 | 2017-08-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034386183 — CC ROAD CHANDRABHAN SE JAGDESH KE GHAR TAK RORA KA PURA | Closed | 55000 | 0 | 2017-08-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034442713 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034504274 — CC ROAD MAIN ROAD SE SHANKAR JI KE MANDIR KI OR | Completed | 22000 | 17698 | 2019-11-08 | 2020-08-05
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034504281 — CC ROAD RAMJANKI MANDIR SE RAMBAHADUR KE MAKAN KI OR | Completed | 22000 | 17776 | 2019-11-08 | 2020-01-03
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034509584 — Cc Road Narendra Se Pramod Ke Ghar Ki Aur Harkijameh | Completed | 22000 | 4224 | 2020-01-16 | 2022-11-02
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034509586 — Cc Road Jabar Singh Ke Ghar Se Betal Ke Ghar Ki Aur Harkijameh | Closed | 22000 | 0 | 2019-10-02
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034509588 — Cc Road Suresh Ke Ghar Se Purushottam Ke Ghar Ki Aur Harkijameh | Completed | 31000 | 29828 | 2020-01-16 | 2020-06-15
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034509589 — Cc Road Asha Ram Ke Ghar Se Bijbhan Ke Ghar Ki Aur Rora | Completed | 89000 | 73392 | 2020-01-16 | 2021-04-20
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034533732 — CC ROAD SCHOOL SE LEKAR VIJAYRAM KE GHAR KI OR | Completed | 26000 | 23750 | 2020-08-26 | 2021-02-10
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034533735 — CC ROAD RAMRATAN KE GONDA SE SHANKAR JI MANDIR KI OR | Completed | 74000 | 72960 | 2020-08-26 | 2021-04-20
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034539364 — CC ROAD SHALA BHAVAN SE SHANTIDHAM KI OR DHANUKPURA | Closed | 98000 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034542975 — CC ROAD SCHOOL SE MAHAVEER KE GHAR KI OR DHANUPURA | Completed | 44000 | 42414 | 2020-12-23 | 2022-04-04
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034542983 — CC ROAD MAHAVEER KE GHAR SE SHANTIDHAM KI OR DHANUKPURA | Completed | 44000 | 43433 | 2020-12-23 | 2022-04-04
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034552864 — CC ROAD MAIN ROAD SE SATPAL KE GONDA KI OR | Closed | 33000 | 0 | 2020-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/22012034566355 — CC ROAD KUA SE SANTOSH KE GHAR KI OR DHANUKPURA | Closed | 35000 | 0 | 2021-01-21
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002050/RC/76 — सी0सी0 रोड निर्माण कार्य दाताराम के मकान से स्‍कूल | Completed | 381046 | 14520 | 2012-12-30 | 2017-01-09
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002050/RS/22012034686045 — SWACHHATA PARISAR HARKIJAMEH | Closed | 43000 | 0 | 2023-04-12
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002050/RS/22012034686315 — SWACHHATA PARISAR | Closed | 43000 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002050/RS/22012034686553 — SWACHHATA PARISAR | Closed | 43000 | 0 | 2023-02-01
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002050/WC/22012034325225 — TALAB NIRMAN KARYA PARITBABA KE PASS HARKIJAMEH | Completed | 98666 | 50912 | 2017-05-23 | 2017-07-18
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702002050/WC/22012034325228 — TALAB NIRMAN KARYA RORA KA PURA RORA | Completed | 97000 | 88064 | 2017-05-19 | 2017-07-27
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002050/WC/22012034438643 — TALAB NIRMAN KARYA GRAM RORA HARKIJAMEH | Closed | 385000 | 0 | 2018-04-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702002050/WC/22012034969550 — Naveen talab nirman virendra ke khet ke pass | Closed | 0 | 0 | 2022-04-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002050/WC/22012034970858 — NAVEEN KHET TALAB NIRMAN KARYA VIRENDRA SINGH | Closed | 356340.1 | 0 | 2022-04-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002050/WC/22012034970873 — NAVEEN KHET TALAB NIRMAN KARYA RAMBETI W/O RAJBAHADUR RORA | Closed | 356340.1 | 0 | 2022-04-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702002050/WC/22012034970882 — NAVEEN KHET TALAB NIRMAN KARYA ARVIND SINGH KE KHET KE PASS | Closed | 356340.1 | 0 | 2022-04-01