## Work List
Exported on: 2026-10-07 03:02:53
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KAKAHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound Wall for Government School for Community | Constr of Compound wall | 1702002053/AV/22012034546707 — Boundary wall Nirman school parisar kakahara | Ongoing | 275177.54 | 0 | 2021-03-04
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608106 — CATTEL SHED SANTOSH / LALTAPRASAD | Ongoing | 101273.16 | 0 | 2020-09-22
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608107 — CATTEL SHED DHARAM / CHOTE SINGH | Ongoing | 101273.16 | 0 | 2020-09-22
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608110 — CATTEL SHED DEVICHARAN / MAJBOOT | Ongoing | 101273.16 | 0 | 2020-09-22
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608111 — CATTEL SHED SURESH / PUNU | Ongoing | 101273.16 | 0 | 2020-09-22
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608112 — CATTEL SHED SANOJ / VISHNATH | Ongoing | 101804.91 | 0 | 2020-09-29
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608114 — CATTEL SHED KISHORI / MUNNA | Ongoing | 101273.16 | 0 | 2020-09-22
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608116 — CATTEL SHED SANTOSH / BALVEER | Ongoing | 101273.16 | 0 | 2020-09-21
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608118 — CATTEL SHED NEELAM / RAMGYA | Ongoing | 101273.16 | 0 | 2020-09-22
BHIND / BHIND | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608121 — CATTEL SHED RAJENDRA / BALVEER | Ongoing | 101804.91 | 0 | 2023-08-27
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608650 — CATTEL SHED SEETARAM / JANDEL | Ongoing | 101804.91 | 0 | 2020-10-01
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608652 — CATTEL SHED JOGENDRA / BABU SINGH | Ongoing | 101804.91 | 0 | 2022-11-15
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702002053/IF/22012034608658 — CATTEL SHED SHANTI / ANGAD | Ongoing | 101804.91 | 0 | 2020-10-01
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002053/IF/22012034776123 — MED BANDHAN SANOJ SINGH KHET PAR | Ongoing | 26600.31 | 0 | 2021-07-01
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002053/IF/22012034776129 — MED BANDHAN TEHSIDAR KHET PAR | Ongoing | 28000.37 | 0 | 2021-07-08
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002053/IF/22012034776148 — MED BANDHAN RAJESH SINGH KHET PAR | Ongoing | 28000.37 | 0 | 2022-01-12
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002053/IF/22012034803816 — MED BANDHAN NARAYAN / DAL SINGH KHET PAR | Ongoing | 28000.37 | 0 | 2021-07-08
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002053/IF/22012034803818 — MED BANDHAN RAJVEER / AMRAT SINGH KHET PAR | Ongoing | 28000.37 | 0 | 2022-01-12
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Check Dam for Individual | Construction of Check Dam/Stop Dam | 1702002053/IF/22012035120617 — KHET TALAB RAMAGYA SINGH KE KHET PAR | Ongoing | 383083.54 | 0 | 2023-10-01
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individual | Construction of Check Dam/Stop Dam | 1702002053/IF/22012035120621 — KHET TALAB RAMSARAN SINGH KE KHET PAR | Ongoing | 383083.54 | 0 | 2023-10-01
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Contour Trench for Individual | Construction of Trench | 1702002053/IF/22012035369350 — kheat talab nirman chhote singh ke kehat par gp kakahara | Ongoing | 147621.16 | 0 | 2025-05-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035534592 — khet talab nirman guddi ke khet par gp kakhara | Ongoing | 147621.16 | 0 | 2025-05-26
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035535293 — khet talab nirman chote singh ke khet par | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035538176 — KHET TALAB NIRMAN KULDEEP KE KHET PAR GP KAKHARA | Ongoing | 147621.16 | 0 | 2025-05-26
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035538187 — NAVEEN KHET TALAB NIRMAN CHATAU KE KHET PAR GP KAKHARA | New | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035538188 — NAVEEN KHET TALAB NIRMAN CHATAU KE KHET PAR GP KAKHARA | Ongoing | 147621.16 | 0 | 2025-05-26
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035576820 — NAVEEN KHET TALAB RAN SINGH/NANDAN SINGH KE KHET PAR GP KAKHARA | Approved | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035576822 — NAVEEN KHET TALAB SUMER SINGH KE KHET PAR GP KAKHARA | New | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035576823 — NAVEEN KHET TALAB SUMER SINGH KE KHET PAR GP KAKHARA | New | 0 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702002053/IF/22012035576828 — NAVEEN KHET TALAB SUMER SINGH KE KHET PAR GP KAKHARA | Ongoing | 450885.64 | 0 | 2025-07-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/134125 — Construction of IAY House -IAY REG. NO. MP-02-002-053-001/65 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/134126 — Construction of IAY House -IAY REG. NO. MP-02-002-053-001/66 | Approved | 27000 | 0 | 2016-02-14
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/4737728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106018022 | Ongoing | 27000 | 0 | 2025-01-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5596584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102653067 | Ongoing | 27000 | 0 | 2025-06-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5596758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121345790 | Ongoing | 27000 | 0 | 2025-05-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5596896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106139442 | Ongoing | 27000 | 0 | 2025-07-22
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5597017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106080980 | Approved | 27000 | 0 | 2025-03-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5597065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124771765 | Ongoing | 27000 | 0 | 2025-07-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5597307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113567953 | Ongoing | 27000 | 3600 | 2025-06-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5597704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122073347 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5597907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122842867 | Ongoing | 27000 | 0 | 2025-07-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5597920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120940267 | Ongoing | 27000 | 0 | 2025-05-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5598056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113567789 | Ongoing | 27000 | 1800 | 2025-06-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5598118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102653314 | Ongoing | 27000 | 0 | 2025-06-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5598190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116737770 | Ongoing | 27000 | 0 | 2025-05-22
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5871156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113568282 | Ongoing | 27000 | 0 | 2026-02-17
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5871181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102653744 | Ongoing | 27000 | 1800 | 2026-02-17
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/5871185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121347212 | Ongoing | 27000 | 0 | 2026-02-27
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702002053/IF/IAY/6049403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125080050 | Approved | 27000 | 0 | 2026-02-10
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002053/LD/22012034523068 — MED BANDHAN NIRMAN SARVESH / RAJA SINGH KE KHET PAR | Ongoing | 33056.1 | 0 | 2020-09-21
BHIND / BHIND | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702002053/LD/22012034529610 — naveen charagah nirman kakahara | Ongoing | 792213.45 | 0 | 2020-12-17
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702002053/RC/22012034471693 — c.c.road nirman ramotar ke dwar se devicharan ke dwar ki or | Ongoing | 35400 | 0 | 2019-11-13
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002053/WC/22012034965249 — khet talav nirman nirbhay singh ket par | Ongoing | 356340.1 | 0 | 2022-07-26