## Work List
Exported on: 2026-10-13 03:11:04
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: DUNGARPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002057/AV/22012034368575 — SHANTI DHAM NIRMAN BEHAD KI JAMEH | Completed | 180000 | 177405.46 | 2017-09-27 | 2018-03-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002057/AV/22012034368576 — SHANTI DHAM NIRMAN DUNGARPURA | Completed | 180000 | 171901.46 | 2017-09-27 | 2018-03-15
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002057/AV/22012034392066 — Shantidham Diviyapura | Ongoing | 180000 | 32364 | 2019-01-30
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702002057/AV/22012034392073 — SHANTIDHAM NIRMAN PHULE KA PURA | Ongoing | 180000 | 32364 | 2019-01-30
BHIND / BHIND | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1702002057/AV/22012034469400 — GAU SHALA NIRMAN DUNGARPURA | Ongoing | 2771628.29 | 1358464.5 | 2020-07-09
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002057/AV/4237 — Anganwadi/Other Rural Infrastructure,DUNGARPURA | Completed | 330000 | 348889 | 2015-12-23 | 2018-05-25
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002057/AV/4239 — Anganwadi/Other Rural Infrastructure,DUNGARPURA | Completed | 330000 | 327088 | 2015-12-24 | 2018-10-20
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702002057/AV/5509 — Anganwadi/Other Rural Infrastructure PHULE KA PURA | Completed | 330000 | 272765 | 2016-08-24 | 2022-11-02
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002057/DP/22012034601815 — पौधारोपण मेरी माटी मेरा देश वसुधा वंदन ग्राम पंचायत भवन डुंगरपुरा | Closed | 56725.4 | 0 | 2023-07-10
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002057/FP/22012034631848 — KACHCHA NALA NIRMAN LAXIRAM KE DARWAJE SE DIVIYAPURA PURA MAIN ROAD PULIYA KE AGE KI AUR | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702002057/FP/22012034637794 — NALA NIRMAN LAXMIRAM KE DWAR SE SANTOSH KE GONDA KI OR | Closed | 560000 | 0 | 2023-04-10
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357527 — PODHA NIRMAN KARYA | Closed | 0 | 0 | 2017-04-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357531 — TALAB NIRMAN KARY | Closed | 335000 | 0 | 2017-04-24
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357748 — VRIKSHAROPAN KARAY SAMUDAYAK STHAL DUNGARPURA | Closed | 0 | 0 | 2017-04-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357750 — VRIKSHAROPAN KARAY SAMUDAYAK STHAL DUNGARPURA | Closed | 335000 | 0 | 2017-04-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357832 — VRIKSHAROPAN KARAY SAMUDAYAK STHAL BEHAD KI JAMEH | Closed | 335000 | 0 | 2017-06-16
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357842 — VRIKSHAROPAN KARAY SAMUDAYAK STHAL DUNGARPURA | Closed | 335000 | 0 | 2017-04-14
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034357848 — VRIKSHAROPAN KARY SAMUDAYAK DUNGARPURA | Closed | 335000 | 0 | 2017-04-14
BHIND / BHIND | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012034649541 — अनिल सिहं पुत्र राजेंद्र सिंह के निजी खेत मे फलौदयान रोपण कार्य | Ongoing | 354000 | 2316 | 2021-04-12
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002057/IF/22012035531389 — NAVEEN KHET TALAB NATHURAM/RAMSHREE KE KHET PAR GP DUNGARPURA | Approved | 55865.38 | 0 | 2025-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002057/IF/22012035641430 — EK BAGIYA MAA KE NAAM PREETI KE KHET PAR GP DUNGARPURA | Ongoing | 266578.64 | 0 | 2026-01-12
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/133953 — Construction of IAY House -IAY REG. NO. MP-02-002-057-001/02 | Completed | 14310 | 15138 | 2018-06-20 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208121 — Construction of IAY House -IAY REG. NO. MP1036097 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208325 — Construction of IAY House -IAY REG. NO. MP1039246 | Completed | 15030 | 15312 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208326 — Construction of IAY House -IAY REG. NO. MP1039261 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208414 — Construction of IAY House -IAY REG. NO. MP1040573 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208693 — Construction of IAY House -IAY REG. NO. MP1044556 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208758 — Construction of IAY House -IAY REG. NO. MP1045407 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/208931 — Construction of IAY House -IAY REG. NO. MP1048287 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/271913 — Construction of IAY House -IAY REG. NO. MP2847474 | Completed | 15030 | 15660 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/305270 — Construction of IAY House -IAY REG. NO. MP1037756 | Completed | 15030 | 15486 | 2017-02-21 | 2018-09-18
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/306728 — Construction of IAY House -IAY REG. NO. MP1040956 | Completed | 15030 | 15486 | 2017-01-25 | 2018-09-18
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/3732980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119860419 | Physically Completed | 18360 | 12852 | 2022-12-21 | 2024-11-21
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/3769884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120561486 | Completed | 18360 | 17136 | 2022-08-09 | 2023-02-04
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/3811812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303304 | Completed | 18360 | 17136 | 2022-07-17 | 2023-02-04
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/4176673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123060840 | Completed | 18360 | 17136 | 2022-08-21 | 2023-02-04
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/445969 — Construction of IAY House -IAY REG. NO. MP1517471 | Completed | 15030 | 15660 | 2017-03-07 | 2018-09-01
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/4521619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303347 | Ongoing | 23490 | 11367 | 2024-11-08
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/4527927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130409714 | Ongoing | 23490 | 4590 | 2024-11-17
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5620543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113939876 | Ongoing | 23490 | 1566 | 2025-09-29
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5620585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119859721 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5620589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113940217 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5620732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119641402 | Ongoing | 23490 | 7569 | 2025-10-02
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5620817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113940407 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5620938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113943688 | Approved | 23490 | 0 | 2025-03-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303450 | Approved | 23490 | 0 | 2025-04-13
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121022145 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121023441 | Ongoing | 23490 | 1305 | 2025-10-02
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119859484 | Approved | 23490 | 0 | 2025-04-30
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113940091 | Ongoing | 23490 | 6003 | 2025-09-29
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113951643 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113953472 | Ongoing | 23490 | 1305 | 2025-09-29
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130409449 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130409607 | Approved | 23490 | 0 | 2025-04-22
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5621965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118841663 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5622061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120818693 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/5681808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303379 | Approved | 23490 | 0 | 2025-03-11
BHIND / BHIND | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002057/IF/IAY/645957 — Construction of IAY House -IAY REG. NO. MP1533146 | Completed | 15030 | 15660 | 2017-03-07 | 2018-09-18
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002057/LD/209 — मेड बन्‍धान कार्य सोमवती / सुरेश्‍ा | Completed | 15600 | 7900 | 2010-10-17 | 2010-10-17
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002057/LD/212 — मेड बन्‍धान कार्य नाथूराम / सूबालाल | Completed | 26000 | 6600 | 2010-10-17 | 2010-10-17
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1702002057/LD/22012034586777 — PLAY GROUND NIRMAN GRAM DUNGARPURA | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002057/LD/240 — मेड बन्‍धान कार्य रामलखन / अजान के खेत पर | Deleted | 21100 | 0 | 2011-01-24
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002057/PG/22012034365783 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002057/PG/22012034366321 — play ground | Closed | 0 | 0 | 2017-10-02
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034286896 — C.C ROAD SCHOOL SE BHIKAM SINGH KE DARWAJE KI AUR | Completed | 126900 | 107007 | 2015-10-14 | 2016-06-10
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034286901 — CC RQAD SHANKAR SINGH KE DARWAJE SE SURENDRA SINGH KE DARWAJE KI OR | Completed | 84609 | 60950 | 2015-10-14 | 2016-09-30
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034308780 — C.C.ROD MEN ROD SE JAGDEESH KE MAKAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034308781 — C.C.ROD MEN ROD SE BADE KE MAKAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034308782 — C.C.ROD BHARAT SINGH KE MAKAN SE AGANVADI TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034308783 — C.C.ROD SHIVSHANKAR KE MANAK SE MATA MANDIR TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034308784 — C.C.ROD MEN ROD SE AGANSADI BHAVAN TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002057/RC/22012034344669 — GREVAL ROAD NIRMAN TEHNGUR ROAD SE PHOLE KE PURA TAK | Completed | 1420000 | 1333254.76 | 2017-07-19 | 2023-09-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034348407 — C.C.ROAD NIRMAN BUDHU HARIJAN KE GHAR SE KAMLESH KE GHAR KI OR DIVIYAPURA | Completed | 99562 | 98520 | 2017-08-23 | 2018-06-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034348409 — C.C.ROAD NIRMAN LAJJARAM HARIJAN KE GHAR SE RADHE HARIAJN KE GHAR KI OR DIVIYAPURA | Completed | 37612 | 38872 | 2017-08-23 | 2018-06-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034349959 — C.C.ROAD NIRMAN SHIVSHNKAR KE MAKAN SE MATA KE MANDIR KI OR DIVIYAPURA | Completed | 51000 | 52908 | 2017-10-04 | 2018-06-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034351694 — C.C.ROAD NIRMAN MAIN ROAD SE JAGDEESH KE GHAR TAK | Completed | 31860 | 41988 | 2017-10-04 | 2018-06-30
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034351695 — C.C.ROAD MEAN ROAD SE BADE KE GHAR TAK | Completed | 33187 | 44886 | 2017-10-04 | 2022-11-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034351696 — C.C.ROAD NIRMAN BHARAT KE GHAR SE AGANVADI KI OR | Completed | 77437 | 75090 | 2017-10-04 | 2018-06-30
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034370886 — C.C.ROAD NIRMAN MEAN ROAD SE AGANVADI BHAVAN KI OR DIVIYAPURA | Completed | 31000 | 14760 | 2019-03-04 | 2022-11-04
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034371636 — C.C.ROAD NIRMAN HARICHARAN KE GHAR SE SURESH KE GHAR KI OR DIVIYAPURA | Closed | 40710 | 0 | 2017-04-14
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034371637 — C.C.ROAD NIRMAN SURESH KE GHAR SE DEVIDAYAL KE KI OR BEHAD KI JAMEH | Completed | 28762 | 31038 | 2018-01-24 | 2021-11-23
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034379896 — सी सी रोड सुरेश के घर से देवीदयाल के घर तक | Closed | 28762 | 0 | 2017-06-28
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034379929 — c c rod munesh ke ghar lakshaman ke ghar tak | Closed | 93000 | 0 | 2017-04-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034380323 — सी सी रोड निर्माण हरिचरन के घर से सुरेश के घर तक | Closed | 40710 | 0 | 2017-04-02
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034381814 — cc road | Closed | 0 | 0 | 2017-10-02
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034394599 — सी सी रोड मुनेश के घर से लक्षमन के घर तक फुले कापुरा | Completed | 93000 | 92394 | 2018-10-04 | 2022-11-04
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034395363 — CC ROAD SCHOOL SE NATHU HARI. KE GHAR KI OR DIVIYAPURA | Completed | 181000 | 179394 | 2018-10-04 | 2022-11-04
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034442708 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034556261 — CC ROAD BALIRAM HARIGEN KE DWAR SE CHHOTE HARIGEN KE KUA KI OR | Completed | 52000 | 50160 | 2021-01-30 | 2021-03-01
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034615082 — CC RAOD JASMANT SINGH KE GHAR SE KUWAR SINGH KE GHAR KI OR | Completed | 15000 | 13464 | 2022-11-28 | 2023-03-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/22012034615083 — CC ROAD MAY NALI SHALA BHAVAN KE PASS SE HAKIM SINGH KE GHAR KI OR | Completed | 120000 | 36720 | 2022-12-12 | 2023-09-20
BHIND / BHIND | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/59 — सी0सी0 रोड निर्माण फूल सिंह परिहार के द्वार से सोवरन सिंह के दरवाजे तक | Completed | 273634 | 39782 | 2013-03-16 | 2017-01-09
BHIND / BHIND | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002057/RC/99572 — gyhhdjh | Deleted | 405440 | 0 | 2009-05-10
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702002057/RS/22012034584820 — SAMUDAYAK SWACHCHHATA PARISAR DUNGARPURA | Ongoing | 43000 | 41124 | 2022-02-12
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034669768 — CONSTRUCTION OF SAMUDAYAK SOKHTA SC BASTI PER | Closed | 10000 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034669774 — CONSTRUCTION OF SAMUDAYAK SOKHTA BAGHEL THOK DUNGARPURA | Closed | 10000 | 0 | 2022-08-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034669784 — CONSTRUCTION OF SAMUDAYAK SOKHTA THAKUR BASTI PER | Completed | 10000 | 9792 | 2022-12-02 | 2023-02-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034669785 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMKARN KE GHAR KE PASS DIVIYAPURA | Closed | 10000 | 0 | 2022-08-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034669786 — CONSTRUCTION OF SAMUDAYAK SOKHTA BHEEKAM SINGH KE GHAR KE PASS BEHAD KI JAMEH | Completed | 10000 | 9792 | 2022-12-02 | 2023-02-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034669787 — CONSTRUCTION OF SAMUDAYAK SOKHTA SHALA BHAVAN KE PASS DIVIYAPURA | Closed | 10000 | 0 | 2022-08-17
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034678634 — CONSTRUCTION OF SAMUDAYAK SOKHTA SUKHDHYAM KE DWAR PER | Completed | 10000 | 9792 | 2022-12-09 | 2023-02-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034678789 — CONSTRUCTION OF SAMUDAYAK SOKHTA THAKUR BASTI PER | Closed | 10000 | 0 | 2022-11-25
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034678790 — CONSTRUCTION OF SAMUDAYAK SOKHTA BHEEKAM SINGH KE GHAR KE PASS | Closed | 10000 | 0 | 2022-11-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034678791 — CONSTRUCTION OF SAMUDAYAK SOKHTA SURESH SINGH KE GHAR KE PASS | Completed | 10000 | 9792 | 2022-12-16 | 2023-02-04
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002057/RS/22012034678793 — CONSTRUCTION OF SAMUDAYAK SOKHTA BADELALA KE DWAR PER BEHAD KI JAMEH | Completed | 10000 | 8160 | 2022-12-07 | 2023-02-04
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002057/WC/22012034330228 — TALAV JIVARMAN BEHED KEE JAMEH | Completed | 97000 | 97008 | 2017-06-21 | 2017-09-25
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002057/WC/22012034330229 — TALAV JIVARAN DUGAR PURA | Completed | 98000 | 97008 | 2017-06-21 | 2017-09-25
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002057/WC/22012034440821 — talab nirman(dug pond) sarve no 600 | Completed | 632000 | 382476 | 2019-03-04 | 2022-11-04
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002057/WC/22012034440924 — NAVEEN TALAB (DUG POND) SARVE NO 41,42BIHADKI JAMEH | Completed | 632000 | 393930 | 2019-03-04 | 2022-11-04
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702002057/WC/22012034897643 — TALAB JIRDODHAR KARYA POKHAR WALA TAL DUNGARPURA | Closed | 0 | 0 | 2021-10-02
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702002057/WC/22012034897648 — TALAB JIRDODHAR MATA KA MANDIR KE PASS DUNGARPURA | Closed | 0 | 0 | 2021-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1702002057/WC/22012034985929 — TALAB JIRDODDHAR KARYA POKHAR WALA TALAB | Completed | 42500 | 31824 | 2022-09-15 | 2023-02-04
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002057/WC/22012034985935 — TALAB JIRDODDHAR KARYA MATA MANDIR KE PASS WALA TALAB | Closed | 42500 | 0 | 2022-04-15
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002057/WC/22012035009894 — NAVEEN TALAB NIRMAN SHALA BHAVAN MATA MANDIR KE PASS | Closed | 599000 | 0 | 2022-04-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002057/WC/22012035009900 — CHECK DAM NIRMAN BHEEKAM SINGH KE KHET KE PASS | Closed | 437000 | 0 | 2022-04-01
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002057/WC/22012035034196 — NAVEEN TALAB NIRMAN SHANTIDHAM KE BAGAL ME PHULE KA PURA | Closed | 0 | 0 | 2022-12-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002057/WC/22012035034197 — NAVEEN TALAB NIRMAN PHULE KA PURA | Closed | 0 | 0 | 2022-12-14
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002057/WC/22012035034550 — AMRIT SAROVAR DAG POND NIRMAN SHANTI DHAM KE PASS | Ongoing | 1485556.35 | 176136 | 2023-02-18
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002057/WC/22012035034560 — AMRIT SAROVAR DAG POND NIRMAN PHULE PURA GAO KE PASS | Closed | 0 | 0 | 2022-12-14