## Work List
Exported on: 2026-10-26 14:53:58
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BHATMASPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702002059/DP/22012034595707 — vasudha vatika panchayat bhavan ke pass braksharopan amrat vatika | Closed | 55847.4 | 0 | 2023-04-14
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702002059/FP/22012034365974 — KACHHA NALA NIRMAN MATA MANDIR SE NARIYA KI OR | Ongoing | 508475.28 | 72046 | 2021-03-22
BHIND / BHIND | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702002059/IC/22012034882768 — BAMBA GAHRIKARAN AND NIRMAN SALINGPURA SE BIJPURI KI OR | Closed | 400170.24 | 0 | 2023-04-14
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034302507 — NADEP TANKA RAMVETI W/O RAJVEER | Deleted | 11800 | 0 | 2016-11-04
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034302509 — NADEP TANKA MAIDAN SINGH S/O PRAN SINGH | Completed | 11800 | 11175 | 2016-11-04 | 2017-04-10
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034302511 — NADEP TANKA RAMSIYA S/O KAPTAN SINGH | Completed | 11800 | 11175 | 2016-11-04 | 2017-04-10
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034302974 — NADEP TANKA SHASHIKANT YADAV S/O RAMPRAKASH YADAV | Completed | 11800 | 11175 | 2016-11-08 | 2017-04-10
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034308236 — NADEP TANKA MOHAR SINGH S/O SHANKAR SINGH | Completed | 11800 | 11172.51 | 2016-12-23 | 2017-11-15
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034309519 — NADEP TANKA RAMJILAL S/O LAYAK SINGH | Deleted | 11800 | 0 | 2016-12-30
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034309520 — NADEP TANKA BHARAT SINGH S/O THAN SINGH | Completed | 11800 | 11005.51 | 2016-12-30 | 2017-11-15
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034311046 — NADEP TANKA SUBEDAR S/O JAGANNATH | Completed | 11800 | 11172.51 | 2017-01-06 | 2017-11-15
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702002059/IF/22012034318432 — NADEP TANKA RAMSEVAK S/O KAPTAN SINGH | Completed | 11800 | 11005.51 | 2017-02-03 | 2017-11-15
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702002059/IF/22012034352749 — BRAKSHA ROPAN KARYA MIDIL SCHOOL OR MATA MANDIR PER | Completed | 335000 | 31300 | 2018-01-21 | 2018-05-15
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002059/IF/22012034353958 — BRAKSHA ROPAN KARYA PS SCHOOL OR TALAB SALINGPURA | Deleted | 0 | 0 | 2017-06-02
BHIND / BHIND | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702002059/IF/22012034353967 — BRAKSHA ROPAN KARYA PS SCHOOL OR HANUMAN JI KE MANDIR PER BHATMASPURA | Deleted | 0 | 0 | 2017-06-02
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002059/IF/22012034760553 — med bandan karya banbaei / ramprakash | Completed | 36351.36 | 10422 | 2021-06-17 | 2021-10-07
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002059/IF/22012034760557 — med banban charan singh bhatmaspura | Completed | 36351.36 | 20844 | 2021-06-17 | 2021-07-11
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002059/IF/22012034760559 — med bandan ramjeelal bhatmaspura | Completed | 34897.31 | 10422 | 2021-06-10 | 2021-09-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002059/IF/22012034760563 — med bandan tilak singh bhatmaspura | Completed | 34897.31 | 10422 | 2021-06-10 | 2021-09-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002059/IF/22012034786552 — med bandan kary ramprakash singh bhatmaspura | Completed | 30681.29 | 10422 | 2021-06-24 | 2021-07-11
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1702002059/IF/22012034786556 — med bandan sumer singh bhatmaspura | Completed | 30681.29 | 10422 | 2021-06-24 | 2022-08-23
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702002059/IF/22012034786559 — med bandan dharmendra singh bhatmaspura | Closed | 30681.29 | 0 | 2021-04-14
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702002059/IF/22012035509410 — KHET TALAB NIRMAN DILEEP SINGH / RAGHUVEER SINGH KE KHET PER | Ongoing | 450885.64 | 261 | 2025-06-03
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1702002059/IF/22012035638328 — Pm awas raju kushawaha | Approved | 0 | 0 | 2025-08-15
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993672654 — Suresh S/o Malkhan singh ka cattle shed | Completed | 115900 | 107762.48 | 2015-09-04 | 2016-01-21
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993672655 — Abdhesh S/o Gulab Singh ka cattle shed | Completed | 115900 | 108080.48 | 2015-08-26 | 2017-03-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993672881 — Durveen Singh S/o Foran singh ka cattle shed | Completed | 115900 | 109034.48 | 2015-09-04 | 2017-03-18
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674356 — Dinesh/Rajveer Singh ka cattle shed | Completed | 115900 | 107444.48 | 2015-09-11 | 2016-01-21
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674365 — Karan Singh S/o Harigovind ka cattle shed | Completed | 115900 | 108875.48 | 2015-09-11 | 2016-01-21
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674368 — Ramnarayan S/o Shriram ka cattle shed | Completed | 115900 | 109511.48 | 2015-09-11 | 2016-01-21
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674370 — Khalak Singh S/o Gambheer Singh ka cattle shed | Completed | 115900 | 112850.48 | 2015-09-11 | 2016-01-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674371 — Ravindra Singh S/o Gambheer Singh ka cattle shed | Completed | 115900 | 109958.48 | 2015-09-11 | 2016-08-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674373 — Girand S/o Rameshwar ka cattle shed | Deleted | 115900 | 0 | 2015-09-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993674375 — Sobran Singh S/o Pahlwan ka cattle shed | Completed | 115900 | 93834.48 | 2015-12-04 | 2017-03-11
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993695057 — CATTLE SHED SUGHAR SINGH S/O KALYAN SINGH BHATMASPURA | Completed | 115900 | 111389.48 | 2015-12-11 | 2016-10-03
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993695064 — CATTLE SHED RATAN SINGH S/O KALYAN SINGH BHATMASPURA | Completed | 115900 | 107762.48 | 2015-12-11 | 2016-10-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993695067 — CATTLE SHED RAMVILASH SINGH S/O KALYAN SINGH BHATMASPURA | Completed | 115900 | 107762.48 | 2015-12-11 | 2016-10-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993699858 — CATTLE SHED RAMKISHAN S/O ABBAL SINGH BHATMASPURA | Completed | 115900 | 110306.48 | 2015-12-23 | 2017-04-17
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993699868 — CATTLE SHED KAMLA W/O NARESH BHATMASPURA | Completed | 115900 | 111260.48 | 2015-12-25 | 2016-07-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993701650 — CATTLE SHED KAILASH SINGH S/O CHHOTELAL BHATMASPURA | Completed | 115900 | 108389.48 | 2016-01-15 | 2016-10-17
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993701683 — CATTLE SHED TILAK SINGH S/O LAYAK SINGH BHATMASPURA | Completed | 115900 | 109418.48 | 2016-01-01 | 2016-07-04
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993704877 — CATTLE SHED MUNNESH S/O VIDHYARAM SHAKYA BHATMASPURA | Completed | 115900 | 108435.48 | 2016-01-15 | 2016-10-17
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993704883 — CATTLE SHED GOPSHRI W/O MUNNI LAL YADAV BHATMASPURA | Completed | 115900 | 110391.48 | 2016-01-15 | 2016-10-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993708089 — CATTLE SHED SHYAMSUNDER / UDAY SINGH BHATMASPURA | Completed | 115900 | 108920.48 | 2016-01-29 | 2016-10-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993708091 — CATTLE SHED KAPTAN SINGH / AMAR SINGH BHATMASPURA | Completed | 115900 | 110558.48 | 2016-01-29 | 2016-10-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993708384 — CATTLE SHED UDAY SINGH S/0 MATAPRASAD SALINGPURA | Completed | 115900 | 107732.48 | 2016-01-29 | 2016-10-27
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993721566 — Cattle shed kalyan Singh s/o lakhan singh | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993722182 — CATTLE SHED RAMSEWAK S/O KAPTAN SINGH BHATMASPURA | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993722185 — Cattle shed pooran s/o pransingh | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993722191 — MAHESH S/0 POORAN SINGH BHATMASPURA | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993725101 — CATTLE SHED SUDAMA LAL S/0 ATAR SINGH BHATMASPURA | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993725107 — CATTELE SHED RAMVEER S/0 AMAR SINGH BHATMASPURA | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993725112 — CATTLE SHED JITENDRA S/0 SUBEDAR SINGH BHATMASPURA | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702002059/IF/9993725113 — CATTLE SHED NANDKISHOR S/0 RADHAMOHAN BHATMASPURA | Deleted | 115900 | 0 | 2015-04-14
BHIND / BHIND | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002059/IF/IAY/1871301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4503336 | Completed | 15660 | 15312 | 2018-08-09 | 2018-11-15
BHIND / BHIND | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002059/IF/IAY/3788494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100678325 | Physically Completed | 18360 | 15624 | 2022-10-05 | 2024-11-21
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002059/IF/IAY/5615462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114981222 | Physically Completed | 23490 | 19575 | 2025-05-31 | 2026-02-28
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002059/IF/IAY/5615473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100688813 | Physically Completed | 23490 | 19836 | 2025-05-22 | 2026-03-15
BHIND / BHIND | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702002059/IF/IAY/5868160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121962049 | Ongoing | 23490 | 0 | 2025-12-23
BHIND / BHIND | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002059/LD/22012034266116 — MED BANDHAN | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002059/LD/22012034316487 — SHANTI DHAM BHATMASPURA | Deleted | 180000 | 0 | 2017-04-14
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702002059/LD/22012034506559 — med bandhan ramjilal ke khet par | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702002059/LD/22012034506560 — med bandhan dharmendra ke khet par bhatmaspura | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1702002059/LD/22012034506707 — med bandan ramprkash ke khet par bhatmaspura | Deleted | 0 | 0 | 2020-01-26
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702002059/LD/22012034551021 — med bandan deelip singh / raghuveer singh bhatmaspura | Completed | 32215.35 | 20844 | 2021-05-19 | 2021-09-15
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002059/LD/22012034551023 — samtalikaran deelip singh ke khet par | Deleted | 0 | 0 | 2021-04-15
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Pebble graded Bund for Community / Repair and Maintenance of Pebble graded Bund for Community | Repair & Maint of Bund | 1702002059/LD/22012034551026 — talab maramati karan shaling pura | Deleted | 0 | 0 | 2021-04-15
BHIND / BHIND | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002059/LD/320 — मेड बन्‍धान कार्य बेदरी / बिशाल भटमासपुरा | Completed | 18300 | 4514 | 2011-12-23 | 2011-12-29
BHIND / BHIND | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002059/LD/80 — मेड बन्‍धान कार्य बद्रीप्रसाद / नन्‍दराम जाटव | Completed | 0 | 5000 | 2010-07-22 | 2010-07-22
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702002059/OP/9425892875 — SHANTIDHAM SALINGPURA | Completed | 180000 | 179150.66 | 2017-05-11 | 2018-02-25
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002059/OP/9425893002 — PANCHAYAT BHAVAN NIRMAN BHATMASPURA | Deleted | 514000 | 0 | 2016-04-03
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702002059/OP/9425893072 — SHANTIDHAM BHATMASPURA | Completed | 180000 | 177946.15 | 2017-05-19 | 2018-02-25
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702002059/PG/22012034365776 — PLAY GROUND | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702002059/PG/9425895958 — KHEL MAIDAN MIDIL SCHOOL KE PASS BHATMASPURA | Completed | 320000 | 182888.4 | 2017-03-24 | 2019-09-15
BHIND / BHIND | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/18 — सी0सी0 रोड मैन रोड से दिलीप सिंह के मकान तक | Completed | 165492 | 127414.87 | 2012-03-25 | 2013-07-04
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034158818 — c.c.road mahaveer singh ke makan se layak singh ke | Completed | 82800 | 73260 | 2014-01-03 | 2014-08-20
BHIND / BHIND | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034208220 — C.C.ROAD UJAGAR SINGH KE MAKAN SE PRIMARY SHALA BH | Completed | 126000 | 117816 | 2014-02-28 | 2015-07-29
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034283399 — CC ROAD SCHOOL SE LEKAR MATA KE MANDIR | Completed | 126732 | 94629 | 2015-08-21 | 2015-12-03
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702002059/RC/22012034297209 — SWAMI JI KE MANDIR SE RAKESH KE KHET TAK PAHUCH MARG BHAMASPURA | Completed | 1377270 | 274752 | 2016-01-22 | 2016-04-20
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034299132 — c.c. road ramnarayan me makan we chhoti bai me maanki or | Completed | 112621 | 25758 | 2016-02-19 | 2016-04-15
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034306320 — C.C. ROAD PRIMARY SCHOOL SE SHANKAR JI KE MANDIR TAK BTMASPURAH | Deleted | 0 | 0 | 2016-01-26
BHIND / BHIND | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034310776 — C.C. ROAD PRIMARY SCHOOL SHANKAR JI KE MANDIR TAK | Deleted | 112621 | 0 | 2015-04-14
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002059/RC/22012034328225 — CC ROAD PAPPU JAMADAR KE MAKAN SE SCHOOL OR MANDIR TAK | Completed | 88500 | 75366 | 2017-02-24 | 2018-10-25
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002059/RC/22012034362894 — CC ROAD MAIN ROAD SE DEVI DAYAL KUSHWAH KE MAKAN TAK | Completed | 33200 | 30444 | 2017-10-06 | 2018-02-15
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002059/RC/22012034366075 — CC ROAD GOVT PRIMARI SCHOOL SE BHARAT SINGH KE MAKAN TAK | Completed | 44300 | 43188 | 2017-11-03 | 2019-02-09
BHIND / BHIND | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034381092 — CC ROAD MAIN ROAD SE GIRAND KE MAKAN TAK | Deleted | 28000 | 0 | 2017-02-20
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034381813 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034389216 — सी सी रोड मेन रोड से करन सिंह के मकान तक सालिंग पुरा | Closed | 11000 | 0 | 2020-05-19
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034393733 — सी सी रोड दुर्वीन के मकान से रामजीलाल के मकान तक भटमास पुरा | Completed | 23000 | 19836 | 2018-12-31 | 2019-02-09
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034393734 — सी सी रोड मेन रोड से राकेश के मकान तक भटमास पुरा | Completed | 47000 | 43848 | 2018-12-10 | 2019-02-09
BHIND / BHIND | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034442693 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034476769 — c c rod mata ke mandir se lalman baba tak bhatmaspura | Closed | 69750 | 0 | 2019-04-26
BHIND / BHIND | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002059/RC/22012034518497 — SUDOOR SADAK DINESH KE MAKAN SE SHANTIDHAM TAK BHATMASPURA | Completed | 1010565.01 | 907155.5 | 2020-03-19 | 2021-09-30
BHIND / BHIND | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702002059/RC/22012034534431 — sudur sadak mata mandir se nariya tak | Ongoing | 1147699.91 | 1001541.56 | 2021-02-04
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702002059/RC/22012034570198 — cc rods dharmendra ke makan de md school ki or | Completed | 76500 | 39780 | 2023-07-31 | 2025-07-01
BHIND / BHIND | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034578058 — cc rods panchayat bhavan se mukti dham kee or | Closed | 69000 | 0 | 2021-04-14
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702002059/RC/22012034614671 — CC ROAD NIRMAN MAIN ROAD SE MAIDAN SINGH KE MAKAN KI OR | Completed | 81000 | 56304 | 2022-11-11 | 2022-12-16
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002059/RS/22012034669755 — CONSTRUCTION OF SAMUDAYAK SOKHTA MANOJ KE HENDPUMP KE PASS | Completed | 10000 | 9792 | 2022-10-12 | 2025-05-11
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002059/RS/22012034669758 — CONSTRUCTION OF SAMUDAYAK SOKHTA SUDAMA KE HANDPUMP KE PASS | Completed | 10000 | 9792 | 2022-11-11 | 2022-11-19
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702002059/RS/22012034669759 — CONSTRUCTION OF SAMUDAYAK SOKHTA RAMVILAS KE HENDPUMP KE PASS | Completed | 10000 | 8568 | 2022-11-02 | 2022-11-10
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002059/RS/22012034677542 — CONSTRUCTION OF SAMUDAYAK NADEP MANOJ KE GHAR KI PASS | Closed | 2000 | 0 | 2023-09-22
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002059/RS/22012034677548 — CONSTRUCTION OF SAMUDAYAK NADEP SUDAMA KE GHAR KE PASS | Closed | 2000 | 0 | 2023-09-22
BHIND / BHIND | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002059/RS/22012034678949 — CONSTRUCTION OF SAMUDAYAK NADEP RAKESH KE GHAR KE PASS | Closed | 0 | 0 | 2022-08-15
BHIND / BHIND | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702002059/RS/22012034678950 — CONSTRUCTION OF SAMUDAYAK NADEP RAKESH KE GHAR KE PASS | Closed | 2000 | 0 | 2023-09-29
BHIND / BHIND | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702002059/SK/9993649392 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BHATMASPURA | Completed | 514000 | 507876 | 2017-10-06 | 2019-04-12
BHIND / BHIND | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702002059/WC/19 — सोख्‍ता गडडा अमर सिंह के मकान के सामने हैण्‍डपम्‍प पर | Completed | 14263 | 14263 | 2009-07-02 | 2009-07-02
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002059/WC/22012034328994 — TALAB MARAMMAT KARYA SCHOOL KE PASS | Completed | 30000 | 23564 | 2017-06-09 | 2017-07-07
BHIND / BHIND | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002059/WC/22012034328996 — TALAB MARAMMAT NIRMAN SCHOOL KE PASS SALINGPURA | Completed | 97000 | 72756 | 2017-06-09 | 2017-07-20
BHIND / BHIND | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702002059/WC/22012034429892 — पंचायत भवन के पास तालाव निर्माण कार्य भटमास पुरा | Completed | 367000 | 220632 | 2019-01-14 | 2021-09-30
BHIND / BHIND | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Earthen Gully Plugs for Comm / Repair and maintenance of Earthen Gully Plugs for Community | Repair & maint of Water Harvesting Structures | 1702002059/WC/22012034675079 — talab maramati karan bhatmaspura | Closed | 344084.2 | 0 | 2021-04-15
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Pebble peripheral Bund for Community / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1702002059/WC/22012035032174 — TALAB SOUNDARIKARAN / GAHRIKARAN NIRMAN PANCHAYAT BHAVAN KE PASS | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002059/WC/22012035032176 — TALAB SUNDARIKARAN / GAHRIKARAN GOVT SCHOOL KE PASS SALINGPURA | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702002059/WC/22012035032177 — TALAB SUNDARIKARAN / GAHRIKARAN GOVT SCHOOL KE PASS SALINGPURA | Closed | 0 | 0 | 2022-10-02
BHIND / BHIND | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702002059/WC/9993672684 — TALAB | Deleted | 99000 | 0 | 2016-05-20