## Work List
Exported on: 2026-10-11 11:12:44
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: PAROSA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003003/AV/2479 — Aanganbadi Bhavan Nirman Sewa Kendra,PAROSA | Completed | 330000 | 321413 | 2014-10-10 | 2016-01-09
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003003/AV/4017 — Aanganbadi/Other Rural Infrastructure,PAROSA | Completed | 330000 | 316991 | 2015-11-25 | 2016-05-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/DP/22012034239732 — Brachya Ropan Karya Parosa | Completed | 335000 | 3096 | 2017-05-08 | 2021-12-05
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003003/IF/22012034352854 — Brachya Ropan Karya Schkool Or Shanti Dham Per Ravat Pura | Completed | 335000 | 27864 | 2017-09-09 | 2021-12-05
BHIND / MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003003/IF/22012034743008 — medbandhan barsha katare | Completed | 17347.34 | 15054 | 2021-05-28 | 2021-07-05
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Gully Plugs for Individual / Construction of Earthen Gully Plugs for Individuals | Boulder Check/Gully Plug | 1702003003/IF/22012034743042 — medbandhan shishupal singh | Completed | 43759.53 | 44004 | 2021-06-04 | 2021-07-05
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652232 — pashu shed ramvivek sharma son of mavasi sharma | Completed | 89000 | 85824 | 2014-09-04 | 2015-01-03
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652401 — pashu shet ramvinod / mavasi | Completed | 89000 | 83783 | 2014-09-04 | 2015-02-04
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652414 — pashu shet ramadhar / mavasi | Completed | 89000 | 83626 | 2014-09-04 | 2015-01-04
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652417 — pashu shet mangal singh / lakhan singh | Completed | 89000 | 79544 | 2014-09-04 | 2016-04-20
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652421 — pashu shet girraj sharma / munnalal sharma | Completed | 89000 | 86452 | 2014-09-04 | 2015-01-03
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652437 — pashu shet satyanarayan / sevaram sharma | Completed | 89000 | 71537 | 2014-09-04 | 2015-01-03
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652441 — pashu shet maniram sharma / harishankar sharma | Completed | 89000 | 81052 | 2014-09-04 | 2016-04-11
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993652442 — pashu shet rambhog / ramroop | Completed | 89000 | 85039 | 2014-09-04 | 2015-01-03
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704617 — cattle shed manoj / sobran | Completed | 115900 | 108853 | 2016-01-29 | 2016-05-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704622 — cattle shed mathuri / matadin | Completed | 115900 | 113782 | 2016-01-29 | 2016-05-11
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704625 — cattle shed balram / ray bahadur | Completed | 115900 | 111397 | 2016-02-18 | 2016-05-11
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704630 — cattle shed ravindra / sarman singh | Completed | 115900 | 113782 | 2016-01-29 | 2016-05-13
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704631 — cattle shed rambaran / santoshi | Completed | 115900 | 111874 | 2016-01-29 | 2016-05-13
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704642 — cattle shed rushtam / ramlakhan | Completed | 115900 | 108694 | 2016-01-29 | 2016-05-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704653 — cattle shed rajveer/ prakash | Completed | 115900 | 112507 | 2016-03-19 | 2016-05-13
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704662 — cattle shed surendra / tilak singh | Completed | 115900 | 111715 | 2016-02-18 | 2016-05-11
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704669 — cattle shed sankar /ahivaran singh | Completed | 115900 | 110443 | 2016-02-18 | 2016-05-11
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704671 — cattle shed hawaldar / surjan singh | Completed | 115900 | 110443 | 2016-02-18 | 2016-05-11
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704673 — cattle shed ashok / vasudev | Completed | 116000 | 112680 | 2016-04-06 | 2017-01-18
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704694 — cattle shed devendra / sri krishna | Completed | 115000 | 113348 | 2016-05-10 | 2017-04-17
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003003/IF/9993704704 — cattle shed radhacharan / ratiram | Completed | 115900 | 112828 | 2016-02-18 | 2016-05-11
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/118352 — Construction of IAY House -IAY REG. NO. MP-02-003-003-001/14 | Completed | 14310 | 15248 | 2016-07-28 | 2018-08-15
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/378591 — Construction of IAY House -IAY REG. NO. MP1671143 | Completed | 15030 | 15188 | 2017-02-01 | 2017-11-16
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/422890 — Construction of IAY House -IAY REG. NO. MP1346715 | Completed | 15030 | 15168 | 2017-02-08 | 2018-08-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/478585 — Construction of IAY House -IAY REG. NO. MP1046399 | Completed | 15030 | 15180 | 2017-07-28 | 2018-09-21
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/544824 — Construction of IAY House -IAY REG. NO. MP3208223 | Completed | 15030 | 15294 | 2017-03-23 | 2018-07-30
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/546041 — Construction of IAY House -IAY REG. NO. MP3242947 | Completed | 15030 | 14970 | 2017-07-01 | 2018-08-05
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/546321 — Construction of IAY House -IAY REG. NO. MP3252955 | Completed | 15030 | 15306 | 2017-03-23 | 2018-08-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/546728 — Construction of IAY House -IAY REG. NO. MP3264315 | Completed | 15030 | 15174 | 2017-07-01 | 2018-08-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/587087 — Construction of IAY House -IAY REG. NO. MP3226074 | Completed | 15030 | 15136 | 2017-07-01 | 2017-09-07
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/751871 — Construction of IAY House -IAY REG. NO. MP2608371 | Completed | 15030 | 15174 | 2017-07-28 | 2018-08-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/916447 — Construction of IAY House -IAY REG. NO. MP2368497 | Completed | 15480 | 11868 | 2017-07-28 | 2018-10-25
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/987410 — Construction of IAY House -IAY REG. NO. MP2568825 | Completed | 15480 | 15204 | 2017-07-28 | 2018-08-23
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/987590 — Construction of IAY House -IAY REG. NO. MP3241789 | Completed | 15480 | 15164 | 2017-07-28 | 2018-08-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003003/IF/IAY/987591 — Construction of IAY House -IAY REG. NO. MP3241952 | Completed | 15480 | 15164 | 2017-07-28 | 2018-08-13
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003003/LD/796 — मेढबंधान राकेश / बच्‍चु मेंहतर | Completed | 20000 | 17568 | 2011-09-07 | 2012-10-01
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003003/LD/885 — खेल का मैदान निर्माण क्रीण्‍णंगन रावतपुरा | Completed | 0 | 19900 | 2012-02-15 | 2015-04-20
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003003/OP/9425892780 — Shanti Dham Nirman[ Ravat pura] Parosa | Completed | 180000 | 180268.99 | 2017-03-25 | 2017-10-25
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003003/PG/9425896267 — Khel Medan[ Ravat pura ] Parosha | Completed | 353000 | 332794 | 2017-03-25 | 2019-01-10
BHIND / MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/131 — पहुंचमार्ग मिटटी कार्य भिण्‍ड मुरैना रोड से अतरदास बाबा की खेरी तक | Completed | 185000 | 124440 | 2011-12-06 | 2011-12-30
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/150 — सीृसीृ रोड करसोलियन का पुरा परोसा | Completed | 0 | 166481 | 2012-04-02 | 2012-10-29
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034169146 — c c road lachman singh ke makan sekasadiya mohlla | Completed | 212600 | 211430 | 2013-06-05 | 2014-10-27
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034173262 — c c road nirman kary ramprakash shrma ke drwaje se | Completed | 145500 | 147386 | 2013-06-29 | 2013-10-31
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034191467 — cc road panchparmeshavar tejpura road se deendyal | Completed | 197500 | 217733 | 2014-03-04 | 2014-10-27
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034191471 — panchparmeshvar cc road rajkumar k makn s badai mo | Completed | 201500 | 203857 | 2014-03-04 | 2014-10-27
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034212263 — panchpar.ccroad nakul singh ke makan se hebran ke | Completed | 236600 | 235729 | 2014-03-05 | 2014-10-27
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034212275 — panchpar. cc road majara lavera ka pura | Completed | 236600 | 228743 | 2014-03-05 | 2014-10-27
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034212487 — panchpar cc road main road se kartar singh ke dwar | Completed | 207000 | 150991 | 2014-03-05 | 2014-10-27
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231058 — Khet sadak yojana Gandharv ke makan se nahar ki oo | Completed | 1456000 | 612509.7 | 2014-10-03 | 2016-10-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231059 — khet sadak yojana main road se nahar tak | Completed | 1344000 | 62643 | 2014-10-03 | 2016-08-08
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231695 — antarik gsb Shishupal ke makan se raghuveer ke makan ki oor | Completed | 709000 | 4710 | 2014-10-20 | 2014-12-15
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231696 — antrik gsb Angad valmik ke makan se chetram ke makan ki oor | Completed | 446000 | 4710 | 2014-10-20 | 2014-12-15
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034231697 — panch par, cc road Ajmer ke makan se dhaniram ke makan ki oor | Completed | 91400 | 87896 | 2014-10-20 | 2015-01-09
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034231698 — panch par c c raod nirmad Bhup singh ke makan se mahesh rathor ke makan ki oor | Completed | 78500 | 76176 | 2014-10-20 | 2015-01-09
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231699 — GSB road main road se atardas baba ke ashram ki oor | Completed | 1390000 | 956044.7 | 2014-10-21 | 2015-11-06
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231910 — Antrik Gsb panchayat bhavan se angad valmik ke ghar ki oor | Completed | 446000 | 7693 | 2014-10-20 | 2014-12-15
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003003/RC/22012034231911 — antrik gsb rawatpura se shishupal ke makan ki oor | Completed | 446000 | 4710 | 2014-10-20 | 2014-12-15
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034231912 — C C road nirmad kalka mandir se gambhir ke makan ki oor | Completed | 52700 | 54398 | 2014-10-20 | 2015-01-09
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034285804 — c c road panchayat bhavan tirahe se shivcharan singh k mkan ki or | Completed | 230000 | 216973 | 2015-10-22 | 2016-05-11
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034325331 — C C Road Ramveer Ke Darbaje Se Thakur Baba Mandir Kee Or | Completed | 159200 | 155811 | 2017-02-08 | 2017-05-30
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034325332 — C C Road Hari Singh Ke Darbaje Se Angad Balmik Ke Makan Kee Or | Completed | 420000 | 396460 | 2017-02-04 | 2017-05-30
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034333207 — C C Road Munna Kushwah Ke Makan Mathuri Kushwah Ke Makan kee or | Completed | 110250 | 95448 | 2017-03-25 | 2017-05-30
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034334122 — C C Road Panchyat Bhavan Se Kamlesh Balmik Ke Makan Kee Or | Completed | 265000 | 243140 | 2017-04-02 | 2017-05-30
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034336904 — C C Road Main Road Se Middle Sckool Tak | Completed | 29500 | 28944 | 2017-05-03 | 2017-05-30
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034347910 — C C Road Raghunandan Ke Makan Se Naresh Ke Makan Tak | Completed | 160000 | 2064 | 2017-08-01 | 2017-08-19
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034372983 — C C Road Chetram Ke Pura Se Angad Balmik Ke Makan Ke Or | Completed | 320000 | 217548 | 2019-01-04 | 2021-12-05
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034396192 — C C Road Ulaphat Singh Ke Makan Se Prabhoonath Ke Makan Kee Or | Completed | 320000 | 75696 | 2019-01-27 | 2021-12-05
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034434273 — C C Road Chetram Ke Pura Se Lakhan Singh Ke Pura Ke Or | Completed | 282000 | 154467 | 2019-01-04 | 2021-12-05
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034514503 — Cc Road Shishupal Ke Makan Se Gaon Ki Oor | Completed | 93000 | 88730 | 2020-04-22 | 2020-06-09
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003003/RC/22012034516216 — Cc Road Lal Singh Ke Makan Se Rajbahadur Ke Makan Ki Oor | Completed | 93000 | 89642 | 2020-02-03 | 2021-01-01
BHIND / MEHGAON | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/65 — पहुचमार्ग परोसा रावतपुरा से शंरपुरा होते हुये परोसा बम्‍बा तक | Completed | 0 | 113280 | 2010-10-03 | 2011-01-03
BHIND / MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003003/RC/96 — पहुचमार्ग परोसा रावतपुरा से भिण्‍ड , मुरैना रोड तक | Completed | 398803 | 291336 | 2011-04-10 | 2011-10-17
BHIND / MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003003/WC/22012034324240 — Talab Nirman Karya Mata Mandir Ke Pass Parosa | Completed | 869000 | 551361 | 2017-05-12 | 2018-04-04
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003003/WC/22012034665651 — DUG TANK NIRMAN KARYA SHANTIDHAM | Completed | 1414219.95 | 1209306.17 | 2021-05-12 | 2022-03-03