## Work List
Exported on: 2026-10-23 22:42:08
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: MANPURA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1702003013/FP/22012034202730 — nali nirman manpura puliya se nahar tak | Completed | 1498000 | 431726.44 | 2015-08-27 | 2016-01-30
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034363374 — कच्चा नाला manpura से sondha की ओर | Completed | 726269.88 | 661920 | 2019-11-15 | 2022-10-31
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003013/FP/22012034366238 — Kachha nala nirman murari ke kua se lawan ke ot | Completed | 834763.3 | 765320 | 2020-07-24 | 2021-04-05
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034366239 — Pakka nala nirman mayaram ke dwar se puliya ta | Completed | 951250.99 | 898083 | 2020-07-20 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034624689 — Kool nirman karya Bamba se Rakesh ke khet tak | Completed | 494368.56 | 420354 | 2021-05-10 | 2023-04-20
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034624772 — nala nirman karya manpura se lawan pul ki or | Completed | 744889.1 | 625127 | 2021-05-24 | 2025-06-29
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034625515 — kachcha nala manpura pul se sondha kool tak | Completed | 1486101.73 | 1236744 | 2021-10-17 | 2022-10-31
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629037 — kool nirmad bamba se kainth ka pura nirpal singh k khet tk | Completed | 437557.4 | 178704 | 2022-05-25 | 2025-06-29
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629040 — kool nirmad bamba se rajpal k khet tk | Completed | 437557.4 | 194616 | 2022-05-25 | 2025-06-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629201 — kachha nala nirman kheriya puliya se gajendra singh k khet tk | Completed | 979027.92 | 407929 | 2023-09-25 | 2025-06-29
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629834 — kool nirmad nahar se banke membar k khet tk | Completed | 448569.2 | 376992 | 2022-09-28 | 2023-04-20
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034630352 — constr of flood/diversion channel for community nahar sidh baba se nale tk | Completed | 666403.36 | 555373 | 2023-05-02 | 2025-06-29
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034630353 — constr of flood/diversion channel for community nahar bhumiya baba mandir se chandrapura tk | Completed | 623235 | 484704 | 2022-11-28 | 2023-05-14
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631088 — flood diversion chanel munna k khet se bhagirath k khet ki ore | Completed | 473021.95 | 246636 | 2024-02-13 | 2025-06-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631092 — flood diversion chanel naher se munna k khet avm rajendra k khet ki ore | Completed | 441335.74 | 370107 | 2023-07-05 | 2025-06-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631093 — flood diversion chanel bamba se shishupal k khet ki ore | Completed | 481236.85 | 305201 | 2023-08-25 | 2025-06-29
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1702003013/IC/22012034387939 — Bamba se lekar kapata Singh ke khet tak | Completed | 476693.22 | 417378 | 2021-03-13 | 2021-06-24
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003013/IF/22012034352776 — vrachchha ropan kary shanti dham manpura | Completed | 335000 | 24224 | 2017-08-17 | 2021-12-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003013/IF/22012034353043 — vrachchha ropan kary panchayat bhavan k pass manpura | Completed | 335000 | 22160 | 2017-07-29 | 2021-12-13
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/118362 — Construction of IAY House -IAY REG. NO. MP-02-003-013-001/539 | Completed | 14310 | 14028 | 2017-01-06 | 2017-02-28
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/118363 — Construction of IAY House -IAY REG. NO. MP-02-003-013-001/559 | Completed | 14310 | 15408 | 2016-07-29 | 2018-11-10
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/118364 — Construction of IAY House -IAY REG. NO. MP-02-003-013-002/41 | Completed | 14310 | 14028 | 2016-07-29 | 2016-12-29
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/2347508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3694734 | Completed | 17100 | 16032 | 2020-10-07 | 2022-10-30
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/2347540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3149006 | Completed | 17100 | 17100 | 2020-10-07 | 2021-04-10
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/2347541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3128633 | Completed | 17100 | 16068 | 2020-10-07 | 2021-12-13
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/3953497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145871945 | Completed | 18360 | 18343 | 2023-05-22 | 2023-08-16
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/3960943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148343189 | Completed | 18360 | 17527 | 2023-01-11 | 2023-08-23
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/4361961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148357640 | Completed | 18360 | 15708 | 2023-01-11 | 2023-04-20
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/542368 — Construction of IAY House -IAY REG. NO. MP3133287 | Completed | 15030 | 14996 | 2017-03-01 | 2018-04-11
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/542728 — Construction of IAY House -IAY REG. NO. MP3145887 | Completed | 15030 | 14996 | 2017-03-01 | 2018-04-06
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/558047 — Construction of IAY House -IAY REG. NO. MP3592605 | Completed | 15030 | 15136 | 2017-03-01 | 2018-04-06
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/560850 — Construction of IAY House -IAY REG. NO. MP3693205 | Completed | 15030 | 15480 | 2017-03-01 | 2018-06-15
BHIND / MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/122 — मेंड बंधान निर्माण रामप्रकाश /ववलूप्रसाद | Completed | 32000 | 29666 | 2009-06-15 | 2009-06-15
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552924 — medvandhan karya nathu singh s/o hukam singh ke khet par | Completed | 40033.59 | 27792 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552927 — medbadhan karya baijnath singh s/o malikhan singh ke khet par | Completed | 33800.04 | 24318 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552928 — Medvandhan kary Virendra Singh s/0 hukam singh ke khet par | Completed | 44226.09 | 32424 | 2021-11-18 | 2022-02-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552929 — medbandan karya bacchu singh s/o hukam singh ke khet par | Completed | 39082.48 | 25476 | 2021-11-18 | 2022-02-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552932 — medbadhan karya ramotarsingh s/o hukam singh ke khet par | Completed | 47466.15 | 31266 | 2021-11-18 | 2022-02-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552936 — Medhvandan kary Radheshyam s/0 hukam singh ke khet par | Completed | 50706.2 | 32424 | 2021-10-14 | 2021-10-27
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552937 — medbandhan karya jogendra singh s/o jitawar singh ke khet par | Completed | 44226.09 | 33582 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552950 — medvandhan karya vidhya bai w/0 vaijnath singh ke khet par | Completed | 48546.16 | 39372 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/325 — मेड बन्‍धान कार्य मोहर सिंह / प्रभूदयाल | Completed | 0 | 6900 | 2010-06-01 | 2010-06-01
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/326 — मेड बन्‍धान कार्य रामस्‍वरूप / घमण्‍डी जाटव | Completed | 0 | 9000 | 2010-09-10 | 2010-09-10
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702003013/OP/9425890800 — Shanti dhham nirman karya manpura | Completed | 1499000 | 1383049 | 2016-11-22 | 2018-07-31
BHIND / MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003013/RC/117 — पहुंचमार्ग मिटटी कार्य चन्‍द्रपुरा से लावन की ओर | Completed | 494000 | 208376 | 2011-06-17 | 2011-12-26
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034176203 — c c road radeshyam ke darwaje se road tak | Completed | 207600 | 198764 | 2013-07-24 | 2013-12-18
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034189320 — c c road sahab ke darwaje se makhan ke darwaje tak | Completed | 65270 | 58066 | 2013-10-02 | 2013-11-29
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034212121 — panchpar.ccroad mata ke mandir se ramdeen jatav ke | Completed | 218002 | 208602 | 2014-03-05 | 2014-05-28
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034212125 — panchpar.ccroad munesh ke dwar se cc road tak | Completed | 65270 | 49035 | 2014-03-05 | 2014-05-27
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034223398 — c.c. raod kuaa se pra. vidhayalay ki or | Completed | 277850 | 193140.5 | 2014-07-28 | 2015-07-20
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034223399 — सी सी रोड प्रेम सिंह जाटव के द्रार से स्कूल की ओ | Completed | 250063 | 151179 | 2014-08-21 | 2014-09-02
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034295360 — cc rod nirmad mandir se sahab singh wali gali hote hue pooran k dwar ki or | Completed | 301000 | 298693 | 2016-01-07 | 2016-03-22
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034312596 — cc rod nirman pooran k ghar se munshi k ghar ki or | Completed | 254800 | 253899 | 2016-05-11 | 2016-07-28
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034312745 — Cc rod atar Singh k dwar se nahar ki or | Completed | 301016 | 299578.8 | 2016-07-26 | 2017-10-02
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034317927 — cc rod nirman kary laturi jadon k dwar se mukhy marg tk | Completed | 117000 | 116606 | 2017-01-20 | 2018-07-18
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034340831 — sudhur sampark sadak manpura men rod se keth ka pura tk | Completed | 2053000 | 1995330.94 | 2017-06-10 | 2020-07-28
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034353472 — c c road nirman Puliya se Kamlesh sharma ke makan tak. Manpura | Completed | 233000 | 231632 | 2017-09-12 | 2017-10-15
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034364833 — c c road nirman MAY NALI PAN SINGH KE DWAR SE BAIJNATH KE DWAR TAK . PADOLIYAN KA PURA | Completed | 79650 | 79464 | 2017-10-25 | 2018-02-05
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034397775 — c c road nirna Lakhan ke dwar se Kharanaj tak | Completed | 61950 | 61596 | 2018-11-30 | 2019-01-10
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034468992 — c c road nirman pooran baretha ke bagal se santosh dhanuk ke dwar tak | Completed | 42375 | 34672 | 2019-10-01 | 2021-04-10
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034527583 — Sudar samparak sadak mandir se Dinesh jadon ke khet tak | Completed | 2038261.62 | 2055959.83 | 2020-09-11 | 2022-10-28
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034586990 — cc road pooran baretha k ghar se panchayat bhawan ki ore | Completed | 127500 | 111168 | 2021-10-14 | 2021-12-13
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/233 — सीसी रोड निर्माण् महादेव मन्दिर से स्‍कूल तक पंचपरमेश्‍वर मद | Completed | 193558 | 174064 | 2012-07-01 | 2012-12-18
BHIND / MEHGAON | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003013/RC/45 — पहुच मार्ग निर्माण | Completed | 164000 | 81738 | 2008-05-26 | 2009-12-25
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702003013/RS/22012034585056 — samudayik swachchta parisar manpura | Completed | 43000 | 42846 | 2021-10-14 | 2023-05-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003013/WC/22012034893413 — Talab jeerdoddhar karya piparavali mata mandir k paas | Completed | 48046.16 | 39372 | 2022-03-09 | 2023-04-20
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935184 — talab jirdodhhar bamba k pas | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935187 — talab jirdodhhar megh singh k khet k pass | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935190 — talab jirdodhhar naresh k khet kpass | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935191 — talab jirdodhhar puliya k pass | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09