## Work List
Exported on: 2026-09-09 13:48:42
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: MANPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034467145 — shanti dham keth ka pura | Deleted | 0 | 0 | 2019-04-14
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1702003013/AV/22012034467873 — Shanti dham chandpura | Deleted | 0 | 0 | 2019-08-07
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702003013/AV/22012034564612 — panchayat bhawan ki boundary wall | Closed | 0 | 0 | 2021-04-01
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034567095 — shantidham nirman karya kaith ka pura | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034567097 — shantidham nirman karya chandrapura | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702003013/AV/22012034604276 — boundryball panchayat bhawan | Closed | 0 | 0 | 2021-10-02
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702003013/AV/22012034604277 — boundryball shaskiya prathmik shala manpura | Closed | 0 | 0 | 2021-10-02
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003013/AV/22012034609592 — boundryball nirmar panchayat bhawann parisar | Ongoing | 1155000 | 62724 | 2022-02-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003013/AV/22012034615804 — maa ki bagiya ps chandrapura | Closed | 0 | 0 | 2022-01-27
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003013/AV/22012034615805 — maa ki bagiya ps manpura | Closed | 0 | 0 | 2022-01-27
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034620274 — maa ke baghiya p.s.v | Closed | 17000 | 0 | 2022-04-04
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034620275 — maa ke baghiya p.s.v | Closed | 17000 | 0 | 2022-04-04
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034620276 — maa ke baghiya p.s.v | Closed | 17000 | 0 | 2022-04-04
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034620277 — maa ke baghiya p.s.v | Closed | 17000 | 0 | 2022-04-04
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003013/AV/22012034621864 — shantidham nirmad gram chandrapura | Ongoing | 289065.78 | 216385.71 | 2022-10-05
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702003013/DP/22012034595538 — Amritvatika plantation gram chandrapura 2023-24 | Closed | 55847.4 | 0 | 2023-07-01
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1702003013/DP/22012034595550 — Amritvatika plantation gram manpura 2023-24 | Closed | 55847.4 | 0 | 2023-07-01
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1702003013/FP/22012034202730 — nali nirman manpura puliya se nahar tak | Completed | 1498000 | 431726.44 | 2015-08-27 | 2016-01-30
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Storm Water Drains / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003013/FP/22012034204196 — naali nirmad kary kuaa se gandhrav valmeek k dwar tak | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034361820 — Nala nirman karya Kuaa se Ramkumar balmik ke dwar tak | Closed | 39600 | 0 | 2018-12-28
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034363374 — कच्चा नाला manpura से sondha की ओर | Completed | 726269.88 | 661920 | 2019-11-15 | 2022-10-31
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034366237 — Kachh naLa nirman manpur se lawan ke or | Closed | 0 | 0 | 2017-05-12
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003013/FP/22012034366238 — Kachha nala nirman murari ke kua se lawan ke ot | Completed | 834763.3 | 765320 | 2020-07-24 | 2021-04-05
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of Diversn Strm Watr Drain for Comm / Repair and maintenance of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034366239 — Pakka nala nirman mayaram ke dwar se puliya ta | Completed | 951250.99 | 898083 | 2020-07-20 | 2022-10-31
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003013/FP/22012034367111 — Pakka nala nirman jitwar ke dwar nahar ke or | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034367160 — कच्चा नाला manpura से sondha की oor | Closed | 726267 | 0 | 2019-08-19
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034624688 — Kool nirman karya Nahar se Murga farm tak | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034624689 — Kool nirman karya Bamba se Rakesh ke khet tak | Completed | 494368.56 | 420354 | 2021-05-10 | 2023-04-20
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034624771 — kool nirman karya bamba se lekar kaith ka pura hote hue narpal kekhet tak | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034624772 — nala nirman karya manpura se lawan pul ki or | Completed | 744889.1 | 625127 | 2021-05-24 | 2025-06-29
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034625335 — nala nirman karya narotam jatav ke dbar se kool tak kaith ka pura | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034625337 — pakka nala nirman karya suresh bhagat ke dbar se brindhaban phoji ke bor tak kaith ka pura | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034625340 — pakka nala nirman karya narotam jatav ke dubar se kool tak | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034625515 — kachcha nala manpura pul se sondha kool tak | Completed | 1486101.73 | 1236744 | 2021-10-17 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034626702 — Kachha nala nirman makhan k khet se manpura ki ore | Closed | 0 | 0 | 2021-09-17
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034626703 — kool nirman bamba se lekar rajpal singh k khet tk | Closed | 0 | 0 | 2021-09-17
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629037 — kool nirmad bamba se kainth ka pura nirpal singh k khet tk | Completed | 437557.4 | 178704 | 2022-05-25 | 2025-06-29
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629038 — kool nirmad naher se murga farm tk | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629039 — pakka nala nirmad atar singh k makan se naher tk | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629040 — kool nirmad bamba se rajpal k khet tk | Completed | 437557.4 | 194616 | 2022-05-25 | 2025-06-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629201 — kachha nala nirman kheriya puliya se gajendra singh k khet tk | Completed | 979027.92 | 407929 | 2023-09-25 | 2025-06-29
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629202 — kachha nala nirman kheriya puliya se gajendra singh k khet tk | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629203 — kachha nala nirman kheriya puliya se gajendra singh k khet tk | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629832 — kool nirmad nahar siddh baba se dulare k khet tk | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629833 — kool nirmad nahar bhumiya mandir se samar singh k khet tk | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003013/FP/22012034629834 — kool nirmad nahar se banke membar k khet tk | Completed | 448569.2 | 376992 | 2022-09-28 | 2023-04-20
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034630352 — constr of flood/diversion channel for community nahar sidh baba se nale tk | Completed | 666403.36 | 555373 | 2023-05-02 | 2025-06-29
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034630353 — constr of flood/diversion channel for community nahar bhumiya baba mandir se chandrapura tk | Completed | 623235 | 484704 | 2022-11-28 | 2023-05-14
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034630354 — constr of flood/diversion channel for community nahar se murga farm tk | Closed | 0 | 0 | 2022-10-02
BHIND / MEHGAON | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631085 — flood diversion chanel manoj k khet se naher tk | Closed | 461183.26 | 0 | 2025-08-05
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631086 — flood diversion chanel naher se mukesh k khet ki ore | Closed | 450841.72 | 0 | 2022-11-25
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631088 — flood diversion chanel munna k khet se bhagirath k khet ki ore | Completed | 473021.95 | 246636 | 2024-02-13 | 2025-06-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631092 — flood diversion chanel naher se munna k khet avm rajendra k khet ki ore | Completed | 441335.74 | 370107 | 2023-07-05 | 2025-06-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003013/FP/22012034631093 — flood diversion chanel bamba se shishupal k khet ki ore | Completed | 481236.85 | 305201 | 2023-08-25 | 2025-06-29
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1702003013/IC/22012034387939 — Bamba se lekar kapata Singh ke khet tak | Completed | 476693.22 | 417378 | 2021-03-13 | 2021-06-24
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of water course Canal for Community / Repair and Maintenance of water course Canal for Community | Repair & Maint of Canal | 1702003013/IC/22012034387940 — Nahar se lekar murga farm tak | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of water courses Canal for Community / Lining of water courses Canal for Community | Lining of Canal | 1702003013/IC/22012034387941 — Nahar se lekar murga farm tak | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1702003013/IC/22012034387942 — Bamba se lekar Ramotar ojha ke khet tak | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003013/IF/22012034352776 — vrachchha ropan kary shanti dham manpura | Completed | 335000 | 24224 | 2017-08-17 | 2021-12-13
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Nursery Raising / Raising of Nursery for Individuals | Nursery Development | 1702003013/IF/22012034352794 — vrachchha ropan kary panchayat bhavan k pass manpura | Deleted | 0 | 0 | 2017-06-15
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003013/IF/22012034352998 — Vrachchha ropan kary manpura nahar se chandpura ki or | Closed | 335000 | 0 | 2017-06-20
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Nursery Raising / Raising of Nursery for Individuals | Nursery Development | 1702003013/IF/22012034353035 — vrachchha ropan kary panchayat bhavan k pass manpura | Deleted | 0 | 0 | 2017-05-05
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003013/IF/22012034353043 — vrachchha ropan kary panchayat bhavan k pass manpura | Completed | 335000 | 22160 | 2017-07-29 | 2021-12-13
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Block Plantation of Biodrainage Trees in Fields for Individuals | Plantation | 1702003013/IF/22012034654503 — BIRCHA ROPAN KARYRADHESHYAM KE KHET PAR | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702003013/IF/22012034655142 — Vrakshropan kary vidhya bai vaijnath singh | Closed | 0 | 0 | 2020-12-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1702003013/IF/22012034655449 — Vidhya bai w/o vaijnath ke khet me braksharopan | Closed | 0 | 0 | 2020-12-21
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702003013/IF/22012034655455 — Rajendra Singh S/O Hukum Singh ke khet me Braksharopan | Closed | 0 | 0 | 2020-12-23
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702003013/IF/22012034655456 — Shishupal singh S/O Sahab Singh ke khet me braksharopan | Closed | 0 | 0 | 2020-12-23
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003013/IF/22012035547415 — Khet talab nirman Lajjaram s/o laxman singh | Approved | 0 | 0 | 2025-04-15
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003013/IF/22012035547435 — khet talab nirman mohar singh S/o laxman singh chandpura | Approved | 0 | 0 | 2025-04-15
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003013/IF/22012035551851 — KHET TALAB NIRMAN KARYA LAJJARAM S/O LAXAN SINGH | New | 0 | 0 | 2025-04-15
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003013/IF/22012035551864 — KHET TALAB NIRMAN KARYA MOHAR SINGH S/O LAJJARAM | New | 0 | 0 | 2025-04-15
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993714426 — cattle sed dev Singh s/o kalyan | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726321 — PASHUSED RAMVEER S/O KHEMRAJ | Deleted | 11500000000 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726329 — PASHUSED MANOJ S/O MOHARMAN | Deleted | 11500000000 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726331 — PASHUSED SURESH S/O BHAJANLAL | Deleted | 11500000000 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726336 — PASHUSED HARDEV S/OCHOTELAL | Deleted | 11500000000 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726344 — PASHUSED SURESH S/O BHAJANLAL | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726349 — PASHUSED RAMCHARAN S/O JANVED | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726353 — PASHUSED RAMDEEN S/OGHAMANDILAL | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726365 — PASHUSED | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993726370 — PASHUSED S/O GHABDU | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728183 — PASHUSED RAMOTAR S/O RAMLAAL | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728194 — PASHUSED SHREERAM S/O KISHAN LAL | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728200 — PASHUSED MANOJ S/O HARCHARAN | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728208 — PASHUSED RAKESH S/O MAYARAM | Deleted | 115900 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728220 — PASHUSED MAHARAJ SINGH S/O BHABOOTI | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728224 — PASHUSED RAVINDRA S/O VIJAYRAM | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728229 — PASHUSED NAHAR SINGH S/O BHABOOTI | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728231 — PASHUSED KELASH S/O SURESH | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728248 — pashused chandan s/o | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728250 — PASHUSED NIROTTAM S/O RAMSAHAY | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993728254 — PASHUSED MURARI S/O PREETAM SINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003013/IF/9993734624 — pasused niraman | Deleted | 0 | 0 | 2015-10-27
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/118362 — Construction of IAY House -IAY REG. NO. MP-02-003-013-001/539 | Completed | 14310 | 14028 | 2017-01-06 | 2017-02-28
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/118363 — Construction of IAY House -IAY REG. NO. MP-02-003-013-001/559 | Completed | 14310 | 15408 | 2016-07-29 | 2018-11-10
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/118364 — Construction of IAY House -IAY REG. NO. MP-02-003-013-002/41 | Completed | 14310 | 14028 | 2016-07-29 | 2016-12-29
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/2347508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3694734 | Completed | 17100 | 16032 | 2020-10-07 | 2022-10-30
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/2347540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3149006 | Completed | 17100 | 17100 | 2020-10-07 | 2021-04-10
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/2347541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3128633 | Completed | 17100 | 16068 | 2020-10-07 | 2021-12-13
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/3953267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143870309 | Approved | 23490 | 0 | 2022-05-04
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/3953497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145871945 | Completed | 18360 | 18343 | 2023-05-22 | 2023-08-16
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/3960943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148343189 | Completed | 18360 | 17527 | 2023-01-11 | 2023-08-23
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/4149394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143870126 | Physically Completed | 18360 | 17680 | 2023-05-23 | 2024-11-21
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/4361961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148357640 | Completed | 18360 | 15708 | 2023-01-11 | 2023-04-20
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/4764269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121803018 | Approved | 23490 | 0 | 2024-09-13
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/4764271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121804590 | Physically Completed | 23490 | 0 | 2026-02-05 | 2026-06-14
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/4805787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143870252 | Physically Completed | 23490 | 4698 | 2026-02-05 | 2026-06-14
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/5258254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121841657 | Physically Completed | 23490 | 0 | 2026-01-12 | 2026-03-29
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/5280848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121802409 | Approved | 23490 | 0 | 2024-10-25
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/5282557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145871971 | Approved | 23490 | 0 | 2025-02-21
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/542368 — Construction of IAY House -IAY REG. NO. MP3133287 | Completed | 15030 | 14996 | 2017-03-01 | 2018-04-11
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/542728 — Construction of IAY House -IAY REG. NO. MP3145887 | Completed | 15030 | 14996 | 2017-03-01 | 2018-04-06
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/558047 — Construction of IAY House -IAY REG. NO. MP3592605 | Completed | 15030 | 15136 | 2017-03-01 | 2018-04-06
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/560850 — Construction of IAY House -IAY REG. NO. MP3693205 | Completed | 15030 | 15480 | 2017-03-01 | 2018-06-15
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003013/IF/IAY/5630611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143870199 | Approved | 23490 | 0 | 2024-09-15
BHIND / MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/122 — मेंड बंधान निर्माण रामप्रकाश /ववलूप्रसाद | Completed | 32000 | 29666 | 2009-06-15 | 2009-06-15
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/22012034265943 — MEDBANDAN RAMSWROOP S/O MOTISINGH | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/22012034265949 — MEDBANDAN SURESH S/O BHAJANLAL | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/22012034265951 — MEDBANDAN S/O | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/22012034265953 — MEDBANDAN HARDEV S/OCHOTELAL | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/22012034265954 — MEDBANDAN BABULAL S/ORAMLAL | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552923 — medvandhan karya nathu singh s/o hukam singh ke khet par | Closed | 35807.62 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552924 — medvandhan karya nathu singh s/o hukam singh ke khet par | Completed | 40033.59 | 27792 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552925 — medvandhan karya nathu singh s/o hukam singh ke khet par | Closed | 43146.07 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552927 — medbadhan karya baijnath singh s/o malikhan singh ke khet par | Completed | 33800.04 | 24318 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552928 — Medvandhan kary Virendra Singh s/0 hukam singh ke khet par | Completed | 44226.09 | 32424 | 2021-11-18 | 2022-02-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552929 — medbandan karya bacchu singh s/o hukam singh ke khet par | Completed | 39082.48 | 25476 | 2021-11-18 | 2022-02-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552932 — medbadhan karya ramotarsingh s/o hukam singh ke khet par | Completed | 47466.15 | 31266 | 2021-11-18 | 2022-02-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552936 — Medhvandan kary Radheshyam s/0 hukam singh ke khet par | Completed | 50706.2 | 32424 | 2021-10-14 | 2021-10-27
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552937 — medbandhan karya jogendra singh s/o jitawar singh ke khet par | Completed | 44226.09 | 33582 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552950 — medvandhan karya vidhya bai w/0 vaijnath singh ke khet par | Completed | 48546.16 | 39372 | 2021-11-18 | 2022-01-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552952 — medvandhan karya vidhya bai w/0 vaijnath singh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552958 — medvandhan karya vidhya bai w/0 vaijnath singh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552964 — medbandhan karya kishori s/o hardayal ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552968 — medbandhan karya ashok s/o munshi | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552972 — Medvandhan kary Dataram s/0 phuljari ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552973 — medbandhan karya abdesh s/o rajaram ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552978 — medbadha karya vijaypal s/o rajaram ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552979 — Medvandhan kary Asharam s/0 phuljari ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552984 — medvandhan karya phudilal s/o matadeen | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552986 — Medvandhan kary manoj s/0 Harcharan ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552988 — medbandhan karya ramotar s/o chetram ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552991 — Medvandhan kary bhuta w/0 chhatarpal par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552992 — medvandhan karya chhatrapal singh s/o kiliyan singh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/LD/22012034552994 — medvandhan karya chhatrapal singh s/o kiliyan singh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003013/LD/22012034552995 — medvandhan kary mahdev singh s/0 rasal singh ke khet par | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/325 — मेड बन्‍धान कार्य मोहर सिंह / प्रभूदयाल | Completed | 0 | 6900 | 2010-06-01 | 2010-06-01
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003013/LD/326 — मेड बन्‍धान कार्य रामस्‍वरूप / घमण्‍डी जाटव | Completed | 0 | 9000 | 2010-09-10 | 2010-09-10
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Maintenance of rural public assets / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1702003013/OP/9425890114 — SHANTI DHAAM MANPURA | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702003013/OP/9425890800 — Shanti dhham nirman karya manpura | Completed | 1499000 | 1383049 | 2016-11-22 | 2018-07-31
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702003013/OP/9425892782 — Shanti dhham nirman karya chandrapura | Deleted | 180000 | 0 | 2017-01-15
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003013/PG/9425896271 — Khel medaan nirman kary manpura | Deleted | 186600 | 0 | 2017-01-15
BHIND / MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003013/RC/117 — पहुंचमार्ग मिटटी कार्य चन्‍द्रपुरा से लावन की ओर | Completed | 494000 | 208376 | 2011-06-17 | 2011-12-26
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034176203 — c c road radeshyam ke darwaje se road tak | Completed | 207600 | 198764 | 2013-07-24 | 2013-12-18
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034189320 — c c road sahab ke darwaje se makhan ke darwaje tak | Completed | 65270 | 58066 | 2013-10-02 | 2013-11-29
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034212121 — panchpar.ccroad mata ke mandir se ramdeen jatav ke | Completed | 218002 | 208602 | 2014-03-05 | 2014-05-28
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034212125 — panchpar.ccroad munesh ke dwar se cc road tak | Completed | 65270 | 49035 | 2014-03-05 | 2014-05-27
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034223398 — c.c. raod kuaa se pra. vidhayalay ki or | Completed | 277850 | 193140.5 | 2014-07-28 | 2015-07-20
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034223399 — सी सी रोड प्रेम सिंह जाटव के द्रार से स्कूल की ओ | Completed | 250063 | 151179 | 2014-08-21 | 2014-09-02
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cross Drainage / Construction of Culvert / cross drainage structues for Community | Culvert | 1702003013/RC/22012034283528 — nali nirman karya puliya se nehar tak | Deleted | 0 | 0 | 2015-05-18
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034295360 — cc rod nirmad mandir se sahab singh wali gali hote hue pooran k dwar ki or | Completed | 301000 | 298693 | 2016-01-07 | 2016-03-22
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034308131 — CC ROD POORAN K DWAR SE MUNSHI K DARWAJE KI OR | Deleted | 254800 | 0 | 2016-04-05
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034308135 — ATAR SINGH K DWAR SE NAHAR TAK | Deleted | 301016 | 0 | 2016-03-15
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034308137 — CC ROD PULIYA SE KAMLESH K DWAR KI OR | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034308140 — CC ROD PATIRAM JATAV K DWAR SE BHEEMSEN K DWAR KI OR PADOLIYAPURA | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034308979 — MUKHY MANTRI SADAK YOJNA KAMLESH K DWAR SE SAHIB SINGH K KET TAK | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034309006 — MUKHY MANTRI SADAK YOJNA pooran k dwar se surat singh k khet tak | Deleted | 0 | 0 | 2016-04-14
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034309067 — MUKHY MANTRI SADAK YOJNA MURARI K KHET SE PRATAP K KHET TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034312596 — cc rod nirman pooran k ghar se munshi k ghar ki or | Completed | 254800 | 253899 | 2016-05-11 | 2016-07-28
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034312745 — Cc rod atar Singh k dwar se nahar ki or | Completed | 301016 | 299578.8 | 2016-07-26 | 2017-10-02
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034317927 — cc rod nirman kary laturi jadon k dwar se mukhy marg tk | Completed | 117000 | 116606 | 2017-01-20 | 2018-07-18
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034326022 — Cc rod nirmad kary. Maharaj singh k dwar se ramcharan k dwar tk kethkapura | Ongoing | 265600 | 261996 | 2017-03-04
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034340831 — sudhur sampark sadak manpura men rod se keth ka pura tk | Completed | 2053000 | 1995330.94 | 2017-06-10 | 2020-07-28
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034353472 — c c road nirman Puliya se Kamlesh sharma ke makan tak. Manpura | Completed | 233000 | 231632 | 2017-09-12 | 2017-10-15
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034364833 — c c road nirman MAY NALI PAN SINGH KE DWAR SE BAIJNATH KE DWAR TAK . PADOLIYAN KA PURA | Completed | 79650 | 79464 | 2017-10-25 | 2018-02-05
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034372967 — cc road | Closed | 0 | 0 | 2017-10-02
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034384390 — c c road nirman LAKHAN KE DWAR SE KHARANJA TAK | Deleted | 61950 | 0 | 2016-10-02
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034397775 — c c road nirna Lakhan ke dwar se Kharanaj tak | Completed | 61950 | 61596 | 2018-11-30 | 2019-01-10
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034432521 — cc road nirman BHARAT KE DWAR SE MANOJ JATAV KE DWAR TAK | Closed | 42120 | 0 | 2016-10-02
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034442121 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034468992 — c c road nirman pooran baretha ke bagal se santosh dhanuk ke dwar tak | Completed | 42375 | 34672 | 2019-10-01 | 2021-04-10
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034470775 — sudoor sadak Manpura se moja manpura tk | Closed | 0 | 0 | 2019-04-14
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034470776 — sudoor road Manpura Se padolya ka pura tk | Closed | 0 | 0 | 2019-04-14
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034470777 — sudoor road manpura se chandpura tk | Closed | 0 | 0 | 2019-04-14
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034470778 — sudoor road padulya pura se bamba tk | Closed | 0 | 0 | 2019-04-14
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034527583 — Sudar samparak sadak mandir se Dinesh jadon ke khet tak | Completed | 2038261.62 | 2055959.83 | 2020-09-11 | 2022-10-28
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1702003013/RC/22012034536216 — Mandir se Dinesh jadon ke khet tak | Closed | 0 | 0 | 2020-07-15
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/22012034586990 — cc road pooran baretha k ghar se panchayat bhawan ki ore | Completed | 127500 | 111168 | 2021-10-14 | 2021-12-13
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034594924 — Sudur Samparak Manpura Se Bamba ke Pul Tak | Closed | 0 | 0 | 2021-10-10
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034594925 — Sudur Samparak Manpura Se Bamba ke Pul Tak | Ongoing | 2493198.27 | 2021964.35 | 2021-11-18
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1702003013/RC/22012034595222 — Sudur samparak sadak gram chandrapura se gram manpura tak | Physically Completed | 2493198.27 | 2452034 | 2021-11-18 | 2026-06-05
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034612229 — sudur sampark sadak manpura pul se siddh baba hote huye chandrapura road tk | Closed | 0 | 0 | 2022-01-27
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003013/RC/22012034613451 — sudur sampark sadak manpura pul se siddh baba hote huye chandrapura road tk | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003013/RC/233 — सीसी रोड निर्माण् महादेव मन्दिर से स्‍कूल तक पंचपरमेश्‍वर मद | Completed | 193558 | 174064 | 2012-07-01 | 2012-12-18
BHIND / MEHGAON | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003013/RC/45 — पहुच मार्ग निर्माण | Completed | 164000 | 81738 | 2008-05-26 | 2009-12-25
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Stabilization Pond for Comm / Repair and maintenance of Stabilization Pond for Community | Repair & maint of Pond/ Tank | 1702003013/RS/22012034513677 — panchayat bhaban ka maintinence | Closed | 0 | 0 | 2021-04-01
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702003013/RS/22012034585056 — samudayik swachchta parisar manpura | Completed | 43000 | 42846 | 2021-10-14 | 2023-05-30
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1702003013/WC/22012034612661 — Khet talab Manoj ke khet mai | Ongoing | 337715.44 | 260505 | 2021-11-19
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003013/WC/22012034893412 — Talab jeerdoddhar karya piparavali mata mandir k paas | Closed | 0 | 0 | 2021-11-29
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003013/WC/22012034893413 — Talab jeerdoddhar karya piparavali mata mandir k paas | Completed | 48046.16 | 39372 | 2022-03-09 | 2023-04-20
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003013/WC/22012034893427 — talab jeerdoddhar karya ramjanki mandir k pass | Physically Completed | 47042.72 | 39372 | 2022-03-19 | 2026-04-16
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003013/WC/22012034972159 — pakka talab gram chandrapura | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702003013/WC/22012034975591 — khet talab baijnath singh k khet pr | Closed | 356340.1 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003013/WC/22012034975601 — khet talab nathu singh k khet pr | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003013/WC/22012034975607 — khet talab bachu singh k khet pr | Closed | 356340.1 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003013/WC/22012034980814 — khet talab nathu singh k khet pr | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WC/22012034985605 — talab jirdodhhar bamba k pas | Closed | 17000 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935183 — talab jirdodhhar indal k ghar pas | Closed | 18000 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935184 — talab jirdodhhar bamba k pas | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935187 — talab jirdodhhar megh singh k khet k pass | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935190 — talab jirdodhhar naresh k khet kpass | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935191 — talab jirdodhhar puliya k pass | Completed | 18000 | 14688 | 2022-05-27 | 2022-06-09
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935313 — talab jirdodhhar manpura | Closed | 18000 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935321 — talab jirdodhhar manpura | Closed | 18000 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935323 — talab jirdodhhar chandrapura | Closed | 18000 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003013/WH/22012034935325 — talab jirdodhhar chandrapura | Closed | 18000 | 0 | 2022-04-14