## Work List
Exported on: 2026-10-26 06:18:56
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: SETHARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1702003017/AV/22012034621277 — boundrywall nirmaan primary school sethari | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003017/AV/22012034623796 — BOUNDRYWALL NIRMAAN KARYA MIDDLE SCHOOL SENTHARI | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003017/AV/22012034623797 — BOUNDRYWALL NIRMAN KARYA MIDDLE SCHOOL SENTHARI | Completed | 1199000 | 178704 | 2022-11-01 | 2026-04-17
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003017/AV/22012034623885 — Pever block govt school middle senthari | Ongoing | 1498390.4 | 119952 | 2022-11-07
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003017/AV/22012034625826 — Khel medan govt middle school senthari | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003017/DP/22012034239734 — Brachya Ropan Karya Road Kinare Sethri | Completed | 335000 | 3096 | 2017-05-08 | 2021-12-13
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1702003017/DP/22012034579660 — braksharopan karya shaskiya school kushwaha mohlla k pass | Ongoing | 427106.07 | 99671 | 2023-08-26
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003017/FP/22012034363380 — Kachha Nala Nriman Kuswah Pura Se Gao Ke Bahar Kee Or | Closed | 0 | 0 | 2018-04-01
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702003017/FP/22012034626612 — Band Daybarajan Chanal Se Jay Singh Ke Khet Kee Or | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034881694 — bandarbayan vishambar k khet se bacchu singh k khet ki ore | Completed | 806721.36 | 544476 | 2022-10-09 | 2026-04-17
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034881695 — bamdarbayan pooran singh k khet se ramlakhan singh k khet ki ore | Completed | 806721.36 | 679898 | 2022-11-01 | 2023-05-25
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034882065 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNITY RATAN SINGH K KHET SE SHANTI DEVI K KHET KI ORE | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034882066 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNITY SHEETAL SINGH K KHET SE BHAGIRATH RATHOR K KHET KI ORE | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034882706 — Construction of sub minor canal for community sheetal singh l khet se bhagirath rathor k khet ki ore | Closed | 0 | 0 | 2023-04-24
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034882707 — Construction of sub minor canal for community sheetal singh l khet se bhagirath rathor k khet ki ore | Completed | 395565.76 | 270283 | 2023-07-21 | 2026-04-17
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1702003017/IC/22012034882708 — constrruction of sub minor canal for community ratan singh k khet se shanti devi k khet ki ore | Completed | 354869.2 | 289068 | 2023-05-10 | 2023-06-24
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882834 — constructio of sub minor canal for community krishndayal k khet se kailash singh k khet ki ore | Completed | 356911.49 | 268957 | 2023-06-30 | 2026-04-17
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882835 — construction of sub minor canal for community bambiya se basant singh k khet ki ore | Completed | 366295.74 | 281996 | 2023-07-28 | 2026-04-17
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882836 — construction of sub minor canal for community sunder singh k khet se bhole singh k khet ki ore | Physically Completed | 375680 | 291720 | 2023-06-23 | 2026-05-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of minor Canal for Community / Construction of minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882957 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNITY GANGA SINGH K KHET SE BAMBIYA TAK | Ongoing | 377290.14 | 64974 | 2023-09-21
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882958 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNITY PRADEEP SINGH K KHET SE PRABHUDAYAL K KHET TAK | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882959 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNIT SHOBHADEVI K KHET SE KALAWATI K KHET TAK | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882960 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNIT SHOBHADEVI K KHET SE KALAWATI K KHET TAK | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882961 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNITY BAMBIYA SE RAJU SINGH K KHET TAK | Closed | 348221.18 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882962 — CONSTRUCTION OF SUB MINOR CANAL FOR COMMUNITY DEEPIKA SINGH K KHET SE NARENDRA SINGH K KHET TAK | Ongoing | 419090.39 | 119561 | 2023-09-28
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of sub-minor Canal for Community / Construction of sub-minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882963 — CONSTRUCTION OF SUB MIONOR CANAL FOR COMMUNITY MUKULNAB K KHET SE DROPADI K KHET TAK | Closed | 338549.82 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of minor Canal for Community / Construction of minor Canal for Community | Construction of Canal | 1702003017/IC/22012034882964 — CONSTRUCTION OF SUB MINOR CNAL FOR COMMUNITY NAR SINGH K KHET SE PUSHPENDRA SINGH K KHET KI ORE | Physically Completed | 379779.92 | 285090 | 2023-07-07 | 2026-04-16
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Lining of minor Canal for Community / Lining of minor Canal for Community | Lining of Canal | 1702003017/IC/22012034882972 — braksharopan karya shaskiya middle school | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003017/IF/22012034353318 — Brachya Ropan Karya Samudayak Sthal Per | Closed | 335000 | 0 | 2017-06-19
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003017/IF/22012034354078 — Brachya Ropan Karya [ P S / M S Schkool And Kanya Shala Or Panchyat Bhavan Ke Pass | Closed | 335000 | 0 | 2017-06-19
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation of Forstry Trees for Individual / Boundary Line Plantation of Forestry Trees for Individuals | Plantation | 1702003017/IF/22012035124826 — braksharopan karya NATHU SINGH/VISHSHWAR sINGH | Ongoing | 133212.69 | 31824 | 2023-08-04
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702003017/IF/22012035124828 — BRAKSHAROPAN KARYA SATYENDRA SINGH/ RAMOTAR SINGH | Ongoing | 133212.69 | 33150 | 2023-08-04
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702003017/IF/22012035124830 — BRAKSHAREOPAN KARYA SHASKIA MADHYAMIK VIDHALYA SCHOOL SENTHARI | Ongoing | 427106.07 | 62543 | 2023-08-04
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1702003017/IF/22012035124834 — BRAKSHAROPAN KARYA YOGENDRA SINGH / POORAN SINGH | Ongoing | 133212.69 | 26520 | 2023-08-04
BHIND / MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702003017/IF/22012035413080 — Satyendra singh s/o ramotar singh Khettalab | New | 0 | 0 | 2025-04-10
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035542262 — Khet talab Gopal Singh S/o Amrit singh ke khet me | Approved | 147621.16 | 0 | 2025-04-14
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035548072 — khet talab nathu singh S/O visheswar ke khet me | Approved | 147621.16 | 0 | 2025-04-17
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035548093 — khet talab Mukesh singh S/O Naval Singh ke khet me | New | 0 | 0 | 2025-04-17
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035548100 — khet talab Mukesh singh S/O Naval Singh ke khet me | Approved | 147621.16 | 0 | 2025-04-17
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035550204 — Khet talab Nirman Karya gabbar Singh S/O ram Singh ke Khet me | Approved | 147621.16 | 0 | 2025-04-17
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035562037 — KHET TALAB NIRMAN SATENDRA S/O RAMAVTAR SINGH KE KHET ME | New | 0 | 0 | 2025-04-17
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702003017/IF/22012035562043 — KHET TALAB NIRMAN SATENDRA S/O RAMAVTAR SINGH KE KHET ME | Approved | 0 | 0 | 2025-04-17
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993705451 — Pashu Shed Mataprashad / Jashmant Bretha | Completed | 116000 | 110907.55 | 2016-04-04 | 2016-09-27
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993705452 — Pashu Shed Lalluram / Jashmant Baretha | Completed | 116000 | 110907.71 | 2016-04-04 | 2016-09-27
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725216 — Pashu Shed Suneel / Rambaran | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725224 — Pashu Shed Ajan singh / Shriram | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725229 — Pshu Shed Sher singh / Raghuveer | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725239 — Pashu Shed Ajay singh / Prakash | Closed | 116000 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725246 — Pashu Shed Preetam singh /Vijay | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725250 — Pashu Shed Devendra singh / kAMAL | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725251 — Pashu Shed Himmat singh / Kedar | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725254 — Pashu Shed Kamle singh / Chote | Completed | 116000 | 111575.55 | 2016-05-29 | 2017-09-27
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725256 — Pashu Shed Hakim singh /Govind | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725257 — Pashu Shed Shanti /Jagannath | Closed | 116000 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725258 — Pashu Shed Sher singh / jagnnath | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725261 — Pashu Shed Vishavnath singh / Ramshvroop | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725263 — Pashu Shed Batna devi / Sungandh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725264 — Pashu Shed Balveer singh /Dulare | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725265 — Pashu Shed Sarjan singh / Chaviram | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725266 — Pashu Shed Ajab singh /Bahadur | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725267 — Pashu Shed Shivnath /Ramlakhan | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725268 — Pashu Shed Ashok /laxman | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725269 — Pashu Shed Ashok /Bhoop singh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725270 — Pashu Shed Vinod singh Uday singh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725271 — Pashu Shed Mahesh /Chote singh | Completed | 116000 | 111575.71 | 2016-05-29 | 2016-09-27
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725272 — Pashu Shed Gyan singh /joharee | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725273 — Pashu Shed Bhore singh Jashamant | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725274 — Pashu Shed Mayaram /Mulu singh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725275 — Pashu Shed Ramveer /Ramshvaroop | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725276 — Pashu Shed Keshav singh / Gopal | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725277 — Pashu Shed Ramvaran singh / Babooram | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725278 — Pashu Shed Kaliyan singh /Baturee | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725279 — Pashu Shed Rambaboo /Pahalban | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725280 — Pashu Shed Pooran singh /Ramcharan | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725281 — Pashu Shed Dinesh singh / Ramvaran | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725282 — Pashu Shed Avadesh /Randheer singh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725283 — Pashu Shed Mohardal /Gyaram | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725284 — Pashu Shed Maniram singh /Ramdayal | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725285 — Pashu Shed Baliram /Chandarbhan | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725286 — Pashu Shed Janak singh /Joharee | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725287 — Pashu Shed Desharaj /Mohar singh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725288 — Pashu Shed Jagdeesh /Munshi | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725293 — Pashu Shed Kishorilal /Dinekumar | Completed | 116000 | 111575.61 | 2016-08-04 | 2016-09-30
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725305 — Pashu Shed Ganesh /Ramshvaroop | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725307 — Pashu Shed Prakash /Hari singh | Completed | 116000 | 111575.61 | 2016-07-28 | 2016-09-30
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725314 — Pashu Shed Surendra /Ramgopal | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993725321 — Pashu Shed Ajay singh /Pooran singh | Closed | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993743735 — Pashu Shed Hakim / Jashvant singh | Completed | 116000 | 111575.55 | 2016-05-29 | 2016-09-27
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993745313 — Pashu Shed Shyamlal / Ramswroop Jatav | Completed | 116000 | 111575.61 | 2016-07-28 | 2016-09-30
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003017/IF/9993745314 — Pashu Shed Naval / Jaghdeesh Dhanuk | Completed | 116000 | 111575.61 | 2016-07-28 | 2016-09-30
BHIND / MEHGAON | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/1899230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4545294 | Completed | 17100 | 13596 | 2018-11-14 | 2021-12-02
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/193196 — Construction of IAY House -IAY REG. NO. MP-02-003-017-001/20 | Approved | 23490 | 0 | 2016-02-21
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/193336 — Construction of IAY House -IAY REG. NO. MP-02-003-017-001/23 | Completed | 14310 | 14028 | 2016-07-28 | 2017-03-01
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/3943845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120584491 | Physically Completed | 23490 | 16122 | 2022-11-08 | 2025-06-02
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/4102327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145780520 | Approved | 23490 | 0 | 2022-05-12
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/4212386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121672454 | Completed | 18360 | 17136 | 2022-09-23 | 2023-05-29
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/4212988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117052573 | Physically Completed | 18360 | 16962 | 2022-11-07 | 2024-11-21
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/4755474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118065852 | Approved | 23490 | 0 | 2024-09-18
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/4762039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120582374 | Approved | 23490 | 0 | 2024-09-18
BHIND / MEHGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/4854349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121670994 | Ongoing | 23490 | 0 | 2026-04-15
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/500049 — Construction of IAY House -IAY REG. NO. MP2251922 | Completed | 15030 | 15395 | 2017-03-04 | 2018-05-15
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/5719799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124825919 | Ongoing | 23490 | 0 | 2026-01-16
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/5720166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124824522 | Ongoing | 23490 | 0 | 2026-01-16
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/5725517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120591434 | Ongoing | 23490 | 0 | 2026-01-15
BHIND / MEHGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003017/IF/IAY/5726223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121673273 | Approved | 23490 | 0 | 2025-04-07
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556488 — Med Bandhan Kadam Singh/ Gyaram Singh | Completed | 49665.57 | 37944 | 2022-09-08 | 2023-05-29
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556489 — Med Bandhan Megh Singh/Asharphi Singh | Completed | 47552.6 | 31892 | 2022-09-16 | 2023-06-24
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556491 — Med Bandhan Mohar Singh/Jagannath Singh | Completed | 47552.6 | 38284 | 2022-09-17 | 2023-07-03
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556492 — Med Bandhan Beti Bai/Kamal Singh | Completed | 46496.1 | 16796 | 2023-06-02 | 2026-04-17
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556494 — Med Bandhan Kaliyan/Prakash Singh | Completed | 43326.64 | 34272 | 2022-09-21 | 2023-05-29
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556496 — Med Bandhan Kamalesh/Jashavant Singh | Ongoing | 46496.1 | 34034 | 2023-06-11
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556498 — Med Bandhan Bacchu Singh/ Karan Singh | Closed | 44383.13 | 0 | 2021-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556499 — Med Bandhan Badan Singh/Govind Singh | Ongoing | 42270.15 | 32708 | 2022-09-24
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556502 — Med Bandhan Narayan /Chhaviram Singh | Ongoing | 45439.62 | 36720 | 2022-12-07
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556503 — Med Bandhan Mohar Singh/Jagaram | Completed | 43854.88 | 34272 | 2022-12-07 | 2023-05-29
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556505 — Med Bandhan Gabbar Singh/Jagaram | Closed | 39100.69 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556506 — Med Bandhan Suraj Singh/Dharm Singh | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556508 — Med Bandhan Vishrim Singh/Kaleechar | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556510 — Med Bandhan Prakash/Hariram | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556512 — Med Bandhan Tilak Singh/ Babu Singh | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556513 — Med Bandhan Raju Singh/Janaved Singh | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1702003017/LD/22012034556514 — Med Bandhan Janak Singh/ Bhagirath Singh | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702003017/LD/22012034592074 — braksharopan jitendra singh/narayan Singh | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003017/LD/22012034592075 — Janak Singh/bhagirath Singh | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702003017/LD/22012034592076 — braksharopan brijesh Singh /poran Singh | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003017/LD/22012034592078 — braksharopan rajesh Singh/nawab singh | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003017/LD/22012034592079 — braksharopan atiraj Singh/badri Singh | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702003017/LD/22012034592080 — braksharopan ashadevi /atar Singh | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1702003017/LD/22012034593879 — MERI MITTI MERA DESH BRAKSHAROPAN SHANTI DHAM SENTHARI | Ongoing | 55847.4 | 4420 | 2023-09-12
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702003017/OP/9425890793 — Shanti Dham Nirman Main Road Ke Pass Sethri | Completed | 1499000 | 1430775.85 | 2016-11-14 | 2021-03-20
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003017/PG/9425896266 — Khel Medan Sethri | Completed | 353000 | 235734 | 2017-03-25 | 2020-05-25
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034231575 — c c road kamale ke makan se umesh ke makan kee or | Completed | 219500 | 210303 | 2014-10-01 | 2015-04-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034231576 — c croad chain singh ke makan se man singh ke makan | Completed | 219500 | 209675 | 2014-10-01 | 2015-04-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034231577 — c c road janak singh ke makan se mahesh ke makan k | Completed | 219500 | 213286 | 2014-10-01 | 2015-04-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034231587 — c c road prathmik kanya shala se munni rathoor ke | Completed | 219500 | 218624 | 2014-10-01 | 2015-04-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034231588 — c c road munna singh ke makan se prathmik kanya sh | Completed | 219500 | 220037 | 2014-10-01 | 2015-04-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034231662 — g s b road jaghdeesh ke makan se munna ke makan kee or | Completed | 298000 | 257869.6 | 2014-10-10 | 2015-04-01
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034231870 — g s b road main road se shkool ke or | Completed | 298000 | 133425.3 | 2014-10-10 | 2016-01-27
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034231871 — khet sadak man singh ke khet se bhadur ke khet kee or | Completed | 1429000 | 1171308.7 | 2014-10-10 | 2015-09-09
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034231872 — sudoor samprak sadak yijana sethari se baretha pura kee or | Completed | 1429000 | 1173239.3 | 2014-10-10 | 2015-09-09
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034262412 — c c road sher singh ke makan se kachare ke makan kee or | Deleted | 220000 | 0 | 2014-10-02
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034262414 — c c road sher singh ke makan se kachare ke makan kee or | Completed | 219500 | 219252 | 2015-01-03 | 2015-05-27
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034296649 — C C Road Baretha Mohalla Se Dinesh Ke Makan Kee Or | Completed | 220000 | 214887 | 2016-01-16 | 2016-09-27
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034296650 — C C Road Narayan Ke Makan Se Kua Kee Or | Completed | 220000 | 212047 | 2016-01-16 | 2016-09-27
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308632 — C C Road Kishori lal Ke Makan Se Relway Phatak Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308635 — C C Road Uday singh tomar Ke Makan Se Chote singh badoriya Ke Makan Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308637 — C C Road Main Road Se Sashakiy Prathmik Shala Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308638 — C C Road Maniram Ke Makan Se Bangali Babu Baretha Ke Makan Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308639 — C C Road Ramprakash Ke Makan Se Main Road Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308640 — Khet Sadak Main Road Se Shrivastav Ke Ket Ki Ohr | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308641 — Khet Sadak Sashaki Madhymik School Se Maharaj Pura Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034308642 — Khet Sadak Baretha Pura Se Rampura Ki Or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034332453 — C C Road Bhoop Singh ke Ghar se Mahipal Ke Ghar Hote Huai Talab Kee Or | Completed | 148000 | 128490 | 2017-03-21 | 2019-03-01
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034332456 — C C Road Bangali Ke Ghar Se Road Kee Or | Completed | 110250 | 98334 | 2017-03-21 | 2019-03-01
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034334593 — C C Road Mukhya Marag Se Nathu Ke Ghar Kee Or | Completed | 148000 | 135508 | 2017-04-06 | 2019-03-01
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034342754 — Sudoor Samparak Sadak Yojana Sethri Se Maharaj Pura Tak | Completed | 1100000 | 788614.48 | 2017-06-25 | 2026-04-17
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034342755 — Sudoor Samparak Sadak Yojana Shaskiya Kanya Shala Se Gathai Main Road Kee Or | Completed | 1100000 | 785490.48 | 2017-07-02 | 2019-08-31
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034342756 — Sudoor Samparak Sadak Yojana Kamlesh Balmik Ke Makan Se Pooran Singh Ke Makan Kee Or | Closed | 1200000 | 0 | 2017-06-25
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034347967 — C C Road Baghwan Singh Ke Makan Se Keshav Ke Makan Kee Or | Completed | 241000 | 137856 | 2019-12-14 | 2022-10-31
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034362581 — Sudoor Samparak Sadak Yojna Sethri Se Bhadoriyan Ke Pura Tak | Completed | 1100000 | 875042.88 | 2017-10-01 | 2019-03-01
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003017/RC/22012034362582 — Sudoor Samparak Sadak Yojna Pooran Singh Pura Se Manhad Kee Or | Completed | 1100000 | 1065830.88 | 2017-10-01 | 2019-03-01
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034373002 — cc road | Closed | 0 | 0 | 2017-10-02
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034392698 — C C Road Pooran Ke Makan Se Bhageerath Ke Makan Kee Or | Completed | 122000 | 55488 | 2019-11-17 | 2020-09-20
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034392700 — C C Road Sajjan Ke Makan Se Main Road Kee Or | Completed | 190000 | 63636 | 2019-11-17 | 2020-09-20
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034392701 — C C Road Kishori Ke Makan Se Bhagavan Singh Ke Makan Kee Or | Completed | 94000 | 53880 | 2019-11-17 | 2020-09-20
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034442201 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034507578 — C C Road Bhaghwan Singh Ke Makan Se Keshav Ke Makan Kee Or | Closed | 0 | 0 | 2017-08-01
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034510331 — C C Road C C Road Se Samudayak Bhavan Ke Or | Completed | 325000 | 165276 | 2020-01-08 | 2020-09-01
BHIND / MEHGAON | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034510332 — C C Road Samudayak Bhavan Se Vinod Ke Ghar Ke Or | Completed | 325000 | 189600 | 2020-01-08 | 2020-09-01
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702003017/RC/22012034537297 — CC ROAD CC ROAD SE MANDIR KI OOR | Completed | 139500 | 136800 | 2020-09-25 | 2021-12-02
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1702003017/RC/22012034537303 — CC ROAD ROAD SE PURA KI OOR | Completed | 93000 | 92340 | 2020-09-25 | 2021-03-20
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034591768 — Sudur Sampark Sadak Mukhya Marg Se Radhe Ke Khet Kee Or | Ongoing | 1482299 | 1449299.86 | 2021-11-11
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003017/RC/22012034591769 — Sudur Sampark Sadak Mukhya Marg Se Radhe Ke Khet Kee Or | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702003017/WC/22012034475929 — Talab Nirman Karya Sethari | Closed | 0 | 0 | 2018-04-01
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003017/WC/22012034556566 — Kachha Naala Naveen Pooran Singh Ke Khet Se Sulatan Singh Ke Khet Kee Or | Completed | 1498629.5 | 1303254 | 2020-12-16 | 2022-10-31
BHIND / MEHGAON | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003017/WC/22012034556575 — Kool Nirman Karya Nahar Se Jay Singh Ke Khet Kee Or | Closed | 0 | 0 | 2020-01-26
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003017/WC/22012034556577 — Kool Nirman Karya Vishambhar Ke Khet Se Mahipal Singh Ke Khet Kee Or | Completed | 409673.2 | 329236 | 2021-01-13 | 2021-12-02
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003017/WC/22012034556579 — Kool Nirman Karya Bamviya Se Sundar Singh Ke Khet Kee Or | Completed | 240524.44 | 156168 | 2021-03-13 | 2021-12-02
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702003017/WC/22012034628500 — Talab Nirman Karya Senthri 1 | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702003017/WC/22012034628501 — Talab Nirman Karya Senthri 2 | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702003017/WC/22012034631708 — Talab Nirman Karya Senthri 1 | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1702003017/WC/22012034631716 — Talab Nirman Karya Senthri 2 ri 1 | Closed | 0 | 0 | 2020-08-15
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003017/WC/22012034895827 — Talab Jeernoddhaar Ram Ke Khet Ke Paas | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003017/WC/22012034895829 — Talab Jeernoddhaar Road Ke Khet Ke Paas | Closed | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702003017/WC/22012034955813 — Dang Tank Road Ke Paas | Closed | 0 | 0 | 2022-04-14
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003017/WC/22012035019672 — NAVVEN TALAB NIRMAAN NAWAB SINGH K KHET KPASS | Closed | 0 | 0 | 2022-08-20
BHIND / MEHGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003017/WC/22012035063221 — dung tank nawab singh k khet k pass | Completed | 1472685.66 | 650845 | 2023-05-26 | 2026-04-17
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702003017/WC/22012035063222 — dung tank mohhar singh k ghar k pass | Closed | 0 | 0 | 2023-04-24
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003017/WC/22012035075749 — dung tank mohar singh k khet k pass | Closed | 0 | 0 | 2023-04-14
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702003017/WC/22012035075750 — dung tank mohar singh k khet k pass | Closed | 0 | 0 | 2023-04-14