## Work List
Exported on: 2026-10-11 15:25:39
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: DAGAR
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702003086/AV/22012034373314 — Shanti Dham Nirman Karya Dagar | Completed | 245000 | 236571 | 2019-02-21 | 2020-06-05
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Crematorium for Community / Repair and Maintenance of Crematorium | Repair & Maint of Community infrastructure | 1702003086/AV/22012034374280 — Shantidham nirman karya Bhagwan singh ka pura Dagar | Completed | 245000 | 240195 | 2019-02-21 | 2020-06-05
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003086/AV/22012034615574 — KHEL MEDAN KHIDAR PURA | Completed | 413138.69 | 246024 | 2022-05-13 | 2022-09-19
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003086/AV/4232 — Aanganbadi/Other Rural Infrastructure,DAGAR | Completed | 330000 | 298934 | 2016-02-18 | 2017-09-29
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003086/FP/22012034328957 — Nala nirman Shrikrishn ke makan se Pooran ke makan tak, Dagar | Completed | 1304000 | 1167094.32 | 2017-09-09 | 2023-09-04
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702003086/FP/22012034328958 — Nala nirman Dagar | Completed | 1349000 | 1334935.88 | 2017-09-09 | 2021-11-10
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034625126 — Band डायवर्जन चैनल baraso मेन रोड से नदी की ओर | Completed | 713310.12 | 717960 | 2021-05-28 | 2021-12-18
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034625127 — Band डायवर्जन चैनल भगवान सिंह पुरा रोड से नदी की ओर | Completed | 698204.08 | 733014 | 2021-05-28 | 2021-12-13
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034625254 — Band डायवर्जन चैनल MUNNI KE KHET SE SHER SINGH KE KHET KI OOR | Completed | 898368.49 | 615774 | 2022-05-23 | 2024-03-11
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034625255 — Band डायवर्जन चैनल MATHA DEEN KE KHET SE MEGNATH KE KHET KI OOR | Completed | 879197.64 | 533154 | 2022-05-23 | 2024-03-11
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034629552 — Contricon of water field chenal Nahar singh baba se nadi ki or | Completed | 822439.43 | 651168 | 2022-11-28 | 2022-12-29
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034629554 — Contraion of water field chenal sadak se nadi ki or | Completed | 803415.33 | 677484 | 2023-05-16 | 2025-05-31
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034631979 — Flood daivarjan chenal Nirman Babu ji ke khet se Hakim ke ke khet tak | Completed | 721241.41 | 627198 | 2023-05-16 | 2023-12-20
BHIND / MEHGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702003086/FP/22012034631996 — Flood daivarjan chenal Nirman Mahesh ke khet se nadi tak | Completed | 706506.37 | 611286 | 2023-04-02 | 2023-09-04
BHIND / MEHGAON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Desilting / Renovation of Community Water Harvesting Ponds for Community | Deepening / Desilting of Flood Channels | 1702003086/FP/9977522138 — नाला निर्माड वघेल मोहल्ला ताल से हरिजन बस्ती पुलिया तक | Completed | 96000 | 80100 | 2013-10-20 | 2014-04-15
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003086/IF/22012034352653 — Braksha Ropan Sadak kinare Baroason Road se Khidarpura Road ke Kinare | Completed | 335000 | 19064 | 2017-07-05 | 2020-05-15
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003086/IF/22012034353669 — Brakasha ropan Sankar ji ki Bagiya , mata ka mandir. Dagar | Completed | 335000 | 17000 | 2017-07-28 | 2020-05-15
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649688 — pashu shaid Ganga charan son of Puranlal | Completed | 89000 | 86291 | 2014-08-12 | 2015-09-09
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649689 — pashu shaid Chhote singh son of baldev singh | Completed | 89000 | 87267 | 2014-08-11 | 2015-10-09
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649690 — pashu shaid Chandr kumari son of Jaysingh | Completed | 89000 | 87133 | 2014-08-11 | 2015-07-09
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649693 — pashu shaid Dashrath son of Jagnath | Completed | 89000 | 87906 | 2014-08-12 | 2015-08-28
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649695 — pashu shaid Sher singh son of Bhageerath | Completed | 89000 | 88246 | 2014-08-12 | 2015-07-01
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649697 — pashu shaid Kuldeep son of Murari | Completed | 89000 | 87942 | 2014-11-04 | 2015-10-05
BHIND / MEHGAON | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993649714 — pashu shaid Hari shankar son of Sukh dayal | Completed | 89000 | 88544 | 2014-10-02 | 2014-10-16
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993689388 — pashu shet makrand singh / mahaveer | Completed | 115900 | 109059 | 2016-02-18 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993689391 — pashu shet rahul sharma / prahlad sharma | Completed | 115900 | 110392 | 2016-04-12 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993689393 — pashu shet dalveer / shrikrashn | Completed | 115900 | 106020.85 | 2016-05-25 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993689394 — pashu shet vishambar / gokul prasad | Completed | 115900 | 108797 | 2016-01-11 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993690010 — pashu shet ranveer sing / vijay singh | Completed | 115900 | 99443.55 | 2016-02-18 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993690015 — pashu shet ramlakhan / surajpal | Completed | 115900 | 104304.03 | 2016-04-12 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993690022 — pashu shet Vanvari / kaliyan | Completed | 115900 | 100884.46 | 2016-01-06 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993690023 — pashu shet munesh / prag singh | Completed | 115900 | 109557 | 2016-04-12 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993690025 — pashu shet jagdeesh / umaray | Completed | 115900 | 109557 | 2016-04-12 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993690032 — pashu shet rajendr singh / bhagwan singh | Completed | 115900 | 108797 | 2016-02-18 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993691071 — pashu shet Raja / Kaliyan | Completed | 115900 | 100427.7 | 2016-01-06 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993691085 — pashu shet Vimala beba / nathu singh | Completed | 115900 | 108797 | 2016-02-19 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993702873 — pashu shet rajaram / gokul | Completed | 115900 | 108797 | 2016-01-12 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993727185 — pashu shed ramsevak / Soorajpal | Completed | 115900 | 100911.8 | 2016-05-25 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003086/IF/9993727186 — pashu shet mataprasad / kalicharan | Completed | 115900 | 106727.32 | 2016-05-25 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/133827 — Construction of IAY House -IAY REG. NO. MP-02-003-086-001/27 | Completed | 14310 | 14044 | 2017-02-22 | 2018-09-01
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/133830 — Construction of IAY House -IAY REG. NO. MP-02-003-086-002/62 | Completed | 14310 | 13416 | 2017-02-22 | 2017-12-31
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/193331 — Construction of IAY House -IAY REG. NO. MP-02-003-086-001/29 | Completed | 14310 | 12018 | 2017-02-22 | 2023-05-25
BHIND / MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/1943547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5635720 | Completed | 17100 | 13812 | 2019-09-12 | 2022-09-19
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/203848 — Construction of IAY House -IAY REG. NO. MP-02-003-086-001/5 | Completed | 15030 | 14532 | 2017-02-22 | 2018-09-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/212932 — Construction of IAY House -IAY REG. NO. MP1110301 | Completed | 15030 | 15289 | 2017-01-25 | 2018-09-26
BHIND / MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2334098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4820843 | Completed | 17100 | 15540 | 2020-02-07 | 2020-09-09
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5618785 | Completed | 17100 | 13680 | 2020-06-26 | 2022-09-19
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5047811 | Completed | 17100 | 14838 | 2020-06-26 | 2021-12-14
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4507320 | Completed | 17100 | 15415.2 | 2020-06-26 | 2022-02-12
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4415058 | Completed | 17100 | 16340 | 2021-01-20 | 2021-12-14
BHIND / MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4391467 | Completed | 17100 | 14952 | 2020-01-23 | 2021-12-14
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3742132 | Completed | 17100 | 16068 | 2020-08-28 | 2022-02-12
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5496743 | Completed | 17100 | 15960 | 2020-06-26 | 2021-12-14
BHIND / MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/2341888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5246028 | Completed | 17100 | 13734 | 2021-04-26 | 2022-09-19
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3254173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2236937 | Completed | 17370 | 17136 | 2022-09-08 | 2023-02-20
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3254514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2396743 | Completed | 17370 | 17340 | 2022-09-01 | 2023-02-19
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3254974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2573430 | Completed | 17370 | 17136 | 2022-07-21 | 2022-10-30
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3261099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4132946 | Completed | 17370 | 16320 | 2022-06-22 | 2023-01-20
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3261325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4160076 | Completed | 17370 | 17068 | 2022-11-25 | 2023-09-21
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3266323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4699227 | Completed | 17370 | 17136 | 2022-09-20 | 2023-01-20
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3268125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4838990 | Completed | 17370 | 17136 | 2022-07-21 | 2022-11-01
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3268209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4846069 | Completed | 17370 | 15912 | 2022-07-21 | 2023-01-20
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3277395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5459092 | Completed | 17370 | 17136 | 2022-07-21 | 2022-10-30
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/3279567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5615878 | Completed | 17370 | 17136 | 2022-09-10 | 2023-01-30
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4149430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144125524 | Completed | 18360 | 17136 | 2022-09-20 | 2023-01-28
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4149437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144132549 | Completed | 18360 | 17136 | 2022-09-20 | 2023-01-25
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4149521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144639553 | Completed | 18360 | 18360 | 2022-09-01 | 2022-11-01
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4149522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144639626 | Completed | 18360 | 17238 | 2023-06-21 | 2023-08-24
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4151659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145489127 | Completed | 18360 | 14688 | 2022-11-25 | 2023-01-20
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4152242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142616584 | Completed | 18360 | 17204 | 2022-11-25 | 2023-09-07
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4152313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143091690 | Completed | 18360 | 17136 | 2022-09-20 | 2023-02-20
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4152314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143092423 | Completed | 18360 | 17901 | 2023-07-06 | 2023-08-21
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4164147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145507251 | Completed | 18360 | 12240 | 2022-09-08 | 2023-01-20
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4326336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145489002 | Completed | 18360 | 18292 | 2022-09-20 | 2023-08-16
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/4366905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143080486 | Completed | 18360 | 17901 | 2023-07-06 | 2023-08-21
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/545530 — Construction of IAY House -IAY REG. NO. MP3227009 | Completed | 15030 | 15300 | 2017-03-01 | 2018-05-15
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/697235 — Construction of IAY House -IAY REG. NO. MP1391607 | Completed | 15030 | 15600 | 2017-11-22 | 2018-09-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/726984 — Construction of IAY House -IAY REG. NO. MP1879796 | Completed | 15030 | 15636 | 2018-03-14 | 2018-09-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/728880 — Construction of IAY House -IAY REG. NO. MP1933794 | Completed | 17100 | 15036 | 2017-11-22 | 2021-12-18
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/745834 — Construction of IAY House -IAY REG. NO. MP2396407 | Completed | 15030 | 15504 | 2017-06-13 | 2018-09-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/748980 — Construction of IAY House -IAY REG. NO. MP2502312 | Completed | 15030 | 15552 | 2017-09-21 | 2018-09-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/749324 — Construction of IAY House -IAY REG. NO. MP2514913 | Completed | 15030 | 15480 | 2017-07-01 | 2018-05-15
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/750865 — Construction of IAY House -IAY REG. NO. MP2573239 | Completed | 15030 | 14520 | 2017-09-21 | 2018-09-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/759745 — Construction of IAY House -IAY REG. NO. MP2944719 | Completed | 15030 | 15516 | 2017-09-01 | 2018-09-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/771103 — Construction of IAY House -IAY REG. NO. MP3484908 | Completed | 15030 | 5160 | 2017-11-22 | 2018-09-25
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/772615 — Construction of IAY House -IAY REG. NO. MP3554157 | Completed | 17100 | 16524 | 2017-11-24 | 2021-12-18
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/773017 — Construction of IAY House -IAY REG. NO. MP3572353 | Completed | 15030 | 15588 | 2017-11-24 | 2018-10-12
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/884976 — Construction of IAY House -IAY REG. NO. MP1931342 | Completed | 15480 | 14580 | 2017-09-21 | 2018-09-29
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/886343 — Construction of IAY House -IAY REG. NO. MP1949737 | Completed | 15480 | 13168 | 2018-01-10 | 2018-09-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/918383 — Construction of IAY House -IAY REG. NO. MP2397237 | Completed | 15480 | 15528 | 2017-09-21 | 2018-09-29
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/927224 — Construction of IAY House -IAY REG. NO. MP2549791 | Completed | 15480 | 15588 | 2018-02-03 | 2018-09-01
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/946169 — Construction of IAY House -IAY REG. NO. MP2944832 | Completed | 15480 | 15516 | 2017-09-21 | 2018-09-29
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/948421 — Construction of IAY House -IAY REG. NO. MP3005767 | Completed | 15480 | 14484 | 2017-07-01 | 2018-09-29
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/967753 — Construction of IAY House -IAY REG. NO. MP3491977 | Completed | 15480 | 15564 | 2017-09-21 | 2018-09-29
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003086/IF/IAY/974106 — Construction of IAY House -IAY REG. NO. MP3651145 | Completed | 15480 | 15552 | 2017-09-21 | 2018-10-12
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/343 — मेढबंधान परिमाल / आशाराम कुशवाह डगर | Completed | 0 | 9600 | 2010-07-24 | 2010-07-30
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/344 — मेढबंधान लक्ष्‍मन / पुनू डगर | Completed | 0 | 8400 | 2010-05-14 | 2010-05-14
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/345 — मेढबंधान परिमाल / आशाराम डगर | Completed | 0 | 9600 | 2010-05-08 | 2010-05-08
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/346 — मेढबंधान लक्ष्‍मन / पुन्‍नू कुशवाह डगर | Completed | 0 | 11400 | 2010-07-31 | 2010-07-31
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/348 — मेढबंधान ज्ञान श्री / रामवरन डगर | Completed | 0 | 10200 | 2010-08-06 | 2010-08-12
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/349 — मेढबंधान रतीराम / भगवन्‍त कुशवाह | Completed | 0 | 11400 | 2010-08-14 | 2010-08-20
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/350 — मेढबंधान प्रहलाद / रामनाथ डगर | Completed | 0 | 10200 | 2010-09-03 | 2010-09-03
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/351 — मेढबंधान भागीरथ / प्‍यारेलाल | Completed | 0 | 10800 | 2010-09-24 | 2010-09-24
BHIND / MEHGAON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/52 — मेढ बंधान छोटीवाई/टीकाराम डगर | Completed | 24500 | 5460 | 2009-06-21 | 2009-01-27
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/647 — मेढबंधान अभिलाख /जगन्‍नाथ | Completed | 22000 | 20400 | 2010-09-30 | 2010-10-12
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/648 — मेढबंधान फूल सिंह / दशरथ सिंह | Completed | 9200 | 8400 | 2010-10-13 | 2010-10-19
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/894 — मेढबंधान वेटीवाई / दिग्विजय सिंह | Completed | 40000 | 13908 | 2011-10-23 | 2011-10-29
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/895 — मेढबंधान विशम्‍भर सिंह / गोकुल सिंह | Completed | 12000 | 11712 | 2011-10-16 | 2011-10-22
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/896 — मेढबंधान शेर सिंह / भागीरथ | Completed | 22000 | 20862 | 2011-07-08 | 2011-07-21
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/897 — मेढबंधान लाखन सिंह / गोपी डगर | Completed | 15000 | 13908 | 2011-08-05 | 2011-08-11
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/898 — मेढबंधान केशकली / राजेन्‍द्र सिंह | Completed | 26000 | 13908 | 2011-10-30 | 2011-11-05
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/899 — मेढबंधान ओमनारायण / सुखदयाल | Completed | 27000 | 25620 | 2011-09-18 | 2011-10-01
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/900 — मेढबंधान दशरथ सिंह / जगन्‍नाथ | Completed | 10000 | 9516 | 2011-10-02 | 2011-10-08
BHIND / MEHGAON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/902 — मेढबंधान डगर विशम्‍भर / गोकुल | Completed | 25000 | 23790 | 2011-07-22 | 2011-08-04
BHIND / MEHGAON | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003086/LD/964 — मेढबंधान डगर भगवान सिह / ज्ञान सिह | Completed | 0 | 26928 | 2012-10-26 | 2012-11-01
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/167 — सीसी रोड निर्माण बरासों रोड से हरिजन वस्‍ती से स्‍कूल की ओर | Completed | 193558 | 164320 | 2012-06-19 | 2012-07-25
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003086/RC/191 — पहुंचमार्ग मिटटी कार्य मैन रोड से ठाकुर मोहल्‍ला तक | Completed | 180000 | 171864 | 2012-04-01 | 2012-09-23
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034171561 — MITTI PAHUCHMARG MAIN ROAD PULIYA SE BHAGBANS | Completed | 490000 | 283824 | 2013-06-14 | 2014-03-20
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034177061 — pahuchmarg main road matadin ke makan se egs bhagb | Completed | 475000 | 361788 | 2013-08-01 | 2014-02-28
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034190260 — pahuchmarg nirmad gram khidarpura siloli marg se hirishankar ke kua tak | Completed | 214000 | 210094 | 2013-10-20 | 2014-02-04
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034190263 — c c road nirmad thakur mohalla se jagga shree shan | Completed | 210000 | 204596 | 2013-10-20 | 2014-05-04
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034208289 — murmi karan matadeen ke makan se e.g.s. lendra bha | Completed | 490000 | 449616 | 2014-03-07 | 2014-08-10
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034208336 — murmikaran main road puliya se bhagban singh ka pu | Completed | 490000 | 440656 | 2014-03-18 | 2014-07-11
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034226804 — MEHGAON mAIN ROAD SE VIJAY SINGH KE KHET TAK | Completed | 1496000 | 1035386 | 2014-08-07 | 2015-12-09
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034267464 — sgsy khaddarpura road se vishwanath rathore ke khet tak | Completed | 1496000 | 782885 | 2015-10-16 | 2016-05-09
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034282417 — murmikaran/bajarikaran Barason main road se khidarpura tak | Completed | 490000 | 433260 | 2016-03-22 | 2017-09-29
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034296233 — panchpar. c c road sher singh ke makan se main road ki oor | Completed | 211291 | 211182 | 2016-01-12 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034317206 — panchpar c c road harijan basti Dalvir ke makan se sardar ke darwaje & sukalal ke ghar ki oor | Completed | 242892 | 240686 | 2016-12-03 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034317215 — Panchpar c c road nirman lakhan ke makan se kamal singh ke makan tak | Completed | 210094 | 209248 | 2017-02-10 | 2017-09-29
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034317234 — panchpar c c jaylal ke makan se bharat ke makan tak | Completed | 210130 | 209069 | 2017-02-10 | 2017-09-29
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034334676 — c c road nirman SEVARAM SHAKYA KE MAKAN SE GANGARAM KUSHWAH KE MAKAN TAK | Completed | 103250 | 60888 | 2017-04-08 | 2019-01-07
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034335625 — c c road nirman CHHOTELAL JATAV KE MAKAN SE SARNAM JATAV KE MAKAN TAK | Completed | 59000 | 34056 | 2017-04-14 | 2017-09-29
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034335626 — panch c c road nirman BALVEER BAGHEL KE MAKAN SE GURDAYAL BAGHEL KE MAKAN TAK | Completed | 154875 | 87420 | 2017-04-14 | 2019-01-07
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034349453 — Gram sampark sadak Dagar se Phool singh ke pura tak | Completed | 3036000 | 2713624.43 | 2017-08-14 | 2020-05-15
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034350537 — Sudur gram sampark sadak Barason road se bhagwan singh pura tak | Completed | 860000 | 856197.16 | 2017-08-23 | 2018-12-26
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034350540 — Sudur gram sampark sadak Konhar-Barason road se siloli tak | Completed | 1448000 | 1343431.68 | 2017-08-22 | 2019-12-09
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034366044 — c c road nirman SHRIKRISHN KUSHWAH KE MAKAN SE JASRAM SHRIWAS KE MAKAN TAK | Completed | 13275 | 13072 | 2017-10-31 | 2019-01-07
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034366051 — c c road nirman GURUDAYAL KE DWAR SE MEGH SINGH KE BAGHEL KE DWAR TAK | Completed | 88500 | 73640 | 2017-10-31 | 2019-12-09
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034366056 — c c road nirman RAMSANEHI JATAV KE MAKAN SE SAMALE JATAV KE MAKAN TAK | Completed | 92925 | 60528 | 2017-10-31 | 2020-05-15
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/22012034366061 — c c road nirman SUNIL JATAV KE MAKAN RADHESHYAM KE MAKAN TAK | Completed | 66375 | 49044 | 2017-10-31 | 2019-03-20
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/22012034531275 — Sudur sampark sadak Barason Road se Mataru ke khet tak Dagar | Completed | 2478504.96 | 2373020.14 | 2020-08-25 | 2022-04-10
BHIND / MEHGAON | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003086/RC/27 — पहुचमार्ग मिटटी कार्य ग्राम खिदरपुरा तुलाराम मेहतर के द्वार से नदी तक | Completed | 275000 | 43002 | 2009-01-20 | 2010-09-02
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003086/RC/281 — सीसी रोड मय नाली शिवसिह के मकान से शाप्राशाल तक | Completed | 193558 | 112464 | 2013-02-01 | 2013-02-21
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003086/RC/282 — सीसी रोड मय नाली शिवसिह के मकान से शाप्राशाला तक | Completed | 0 | 77400 | 2012-11-10 | 2013-02-21
BHIND / MEHGAON | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003086/WC/22012034446229 — Naveen Talab Nirman Bhagwan singh pura | Completed | 896000 | 878360 | 2019-03-08 | 2024-03-11
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034706715 — नवीन तालाब निर्माण मकरंद के खेत के पास | Completed | 1192780.1 | 1131760.6 | 2021-05-29 | 2021-12-18
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of gabion Spur for Comm / Repair and Maintenance of Wire crate (gabion) Spur for Community | Repair & maint of Water Harvesting Structures | 1702003086/WC/22012034719386 — NAMIN TALAB NIRMAN SANTHI DHAM KE PASS DAGAR | Completed | 1430184.89 | 1200577.6 | 2021-06-15 | 2022-11-02
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1702003086/WC/22012034719395 — NAMIN TALAB NIRMAN BHAGABAN SINGH KE PURA ROAD PAR | Completed | 1492882.07 | 1096371.6 | 2021-06-01 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034733232 — KHET TALAB RAMSANEHI KE KHET KE PASS | Completed | 337715.44 | 144750 | 2021-06-09 | 2022-11-20
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034733237 — KHET TALAB MANSARAM KE KHET KE PASS | Completed | 337715.44 | 144750 | 2021-06-09 | 2022-11-20
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034733241 — KHET TALAB MATRU KE KHET KE PASS | Completed | 337715.44 | 120432 | 2021-06-12 | 2022-11-21
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034733248 — KHET TALAB CHITAMAN KE KHET KE PASS | Completed | 337715.44 | 121590 | 2021-06-12 | 2026-04-20
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034753131 — नवीन तालाब निर्माण हार में | Completed | 1490698.49 | 1058715 | 2022-01-24 | 2022-10-31
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034753173 — KHET TALAB BABHURAM | Completed | 337715.44 | 183600 | 2022-06-07 | 2022-11-21
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034753198 — KHET TALAB BASHUDEB | Completed | 337715.44 | 195840 | 2022-06-07 | 2022-11-21
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034753221 — KHET TALAB DINESH | Completed | 337715.44 | 177480 | 2022-06-07 | 2022-11-21
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034765897 — NAMIN TALAB NIRMAN GOPIRAM DHANUK KE KE KHET KE PASS | Completed | 1474081.65 | 1196980.25 | 2021-06-21 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034765900 — NAMIN TALAB NIRMAN RAJARAM KE KHET KE PASS | Completed | 1468502.65 | 1235703.6 | 2021-06-24 | 2022-11-02
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034765903 — NAMIN TALAB NIRMAN CHINTAMAN KE KHET KE PASS | Completed | 1430025.55 | 1186973.25 | 2021-07-12 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034765906 — NAMIN TALAB NIRMAN SIKANDAR KE KHET KE PASS | Completed | 1454866.3 | 1238020.31 | 2021-08-10 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034794229 — नवीन तालाब निर्माण कार्य प्रजापति के खेत के पास | Completed | 1402786.81 | 1294375.91 | 2021-08-10 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034794230 — नवीन तालाब निर्माण कार्य डगर | Completed | 1409292.97 | 1220650.37 | 2021-08-10 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034796227 — NAMIN TALAB HARJAN BASHTI KE PASS KHIDARPURA | Completed | 1483279.1 | 975101 | 2022-01-24 | 2024-01-16
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034855927 — NAMIN TALAB NIRMAN BARSO MOJE KE PASS | Completed | 1473041.17 | 1209201 | 2022-04-10 | 2022-10-31
BHIND / MEHGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1702003086/WC/22012034855928 — NAMIN TALAB NIRMAN VIRGAMA BOJE KE PASS | Completed | 1474055.01 | 1291209 | 2022-04-10 | 2022-10-31
BHIND / MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702003086/WH/19960576 — Talab Jirnodhar Bhagwan singh ka pura , Dagar | Completed | 84000 | 61920 | 2017-05-22 | 2019-12-09