## Work List
Exported on: 2026-10-07 13:28:20
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: MEHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003095/AV/22012034536303 — PANCHAYAT BHAVAN NIRMAN KARYA GP MEHARA | Ongoing | 257000 | 121980 | 2020-09-17
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1702003095/AV/22012034563063 — PAKKA CHABUTRA NIRMAN KRASHI UPARJAN KENDRA MEHARA | Ongoing | 307550.88 | 45204 | 2021-03-24
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Bio Drainage / Block Plantation of Biodrainage Trees in fields for Community | Works for Flood Control and Protection | 1702003095/FP/22012034204434 — naala nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Flood Control and Protection | Bio Drainage / Block Plantation of Biodrainage Trees in fields for Community | Works for Flood Control and Protection | 1702003095/FP/22012034204436 — naala nirman | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003095/IF/22012034352225 — braksha ropan karya mehara | Deleted | 0 | 0 | 2017-04-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003095/IF/22012034352228 — braksha ropan kary lalpura | Completed | 335000 | 23708 | 2017-08-01 | 2021-10-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003095/IF/22012034352234 — braksha ropan karay chandrapura | Completed | 335000 | 9288 | 2017-07-04 | 2021-10-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003095/IF/22012034352258 — braksha ropan karay mehara | Closed | 335000 | 0 | 2017-04-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003095/IF/22012034352260 — braksha ropan karay lalpura | Completed | 335000 | 8772 | 2017-08-01 | 2021-10-14
BHIND / MEHGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702003095/IF/22012034352282 — braksha ropan karay chandrapura | Completed | 335000 | 26288 | 2017-08-01 | 2021-10-14
BHIND / MEHGAON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1702003095/IF/22012034767145 — Med bandhan shivraj singh so Ramsiya singh | Deleted | 0 | 0 | 2021-04-14
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1702003095/IF/22012035137188 — अमृत वाटिका कार्य शास.प्रा. विद्यालय मेहरा | Ongoing | 55847.4 | 6630 | 2023-09-17
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697756 — pashushed -suresh s/o jivanlal | Completed | 115900 | 114756 | 2016-01-15 | 2016-02-04
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697929 — pashushed-lakhan/jabar singh | Completed | 115900 | 109827 | 2015-12-27 | 2016-02-03
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697936 — pashushed-kamlesh/vadri | Completed | 115900 | 109282 | 2015-12-27 | 2016-05-08
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697940 — pashushed-tulsiram/amaan singh | Completed | 115900 | 113007 | 2015-12-27 | 2016-01-20
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697942 — pashushed-mehtaab/raamsiya | Completed | 115900 | 113961 | 2015-12-27 | 2016-01-20
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697943 — pashushed-kaliyaan/raghu | Completed | 115900 | 113961 | 2015-12-27 | 2016-01-20
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697944 — pashushed-lokman/serman | Deleted | 0 | 0 | 2015-10-03
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697951 — pashushed-lokman/ serman | Completed | 115900 | 113961 | 2015-12-27 | 2016-01-20
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697952 — pashushed- raamswaroop/ dayaram | Completed | 115900 | 114438 | 2015-12-27 | 2016-02-03
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993697958 — pashushed-suresh/ jeevanlaal | Deleted | 115900 | 0 | 2015-12-23
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699933 — pashushed- raju / ramsiya | Completed | 115900 | 114597 | 2016-01-15 | 2016-02-04
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699939 — pasushed- mulchandra/ hare singh | Completed | 115900 | 114120 | 2016-01-05 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699947 — pashushed-gambhir/ganga singh | Completed | 115900 | 114120 | 2016-01-29 | 2016-02-13
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699949 — pashushed-mohar singh/raamdeen | Deleted | 115900 | 0 | 2015-10-03
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699952 — pasushed-bhagwandas/goti | Completed | 115900 | 114756 | 2016-01-15 | 2016-02-04
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699955 — pashushed-sitaram/harpal | Completed | 115900 | 114756 | 2016-01-15 | 2016-02-04
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993699962 — pashushed-satrughan/tilak singh | Completed | 115900 | 114756 | 2016-01-15 | 2016-02-04
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993702574 — medbandhan- bajjo w/o ramdulare mishra | Completed | 37900 | 26712 | 2016-02-11 | 2016-02-24
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993702577 — medbandhan- bajjo w/o ramdulare mishra | Deleted | 0 | 0 | 2015-10-03
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993702585 — medbandhan- janved,ramjilaal s/o mutte jatav | Completed | 59800 | 45792 | 2016-02-11 | 2016-02-24
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993707001 — pashushed-rajesh s/o bati | Deleted | 115900 | 0 | 2015-12-25
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993707132 — pashushed- rajesh s/o bati | Completed | 115900 | 113166 | 2016-01-29 | 2016-02-13
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993707135 — pashushed- rakesh s/o jaikam | Completed | 115900 | 114120 | 2016-01-29 | 2016-02-13
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710722 — pashushed - devlaal / kashiram | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710724 — pashushed - ramdulare / jai singh | Closed | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710725 — pashushed - gulab singh / devicharan | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710726 — pashushed - lakhan / suraj pal | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710727 — pashushed - ratiram / gebu | Completed | 115900 | 110674 | 2016-04-03 | 2016-04-18
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710728 — pashushed - amar singh / parbhole | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710729 — pashushed - harsevak / panne | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710730 — pashushed - aasharam / amaan singh | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710731 — pashushed - kushvir singh / parvat singh | Completed | 115900 | 111622 | 2016-02-11 | 2016-05-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710732 — pashushed - veer singh / bhawani | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710834 — pashushed-arvind singh/jai singh | Completed | 115900 | 112212 | 2016-02-11 | 2016-02-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710883 — pashushed- raamveer / heera | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710884 — pashushed- mohan / aasharam | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710886 — pashushed- dilip singh / ramcharan singh | Completed | 115900 | 110674 | 2016-04-03 | 2016-04-18
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993710888 — pashushed- janved / gutte | Completed | 115900 | 109191 | 2016-02-22 | 2016-03-08
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712336 — pashushed- ramnaresh / rambaks | Completed | 115900 | 111640 | 2016-02-22 | 2016-05-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712348 — pashushed- pooran / dwarika | Completed | 115900 | 109855 | 2016-02-22 | 2016-05-08
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712474 — pashushed- bhole / chandan | Completed | 115900 | 111676 | 2016-05-09 | 2016-05-22
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712478 — pashushed- ramesh / jwaali | Completed | 115900 | 110674 | 2016-04-03 | 2016-04-18
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712480 — paashushed- judawan / deene | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712481 — pashushed- kalyaan / shripal | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712483 — pashushed- kiledar / bharose | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993712485 — pashushed- shrimant / gangole | Deleted | 115900 | 0 | 2016-02-10
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727024 — pashushed- balveer/jasvant | Deleted | 115900 | 0 | 2016-04-15
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727067 — pashushed- surendra / ramprakash | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727085 — pashushed- anil / padam | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727092 — pashushed- avdhesh / gyaprasad | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727097 — pashushed- karan/ jagat | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727105 — pashushed- ram mahesh/ bhagirath | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727109 — pashushed- sujan / jahar | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727110 — pashushed - keshav / gyaan singh | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727111 — pashushed - ripudaman / gyan singh | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727115 — pashushed - suresh / tulsiram | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727119 — pashushed - santosh / vidhyaram | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727120 — pashushed- arvind / jeevanlal | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727122 — pashushed - sitaram / durjan | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727123 — pashushed - shishupal / vindravan | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727124 — pashushed - pradip / ramlakhan | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727126 — pashushed - ramjilal / baburam | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727127 — pashushed - ramhet / pooran | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727131 — pashushed - kok singh / balram | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727133 — pashushed - bharat / bedri | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727136 — pashushed - kamlesh / lokman | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727139 — pashushed - gyaanvati / tej singh | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727142 — pashushed - harcharan / ghamandi | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993727144 — pashushed - ramjilal / gutte | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727182 — medbandhan - surendra / ramprakash | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727185 — medbandhan - anil / padam | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727188 — medbandhan - avdhesh / gyaprasad | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727193 — medbandhan - keshav / gyaan singh | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727197 — medbandhan - ripudaman / gyaan singh | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727199 — medbandhan - shishupal / vindravan | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727200 — medbandhan - pradip / ramlakahan | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702003095/IF/9993727203 — medbandhan - gyanvati / tej singh | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993739569 — pashushed nirman - ramsiya s/o ghasiram | Completed | 115900 | 109672 | 2016-05-09 | 2016-05-22
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702003095/IF/9993739590 — pashushed nirman - om prakash | Completed | 115900 | 111676 | 2016-05-09 | 2016-05-22
BHIND / MEHGAON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/2140271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5024238 | Approved | 23490 | 0 | 2019-06-24
BHIND / MEHGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/3286270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5382545 | Approved | 23490 | 0 | 2021-10-25
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/3286776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5538091 | Completed | 17370 | 17136 | 2022-05-06 | 2022-10-30
BHIND / MEHGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/3304902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5574166 | Completed | 17370 | 17238 | 2023-05-10 | 2023-09-04
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/3388533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2743851 | Completed | 17370 | 17136 | 2022-07-20 | 2022-10-30
BHIND / MEHGAON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/4325693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143366657 | Completed | 18360 | 15096 | 2022-12-10 | 2024-11-06
BHIND / MEHGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/4804175 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143373283 | Approved | 23490 | 0 | 2024-09-14
BHIND / MEHGAON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702003095/IF/IAY/561467 — Construction of IAY House -IAY REG. NO. MP3713329 | Completed | 15030 | 12615 | 2017-02-04 | 2018-05-07
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003095/LD/22012034307862 — shanti dhaam mehra | Completed | 245000 | 238792 | 2017-03-25 | 2020-07-29
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702003095/LD/22012034310249 — shanti dham lalpura | Completed | 180000 | 179340 | 2017-04-14 | 2020-07-29
BHIND / MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702003095/LD/22012034310251 — shantidham chandrapura | Completed | 180000 | 179340 | 2017-08-25 | 2020-08-20
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003095/LD/509 — मेढबंधान मेहरा चन्‍दन / भाव सिह | Completed | 13000 | 6000 | 2010-05-16 | 2010-11-16
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003095/LD/510 — मेढबंधान जगत सिह / कलयाण सिह | Completed | 13000 | 6500 | 2010-06-22 | 2010-06-28
BHIND / MEHGAON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702003095/LD/511 — मेढबंधान मेहरा फूला बेबा / ग्‍याप्रसाद | Completed | 20000 | 7300 | 2010-05-16 | 2010-11-23
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702003095/OP/9425890116 — baundriwall nirman- sha. pra. shala bhavan chandrapura | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702003095/OP/9425890118 — baundriwall nirman - sha. pra. shala bhavan lalpura | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702003095/OP/9425890119 — baundriwall nirman - sete light shala mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702003095/OP/9425890120 — baundriwall birman- sha. ma. shala bhavan mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702003095/OP/9425890121 — panchyat bhawan nirman - gram panchyat mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702003095/PG/22012034304709 — play ground lalpura | Completed | 186000 | 184984 | 2017-04-14 | 2020-11-13
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003095/PG/22012034304712 — play ground chandrapura | Deleted | 186600 | 0 | 2017-01-26
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702003095/PG/9425888698 — playground- gram mehra | Completed | 353000 | 30242 | 2017-03-25 | 2019-08-01
BHIND / MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003095/RC/109 — पहुचमार्ग मेहरा चंद्रपुरा पीपल से मैन रोड एवं स्‍कूल से दर्शन सिह के पुरा तक | Completed | 0 | 40626 | 2011-07-23 | 2011-07-28
BHIND / MEHGAON | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003095/RC/165 — मिटटी कार्य पहुचमार्ग हरिजन कॉलोनी से मैन रोड तक मेहरा | Completed | 0 | 96380 | 2011-10-25 | 2011-11-07
BHIND / MEHGAON | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003095/RC/2 — मिट्रटीकार्य पहुंचमार्ग मेहरा महावीर मंदिर से रूहेरा मेंडे तक | Completed | 183600 | 11135 | 2008-05-04 | 2016-08-12
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034167686 — c c road rampal patel ke darwaje se gon baba ke st | Completed | 205000 | 196760 | 2013-05-15 | 2013-07-10
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034167688 — murmikaran shivsingh ke darwaje ki orr chandrapura | Completed | 67000 | 63164 | 2013-05-28 | 2014-04-17
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034194379 — kok singh ke dwar se darshn singh ke dwar ki oor | Completed | 229433 | 223753 | 2014-02-02 | 2014-05-28
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034194388 — man singh ke dwar se mata mandir ki oor | Completed | 229433 | 226381 | 2014-02-02 | 2014-05-28
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034203052 — c c road gyan singh kushwah ke darwaje se shriman | Completed | 226810 | 217442.7 | 2014-03-06 | 2014-05-28
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034203057 — c c road main road se kuwar baba ki oor | Completed | 226810 | 223803 | 2014-03-07 | 2014-05-28
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034225150 — khet sadak-badri singh ke khet se narottam singh k | Completed | 1490000 | 1308659.7 | 2014-07-18 | 2016-01-28
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034225152 — khet sadak-lajjaram ke khet se jai narayan ke khet | Completed | 1022000 | 822654.88 | 2014-07-18 | 2016-01-18
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034227912 — cc road nirmad-hakim ke dwar se bal singh ke dwar ki or | Completed | 237240 | 224920 | 2014-08-31 | 2014-10-22
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034294760 — khet sadak -batiram prajapati ke khet se sirnaam singh ke khet tak | Deleted | 1419017 | 0 | 2016-01-01
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034294771 — khet sadak- hanuman ji ke mandir se veersingh tomar ke khet tak | Completed | 1296072 | 311958 | 2016-01-07 | 2016-12-30
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034294909 — c.c.road-mata mandir se ramvaran ke darwaje ki or | Deleted | 273000 | 0 | 2016-01-01
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034295157 — c.c.road- jagendra ke dwar se ramdas ke dwar ki or | Deleted | 251000 | 0 | 2016-01-01
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034295162 — c.c.road- padam ke dwar se hanuman ji ke get ki or | Completed | 210000 | 211755 | 2016-04-03 | 2016-12-10
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034295165 — kharanja nirman- gond baba ke sthan se setelight shala ki or | Deleted | 714000 | 0 | 2016-01-01
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034295172 — kharanja nirman- main road se shiv singh ke makan ki or chandrapura | Completed | 477000 | 475366 | 2016-01-15 | 2019-08-01
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034299027 — khet sadak- kailash pandit ke khet se jagat singh ki or | Completed | 1383263 | 148296 | 2016-04-03 | 2016-08-12
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308515 — khet sadak- kunwar baba ke sthan se motiram chakva ke khet tak mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308517 — khet sadak - hanuman ji ke mandir se nathu singh ke tubewel tak mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308519 — khet sadak- krishna mehtar ke ghar ke bagal se babu singh ke khet tak mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308520 — khet sadak- sernam singh ke tubewel se rai singh ke khet tak mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308522 — khet sadak - pushp baba ke sthan se sidhh baba ke sthan tak mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308523 — khet sadak- santu baba ke khet se balveer singh ke khet tak mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308524 — khet sadak - sha. pra. vidhalaye se sidhh baba ke sthan tak lalpura | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034308535 — c.c.road- mangal singh kushwah ke bagal se jasrath singh kushwah ki or mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034308536 — c.c.road- hoti prajapati ke dwar se batiram prajapati ke dwar ki or mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034308537 — c.c.road- lakhan patwa ke dwar se aasharam dhobi ke dwar ki or lalpura | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034308538 — c.c.road- narendra singh ke dwar se school wali rasta ki or chandrapura | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308569 — kharnja nirman- mangal kushwah ke dwar se missil school ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034308570 — kharanja nirman- gambhir ke dwar se setelight shala ki or | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034313891 — c.c. road mangal singh kushwah ke ghar ke bagal se jasrath kushwah ke makan ki or | Completed | 258000 | 107214 | 2017-02-26 | 2017-09-30
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034313892 — c.c.road- jagendra ke dwar se ramdas ke dwar ki or mehra | Completed | 251000 | 243890 | 2017-02-26 | 2017-03-18
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034313893 — c.c. road- mata mandir se ramvaran ke darwaje ki or mehra | Completed | 273000 | 271224 | 2016-12-22 | 2017-01-25
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034333258 — c.c. Road gyan singh ke makan se kushvir ke makan tak | Completed | 18000 | 16842 | 2017-03-25 | 2019-08-20
BHIND / MEHGAON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034333259 — c.c.Road | Deleted | 0 | 0 | 2017-01-26
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034362084 — sudur sampark road-gram mehra se sanjaypura road tk | Completed | 2400000 | 2207165.51 | 2017-09-29 | 2020-06-20
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362277 — c.c. road may naali nathu prajapati ke makan ke bagal se motiram ke kuaa tak | Completed | 15000 | 1032 | 2017-09-30 | 2020-06-04
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362279 — c.c. road may naali - hardayal kushwah ke dwar se harvansh kushwah ke makan tak | Completed | 18000 | 11040 | 2017-09-30 | 2020-08-21
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362280 — c.c. road may naali ramdulare ke makan se suresh ke makan tak | Completed | 133000 | 134088 | 2017-09-30 | 2019-05-01
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362282 — c.c. road may naali shivdayal ke dwar se balveer ke dwar tak | Closed | 42000 | 0 | 2017-04-14
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362283 — c.c. road may naali - seetaram kadere ke makan se shashkie prathmik vidhyalay tak | Completed | 88000 | 72648 | 2017-09-30 | 2020-08-21
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362285 — c.c. road may naali - balveer singh ke makan se shashkie prathmik vidhyalay ke raste tak | Completed | 22050 | 1032 | 2017-09-30 | 2019-12-20
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362286 — c.c. road may naali mohan singh ke makan se jitendra singh ke makan tak | Completed | 31000 | 24972 | 2017-09-30 | 2020-08-21
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362287 — c.c. road may naali - megh singh ke makan se shrimant kori ke makan tak | Completed | 29000 | 23832 | 2017-09-30 | 2020-06-24
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362288 — cc. road may naali ramjilal ke makan se asharam baretha ke makan tak | Completed | 31000 | 34188 | 2017-09-30 | 2020-06-04
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362291 — pakki naali nirman - chandan master ke dwar se jhada ke makan tak | Completed | 5000 | 5256 | 2017-09-30 | 2019-08-20
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362292 — pakki naali nirman - madhu prajapati ke dwar se judawan ke dwar tak | Completed | 23100 | 1032 | 2017-09-30 | 2017-10-20
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362293 — pakki nali nirman - kalicharan kushwah ke makan se hanuman ji ke mandir tak | Completed | 62000 | 25320 | 2017-09-30 | 2019-12-22
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034362294 — pakki naali nirman - govind singh ke dwar se raghunath ke ghar tak | Completed | 27000 | 25320 | 2017-09-30 | 2019-12-20
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034372971 — cc road | Deleted | 0 | 0 | 2017-10-02
BHIND / MEHGAON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034382428 — C C road | Deleted | 0 | 0 | 2017-10-02
BHIND / MEHGAON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034442124 — cc road | Deleted | 0 | 0 | 2019-01-26
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034523289 — sudoor sampark sadak gram lalpura se shanti dham ki oor | Closed | 0 | 0 | 2020-05-23
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702003095/RC/22012034533538 — KHET SADAK NIRMAN HARISHCHANDRA KE KHET SE AMAR SINGH KE KHET KI OR | Closed | 0 | 0 | 2020-07-05
BHIND / MEHGAON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034560293 — CC ROAD UDAYVEER KE MAKAN SE PURUSBABA KE CHABUTARA TAK MEHARA | Completed | 100000 | 111755 | 2021-02-22 | 2022-02-27
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034567535 — CC ROAD MAY NALI NIRMAN MUKHY MARG SE TILAK SINGH KE MAKAN TAK | Completed | 34000 | 32850 | 2022-02-27 | 2022-10-31
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034619350 — cc road niman mukhya marg se visambhar ke makan tk gram chandra pura | Deleted | 0 | 0 | 2021-10-02
BHIND / MEHGAON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/22012034619351 — cc road niman mukhya marg se visambhar ke makan tk gram chandra pura | Deleted | 0 | 0 | 2021-11-16
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/227 — सीसी रोड निर्माण हरप्रसाद के द्वार से कल्‍याण जाटव के मकान तक | Completed | 193558 | 172086 | 2012-09-21 | 2013-01-17
BHIND / MEHGAON | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/228 — सीसी रोड निर्माण मय नाली के ग्राम मेहरा शासकीय प्राथमिक शाला से महामन्‍त सिह के द्वार तक | Completed | 0 | 120060 | 2012-09-21 | 2012-10-29
BHIND / MEHGAON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702003095/RC/299 — c c road gyan sing ke dwar se sishupal singh ke dw | Completed | 203000 | 127088 | 2013-05-15 | 2013-07-10
BHIND / MEHGAON | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702003095/RC/3 — पहुंच मार्ग मिट्रटीकार्य मेहरा से हरिजनकालॉनी अमायन तक | Completed | 164000 | 32625 | 2008-05-18 | 2010-12-25
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034240446 — shouchalaya nirmad gram mehra 1 | Completed | 54000 | 52730 | 2014-04-20 | 2014-10-20
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1702003095/RS/22012034240725 — shauchalay nirman2 gram mehra | Completed | 54000 | 53829 | 2014-07-21 | 2014-10-03
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034266307 — shauchalay nirmad gp mehra 3 | Completed | 54000 | 52730 | 2014-09-20 | 2014-10-03
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034266316 — sochalya nirmad gp mehra -4 | Completed | 54000 | 52730 | 2014-09-20 | 2014-10-03
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1702003095/RS/22012034266320 — socalya nimad gp mehra-5 | Completed | 54000 | 51160 | 2014-10-08 | 2014-10-14
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034266325 — socalya nirmad gp mehra-6 | Completed | 54000 | 52730 | 2014-09-26 | 2014-10-15
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034266329 — socalya nirmad gp mehra-7 | Completed | 54000 | 52730 | 2014-09-26 | 2014-10-15
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034266333 — socaalya nirmad gp mehra-8 | Completed | 54000 | 54928 | 2014-10-08 | 2014-10-21
BHIND / MEHGAON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702003095/RS/22012034276345 — scoachalya nirmad gp mehra 9 | Deleted | 54000 | 0 | 2014-11-12
BHIND / MEHGAON | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702003095/RS/22012035136350 — Community Toilet Gram Mehra | Ongoing | 43000 | 28971 | 2025-05-28
BHIND / MEHGAON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702003095/WC/22012034324268 — talab unnyan karya lalpura | Completed | 101000 | 94600 | 2017-05-12 | 2017-09-10
BHIND / MEHGAON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702003095/WC/22012034554318 — naveen talab nirman lalpura | Completed | 1659959.72 | 1448305.97 | 2020-07-23 | 2024-10-10
BHIND / MEHGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702003095/WC/22012034554319 — khet talab nirman bhuri w/o surendra singh | Closed | 0 | 0 | 2020-05-23
BHIND / MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702003095/WC/22012035301110 — डग वैल रिचार्ज पिट हनुमान जी मंदिर के पास ग्राम मेहरा | Deleted | 0 | 0 | 2025-04-17
BHIND / MEHGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702003095/WC/22012035301112 — डगवैल रिचार्ज पिट हनुमानजी मंदिर के कूप पर ग्राम मेहरा | Physically Completed | 30711.54 | 25569.5 | 2025-05-13 | 2026-04-16
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Model Talab / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702003095/WH/19955649 — talab unnayan karya gram mehra | Deleted | 0 | 0 | 2016-01-26
BHIND / MEHGAON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Excavation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702003095/WH/19955650 — talab unnayan karya gram lalpura | Deleted | 1467000 | 0 | 2016-01-27