## Work List
Exported on: 2026-09-06 17:25:10
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BAKNASA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004014/AV/22012034374867 — शांतीधाम निर्माण कार्य पुरोहित का पुरा ग्राम बकनासा ग्राम पंचायत बकनासा | Completed | 180000 | 161621.93 | 2018-10-05 | 2020-05-15
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702004014/AV/22012034389335 — सामुदायिक भवन निर्माण कार्य बकनासा ग्राम पंचायत बकनासा | Completed | 180000 | 184280 | 2018-10-05 | 2020-03-01
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702004014/AV/22012034389395 — सामुदायिक भवन निर्माण कार्य बम्‍होरा ग्राम पंचायत बकनासा | Completed | 180000 | 195476 | 2018-12-20 | 2020-03-01
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004014/AV/22012034628114 — शांतीधाम निर्माण कार्य लालनकापुरा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2022-08-15
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Farm Forestry -Comm / Wasteland Block Plantation of Farm Forestry Trees for Community | Plantation | 1702004014/DP/22012034522020 — गोचर / चरनोई भूमि पर चारागाह विकास कार्य ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1702004014/DP/22012034600525 — Amrit vatika Amrit sarobar pancham singh ke khet ke pass baknasha | Closed | 0 | 0 | 2023-06-05
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004014/FP/GIS/28712 — नवीन नाला निर्माण कार्य बम्‍होरा में मुख्‍य मार्ग से लेकर देबू के कुआ तक ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2021-07-01
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004014/IF/22012034352334 — vriksharopan karya school parisar baknasa | Completed | 335000 | 32852 | 2017-06-20 | 2019-08-27
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004014/IF/22012034354249 — वृक्षारोपण कार्य सड़क किनारे बहमोरा | Completed | 335000 | 1032 | 2017-08-01 | 2019-08-27
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004014/IF/22012034354742 — BRAKSHA ROPAN KARYA SAMUDHYAAK JAGAH BAMHOURA | Closed | 335000 | 0 | 2017-06-20
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004014/IF/22012034354744 — BRAKSHA ROPAN KARYA SAMUDHYAK JAGAH BAKNASA | Closed | 335000 | 0 | 2017-06-20
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Afforestation of wasteland Forestry trees for individual | Plantation | 1702004014/IF/22012035137145 — अमृत वाटिका (वृक्षारोपण कार्य) अमृत सरोवर पंचम सिंह तोमर के खेत के पास ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2023-04-14
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004014/IF/22012035420777 — khet talab nirman karya ramdun putra ram bharose ke khet par baknasa | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004014/IF/22012035420836 — khet talab nirman karya chote singh putra rambharose ke khet par baknasa | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004014/IF/22012035458716 — khet talab nirman karya ramdun putra ram bharose ke khet par baknasa | Ongoing | 147621.16 | 522 | 2025-05-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004014/IF/22012035458741 — khet talab nirman karya chote singh putra rambharose ke khet par baknasa | Ongoing | 147621.16 | 15921 | 2025-05-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004014/IF/22012035541167 — khet talab nirman karya bangali singh purta deevan singh ke khet par baknasa | Ongoing | 147621.16 | 96309 | 2025-06-10
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926734584 — MEDBANDHAN KARYA BHANTA S/O ROSHAN | Completed | 17100 | 16014 | 2014-06-03 | 2014-09-01
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926734588 — MEDBANDHAN KARYA NARESH S/O DURJAN | Completed | 41800 | 28260 | 2014-06-03 | 2014-09-01
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926738771 — MEDBANDHAN KARYA BATURI S/O RAMHET | Completed | 17100 | 14130 | 2014-06-17 | 2014-09-01
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926738772 — MEDBANDHAN KARYA KHIYALI S/O MUNGARAM | Completed | 15000 | 13188 | 2014-06-17 | 2014-09-01
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926738774 — MEDBANDHAN KARYA RAMSHNEHI S/O NADARI | Completed | 17100 | 13188 | 2014-06-17 | 2014-09-01
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926738776 — MEDBANDHAN KARYA KAILASH NARAYAN S/O JHAMANN | Completed | 9600 | 8949 | 2014-06-17 | 2014-09-01
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004014/IF/9926738778 — MEDBANDHAN KAREYA FIROJ S/O ASARFI KHA | Completed | 14700 | 14130 | 2014-06-17 | 2014-09-01
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004014/IF/9993709270 — पशुशेड निर्माण कार्य राधेश्‍याम पुत्र मातादीन | Completed | 95000 | 81465.5 | 2016-02-02 | 2017-06-25
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004014/IF/9993709273 — पशुशेड निर्माण कार्य गंगाप्रसाद पुत्र सुबालाल | Completed | 95000 | 78356.6 | 2016-02-02 | 2017-06-25
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004014/IF/9993709275 — पशुशेड निर्माण कार्य रामवीर पुत्र मातादीन | Completed | 95000 | 80264.6 | 2016-02-02 | 2017-06-25
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004014/IF/9993709276 — पशुशेड निर्माण कार्य रूपसिंह पुत्र चतुरीलाल | Completed | 95000 | 80264.6 | 2016-02-02 | 2017-06-25
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004014/IF/9993725483 — पशुशेड निर्माण कार्य ग्राम बकनासा | Deleted | 0 | 0 | 2016-01-26
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/1871452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4617047 | Completed | 15660 | 14616 | 2018-11-20 | 2019-07-01
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/1871622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4736771 | Completed | 15660 | 14616 | 2018-11-20 | 2019-06-01
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/1872420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4703091 | Completed | 17100 | 13762 | 2018-11-20 | 2021-05-22
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/1893272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4584915 | Completed | 15660 | 13420 | 2018-11-20 | 2019-11-25
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/239471 — Construction of IAY House -IAY REG. NO. MP1498274 | Completed | 15030 | 15480 | 2017-02-21 | 2018-03-05
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/239992 — Construction of IAY House -IAY REG. NO. MP1509721 | Completed | 15030 | 14939 | 2017-02-21 | 2018-05-04
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/266618 — Construction of IAY House -IAY REG. NO. MP3950794 | Completed | 15030 | 14942 | 2017-02-21 | 2018-10-15
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/372246 — Construction of IAY House -IAY REG. NO. MP1273248 | Completed | 15030 | 13894 | 2017-02-21 | 2021-08-30
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/374585 — Construction of IAY House -IAY REG. NO. MP1385249 | Completed | 15030 | 13450 | 2017-02-21 | 2021-08-30
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/378152 — Construction of IAY House -IAY REG. NO. MP1630907 | Completed | 15030 | 15174 | 2017-02-21 | 2018-07-22
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/3787962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135035058 | Physically Completed | 18360 | 15708 | 2022-08-30 | 2024-11-21
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/3788128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135467488 | Physically Completed | 18360 | 18258 | 2022-08-30 | 2024-11-21
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/3875907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142775093 | Physically Completed | 18360 | 14382 | 2022-08-30 | 2024-11-21
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/3877035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142810655 | Physically Completed | 18360 | 15840 | 2022-08-30 | 2024-11-21
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/3880002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142996454 | Physically Completed | 18360 | 14484 | 2022-08-30 | 2024-11-21
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/3882662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143089790 | Physically Completed | 18360 | 16338 | 2022-08-30 | 2024-11-21
BHIND / GOHAD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4326261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142584161 | Physically Completed | 18360 | 12594 | 2023-12-21 | 2024-11-21
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4326268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142787727 | Completed | 18360 | 16482 | 2022-11-18 | 2024-08-20
BHIND / GOHAD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4359440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142840844 | Physically Completed | 18360 | 14184 | 2023-12-20 | 2024-11-21
BHIND / GOHAD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4373869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142565895 | Physically Completed | 18360 | 3978 | 2023-12-20 | 2024-11-21
BHIND / GOHAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4383820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148599895 | Physically Completed | 18360 | 8748 | 2024-05-09 | 2024-11-21
BHIND / GOHAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4799069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142991300 | Ongoing | 23490 | 4860 | 2024-12-21
BHIND / GOHAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4799076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142999422 | Ongoing | 23490 | 15660 | 2024-12-21
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/4804277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143502125 | Physically Completed | 23490 | 20358 | 2025-09-24 | 2026-06-07
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/706705 — Construction of IAY House -IAY REG. NO. MP1522386 | Completed | 15030 | 14430 | 2017-07-25 | 2018-09-28
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/708911 — Construction of IAY House -IAY REG. NO. MP1547042 | Completed | 15030 | 14812 | 2018-03-06 | 2019-11-25
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/710214 — Construction of IAY House -IAY REG. NO. MP1563141 | Completed | 15030 | 14826 | 2017-12-13 | 2018-08-14
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/710346 — Construction of IAY House -IAY REG. NO. MP1564768 | Completed | 15030 | 15288 | 2017-09-19 | 2018-07-17
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/733519 — Construction of IAY House -IAY REG. NO. MP2064491 | Completed | 15030 | 14620 | 2017-07-25 | 2018-03-05
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/756624 — Construction of IAY House -IAY REG. NO. MP2802889 | Completed | 15030 | 15480 | 2017-07-25 | 2018-03-05
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/758305 — Construction of IAY House -IAY REG. NO. MP2880947 | Completed | 15030 | 14620 | 2017-07-25 | 2018-03-05
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/759870 — Construction of IAY House -IAY REG. NO. MP2951103 | Completed | 15030 | 15480 | 2017-07-25 | 2018-03-05
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/777451 — Construction of IAY House -IAY REG. NO. MP3827910 | Completed | 15030 | 14792 | 2017-07-25 | 2018-03-05
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/777874 — Construction of IAY House -IAY REG. NO. MP3855932 | Completed | 15030 | 15308 | 2017-07-25 | 2018-03-05
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004014/IF/IAY/948998 — Construction of IAY House -IAY REG. NO. MP3019544 | Approved | 23490 | 0 | 2017-04-03
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702004014/LD/22012034293101 — मुक्तिधाम निर्माण कार्य ग्राम बम्होरा GP बकनासा | Completed | 1111000 | 962976 | 2016-11-29 | 2018-01-21
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/LD/22012034467211 — नाला निर्माण कार्य पहुआ से रिहार तक बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1094073.57 | 545360 | 2020-04-22 | 2024-08-19
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/LD/22012034467212 — नाला निर्माण कार्य बाबा के कुआ से बम्‍होरा तक ग्राम बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1095166.31 | 855956 | 2019-12-12 | 2020-06-04
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555089 — WORK MEDH BANDHAN PREM SINGH / HUBBILAL SINGH GRAM BAMOHRA GRAM PANCHAYAT BAKNASA | Closed | 12346.54 | 0 | 2021-04-16
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555120 — WORK- MEDH BANDHAN LAKHAN SINGH/ BHUPSINGH GRAM BAMHORA GRAM PANCHAYAT BAKNASA | Closed | 28958.83 | 0 | 2021-04-16
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555122 — Medbandhan Work - Devendra Singh/ Bhupsingh Gram Bamhora GP Baknasa | Closed | 40459.65 | 0 | 2021-04-18
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555123 — Medbandhan Work - Neeraj Devi / Chhatar Singh Gram Bamhora GP Baknasa | Closed | 20013.75 | 0 | 2021-04-18
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555124 — Medbandhan Work - Munni Devi/Lakhan singh Gram bamhora GP Bakansa | Closed | 40459.65 | 0 | 2021-04-19
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555126 — Medbandhan Work - Pritam Singh /Bhupsingh Gram bamhora GP Baknsa | Closed | 40459.65 | 0 | 2021-04-16
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555128 — Medbandhan Work - Dulichan/Prahlada Gram Bamhora GP Baknasa | Closed | 11068.67 | 0 | 2021-04-16
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555129 — Medbandhan Work - Rajka Beva / shriram gram bamhora GP Baknasa | Closed | 38542.92 | 0 | 2021-04-18
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555131 — Medbandhan Work -Naresh Singh /Rajveer Singh Gram bamhora GP Baknasa | Closed | 40459.65 | 0 | 2021-04-17
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555137 — Medbandhan Work - Satyapal Singh/Gajendra Singh Gram bamhora GP Baknasa | Closed | 34709.31 | 0 | 2021-04-20
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555138 — Medbandhan Work - Sultan Singh/Jwala Singh GP Baknasa | Closed | 40459.65 | 0 | 2021-04-16
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004014/LD/22012034555139 — Medbandhan Work - Gajendra Singh / Madho Singh GP Baknasa | Closed | 38542.92 | 0 | 2021-04-20
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Waterlogged Land for Community / Reclamation of Community Waterlogged Land | Land Development | 1702004014/LD/22012034557952 — WORK KHET TALAV NIRMAN RAJU SINGH SIKARWAR /BANGALI SINGH SIKARWAR G P BAKNASA | Closed | 338902.57 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Waterlogged Land for Community / Reclamation of Community Waterlogged Land | Land Development | 1702004014/LD/22012034557954 — WORK Khat Talav Nirman Deshraj Singh/ Ranjeet singh G P BAKNASA | Closed | 338902.57 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/LD/22012034574221 — C.C.Nali Work - शांतीधाम वाली रोड से प्रा शा भवन तक बम्‍होरा ग्रा पं बकनासा | Closed | 90000 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/LD/22012034574227 — C.C.Nali Work - हनुमान मंदिर से प्राथमिक शाला भवन तक बम्‍होरा GP Baknasa | Closed | 57600 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/LD/22012034574231 — C.C.Nali Work - Jandel ke ghar se vishambhar gurjar ke makan ki or GP Baknasha | Closed | 38400 | 0 | 2021-04-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712400 — madbhandhan koksingh/rustamsingh | Completed | 14700 | 11304 | 2014-07-15 | 2014-09-01
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712404 — madhbhandhan bishambhar/harikhanth | Completed | 21300 | 7536 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712481 — madbhandhan setansingh/mohansingh | Completed | 64100 | 10362 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712485 — madbhandhan jagdesh/vijaysingh | Completed | 15800 | 8478 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712527 — madbhandhan naharsingh/kundansingh | Completed | 17000 | 14130 | 2014-07-15 | 2014-09-01
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712534 — madbhandhan sultansingh/juyalasingh | Deleted | 52700 | 0 | 2014-07-22
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712549 — madbhandhan ramdayal/kasiram | Completed | 19900 | 10362 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712552 — madhbhandhan guddi/mahipal | Completed | 17600 | 9420 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712553 — madbhandhan durarikasingh/madansingh | Completed | 28300 | 9420 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004014/LD/9926712554 — madbhandhan puransingh/madhosingh | Completed | 11700 | 10362 | 2014-07-15 | 2016-08-14
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702004014/PG/22012034310982 — खेल मैदान निर्माण कार्य बकनासा | Completed | 353000 | 216009.6 | 2017-05-09 | 2019-08-27
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034191236 — CC ROAD NIRMAN WORK MAIN ROAD SCHOOL KE SAMANE SE | Completed | 126937 | 126723 | 2013-12-24 | 2014-09-01
BHIND / GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034191237 — CC ROAD NIRMAN WORK BHAGWAN SINGH KE MAKAN SE BHUR | Completed | 143862 | 18840 | 2014-06-17 | 2014-09-01
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034191238 — CC ROAD NIRMAN WORK MAIN ROAD SE KHILMAN SINGH KE | Completed | 42312 | 25258 | 2013-12-24 | 2014-09-01
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034191239 — CC ROAD NIRMAN WORK HANUMAN MANDIR SE RAMOUTAR KE | Completed | 187492 | 145631 | 2013-12-24 | 2014-09-01
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034291946 — सी सी रोड निर्माण भूरे सिंह की दुकान से लेकर श्रीचन्‍द्र के दरवाजे तक | Completed | 63750 | 62388 | 2015-12-08 | 2017-06-25
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034293996 — मिटृटी बजरी रोड निर्माण कार्य खेत सडक योजना मैन रोड बम्‍होरा से पडुआ तक (बम्‍होरा) बकनासा | Completed | 1473000 | 426550.3 | 2015-12-22 | 2017-06-15
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034316208 — सी सी रोड निर्माण कार्य प्राथमिक शाला भवन से छोटे जाटव के घर तक बम्होरा | Deleted | 230000 | 0 | 2016-09-28
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034340601 — सुदूर संपर्क सड़क ग्राम बम्होरा में पडुआ से रिहार तक | Completed | 1451000 | 1386098.98 | 2017-06-06 | 2020-05-10
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034341430 — सुदूर संपर्क सड़क ग्राम बम्होरा मे पडुआ से रिहार तक | Deleted | 1451000 | 0 | 2017-01-26
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034341433 — सुदूर संपर्क सड़क ग्राम लालन का पुरा से नीमडाडा तक | Deleted | 1410000 | 0 | 2017-01-26
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034378326 — sudur road bamhora se baba ke kua tak bamhora | Completed | 1300000 | 1187429.71 | 2017-12-15 | 2020-05-10
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034378330 — sudur road rihar se barahed pariksha bahora baknasa | Completed | 1300000 | 1167502.52 | 2017-12-15 | 2020-05-10
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034508571 — सीसी रोड main road se khyali jatav ke makan tak avam main road se panch bangla | Closed | 37520 | 0 | 2019-10-02
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034508697 — सीसी रोड निर्माण कार्य सामुदायिक भवन से दुलीचन्‍द के मकान तक ग्राम पंचायत बकनासा | Completed | 23000 | 20844 | 2021-12-08 | 2024-02-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034515059 — ग्रेवल रोड निर्माण कार्य पुरोहित का पुरा से शांतीधाम बकनासा तक ग्राम पंचायत बकनासा | Physically Completed | 2252498.69 | 831747.65 | 2020-09-26 | 2026-05-28
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034522478 — सुदूर संपर्क सडक निर्माण कार्य बम्‍होरा से पुलिस चौकी की ओर ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034532010 — सुदूर संपर्क सडक ग्राम बम्‍होरा से शांतीधाम बम्‍हौरा तक ग्राम पंचायत बकनासा | Ongoing | 1445461.27 | 520346.84 | 2020-09-04
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034532011 — सुदूर संपर्क सडक ग्राम बकनासा लालनकेपुरा से बकनासा बम्‍बा तक ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034532174 — सुदूर संपर्क सडक पुरोहित के पुरा से शांतीधाम तक ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034532227 — Sudoor road baknasa purehit ke pura se shantidham baknasa tak gp baknasa | Closed | 0 | 0 | 2020-05-15
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004014/RC/22012034554436 — ग्रेवल रोड निर्माण कार्य ग्राम बम्‍होरा से लेकर परीक्षा मेढे तक ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-08-15
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/22012034597214 — सीसी रोड एवं नाली निर्माण कार्य PANCHAM KE MAKAN SE MAIN ROAD KI OR | Closed | 31000 | 0 | 2021-10-02
BHIND / GOHAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/238 — बकनासा मेन रोड से सुरेश मेहतर के दरवाजे की ओर पंचपरमेश्‍वर | Completed | 0 | 44182 | 2012-11-28 | 2013-01-15
BHIND / GOHAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004014/RC/354 — 1702004014/RC/354 | Completed | 171385 | 49896 | 2013-02-12 | 2014-01-11
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702004014/RS/22012034599087 — सीसी नाली निर्माण कार्य - Rajesh singh ke darwaje se Rasal ke ghar ki or Lalankapura GP Baknasha | Closed | 33900 | 0 | 2021-11-02
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1702004014/RS/22012034599100 — सीसी नाली निर्माण कार्य SINTU KE BUNGLA W SE LEKAR MAIN ROAD TAK GP Baknash | Closed | 45000 | 0 | 2021-10-12
BHIND / GOHAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004014/WC/22012034323258 — TANK RENOVATION BUND STRENTHNING KARYA GRAM PUROHIT KA PURA GRAM BAKNASA | Deleted | 121500 | 0 | 2017-05-04
BHIND / GOHAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004014/WC/22012034323263 — TANK RENOVAION BUND STRENTHNING KARYA GRAM BAMHORA | Completed | 174000 | 132612 | 2017-06-27 | 2018-04-04
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004014/WC/22012034324836 — टँक रिनोवेशन बंड स्ट्रेथनिंग कार्य पुरोहित का पुरा | Deleted | 121500 | 0 | 2016-04-20
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004014/WC/22012034381601 — Talab Work GP Bakanasha | Closed | 0 | 0 | 2017-01-26
BHIND / GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702004014/WC/22012034426426 — परकोलेशन टेंक निर्माण कार्य बकनासा ग्राम पंचायत बकनासा | Completed | 772000 | 754998 | 2019-01-24 | 2019-11-23
BHIND / GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034435854 — Talab Work Baknasa | Closed | 0 | 0 | 2019-01-26
BHIND / GOHAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034476271 — नवीन तालाब निर्माण कार्य पुरोहित का पुरा ग्राम पंचायत बकनासा | Completed | 973086.87 | 936474.33 | 2019-09-18 | 2020-11-20
BHIND / GOHAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034476484 — नवीन तालाब निर्माण कार्य लालन का पुरा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2019-04-14
BHIND / GOHAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004014/WC/22012034476485 — चैकडेम / स्टॉपडेम निर्माण कार्य बकनासा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2019-04-14
BHIND / GOHAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034480693 — नवीन तालाब निर्माण कार्य बाबा के खेत पर बम्‍होरा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2019-04-14
BHIND / GOHAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034540794 — नवीन तालाब निर्माण कार्य जग्‍गा के पास बकनासा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2019-08-15
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034540795 — डगटेंक निर्माण कार्य मुक्तिधाम के पास बम्‍होरा ग्राम पंचायत बकनासा | Physically Completed | 962004.35 | 886206 | 2020-06-04 | 2026-04-16
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034550531 — नवीन तालाब निर्माण कार्य जूहरिया के पास बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1421471.77 | 1320011.82 | 2020-06-04 | 2025-05-24
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034550532 — नवीन तालाब निर्माण कार्य पुरानेगांव के पास बम्‍होरा ग्राम पंचायत बकनासा | Ongoing | 1415019.53 | 1332888 | 2020-12-29
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034550533 — नवीन तालाब निर्माण कार्य बकनासा मंदिर के पास नरखारा ग्राम पंचायत बकनासा | Completed | 1426202.99 | 1139857 | 2020-06-25 | 2022-07-01
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034550534 — नवीन तालाब निर्माण कार्य मुक्तिधाम के पास बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1373545.32 | 1049685.7 | 2020-06-05 | 2023-12-02
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034555884 — नवीन तालाब निर्माण कार्य पोहरा के पास ग्राम पंचायत बकनासा | Completed | 1328572.89 | 1142302.2 | 2020-09-04 | 2025-05-24
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034555885 — नवीन तालाब निर्माण कार्य डाडे के पास ग्राम पंचायत बकनासा | Ongoing | 1044146.12 | 937527 | 2021-01-05
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034555886 — तालाब निर्माण कार्य चमला के पास ग्राम पंचायत बकनासा | Completed | 1316368.18 | 1148598.2 | 2020-08-28 | 2025-04-18
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/WC/22012034566702 — नाला निर्माण कार्य पुरेहित के पुरा से नदी की ओर ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004014/WC/22012034566703 — नाला निर्माण कार्य भीकमसिंह के पुरा पर ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034604700 — नवीन तालाब निर्माण कार्य नईतोर के पास बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1441919.98 | 1325214 | 2021-03-04 | 2022-07-01
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034614726 — तालाब निर्माण कार्य लोकमन के खेत के पास बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1161152.49 | 1021770 | 2021-03-01 | 2022-07-01
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034614727 — तालाब निर्माण कार्य गोरावाला खार बम्‍होरा ग्राम पंचायत बकनासा | Completed | 1166280.69 | 1056504 | 2021-03-02 | 2022-07-01
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034614728 — तालाब निर्माण कार्य कप्‍तानसिंह के तीर के पास बम्‍होरा ग्राम पंचायत बकनासा | Physically Completed | 1479486.04 | 1324300 | 2021-03-16 | 2026-04-16
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034614729 — डगटेंक निर्माण कार्य मुक्तिधाम के पास बकनासा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2020-08-15
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034972434 — अमृत सरोवर निर्माण कार्य पंचमसिंह तोमर के खेत के पास बमोरा ग्राम पंचायत बकनासा | Ongoing | 2533000 | 2261533.31 | 2022-05-20
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012034972499 — अमृत सरोवर निर्माण कार्य बिहारी वाले के खेत के पास बमोरा ग्राम पंचायत बकनासा | Ongoing | 2150000 | 1162239 | 2023-06-17
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012035023497 — AMRIT SAROVAR DANG POND NIRMAN RAJU KE KHET KE PASS LALANPURA GP BAKNASA | Ongoing | 1470298.38 | 122808 | 2023-01-19
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012035023501 — AMRIT SAROVAR DANG POND NIRMAN PARIMAL KE KHET KE PASS LALANPURA GP BAKNASA | Closed | 0 | 0 | 2022-11-01
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/22012035023678 — AMRIT SAROVAR TALAB NIRMAN PARIMAL KHET KE PASS LALANPURA GP BAKNASA | Ongoing | 1498524.1 | 214506 | 2023-01-19
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/GIS/28707 — नवीन तालाब निर्माण कार्य बलवीरसिंह के खेत के पास बम्‍होरा ग्राम पंचायत बकनासा | Ongoing | 1145132.2 | 323082 | 2021-09-22
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/GIS/28708 — नवीन तालाब निर्माण कार्य भटपुरावाली तीर के पास बम्‍होरा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2021-07-01
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/GIS/28709 — नवीन तालाब निर्माण कार्य मुक्तिधाम के पास बकनासा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2021-07-01
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/GIS/28710 — नवीन तालाब निर्माण कार्य सुल्‍तानसिंह के तीर के पास बकनासा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2021-07-01
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004014/WC/GIS/28711 — नवीन डगटेंक निर्माण कार्य सुरेन्‍द्रसिंह के खेत के पास बम्‍होरा ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2021-07-01
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004014/WH/22012034454365 — तालाब जीर्णोद्धार निर्माण कार्य माता मंदिर के पास ग्राम पंचायत बकनासा | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004014/WH/22012034454366 — तालाब जीर्णोद्धार निर्माण कार्य स्वराज भवन के पास बम्होरा ग्राम पंचायत बकनासा | Closed | 9948.99 | 0 | 2021-04-14
BHIND / GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702/RC/22012034152756 — ग्राम सपंर्क सडक योजना | Completed | 2031000 | 194040 | 2010-06-06 | 2016-08-14
BHIND / GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702/RC/22012034153073 — gram sampark sadak yojna | Deleted | 0 | 0 | 2010-04-30