## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702004015/LD/22012034542587 — पक्‍का चबूतरा / प्‍लेटफार्म निर्माण कार्य उपार्जन केन्‍द्र बाराहेड (चकटैटोन) ग्राम पंचायत बारा | Deleted | 0 | 0 | 2021-01-26 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702004016/AV/22012034391957 — आंगनबाडी भवन निर्माण कार्य टैटोन ग्राम पंचायत टैटोन | Ongoing | 330000 | 115774 | 2018-10-05 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004016/AV/22012034628108 — शांतीधाम निर्माण कार्य चक टैटोन | Closed | 0 | 0 | 2022-08-15 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004016/AV/22012034628110 — शांतीधाम निर्माण कार्य नवीन कालोनी टैटोन | Closed | 0 | 0 | 2022-08-15 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1702004016/DP/22012034556851 — मां की बगिया शा.मा.वि.टैटोन | Closed | 12000 | 0 | 2022-04-14 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702004016/FP/22012034367425 — cc nali nirman karya kua se talab ki or | Closed | 23000 | 0 | 2020-09-19 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1702004016/FP/22012034624682 — flood control chenal teton se barahet ki or | Closed | 0 | 0 | 2021-04-14 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1702004016/FP/22012034624683 — flood control chenal radi ki puliya se barahet ki seema tak | Closed | 0 | 0 | 2021-04-14 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034626251 — constrection of two row HPC & ex.of Flood control chennel | Closed | 604650 | 0 | 2021-07-10 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702004016/FP/22012034627010 — CC NALI NIRMAN KARANSINGH KE GHAR SE SCHOOL BAUNDRYBALL KI OR | Completed | 23300 | 28152 | 2022-04-30 - 2022-07-01
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034630827 — cc nali nirman school baundryball se nale ki or | Closed | 50900 | 0 | 2022-11-17 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034630890 — Flood contor kamles se khet se setaram ki khet ki or garam teton | Physically Completed | 396057 | 298776 | 2023-01-15 - 2026-06-10
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034630891 — Flood contor bammba se rinku ki khet ki or GP Teton | Physically Completed | 499766.99 | 418939 | 2023-01-15 - 2026-06-10
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034630893 — Flood control riknu ki khet se rambeer ki khet ki or gram teton | Physically Completed | 321721.7 | 209168 | 2022-12-02 - 2026-06-10
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1702004016/FP/22012034632059 — Mainor sichai chennal jhan singh ke khet ke pass se khatik ke khet ki or | Closed | 0 | 0 | 2022-12-24 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1702004016/FP/22012034632060 — Mainor sichai chennal vishambhar singh ki makan ke pass se kaptan ki khet ki or | Closed | 0 | 0 | 2022-12-24 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034633616 — Mainor sichai chennal sardar bittu ki khet se setaram ki khat ki or | Ongoing | 943600.58 | 13260 | 2023-08-17 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034633617 — Mainor sichai chennal natu ki khte se serpur ki seema tak | Ongoing | 983107.86 | 13260 | 2023-08-17 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034634253 — Mainor sichai chennal jhan singh ke khet ke pass se khatik ke khet ki or | Ongoing | 932895.67 | 231166 | 2023-08-17 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004016/FP/22012034634254 — Mainor sichai chennal vishambhar singh ki makan ke pass se kaptan ki khet ki or | Ongoing | 965260.08 | 13260 | 2023-08-17 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004016/IF/22012034341312 — वृक्षारोपण कार्य बारहेट रोड से टेटोंन तक | Completed | 335000 | 15900 | 2017-06-21 - 2019-07-20
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702004016/IF/22012034348507 — नाडेप टाका निर्मांक कार्य मनीराम पुत्र तुलशीराम | Completed | 13800 | 2924 | 2017-06-14 - 2019-10-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004016/IF/22012034369146 — वृक्षारोपण कार्य सड़क किनारे पुलिया से लेकर सुनाई मंदिर के सामने की ओर | Completed | 335000 | 13664 | 2017-07-28 - 2019-07-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004016/IF/22012035445316 — khet talab nirman karya basudevi so suresh singh | Closed | 147621.16 | 261 | 2025-05-15 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004016/IF/22012035529758 — khet talab nirman karya harjindar singh so gurdayal singh ke khet par teton | Closed | 147621.16 | 1566 | 2025-07-13 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004016/IF/22012035537709 — khet talab nirman karya sobaran singh so bhibhuti singh ke khet par teton | Physically Completed | 147621.16 | 94221 | 2025-06-08 - 2026-06-09
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004016/IF/22012035566483 — khet talab rampyari W/O balram teton | Deleted | 0 | 0 | 2025-04-14 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004016/IF/22012035566883 — khet talab nirman karya rampyari wo balram ke khet par teton | Deleted | 0 | 0 | 2025-04-01 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004016/IF/9993702370 — PASHU SHED NIRMAAN KARYA BHAJANLAL S/O PREETAM SINGH | Completed | 95000 | 94914.24 | 2016-01-13 - 2016-10-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004016/IF/9993702381 — PASHU SHED NIRMAAN KARYA BASHUDEV S/O LAJJARAM | Completed | 95000 | 94910.04 | 2016-01-20 - 2016-10-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004016/IF/9993702384 — PASHU SHED NIRMAAN KARYA RAM SINGH S/O RAMCHARAN SINGH | Deleted | 95000 | 0 | 2015-10-03 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004016/IF/9993702386 — PASHU SHED NIRMAAN KARYA SONERAM S/O GURELAL | Completed | 95000 | 94914.24 | 2016-01-20 - 2016-10-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004016/IF/9993713608 — पशु शेड निर्माण कार्य शारदा पत्नी मलखान सिंह | Deleted | 0 | 0 | 2016-01-27 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/125079 — Construction of IAY House -IAY REG. NO. MP-02-004-016-001/33328641 | Completed | 14310 | 13026 | 2016-08-11 - 2016-10-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/125080 — Construction of IAY House -IAY REG. NO. MP-02-004-016-001/33750701 | Completed | 14310 | 13026 | 2016-07-27 - 2016-10-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/125081 — Construction of IAY House -IAY REG. NO. MP-02-004-016-001/33782398 | Completed | 14310 | 13026 | 2016-08-24 - 2017-01-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/125082 — Construction of IAY House -IAY REG. NO. MP-02-004-016-001/33935276 | Completed | 14310 | 13026 | 2016-08-03 - 2017-01-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/1916639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4629746 | Completed | 15660 | 15660 | 2018-10-04 - 2019-01-18
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/202943 — Construction of IAY House -IAY REG. NO. MP-02-004-016-001/33934828 | Completed | 15030 | 13026 | 2016-11-30 - 2017-03-22
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/3736694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122748349 | Completed | 18360 | 10608 | 2023-05-04 - 2023-09-20
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/3746042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120030891 | Physically Completed | 18360 | 13656 | 2023-12-13 - 2024-11-21
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4373645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131118288 | Completed | 18360 | 15912 | 2023-04-18 - 2023-07-18
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779786 | Ongoing | 19890 | 13809 | 2024-01-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779801 | Ongoing | 19890 | 14052 | 2024-01-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779813 | Ongoing | 19890 | 12990 | 2024-02-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779817 | Ongoing | 19890 | 8373 | 2024-02-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779843 | Ongoing | 19890 | 8947 | 2024-02-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779845 | Ongoing | 19890 | 6915 | 2024-02-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779851 | Ongoing | 19890 | 10206 | 2024-03-16 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779886 | Ongoing | 19890 | 8947 | 2024-02-28 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4434464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151779909 | Ongoing | 19890 | 9963 | 2024-03-16 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4760163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119805543 | Ongoing | 23490 | 20007 | 2024-11-12 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4775297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122688220 | Ongoing | 23490 | 15111 | 2024-11-12 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/4794487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145743277 | Ongoing | 23490 | 21060 | 2025-02-14 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5519941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131116806 | Physically Completed | 23490 | 23229 | 2025-07-25 - 2026-02-11
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5519942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131117176 | Ongoing | 23490 | 14094 | 2025-07-25 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5522147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119820731 | Completed | 23490 | 23490 | 2025-05-22 - 2025-12-15
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5522627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115905450 | Physically Completed | 23490 | 21663 | 2025-05-22 - 2026-02-11
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5524679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119786635 | Ongoing | 23490 | 20358 | 2025-05-22 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5525592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130750622 | Ongoing | 23490 | 21663 | 2025-05-22 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5526378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132198956 | Ongoing | 23490 | 20097 | 2025-05-22 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5526528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132201054 | Ongoing | 23490 | 20097 | 2025-05-22 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5528814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119824812 | Completed | 23490 | 23490 | 2025-05-22 - 2025-12-15
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5530546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119806453 | Physically Completed | 23490 | 23229 | 2025-06-19 - 2026-02-11
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5530645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127151913 | Physically Completed | 23490 | 21663 | 2025-05-20 - 2026-01-22
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5532741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127741778 | Completed | 23490 | 23490 | 2025-05-21 - 2025-12-15
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5532846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130746910 | Physically Completed | 23490 | 22968 | 2025-07-25 - 2026-02-03
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5620845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119807256 | Ongoing | 23490 | 17226 | 2025-07-23 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5621353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132424336 | Ongoing | 23490 | 21924 | 2025-07-23 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5621516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145356785 | Physically Completed | 23490 | 21924 | 2025-05-22 - 2026-06-14
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5621904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132202469 | Ongoing | 23490 | 15660 | 2025-07-25 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5709962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132248046 | Ongoing | 23490 | 22185 | 2025-07-30 -
BHIND / GOHAD / TETON | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004016/IF/IAY/5728426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132199290 | Ongoing | 23490 | 23490 | 2025-09-11 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034222583 — MEDBANDHAN AMERSINGH / MATHURA PRASAD (TETON ) | Deleted | 0 | 0 | 2015-01-26 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702004016/LD/22012034243297 — MUKTIDHAM KE CHABUTRE KA NIRMAAN KARYA TETON | Completed | 188600 | 187592 | 2015-12-09 - 2018-08-02
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702004016/LD/22012034243543 — PASHU ABRODHAK DEEWAR (C.P.W) MUKTIDHAM PARISAR TETON | Deleted | 1171636 | 0 | 2015-12-09 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034246687 — PASHU ABRODHAK DEEWAL (C.P.W.) S.P.V.TETON OR S.P.V.RADI KA PURA | Completed | 297500 | 202702 | 2016-01-06 - 2018-08-02
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034246694 — PASHU ABRODHAK DEEWAL (C.P.W) P.V. NAVEEN COLONI | Completed | 297500 | 173494 | 2016-01-06 - 2018-08-02
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702004016/LD/22012034314786 — SAMUDAYAK BHAVAN NIRMAN KARY G.P.TETON | Completed | 162000 | 154380 | 2017-06-14 - 2020-07-21
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702004016/LD/22012034542589 — पक्‍का चबूतरा / प्‍लेटफार्म निर्माण कार्य उपार्जन केन्‍द्र बाराहेड (चकटैटोन) ग्राम पंचायत टैटोन | Ongoing | 802553.42 | 191029.78 | 2021-03-14 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552215 — MAD BANDHAN KARYA BAIJANTI/VINOD GRAM PANCHYAT TETON | Completed | 40697.02 | 40530 | 2021-05-15 - 2021-10-20
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552216 — MAD BANDHAN KARYA GAJENDRA SINGH/LALARAM GARAM PANCHYAT TETON | Completed | 40185.87 | 40530 | 2021-05-16 - 2021-10-20
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552217 — MAD BANDHAN KARYA RAMOTAR SINGH/GAMNDILAL GRAM PANCHYAT TETON | Physically Completed | 40441.44 | 31266 | 2021-05-16 - 2026-06-10
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552218 — MAD BANDHAN KARYA DARAM SINGH/BOGIRAM GARAM PANCHYAT TETON | Completed | 40697.02 | 38214 | 2021-05-16 - 2021-06-20
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552219 — MAD BANDHAN KARYA KANTA DEVI/RAMKISHAN GARAM PANCHYAT TETON | Completed | 40441.44 | 39372 | 2021-05-16 - 2021-07-25
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552220 — MAD BANDHAN KARYA YOGESH/VINOD SINGH GRAM PANCHYAT TETON | Completed | 40185.87 | 22002 | 2021-05-23 - 2022-07-01
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552221 — MAD BANDHAN KARYA RAMSANHE/RAM SINGH GRAM PANCHYAT TETON | Completed | 40185.87 | 25476 | 2021-06-13 - 2022-07-13
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034552811 — MAD BANDHAN KARYA DAYAL SINGH/BAHADUR SINGH GRAM PANCHYAT TETON | Completed | 40441.44 | 33582 | 2021-05-30 - 2021-12-16
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556931 — MAD BANDHAN KRYA HARDAVI/RAJENDAR SINGH GARAM TETON | Completed | 39802.58 | 43536 | 2021-05-30 - 2022-04-26
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556933 — MAD BANDHAN KARYA RAMOTAR/SARDAR SINGH GARAM TETON | Completed | 39802.58 | 29940 | 2021-05-30 - 2022-05-12
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556935 — MAD BANDHAN KARYA JABAR SINGH/SARDAR SINGH | Closed | 0 | 0 | 2021-04-14 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556938 — MAD BANDHAN KARYA DARMVEER/RAMKISHAN GARAM TETON | Completed | 40441.44 | 25242 | 2021-06-06 - 2022-07-13
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556939 — MAD BANDHAN KARYA VISHMBAR/BABUTI SINGH GARAM TETON | Completed | 39802.58 | 32424 | 2021-05-30 - 2021-11-01
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556940 — MAD BANDHAN KARYASANDEEP SINGH/RAMVEER SINGH GARAM TETON | Completed | 38524.72 | 26268 | 2021-05-30 - 2022-07-13
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556941 — MAD BANDHAN KARYA PARDEEP/RAMVEER SINGH | Completed | 37885.71 | 31560 | 2021-06-27 - 2022-08-13
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556943 — MAD BANDHAN KARYA RANI BAI/BADRE SINGH GARAM TETON | Completed | 40441.44 | 39372 | 2021-05-30 - 2021-07-10
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556945 — MAD BANDHAN KARYA RAMVEER SINGH/VISHUNPAL | Completed | 38524.72 | 1158 | 2021-07-11 - 2023-08-23
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556947 — MAD BANDHAN KARYA UDAY/BADRE GARAM TETON | Closed | 37885.71 | 0 | 2021-04-14 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556949 — MAD BANDHAN KARYA GAYAN SINGH/KAMLISH SINGH | Completed | 41719.31 | 35898 | 2021-05-30 - 2021-11-01
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556951 — MAD BANDHAN KARYA VISHAL SINGH | Completed | 37885.71 | 27558 | 2021-05-30 - 2022-05-31
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034556952 — MAD BANDHAN KARYAASHOK SINGH/RAMGOPAL GARAM TETON | Completed | 38524.72 | 34008 | 2021-06-27 - 2022-08-13
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004016/LD/22012034557857 — MAD BANDHAN KARYA JABAR SINGH/SARDAR SINGH | Closed | 0 | 0 | 2021-04-14 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004016/LD/22012034593688 — AMRAT VATIKA SUNAE MANDER KI PASS GARM PANCHYAT TETON | Ongoing | 55847.4 | 9282 | 2023-08-17 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1702004016/OP/9425893082 — सामुदायिक भवन निर्माण कार्य ग्राम पंचायत टेटोंन | Deleted | 162000 | 0 | 2017-01-26 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702004016/PG/9425896151 — खेल मैदान निर्माण कार्य रडी का पुरा टटोन | Completed | 320000 | 215479.2 | 2017-05-03 - 2020-03-15
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034177173 — CC Road Mukhy Marg se School Tak Teton | Completed | 180918 | 154309 | 2013-08-07 - 2013-09-27
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034183987 — CC ROAD ROOP SINGH KE DWAR SE TRILOK SINGH KE DWAR | Completed | 146000 | 144982 | 2013-10-02 - 2014-04-23
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034285000 — CC ROAD NIRMAAN KARYA GURUJINDER KE GHAR SE NIRMAL KE GHAR TAK CHAK TETON (TETON) | Completed | 127419 | 127179 | 2015-09-30 - 2016-10-20
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004016/RC/22012034292341 — MUKTIDHAM PAHUCH MARG MITTI BAJRI ROAD NIRMAAN KARYA KHET SADAK YOJNA GRAVAL ROAD NIRMAAN MANDIR SE | Deleted | 389500 | 0 | 2015-10-03 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004016/RC/22012034365567 — सुदूर सपक निर्माण नहर से चकटेटौन की ओर GP Teton | Completed | 1474000 | 1459162.18 | 2017-11-01 - 2020-06-03
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004016/RC/22012034365570 — सुदूर सपक सडक निर्माण नहर से रडी के पुरा तक GP Teton | Completed | 778000 | 775887.54 | 2017-11-01 - 2020-06-03
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004016/RC/22012034385805 — murmikaran/gsb karya pahunch marg barahed barona road se chak teton tak | Closed | 27000 | 0 | 2018-01-26 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034512505 — CC Road Work - बाराहेड रोड से लाखन के द्वारा की ओर टैटोन | Completed | 11700 | 19542 | 2020-05-21 - 2021-10-24
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034512507 — C.C.Road Work - सीसी मैन रोड से ज्ञानसिंह के द्वारा तक टैटोन | Completed | 14550 | 13680 | 2020-05-21 - 2020-07-03
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034512508 — CC Road Work - रोड से पानसिंह के द्वारा की ओर टैटोन | Completed | 11700 | 17100 | 2020-06-11 - 2020-08-11
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034524506 — सीसी रोड निर्माण कार्य barahet road se vishambhar ke makan ki or टैटोन | Closed | 23250 | 0 | 2020-04-14 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034540580 — CC ROAD SUNAHI MANDIR SE BARAHET ROAD KI OR | Closed | 0 | 0 | 2020-04-14 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034540581 — CC ROAD MANDIR SE BABURAM ADIWASI KE MAKAN KI OR | Deleted | 0 | 0 | 2020-04-14 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034563047 — CC ROAD MANDIR SE BABURAM ADIWASI KE MAKAN KI OR | Ongoing | 46500 | 57462 | 2021-10-23 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034563048 — CC ROAD SUNAHI MANDIR SE BARAHET ROAD KI OR | Completed | 50700 | 49794 | 2021-05-02 - 2021-05-17
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/22012034824741 — सीसी निर्माण कार्य बाबा के चबूतरे से बाबा आदिवासी के द्बार की ओर | Approved | 0 | 0 | 2024-05-16 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004016/RC/249 — सीसी मेवाराम से बाबूसिह के मकान तक टेटोन पंचपरमेश्‍वर | Completed | 141727 | 90407 | 2013-02-25 - 2016-08-14
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702004016/RS/22012034594213 — सामुदायिक ग्रामीण स्‍वच्‍छता परिसर ग्राम पंचायत TETON | Completed | 43000 | 33480 | 2022-02-03 - 2024-02-14
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1702004016/RS/22012035122334 — Mukti dham irman karya radi ka pura garam panchyat tetion | Closed | 0 | 0 | 2024-01-24 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004016/WC/22012034294183 — तालाब गहरीकरण टेटोंन | Deleted | 94000 | 0 | 2016-04-22 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004016/WC/22012034323267 — TANK RENOVATION BUND STRENTHNING KARYA GRAM TETON | Deleted | 271000 | 0 | 2016-10-15 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004016/WC/22012034323913 — टैंक रिनोवेशन बैंड स्ट्रेथिंनिंग कार्य ग्राम टेटोंन | Completed | 271000 | 203752 | 2017-10-25 - 2023-08-23
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004016/WC/22012034355820 — BORI BHANDHAN GRAM TETON | Completed | 20000 | 14448 | 2017-09-27 - 2018-01-01
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004016/WC/22012034381723 — Talab Work - GP Teton | Closed | 0 | 0 | 2017-01-26 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1702004016/WC/22012034388584 — sokpit nirman panchayat bhavan parisar handpump ke pas teton | Completed | 14000 | 13988 | 2018-05-20 - 2019-04-01
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004016/WC/22012034390463 — tank renovation and bund srengthening | Deleted | 271000 | 0 | 2016-04-14 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004016/WC/22012034436600 — Checkdame work | Closed | 0 | 0 | 2019-01-26 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702004016/WC/22012034467584 — Dagtank Work - Gram Radi ke pura me GP Teton | Completed | 704642.86 | 631074 | 2020-09-24 - 2022-07-13
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004016/WC/22012034519567 — कच्‍चानाला निर्माण कार्य बाराहेडमौज से शेरपुर सीमा तक टैटोन | Closed | 0 | 0 | 2019-08-15 -
BHIND / GOHAD / TETON | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004016/WC/22012034519568 — कच्‍चानाला निर्माण कार्य ग्राम टैटोन से कंचनपुर सीमा तक ग्राम पंचायत टैटोन | Completed | 1093244.13 | 948572 | 2020-09-24 - 2025-09-13
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702004016/WC/22012035016544 — roof water harvesting samudayak bhawan sunahi | Closed | 11000 | 0 | 2022-04-03 -
BHIND / GOHAD / TETON | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004016/WH/22012034456030 — तालाब जीर्णोद्धार कार्य टैटोन ग्राम पंचायत टैटोन | Closed | 0 | 0 | 2021-04-14 -