## Work List
Exported on: 2026-09-10 22:48:34
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: RAYATPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004019/AV/22012034470731 — शांतीधाम निर्माण कार्य प्रेमसिंह का पुरा ग्राम पंचायत रायतपुरा | Closed | 0 | 0 | 2019-04-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004019/AV/22012034564331 — शांतीधाम निर्माण कार्य प्रेमसिंहकापुरा ग्राम पंचायत रायतपुरा | Closed | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004019/AV/22012034628111 — शांतीधाम निर्माण कार्य खेरे का पुरा ग्राम पंचायत रायतपुरा | Closed | 0 | 0 | 2022-08-15
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004019/AV/22012034628112 — शांतीधाम निर्माण कार्य प्रेमसिंह का पुरा ग्राम पंचायत रायतपुरा | Closed | 0 | 0 | 2022-08-15
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702004019/AV/3821 — Anganwadi/Other Rural Infrastructure,RAYATPURA | Physically Completed | 330000 | 252476 | 2015-12-07 | 2026-05-26
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034631774 — FLOOD CONTROL CHENNAL NIRMAN KARYA RULE BALIKOOL SE RANJEET SINGH KE KHET KE AUR RAYATPURA | Closed | 0 | 0 | 2022-04-01
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034632775 — flood control chennal nirman karya sherpur road se rund bali kool jasveer ke khet ki aur rayatpura | Physically Completed | 978151.71 | 188955 | 2023-06-24 | 2026-06-23
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034632776 — flodd control chennal nirman karya sherpur road se rayatpura gaon ki aur | Physically Completed | 978151.71 | 223652 | 2023-06-24 | 2026-06-23
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034632777 — flood control chennal nirman karya rund wale naale se ranjeet singh ke khet ki or rayatpura | Physically Completed | 574647.12 | 218790 | 2023-06-24 | 2026-06-12
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633850 — flood control chennal nirman karya heera singh ke khet se monu ke khet ki aur rayatpura | Ongoing | 468259.43 | 31382 | 2023-07-15
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633851 — flood control chennal nirman karya high school main road se prem singh ke pura ki aur rayatpura | Physically Completed | 738972.15 | 448033 | 2023-07-22 | 2026-05-26
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633852 — flood control chennal nirman karya bhajan singh ke khet se dalveer singh ke khet ki aur rayatpura | Ongoing | 378922.8 | 31382 | 2023-07-15
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633853 — flood control chennal nirman karya ravindra singh ke khet se bhupenda singh ke khet ki aur rayatpura | Ongoing | 378922.8 | 14144 | 2023-07-15
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633854 — flood control chennal nirman karya skhvinder singh ke khet se jandel singh ke khet ki aur rayatpura | Ongoing | 378922.8 | 13702 | 2023-07-15
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633855 — flood control chennal nirman karya trilok singh ke khet se sukhvinder, rajendra ke khet ki aur | Ongoing | 505965 | 11492 | 2023-07-15
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004019/FP/22012034633856 — flood control chennal nirman karya raju tomar ke khet wherehouse se nonera lallu singh ke pura ki or | Ongoing | 674420.34 | 12376 | 2023-07-15
BHIND / GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of minor Canal for Community / Construction of minor Canal for Community | Construction of Canal | 1702004019/IC/22012034386079 — Canal work Raiyatpura | Closed | 0 | 0 | 2019-01-26
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004019/IF/22012034346773 — बृक्षारोपण कार्य रायतपुरा से कतन्नी(शंकर पुर) का पुरा तक | Completed | 335000 | 36460 | 2017-06-19 | 2019-10-20
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004019/IF/22012034354477 — वृक्षारोपण कार्य बाबा की टेकरी से रायतपुरा तक ग्राम पंचायत रायतपुरा | Completed | 335000 | 1032 | 2017-08-14 | 2019-10-20
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004019/IF/22012034354486 — वृक्षारोपण कार्य महेंद्र दास बाबा की पुलिया से खेड़े के पुरा तक ग्राम शंकरपुर ग्राम पंचायत रायतपुरा | Completed | 335000 | 1032 | 2017-08-14 | 2019-10-23
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004019/IF/22012034354492 — वृक्षारोपण कार्य महेंद्र दास बाबा की पुलिया से कतनी के पुरा तक ग्राम शंकरपुर ग्राम पंचायत रायतपुरा | Completed | 335000 | 1032 | 2017-08-14 | 2019-10-20
BHIND / GOHAD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1702004019/IF/22012034499617 — Plantation Work - Rayatpura | Closed | 335000 | 0 | 2019-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811738 — medbandhan work -jagdev singh / parmal singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811739 — medbandhan work - satnam singh \ parmar singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811742 — medbandhan work - hardev singh / preetam singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811747 — medbandhan work -baksis singh/ trilok singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811751 — medbandhan work -ranjeet / preetam singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811761 — medbandhan work - sukh vinder kour / niranjan singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811769 — medbandhan work - dheer singh / narayan singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811771 — medbandhan work - dheer singh / narayan singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811778 — medbandhan work - palvinder singh / jeet singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811779 — medbandhan work - palvinder singh / jeet singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811784 — medbandhan work - hari singh / kehar singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811787 — medbandhan work - kamal jeet singh / hari singhgp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811789 — medbandhan work -kuldeep singh/ amreek singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811790 — medbandhan work -kuldeep singh/ amreek singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004019/IF/22012034811792 — medbandhan work -mandeep singh / sukh vinder singh gp rayatpura | Closed | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1702004019/IF/22012035124854 — नवीन वृक्षारोपण कार्य महेन्द्र दास गुरूद्वारे के पास खेडे का पुरा ग्राम पंचायत रायतपुरा | Closed | 227636.2 | 0 | 2023-06-28
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1702004019/IF/22012035137107 — Amrit batika Mahendra das gurudwara ke parisar me khade ka pura rayatpura | Closed | 55847.4 | 0 | 2023-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004019/IF/22012035516566 — खेत तालाब निर्माण कर दर्शन सिंह के खेत में ग्राम पंचायत rayatpura | Deleted | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004019/IF/22012035521561 — khet talab nirman karya harvindar singh ke khet par rayatpura | Ongoing | 248599.44 | 261 | 2025-05-17
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004019/IF/22012035521572 — khet talab nirman karya malkit singh so surtar singh ke khet par rayatpura | Ongoing | 147621.16 | 261 | 2025-05-17
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004019/IF/22012035522354 — dug bell rechage pit nirman karya sisambale kua ke pass rayatpura | Deleted | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004019/IF/22012035522370 — dugbell rechage pit nirman karya avtar singh ke khet ke kua ke pass rayatpura | Deleted | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1702004019/IF/22012035523123 — dugbell rechage pit nirman karya shisham bale kua ke pass rayatpura | Physically Completed | 25899.46 | 18396 | 2025-06-15 | 2026-06-12
BHIND / GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1702004019/IF/22012035523135 — dugbell rechege pit nirman karya avtar singh ke khet ke kua ke pass rayatpura | Physically Completed | 25899.46 | 16851 | 2025-05-21 | 2026-06-12
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9926726048 — PASHU SHED NIRMAAN KARYA RAMANJEET KAUR W/O NIDARP | Completed | 89000 | 50761.8 | 2014-04-28 | 2015-05-20
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9926726049 — PASHU SHED NIRMAAN KARYA KAMALJEET SINGH S/O PRATA | Completed | 89000 | 50761.8 | 2014-04-28 | 2015-05-20
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993697971 — Cattle Shed Nirman kary Swaroop singh s/o Krapal singh Shankar pur | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993698165 — Cattle Shed Nirman kary Swaroop singh s/o Krapal singh | Completed | 103660 | 101905 | 2015-12-21 | 2016-05-20
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Soil Cover on Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004019/IF/9993698170 — Cattle Shed Nirman kary Swaroop singh s/o Krapal singh | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993698402 — Cattle Shed Nirman kary Jasvant singh s/o Surjan singh | Completed | 103660 | 102223 | 2015-12-21 | 2016-05-20
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993701279 — Cattle Shed Nirman Kary Laljiram s/o Laturilal | Deleted | 103660 | 0 | 2015-12-30
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993701284 — Cattle Shed Nirman Kary Ramsevak s/o Bharosilal | Completed | 103660 | 5406 | 2016-01-04 | 2016-04-15
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993701287 — Cattle Shed Nirman Kary Surjeet singh s/o Jagtar singh | Deleted | 103660 | 0 | 2015-12-30
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993720907 — Pashu Shed Nirman Kary Sukhdev singh s/o Seva singh | Deleted | 0 | 0 | 2016-01-27
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702004019/IF/9993720914 — PASHU SHED NIRMAN KARY RACHHPAL KAUR W/O KULVANT SINGH | Deleted | 0 | 0 | 2016-01-27
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/1871766 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4363207 | Completed | 15660 | 15468 | 2018-11-15 | 2020-06-20
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/1872314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5365620 | Completed | 17100 | 12732 | 2018-10-30 | 2023-07-18
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/1872427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4726414 | Completed | 17100 | 12732 | 2018-10-30 | 2021-04-01
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/1872833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5329274 | Completed | 17100 | 13254 | 2018-10-30 | 2021-04-01
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/247560 — Construction of IAY House -IAY REG. NO. MP1773392 | Completed | 15030 | 16272 | 2017-02-13 | 2017-10-12
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/273990 — Construction of IAY House -IAY REG. NO. MP3126777 | Completed | 15030 | 15170 | 2017-02-13 | 2017-10-05
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004019/IF/IAY/274124 — Construction of IAY House -IAY REG. NO. MP3145341 | Completed | 15030 | 15120 | 2017-02-13 | 2017-07-29
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702004019/LD/22012034229355 — MUKTIDHAM ME VIAKS KARYA SAMTLAIKARAN RCC ROAD AND BOUNDRY WALL NIRMAN RAYATPURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702004019/LD/22012034229358 — MUKTIDHAM ME VIKAS KARYA SAMTALIKARAN RCC SHED AND BOUNDRYWALL NIRMAN RAYATPURA | Completed | 250000 | 227281 | 2015-09-14 | 2016-05-20
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702004019/LD/22012034250253 — Cattle Protection ball Nirman kary M/S Bhawan Rayatpura | Completed | 874000 | 15264 | 2016-01-11 | 2021-11-01
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004019/LD/22012034271623 — Talab Gaharikaran Kary Katani ka pura | Completed | 99300 | 21042 | 2016-05-09 | 2019-10-20
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702004019/LD/22012034312753 — shanti dham shankarpur katanni ka pura | Completed | 245000 | 164540.8 | 2017-05-08 | 2021-11-01
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702004019/LD/22012034312761 — khel maidan shankar pur khede ka pura | Deleted | 0 | 0 | 2017-05-08
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1702004019/LD/22012034543363 — पक्‍का चबूतरा निर्माण कार्य गेहू उपार्जन केन्‍द्र शंकरपुर ग्राम पंचायत रायतपुरा | Completed | 802553.42 | 668673.63 | 2021-03-12 | 2022-07-01
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004019/LD/22012034566931 — C.C.Nali Construction Work - बाराहेड मैन रोड से मंजीत के घर की ओर ग्रा पं रायतपुरा | Completed | 112500 | 79162 | 2021-08-09 | 2023-08-23
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702004019/PG/22012034312046 — खेल मैदान शंकरपुरा माजरा खेड़े क पूरा | Completed | 153600 | 8256 | 2017-06-26 | 2019-10-20
BHIND / GOHAD | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/125 — खरजा निर्माण लम्‍बरदार के घर से महेन्‍द्र सिह के घर तक | Completed | 0 | 69240 | 2010-12-22 | 2010-12-22
BHIND / GOHAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/200 — सी0सी0निर्माण कार्य मेन रोड से भगवान के मकान तक रायतपुरा पंचपरमेश्‍वर | Completed | 0 | 59680 | 2012-05-30 | 2012-06-25
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034191186 — CCROAD NIRMAN MAIN ROAD SE KULDEEP SINGH KE GHAR T | Completed | 124000 | 114051 | 2014-02-11 | 2015-05-20
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294783 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294784 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294788 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294852 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294853 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294854 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294855 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Deleted | 0 | 0 | 2015-04-16
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034294862 — C.C.NIRMAN KARY MALMINDER SINGH KE GHAR SE HARDEV SINGH KE GHAR KI OR KHEDE KA PURA | Completed | 74747 | 7632 | 2016-01-04 | 2016-12-27
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034352762 — सी सी रोड से मेजर सिंह के घर तक प्रेम सिंह का पुरा ग्राम पंचायत रायतपुरा | Completed | 345600 | 25224 | 2017-10-30 | 2021-11-01
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034365132 — मैन सी सी रोड से रणजीत सिंह के घर तक ग्राम रायतपुरा ग्राम पंचायत रायतपुरा | Completed | 204050 | 25044 | 2017-10-30 | 2021-11-01
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034365135 — बाराहेड मैन रोड से गोवेर्मेंट स्कूल बिलडिंग तक ग्राम पंचायत रायतपुरा | Completed | 264000 | 20856 | 2017-10-30 | 2021-11-01
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004019/RC/22012034375901 — Sudur sampark Sadak Work - Rayatpura GP Rayatpura | Closed | 0 | 0 | 2017-01-26
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004019/RC/22012034398558 — सी सी रोड निर्माण कार्य मय नाली पचायत भवन से अमरीक के घर तक | Closed | 412000 | 0 | 2018-04-14
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034531768 — C.C.Road & Nali Work - Gurumukhsingh ke makan se amriksingh ke makan tak & other galiya Rayatpura | Completed | 177225 | 177048 | 2020-09-02 | 2021-09-01
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004019/RC/22012034543152 — सुदूर रोड निर्माण गुरुद्वारा शंकर पुर से कुलवंत सिंह के खेत तक ग्राम पंचायत रायतपुरा | Physically Completed | 1097766.66 | 711229.63 | 2021-01-17 | 2026-06-12
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/22012034553659 — सीसी रोड एवं नाली निर्माण प्रतापसिंह के घर से सरदारसिंह के घर की ओर ग्राम पंचायत रायतपुरा | Completed | 69750 | 45000 | 2021-01-16 | 2022-07-01
BHIND / GOHAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004019/RC/350 — 1702004019/RC/350 | Completed | 177118 | 160633 | 2013-02-10 | 2013-12-26
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034186158 — INDIVISUAL LATRIN NIRMAN JAGDEESH SINGH | Deleted | 4500 | 0 | 2013-08-17
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034186458 — INDIVIDUAL LATRIN NIRMAN ADIRAM | Completed | 4500 | 2628 | 2014-01-13 | 2014-02-20
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034191993 — individual latrin lakhan singh | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034191998 — individual latrin arjun singh | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034192002 — individual latrin nirman kadam singh | Completed | 4500 | 2628 | 2014-01-13 | 2014-02-20
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034192035 — individual latrin nirman geeta bai | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034192041 — individual latrin nirman kedar | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034192171 — individual latrin nirman amro bai | Completed | 4500 | 2628 | 2014-01-13 | 2014-01-21
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034192172 — individual latrin nirman kantho bai | Completed | 4500 | 2628 | 2014-01-13 | 2014-01-21
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034193237 — INDIVIDUAL LATRIN NIRMAN PALVINDAR S/O AMAR SINGH | Deleted | 4500 | 0 | 2013-08-17
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034194564 — individual latrin nirman narendra s/o swaroop | Completed | 4500 | 2628 | 2014-02-24 | 2014-03-30
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034195730 — individual latrin kashmir singh s/o hajuri | Deleted | 4500 | 0 | 2013-08-17
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034199267 — INDIVIDUAL LATRIN HARI SINGH S/O KEHAR SINGH | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034199281 — INDIVIDUAL LATRIN KISHAN SINGH S/O KEHAR SINGH | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034208614 — INDIVIDUAL LATRINE PARASHRAM/ARJUN SINGH | Completed | 4500 | 2628 | 2014-02-24 | 2014-03-30
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034208618 — INDIVIDUAL LATRINE RAMVARAN/LAL SINGH | Completed | 4500 | 2628 | 2014-02-24 | 2014-03-30
BHIND / GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034215317 — INDIVIDUAL LATRINE RANJEET SINGH/PREETAM SINGH | Completed | 5400 | 942 | 2014-06-16 | 2014-08-25
BHIND / GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/22012034244636 — INDIVIDUAL HOUSEHOLD LATRINE AJVINDAR SINGH SO SWA | Completed | 5400 | 2826 | 2014-06-23 | 2014-08-25
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702004019/RS/22012034504092 — सामुदायिक ग्रामीण स्‍वच्‍छता परिसर मिडिल स्‍कूल रायतपुरा ग्राम पंचायत रायतपुरा | Completed | 43000 | 41924 | 2021-01-10 | 2022-07-01
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/80777 — sauchlay nirman deenanath | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83198 — individual latrin ramgopal/darshanlal | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83226 — individual latrin nirman satyanarayan/darshanlal | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83249 — individual latrin nirman chandrakali/lakhan singh | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83261 — individual latrin nirman lal singh/gangaram | Completed | 4500 | 4428 | 2013-12-22 | 2013-12-31
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83324 — individual latrin maharaj singh/kalicharan | Completed | 4500 | 4428 | 2013-12-22 | 2013-12-31
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83327 — individual latrin ashok/kalicharan | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83334 — individual latrin santosh/bhogiram | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83342 — individual latrindataram/bhogiram | Completed | 4500 | 4428 | 2014-02-10 | 2014-02-21
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83346 — individual latrin ramnivas/gopiram | Completed | 4500 | 4428 | 2013-12-22 | 2013-12-31
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83353 — individual latrin nathuram/harigyan | Completed | 4500 | 4428 | 2013-12-22 | 2013-12-31
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83356 — individual latrin moharsingh/tejsingh | Completed | 4500 | 4136 | 2013-12-22 | 2013-12-31
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83361 — individual latrin rajaram/jaganlal | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83362 — individual latrin angoori bai/baburam | Deleted | 4500 | 0 | 2013-04-16
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1702004019/RS/83368 — INDIVIDUAL LATRIN RANJEET/RAMNATH | Completed | 4500 | 4428 | 2013-12-22 | 2013-12-31
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702004019/WC/22012034326704 — पार सुद्रढकरण तालाब खेड़े क पूरा (शंकरपुर) | Deleted | 666000 | 0 | 2017-06-26
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004019/WC/22012034381737 — Talab Work - GP Rayatpura | Closed | 0 | 0 | 2017-01-26
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004019/WC/22012034501950 — नाला निर्माण कार्य रवा की पुलिया से कंचनपुर पुलिया तक ग्राम पंचायत रायतपुरा | Completed | 1238386 | 543874 | 2020-07-07 | 2022-07-01
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004019/WC/22012035023000 — अमृत सरोवर डॉग टैंक धीर सिंह पटेल के घर के पास कतरनी का पुरा शंकरपुर GP Rayatpura | Closed | 0 | 0 | 2022-04-14
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004019/WC/22012035024649 — सामुदायिक जल संचय तालाब कार्य धीर सिंह के घर के पास कतरनी का पुरा GP Rayatpura | Physically Completed | 1485020.85 | 356284 | 2022-12-20 | 2026-06-23
BHIND / GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702004019/WC/22012035298041 — dugbel rechage pit nirman karya sheesham bala kua ke pass rayatpura | Closed | 25899.46 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702004019/WC/22012035298045 — dugbel rechage pit nirman karya avatar singh ke khet ke pass rayatpura | Closed | 25899.46 | 0 | 2025-04-01