## Work List
Exported on: 2026-10-07 03:02:39
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: EKHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1702004024/AV/22012034635643 — RCC NALA NIRMAN KARYA :- JATAV BASHTI SE ROAD KI OUR OR NALE KI OUR IKHARA GP IKHARA | Ongoing | 1434000 | 0 | 2023-05-31
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1702004024/AV/22012034635756 — MUKTI DHAM NIRMAN KARYA GP EKHARA | Ongoing | 285092.33 | 0 | 2023-09-05
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1702004024/AV/22012034635757 — MUKTI DHAM NIRMAN KARYA CHAK TUKEDA GP EKHARA | Ongoing | 286226.59 | 0 | 2023-09-05
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1702004024/AV/22012034635758 — MUKTI DHAM NIRMAN KARYA INDRAAWAS COLONY GP EKHARA | Ongoing | 287167.97 | 0 | 2023-09-05
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1702004024/AV/5039 — आँगनबाड़ी भवन निर्माण कार्य इन्द्राआवश कॉलोनी (चकतुकेड़ा) | Ongoing | 330000 | 0 | 2016-12-17
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Repair & Maintenance of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034629143 — FLOOD CONTROL CHENNAL NIRMAN KARYA JASVEER SINGH KE KHET SE SAHIB SINGH KE KHET KI AUR | Ongoing | 702647.9 | 0 | 2023-02-01
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034630888 — Flood Control Channel Work तालाब से भदौरियाकेपुरा की पुलिया तक चकतुकेडा ग्राम पंचायत इकाहरा | Ongoing | 1100274.38 | 0 | 2023-02-01
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034633155 — water corse chanal nonera moje se trilok singh ke khet par gp ekhara | Ongoing | 1066880 | 0 | 2023-09-05
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034633156 — water corse chanal ranjeet ke khet se indira awas kaloni tak gp ekhara | Ongoing | 478755.3 | 0 | 2023-09-05
BHIND / GOHAD | 2025-2026 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034633157 — water corse chanal babma se nariya ki or chaktukeda gp ekhara | Ongoing | 634316.33 | 0 | 2025-07-02
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034633158 — water corse chanal school ki puliya se tukeda ke nale ki or chaktukeda gp ekhara | Ongoing | 574907.42 | 0 | 2023-09-05
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702004024/FP/22012034633721 — water corse feeld chanal santosh ke khet se kakraripura ki or gp ekhara | Ongoing | 712607.15 | 0 | 2023-09-05
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702004024/IF/22012034584305 — मेढ बंधान निर्माण कार्य - बेवा मिथलेश / महेश शर्मा ग्राम पंचायत इकाहरा | Ongoing | 39824.27 | 0 | 2020-09-19
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004024/IF/22012035470324 — khet talab nirman karya ravi putra shri kaushal kishor ikhara | New | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004024/IF/22012035470329 — khet talab nirman karya ravi putra shri kaushal kishor ikhara | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004024/IF/22012035532306 — khet talab nirman karya ramotar putra rajaram ke khet par ikhara | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004024/IF/22012035532309 — khet talab nirman karya ramprasad putra rajaram ke khet par ikhara | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004024/IF/22012035554381 — JGSY KHET TALAB NIRMAN KARYA HARJENDRA SO HARIVANSH KE KHET PAR IKHARA | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004024/IF/22012035554383 — JGSY KHET TALAB NIRMAN KARYA HARPREET KAUR SO AMAR DEEP SINGH KE KHET PAR IKHARA | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004024/IF/22012035590819 — Ek Bagiya Maa ke Naam Ramdulari GP Ekahara | Ongoing | 278062.61 | 119702.41 | 2026-01-10
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004024/IF/22012035634860 — Ek Bagiya Maa Ke Naam MALATI DEVI GP Ekahara | Approved | 198176.38 | 0 | 2025-08-15
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004024/IF/22012035634873 — Ek Bagiya Maa Ke Naam Lata GP Ekahara | Approved | 198176.38 | 0 | 2025-08-15
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004024/IF/22012035634876 — Ek Bagiya Maa Ke Naam KRISHNA GOUR GP Ekahara | Ongoing | 198266.42 | 0 | 2026-01-10
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004024/IF/22012035637285 — Ek Bagiya Maa Ke Naam Lila GP Ekahara | Ongoing | 198176.38 | 0 | 2026-01-10
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702004024/IF/22012035637293 — Ek Bagiya Maa Ke Naam Geeta Bai GP Ekahara | Ongoing | 198176.38 | 0 | 2026-01-10
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Development of Waterlogged Land for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004024/LD/22012034573363 — नाला निर्माण कार्य त्रिलोचन के घर से मैनरोड की ओर ग्राम पंचायत इकाहरा | Ongoing | 749500 | 0 | 2021-11-19
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702004024/RC/22012034532180 — सुदूर संपर्क सडक कुलदीप के खेत से तिललोक के खेत की ओर चकतुकेडा ग्राम पंचायत इकाहरा | Ongoing | 2046095.65 | 0 | 2020-09-28
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja Road for Community | Construction of Road and Culvert | 1702004024/RC/22012034637215 — pewars blok nirman karya :-sikh samudayik mela parisar chaktukeda gp ikhara | Ongoing | 1443000 | 0 | 2023-06-01
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004024/WC/22012034617619 — चैकडेम निर्माण कार्य मुन्‍नालाल के खेत के पास ग्राम पंचायत इकाहरा | Ongoing | 1434680.62 | 0 | 2021-03-06
BHIND / GOHAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1702004024/WH/22012034939820 — तालाब जीर्णोद्धार कार्य रामप्रसाद गौड के खेत के पास ग्राम पंचायत इकहारा | Approved | 0 | 0 | 2024-04-14