## Work List
Exported on: 2026-10-12 11:15:40
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BADAGAR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587699 — Cattle Shed Work - Ramkumar / Jagdeesh GP Badagar | Ongoing | 63531.21 | 0 | 2020-08-01
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587700 — Cattle Shed Work - Shanti / Sirnam GP Badagar | Ongoing | 63531.21 | 0 | 2020-08-01
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587708 — Cattle Shed Work - Gangadhar / Rameswar GP Badagar | Ongoing | 63531.21 | 0 | 2020-08-10
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587711 — Cattle Shed Work - Kailashnarayan / Matadeen GP Badagar | Ongoing | 63531.21 | 0 | 2020-08-01
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587712 — Cattle Shed Work - Rajendra / Jaishreeram GP Badagar | Ongoing | 63531.21 | 0 | 2020-09-08
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587714 — Cattle Shed Work - Basanti / Hariram GP Badagar | Ongoing | 63531.21 | 0 | 2020-08-01
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034587716 — Cattle Shed Work - Beti / Rambihari GP Badagar | Ongoing | 63531.21 | 0 | 2020-08-01
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034590230 — Cattle Shed Work - Brajesh / Mahadev GP Badagar | Ongoing | 101273.16 | 0 | 2020-08-10
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034590240 — Cattle Shed Work - Ramsanehi / Asharam GP Badagar | Ongoing | 63531.21 | 0 | 2020-09-08
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034590241 — Cattle Shed Work - Ramkishore / Asharam GP Badagar | Ongoing | 63531.21 | 0 | 2020-09-08
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034590781 — Cattle Shed Work - Vijaysingh / Jardansingh GP Badagar | Ongoing | 101273.16 | 0 | 2020-08-10
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034594221 — Pashu shed nirman dinesh singh gp badagar | Ongoing | 101273.16 | 0 | 2020-08-10
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034594277 — Cattle Shed Work - ram kumar/ jagdeeshG.P Badaghar | Ongoing | 101273.16 | 0 | 2020-08-12
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034594280 — Cattle Shed Work - vijay singh / suresh G.P Badaghar | Ongoing | 63531.21 | 0 | 2020-09-08
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034597644 — Cattle Shed Work - Narendra / Dasrath GP Badagar | Ongoing | 63531.21 | 0 | 2022-05-12
BHIND / GOHAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702004049/IF/22012034597646 — Cattle Shed Work - Lallesh / Ramswroop GP Badagar | Ongoing | 63531.21 | 0 | 2020-09-08
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004049/IF/22012035356488 — khet talab nirman karya rajenda singh so babu singh ke khet par bankepur gp badagar | Approved | 0 | 0 | 2025-04-01
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004049/IF/22012035524763 — khet talab nirman karya keshav singh so raghuveer singh gram bankepur gp badagar | Ongoing | 227336.6 | 0 | 2025-05-21
BHIND / GOHAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/4518395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106344288 | Ongoing | 27000 | 0 | 2024-10-21
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5838615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105309213 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5838628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889286 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5838857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889319 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5838932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105309366 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5839039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889364 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5839084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114889265 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5839290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106344352 | Physically Completed | 23490 | 0 | 2025-12-16 | 2026-08-09
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004049/IF/IAY/5839371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105245342 | Ongoing | 27000 | 0 | 2025-12-16
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702004049/LD/22012034580548 — अर्थन ग्रेडेड बंड निर्माण कार्य अहिवरन के खेत से नहर की ओर ग्राम पंचायत बडागर | Ongoing | 1302108.2 | 0 | 2023-09-11
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1702004049/LD/22012034580718 — अर्थन ग्रेडेड बंड निर्माण कार्य Bhagat singh ke khet kai pass GP Badagar | Ongoing | 1347394.59 | 0 | 2023-08-24
BHIND / GOHAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702004049/RC/22012034826283 — CC ROAD NIRMAN KARYA PATEL KE GHAR SE MHADEV MANDIR TAK GP BADAGAR | Ongoing | 70000 | 0 | 2025-02-10
BHIND / GOHAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702004049/RC/22012034836313 — cc road nirman karya shiram prajapati ke ghar se raghunath ke goda tak gram bankepur gp badagar | New | 0 | 0 | 2025-01-26
BHIND / GOHAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702004049/RC/22012034837007 — CC ROAD NIRMAN KARYA SHREERAM PRAJAPATI KE GHAR SE RAGHUNATH KE GODA TAK GP BADAGAR | Ongoing | 48000 | 0 | 2025-03-08
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702004049/WC/22012034936355 — construction of flood/diversion channel for community suresh ke makaan se bhumiya baba ki or | Ongoing | 1206317.47 | 0 | 2022-05-14