## Work List
Exported on: 2026-10-15 07:52:12
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: CHHEKORI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702004076/AV/22012034400430 — khel medan baundri bal | Deleted | 0 | 0 | 2019-01-26
BHIND / GOHAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1702004076/DP/22012034482086 — Plantation Work Chhekuri GP Chhekuri | Closed | 335000 | 0 | 2019-04-14
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702004076/FP/22012034630109 — flood control chenal Mau mehganv road ki puliya se amrat sarovar ki or gp chekuri | Completed | 264958.89 | 203184 | 2022-12-22 | 2023-08-15
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004076/FP/22012034630110 — flood control chenal amrat sarovar se chekuri road ki or gp chhekuri | Completed | 912493.44 | 623322 | 2022-12-22 | 2023-08-15
BHIND / GOHAD | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702004076/FP/22012034632988 — Flood Control Chenal Mau Chhekuri Road Se Barah Masi Talab Ki or Chhekuri | Completed | 1387994.88 | 458354 | 2023-07-26 | 2025-04-18
BHIND / GOHAD | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702004076/IF/1000034980 — MEDBANDHAN WORK AASHARAM S/O RAMDEEN KUSHWAH | Completed | 41137 | 37962 | 2014-01-02 | 2014-06-04
BHIND / GOHAD | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702004076/IF/1000034989 — MEDBANDHAN WORK GENDALAL S/O HARDAYAL BAGHEL | Deleted | 34200 | 0 | 2013-08-17
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004076/IF/22012034352064 — shanti dham me braksha ropan karya | Deleted | 0 | 0 | 2017-06-07
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004076/IF/22012034352069 — shanti dham me braksha ropan karya | Completed | 335000 | 61096 | 2017-06-22 | 2021-10-29
BHIND / GOHAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702004076/IF/22012034354329 — Birksha ropan karya sidh baba mandir chhaikuri | Completed | 335000 | 58952 | 2017-07-06 | 2021-10-29
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004076/IF/22012035098906 — Khet Talab Nirman Work Avinash Ke khet par- Chhekuri | Physically Completed | 387261.22 | 253170 | 2025-04-22 | 2026-05-28
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Agro Forestry Block Plantation for Individual | Plantation | 1702004076/IF/22012035137126 — Vriksha Ropan Work (Amrat Vatika) Shala Bhavan Chhekuri | Ongoing | 54564.94 | 5347 | 2023-08-16
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702004076/IF/22012035521568 — Khet Talab Nirman Karya Chhunnalal Putra Sarnam Singh Gram Panchayat Chhekuri | Physically Completed | 147621.16 | 103617 | 2025-05-21 | 2026-05-08
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004076/IF/22012035521937 — Khet Talab Guddi Bai Bewa Heera Singh Gram Panchayat Chhekuri | Ongoing | 147621.16 | 20619 | 2025-05-21
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004076/IF/9926739518 — MEDBANDHAN KARYA JANAK SINGH S/O RAMDEEN | Completed | 52300 | 48042 | 2014-07-03 | 2014-11-05
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004076/IF/9926740186 — MEDBANDHAN KARYA BABURAM S/O MANGAKL KORI | Completed | 52300 | 40962 | 2014-07-03 | 2015-09-02
BHIND / GOHAD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004076/IF/9926740263 — MEDBANDHAN KARYA RAJARAM S/O KHACHRU | Completed | 52300 | 49926 | 2014-06-26 | 2014-10-22
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702004076/IF/9993674227 — MEDBANDHAN WORK SONABAI WO SHEETAL | Completed | 44200 | 41022 | 2015-10-01 | 2015-12-23
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004076/IF/9993674228 — MEDBANDHAN WORK RAMNARESH BAGERA SO FOOL SINGH | Completed | 64400 | 58194 | 2015-12-24 | 2016-03-30
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702004076/IF/9993674229 — MEDBANDHAN WORK SHRIKRISHAN BAGERA SO MATADEEN | Completed | 35100 | 32436 | 2015-09-10 | 2015-09-23
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004076/IF/9993721840 — MEDBANDHAN | Deleted | 0 | 0 | 2016-01-26
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004076/IF/9993721903 — med bandhan karya | Deleted | 0 | 0 | 2016-01-26
BHIND / GOHAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004076/IF/IAY/1870692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4184411 | Completed | 15660 | 15486 | 2018-11-01 | 2019-03-23
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004076/IF/IAY/195379 — Construction of IAY House -IAY REG. NO. MP-02-004-076-001/29553984 | Completed | 14310 | 3006 | 2017-02-23 | 2017-03-24
BHIND / GOHAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004076/IF/IAY/195380 — Construction of IAY House -IAY REG. NO. MP-02-004-076-001/29555074 | Completed | 14310 | 13026 | 2016-07-14 | 2017-01-26
BHIND / GOHAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702004076/IF/IAY/4218510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131742935 | Completed | 18360 | 18360 | 2022-08-16 | 2023-02-28
BHIND / GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/144 — मेडवंधान कार्य श्री लाल पुत्र ग्‍यादीन | Completed | 0 | 13452 | 2010-12-12 | 2010-12-12
BHIND / GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/145 — मेडवंधान कार्य प्रानसिह मिर्दा के खेत पर | Completed | 0 | 13116 | 2010-12-15 | 2010-12-15
BHIND / GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/149 — मेडवंधान कार्य गुन्‍ने लाल पुत्र देवलाल | Completed | 0 | 4800 | 2010-10-21 | 2010-10-21
BHIND / GOHAD | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/22012034262641 — SANTI Dham karya | Deleted | 0 | 0 | 2016-01-26
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/22012034294340 — Shanti dham chhaikuri | Deleted | 0 | 0 | 2016-04-16
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/22012034294359 — Shanti dham chhaikuri | Deleted | 0 | 0 | 2016-04-16
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702004076/LD/22012034294360 — shanti dham chhaikuri | Completed | 1170960 | 1119699.5 | 2016-12-08 | 2017-10-24
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/LD/22012034368987 — नाला निर्माण कार्य गा‍ेविन्‍दसिंह के खलियान से सुनाव नाला तक ग्राम पंचायत छैकुरी | Completed | 635000 | 206088 | 2018-07-05 | 2019-01-17
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702004076/LD/22012034543738 — पक्‍का चबूतरा / प्‍लेटफार्म निर्माण कार्य उपार्जन केन्‍द्र छैकुरी ग्राम पंचायत छैकुरी | Deleted | 0 | 0 | 2021-01-26
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/LD/22012034583195 — बोल्डर नाला निर्माण कार्य मैन रोड से शाला भवन की ओर ग्राम पंचायत छैकुरी | Completed | 666000 | 636735 | 2022-11-03 | 2023-12-19
BHIND / GOHAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/439 — मेडबंधान गुड़डीबाई/हरीसिह कुशवाह | Completed | 0 | 22692 | 2011-08-17 | 2011-08-30
BHIND / GOHAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/440 — मेउबध्‍ंाान गंगासिह/महाराजसिह मिर्ध | Completed | 0 | 29280 | 2011-09-14 | 2011-09-30
BHIND / GOHAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/453 — मेउबंधान समोखन सिह के खेत पर | Completed | 0 | 14640 | 2011-10-16 | 2011-10-22
BHIND / GOHAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/458 — मेउबध्‍ंाान रामसिया/खचेरू | Completed | 0 | 27072 | 2011-09-24 | 2012-12-11
BHIND / GOHAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/497 — मेढबन्‍धान कार्य नारायण सिह पुत्र गयाप्रसाद ग्राम छेंकुरी | Completed | 0 | 13908 | 2011-11-16 | 2012-12-11
BHIND / GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702004076/LD/70 — मेढबन्‍धान शिव सिंह / भूप सिंह | Completed | 0 | 3600 | 2010-08-08 | 2010-08-23
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702004076/PG/22012034311131 — Khel medan kary chhaikuri GP Chhekuri | Completed | 320000 | 293856 | 2017-06-01 | 2018-02-07
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034190519 — CC ROAD BRIJRAJSINGH MIRDHA K MAKAN SE SAHABSINGH | Completed | 111000 | 104160 | 2014-02-13 | 2016-10-21
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034192438 — CC ROAD JANAK SINGH KUSHWAH KE MAKAN SE ARJUN SING | Completed | 111000 | 106456 | 2014-01-09 | 2014-03-21
BHIND / GOHAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034222786 — CC ROAD NIRMAAN KARYA VISHAL SINGH PABAIYA KE HEND | Completed | 118000 | 111972 | 2014-07-31 | 2014-10-01
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034300185 — CC RAUD | Deleted | 0 | 0 | 2016-04-26
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034300194 — CC RAUD | Deleted | 0 | 0 | 2016-01-26
BHIND / GOHAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702004076/RC/22012034305795 — KHET SADAK BIRENDR MIRDHA KE MAKAN SE SHANTI DHAM TAK | Deleted | 0 | 0 | 2016-01-26
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034342851 — CC Rod ramsiya baghel ke makan se damar rod tak | Deleted | 127000 | 0 | 2017-04-23
BHIND / GOHAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034350580 — CC Rod niraman karya samudayak bhavan men rod se puttu singh ke makan tak | Completed | 365000 | 174408 | 2017-08-31 | 2018-03-08
BHIND / GOHAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702004076/RC/22012034375730 — Khet Sadak Work - Chhenkuri main road se Shantidham tak GP Chhenkuri | Deleted | 0 | 0 | 2017-01-26
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034395880 — C.C.Road Work - Balkishan ke makan se chakrapan jatav ke makan tak GP Chhekuri | Completed | 33200 | 32364 | 2018-10-04 | 2018-11-17
BHIND / GOHAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034395890 — C.C.Road Work - Samant tomar ke makan se bal beer ke makan tak GP Chekuri | Completed | 38000 | 38628 | 2018-10-04 | 2018-11-17
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034470857 — C.C.Road Work - बदनसिंह के घर से रफीक के घर तक ग्राम पंचायत छैकुरी | Completed | 40000 | 55088 | 2019-08-08 | 2019-10-03
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034470858 — C.C.Road Work - नारायणसिंह के मकान से कैलाश नारायण दीक्षित के घर तक ग्राम पंचायत छैकुरी | Completed | 18000 | 19008 | 2019-08-08 | 2019-09-26
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034470859 — C.C.Road Work - तेजपाल जाटव के मकान से नरेशसिंह पवईया के मकान तक ग्राम पंचायत छैकुरी | Completed | 19000 | 21472 | 2019-08-08 | 2019-10-03
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034510242 — सीसी रोड निर्माण कार्य देवेन्‍द्रसिंह के मकान से नवलसिंह के मकान तक ग्राम पंचायत छैकुरी | Completed | 67000 | 66528 | 2020-01-02 | 2020-01-25
BHIND / GOHAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034510244 — सीसी रोड निर्माण कार्य मैनरोड से घनश्‍यामसिंह के मकान तक ग्राम पंचायत छैकुरी | Completed | 30000 | 29920 | 2019-12-26 | 2020-01-03
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034543060 — CC Road Work Men Road Se Samant Tomar ke Makan Ki Or Gram Chhekuri | Completed | 42000 | 41040 | 2020-11-12 | 2020-12-01
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034543063 — CC Road Work Ramshankar Shakya Ke Makan Se Asharam Kushwah ke Makan Ki Or Gram Chhekuri | Completed | 63000 | 49020 | 2020-11-12 | 2020-12-15
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034543064 — CC Road Work Ramesh Pujari Ke Makan Se Ramshankar ke Makan Ki Or Gram Chhekuri | Completed | 63000 | 49020 | 2020-11-12 | 2020-12-14
BHIND / GOHAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034585226 — CC ROAD NIRMAN SANTOSH JATAV KE MAKAN SE VISHAL SINGH KE MAKAN TAK GP CHHEKURI | Completed | 44800 | 42846 | 2021-10-14 | 2021-10-30
BHIND / GOHAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034826344 — cc road or nali nirman main road se heera singh pawaiya ke makan ki or gp chhekuri | Closed | 37300 | 0 | 2025-02-17
BHIND / GOHAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702004076/RC/22012034836936 — CC ROAD NIRMAN OR NALI ASHU JAMADAR KE MAKAN SE DEVIPURA ROAD KI OR GP CHHEKURI | Ongoing | 37200 | 26000.64 | 2025-02-26
BHIND / GOHAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/234 — अलबेला सिह मिर्धा के घर से रेणुका मंदिर | Completed | 0 | 13000 | 2012-07-31 | 2013-08-14
BHIND / GOHAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/274 — सी0सी0निर्माण अलबेल सिह मिर्धा के मकान से रेनुका म | Completed | 113133 | 77410 | 2012-06-13 | 2013-08-20
BHIND / GOHAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702004076/RC/329 — सी0सी0रोड निर्माण कार्य रेणुका माता मंदिर से राधा | Completed | 121661 | 92140.01 | 2013-08-29 | 2014-02-26
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702004076/RS/22012034501680 — सामुदायिक ग्रामीण स्‍वच्‍छता परिसर ग्राम पंचायत chhekuri | Completed | 43000 | 41040 | 2020-11-26 | 2021-01-31
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702004076/WC/22012034294123 — Baray masi talab gahari karan | Deleted | 98000 | 0 | 2016-05-26
BHIND / GOHAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004076/WC/22012034323283 — TALAB MARAMMAT KARYA GRAM CHHEKURI | Completed | 190000 | 70004 | 2017-05-11 | 2017-10-24
BHIND / GOHAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702004076/WC/22012034355247 — bori bandhan karay sunav nala dhoriya ghat chhaikuri | Completed | 14000 | 9288 | 2017-09-28 | 2017-10-16
BHIND / GOHAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702004076/WC/22012034356772 — Bori bandhan karya school ke pass sunav nala chhaikuri | Completed | 1600000000 | 11352 | 2017-10-05 | 2017-10-24
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004076/WC/22012034381675 — Talab Work - GP Chhekuri | Deleted | 0 | 0 | 2017-01-26
BHIND / GOHAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Feeder Channel / Construction of Feeder Canal for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/WC/22012034383354 — Nala Work - Govindsingh ke khaliyan se sunav nala tak GP Chhenkuri | Deleted | 0 | 0 | 2017-01-26
BHIND / GOHAD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702004076/WC/22012034394908 — नवीन तालाब / पोखर निर्माण कार्य छैकुरी ग्राम पंचायत छैकुरी | Completed | 1239000 | 800832 | 2018-07-12 | 2020-11-21
BHIND / GOHAD | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/WC/22012034550958 — नाला निर्माण कार्य झोदा के नजदीक से छैकुरी की ओर ग्राम पंचायत छैकुरी | Completed | 1260183.05 | 998304 | 2020-07-30 | 2021-08-31
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012034550961 — चैकडेम / स्‍टॉपडेम निर्माण कार्य धोरियाघाट के पास ग्राम पंचायत छैकुरी | Completed | 1461833.94 | 1403007.52 | 2021-03-14 | 2021-06-30
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012034550962 — चैकडेम / स्‍टॉपडेम निर्माण कार्य राजीव शर्मा के खेत के पास ग्राम पंचायत छैकुरी | Deleted | 0 | 0 | 2020-04-14
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1702004076/WC/22012034587915 — Kachcha Nala Nirman Sharma ji Ke khet se Shala Bhavan Ki Or Gram Chhekuri | Completed | 1442475.9 | 1109280 | 2020-11-26 | 2021-05-31
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012034623270 — Chek Dam/ Stop Dam Jhora Ka har Dhouriya Ghat Gram Panchayat Chhekuri | Deleted | 0 | 0 | 2021-01-23
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012034623271 — Chek Dam/ Stop Dam Pandit Ji ke Har Me Sunao Nala Par Gram Panchayat Chhekuri | Completed | 1428025.17 | 1360170.23 | 2021-03-14 | 2021-06-30
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012034623272 — Chek Dam/ Stop Dam Shala Bhavan Ke Pas Gram Panchayat Chhekuri | Completed | 1458219.31 | 1405026.49 | 2021-03-18 | 2021-06-30
BHIND / GOHAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004076/WC/22012034623273 — Kaccha Nala Nirman Jhoda Ke har Se Gangeva Dev Sthan Ki Or Gram Panchayat - Chhekuri | Completed | 1489761.03 | 1243656 | 2021-03-14 | 2022-10-20
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1702004076/WC/22012034755609 — Kachcha Nala Nirman Shala Bhavan Se Pancham Baghel ke Khet Ki Or Gram Panchayat Chhekuri | Completed | 1477378.64 | 1144409 | 2021-06-11 | 2023-03-31
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1702004076/WC/22012034755625 — Kachcha Nala Nirman Gangeva Se Dinesh Pavia ke Khet Ki Or Gram Panchayat Chhekuri | Completed | 1473192.95 | 1115485 | 2021-06-11 | 2025-06-26
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1702004076/WC/22012034755626 — Kachcha Nala Nirman Gangeva Se Dinesh Pavia ke Khet Ki Or Gram Panchayat Chhekuri | Deleted | 0 | 0 | 2021-04-14
BHIND / GOHAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1702004076/WC/22012034884515 — तालाब जीर्णोद्धार एव बंड रिनोवेशन कार्य बारहमासी तालाब- छेकुरी | Deleted | 0 | 0 | 2021-11-01
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/WC/22012034941635 — Kachcha Nala Nirman Kary Barah Masi Talab Se Dang Chhekuri Ki Or | Completed | 805856.18 | 783120 | 2022-05-07 | 2022-06-13
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004076/WC/22012034941667 — Navin Talab Nirman Abilakh Ke Khet ke Pas Gram Panchayat- Chhekuri | Deleted | 0 | 0 | 2022-04-01
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702004076/WC/22012034970325 — अमृत सरोवर निर्माण कार्य अभिलास परिहार के खेत के पास ग्राम पंचायत छैकुरी | Completed | 2418000 | 2089764.4 | 2022-05-16 | 2024-01-10
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/WC/22012034994693 — Kachcha Nala Nirman Kary Amrat Sarovar Se Mou Mehgao Road Puliya Ki Or Gram Panchayat Chhekuri | Deleted | 0 | 0 | 2022-08-16
BHIND / GOHAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702004076/WC/22012034994700 — कच्चा नाला निर्माण कार्य अमृत सरोवर से मौ कनाथर रोड की ओर ग्रामपंचायत छेकुरी | Deleted | 0 | 0 | 2022-08-16
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012035012608 — CHECK DAM NIRMAN WORK HEERA LAL KE KHET KE PAS | Deleted | 0 | 0 | 2022-10-04
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702004076/WC/22012035012611 — check dam nirman kary hira singh ke khet ke pass gram panchayat chhekuri | Deleted | 0 | 0 | 2022-10-04
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702004076/WC/22012035020704 — डगटैंक तालाब निर्माण जलसंचय हेतु बारहमासी तालाब के ऊपर छैकुरी | Deleted | 0 | 0 | 2022-11-24
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702004076/WC/22012035026294 — तालाब जीर्णोद्धार अमृतसरोवर बारहमासी तालाब बंण्ड एंव पिचिंग कार्य ग्राम पंचायत छैकुरी | Deleted | 0 | 0 | 2022-11-24
BHIND / GOHAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702004076/WC/22012035071420 — डगटैंक/तालाब निर्माण कार्य जल संचयन हेतु -छैकुरी | Ongoing | 1341876.91 | 99892 | 2023-08-09
BHIND / GOHAD | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004076/WC/52 — सौकपिट निर्माण उदयवीर सिंह के हैण्‍डपम्‍प के पास | Completed | 9440 | 9440 | 2009-07-01 | 2009-07-01
BHIND / GOHAD | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702004076/WC/53 — सौकपिट निर्माण की हनुमान मंदिर वाले हैण्‍डपम्‍प के पास | Completed | 9650 | 9650 | 2010-05-12 | 2010-05-12
BHIND / GOHAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702004080/IF/9993694555 — medbandhan work karan singh / sukhwasee | Deleted | 0 | 0 | 2015-10-04