## Work List
Exported on: 2026-10-11 19:39:27
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GURYANCHHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / GOHAD | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004086/IF/22012034665847 — खेत तालाब निर्माण कार्य राममूर्ति / गिरवर ग्राम पंचायत गुरियांची | Ongoing | 337715.44 | 0 | 2021-11-19
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004086/IF/22012035503368 — Khet talab nirman karya chadniYadav/Narendra yadav ke khet par simiriya gp guriyachi | Ongoing | 236601.74 | 0 | 2025-05-17
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702004086/IF/22012035519841 — Khet talab nirman karya Atabal singh parihar ke khet par simiriya gp guriyachi | Ongoing | 229229.59 | 0 | 2025-05-20
BHIND / GOHAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702004086/IF/IAY/5440270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147270212 | Ongoing | 27000 | 0 | 2026-02-12
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1702004086/WC/22012034647253 — CONTOUR TRANCH NIRMAAN KARYA PAHADIYA PAR GURIYANCHI | Ongoing | 1479466.82 | 0 | 2022-05-19
BHIND / GOHAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702004086/WC/22012034750127 — NAVEEN TALAB NIRMAAN KARYA PAHADI PR Guriyanchi | Ongoing | 1290491.76 | 0 | 2022-05-19
BHIND / GOHAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1702004086/WC/22012035253943 — Samudayik dung tank kayamsingh chouhan ke khet ke pass gp guryanchi | Approved | 0 | 0 | 2024-10-02
BHIND / GOHAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1702004086/WH/22012034939780 — Talab marammt karya road ke pas simiriya | New | 0 | 0 | 2024-04-25