## Work List
Exported on: 2026-10-22 05:54:57
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PACHOKHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1702005017/AV/22012034510228 — Aaganwadi Bhawan Nirman-Gandh Bahoripura | Ongoing | 312000 | 0 | 2020-09-06
BHIND / RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1702005017/DP/22012034496553 — Plantation santoshi mata mandir ke pass pachokhara | Ongoing | 390826.48 | 0 | 2020-09-27
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012034352560 — vriksharopan harijan basti | Ongoing | 335000 | 0 | 2017-08-10
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012034353595 — vriksharopan road side kaloni se pachokhra | Ongoing | 335000 | 0 | 2017-08-10
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702005017/IF/22012034615039 — Pashu Shed Nirman-Ratiram/Nathu, Pachokhara | Ongoing | 101273.16 | 0 | 2020-09-27
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702005017/IF/22012034615040 — Pashu Shed Nirman-Ravindra Singh/Subhash | Ongoing | 101273.16 | 0 | 2020-09-27
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702005017/IF/22012034615042 — Pashu Shed Nirman-Rajesh Singh/Ramdeen | Ongoing | 101273.16 | 0 | 2020-09-27
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702005017/IF/22012034615052 — Pashu Shed Nirman-Dharmendra Singh/Johri Singh | Ongoing | 101273.16 | 0 | 2020-09-27
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individual | Cattle Shed | 1702005017/IF/22012034615053 — Pashu Shed Nirman-Sahdev Singh/Dwarika | Ongoing | 101273.16 | 0 | 2020-09-27
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005017/IF/22012034813789 — Mead Bandhan Pratap / Kamtaprasad | Ongoing | 44561.71 | 0 | 2021-10-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1702005017/IF/22012035614456 — EK BAGIYA MAA KE NAM HEMLEKHA | Approved | 0 | 0 | 2025-08-15
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1702005017/IF/22012035614467 — EK BAGIYA MAA KE NAM ANJU/RAMSARAN | Approved | 0 | 0 | 2025-08-15
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1702005017/IF/22012035614472 — EK BAGIYA MAA KE NAM SHAKUNTLA DEVI | Approved | 0 | 0 | 2025-08-15
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035614872 — EK BAGIYA MAA KE NAM HEMLEKHA | Ongoing | 263510.03 | 3600 | 2025-09-11
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035614874 — EK BAGIYA MAA KE NAM SHAKUNTLA DEVI | Ongoing | 263510.03 | 3600 | 2025-09-11
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035614875 — EK BAGIYA MAA KE NAM ANJU/RAMSARAN | Ongoing | 263510.03 | 0 | 2025-10-31
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035617549 — EK BAGIYA MAA KE NAM VARSHA DEVI/PUSHPENDRA SINGH | Ongoing | 263510.03 | 0 | 2025-10-31
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035617553 — EK BAGIYA MAA KE NAM RASHMI/RAVINDRA SINGH | Ongoing | 263510.03 | 0 | 2026-08-06
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035623026 — EK BAGIYA MAA KE NAM ARTI/PUSHPENDRA | Approved | 266577.25 | 0 | 2025-09-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035623027 — EK BAGIYA MAA KE NAM MURTI/ | Ongoing | 266577.25 | 0 | 2025-10-31
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035623028 — EK BAGIYA MAA KE NAM MUNNI DEVI/NIRANJAN | Ongoing | 266577.25 | 0 | 2025-10-31
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035623030 — EK BAGIYA MAA KE NAM SUMAN/DURAGPAL | Approved | 266577.25 | 0 | 2025-09-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035639808 — EK BAGIYA MAA KE NAAM SANJU DEVI | Approved | 266578.64 | 0 | 2025-09-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035639812 — EK BAGIYA MAA KE NAAM SARITA DEVI | Approved | 266578.64 | 0 | 2025-09-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035640438 — EK BAGIYA MAA KE NAAM Sapna Devi/Jitndra Singh | Approved | 266578.64 | 0 | 2025-09-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035654998 — EK BAGIYA MAA KE NAM DEEPKA SHARMA/ATUL SHARMA | Approved | 266578.64 | 0 | 2025-08-15
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035657265 — EK BAGIYA MAA KE NAM bebi devi/rajkumar | Ongoing | 266578.64 | 0 | 2026-09-22
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005017/IF/22012035657266 — EK BAGIYA MAA KE NAM gyanvati/satendra | Approved | 266578.64 | 0 | 2025-09-02
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/2350791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3138579 | Ongoing | 27000 | 0 | 2026-04-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/2351010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3651374 | Ongoing | 27000 | 0 | 2026-01-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/4743053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113830055 | Ongoing | 27000 | 0 | 2025-05-11
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/4937734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105704697 | Approved | 27000 | 0 | 2025-03-09
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/4940516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106217139 | Ongoing | 27000 | 0 | 2025-12-31
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5302033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120799282 | Approved | 27000 | 0 | 2025-03-16
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5707520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115337547 | Approved | 27000 | 0 | 2025-05-21
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5845698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132908816 | Approved | 27000 | 0 | 2025-02-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149604158 | Ongoing | 27000 | 9000 | 2026-01-29
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114002293 | Completed | 23490 | 0 | 2026-01-29 | 2026-07-13
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113829381 | Physically Completed | 23490 | 3300 | 2026-01-29 | 2026-08-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106855433 | Completed | 23490 | 0 | 2026-01-29 | 2026-07-20
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126475256 | Physically Completed | 23490 | 4800 | 2026-01-29 | 2026-08-09
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120377785 | Ongoing | 27000 | 0 | 2026-01-29
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105796170 | Physically Completed | 23490 | 3300 | 2026-01-29 | 2026-08-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105788392 | Ongoing | 27000 | 4800 | 2026-01-29
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113702049 | Completed | 23490 | 0 | 2026-01-29 | 2026-07-13
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105597280 | Physically Completed | 23490 | 0 | 2026-01-29 | 2026-08-23
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144847708 | Ongoing | 27000 | 4800 | 2026-01-29
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/5877423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106263492 | Ongoing | 27000 | 4800 | 2026-01-29
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6050414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105785790 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6050824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105786977 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6051511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105788911 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6051888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106217289 | Approved | 27000 | 0 | 2025-09-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115014213 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105694521 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117773869 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149585152 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106490654 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114721742 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105794526 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6052698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106265750 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6053230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105794636 | Ongoing | 27000 | 0 | 2026-07-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6053274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105794739 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6053364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105793015 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6053514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100670447 | Ongoing | 27000 | 7200 | 2026-07-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6053555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150135233 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6053606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106128049 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105786641 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149660067 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106440696 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106441091 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106439517 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105792890 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106216830 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105792694 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114720915 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150002688 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105792544 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6056752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105792089 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6057194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114720885 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6057843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105794824 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6057934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150168867 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6057979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150113456 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6057980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114720748 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6057981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151127106 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6058117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114720714 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6058430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105790276 | Approved | 27000 | 0 | 2026-02-26
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6058431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105795522 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6058517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105789979 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6237557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105794129 | Approved | 27000 | 0 | 2026-03-24
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/6237791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106265679 | Approved | 23490 | 0 | 2026-04-16
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1702005017/IF/IAY/831484 — Construction of IAY House -IAY REG. NO. MP1053363 | Ongoing | 27000 | 0 | 2026-04-18
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702005017/RC/22012034523567 — Sudur sadak Nodha road se dariyapura tak pachokhara | Ongoing | 1629058.35 | 0 | 2020-07-12
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702005017/RC/22012034557720 — sudur sadak gram gandh se muratpura ki or pachokhara | Ongoing | 2447957.65 | 0 | 2021-03-02
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702005017/RS/22012034525834 — kachara upchar bhandar sed usar sthan stedeum ke pas pachokhara | Ongoing | 43305 | 0 | 2021-06-19
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1702005017/RS/22012034537348 — nadep nirman heera singh ke ghar ke pass pachokhara | Ongoing | 1627 | 0 | 2021-07-09