## Work List
Exported on: 2026-09-08 09:50:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: SURGHAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Building for Gram Panchayats / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034371121 — PANCHAYAT BHAVAN NIRMAN | Deleted | 514000 | 0 | 2016-10-02
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702005038/AV/22012034393590 — शांति धाम निर्माण ग्राम अहरौली | Ongoing | 180000 | 179816 | 2019-02-03
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034393591 — पंचायत भवन निर्माण ग्राम सुरघान | Ongoing | 514000 | 499608 | 2019-01-13
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702005038/AV/22012034393668 — SHANTI DHAM NIRMAN GRAM SURGHAN | Ongoing | 245000 | 216577.06 | 2019-01-13
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034620061 — Maa Ki Bagiya Govt. Primary School, Ahroli, Surghan | Ongoing | 5600 | 2448 | 2022-12-15
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034620067 — Maa Ki Bagiya Govt. Middle School, Ahroli, Surghan | Closed | 0 | 0 | 2022-04-14
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034620069 — Maa Ki Bagiya Govt. Middle School, Ahroli, Surghan | Ongoing | 5600 | 2448 | 2022-12-15
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034620070 — Maa Ki Bagiya Govt. Primary School, Kanhaipura, Surghan | Ongoing | 5600 | 2448 | 2022-12-15
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702005038/AV/22012034620073 — Maa Ki Bagiya Govt. Primary School, Surghan | Ongoing | 5600 | 2448 | 2022-12-15
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702005038/DP/22012034579892 — Braksharopan P school surghan | Closed | 0 | 0 | 2023-04-14
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702005038/DP/22012034579893 — Braksharopan shantidham parisar surghan | Closed | 0 | 0 | 2023-04-14
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702005038/DP/22012034579894 — braksharopan P school Ahroli | Closed | 430106.07 | 0 | 2023-04-14
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1702005038/DP/22012034579895 — Braksharopan shantidham parisar ahroli | Closed | 430106.07 | 0 | 2023-04-14
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1702005038/FP/22012034629207 — Nala Nirman Prem Singh ke Ghar Se Heera Singh Ke Gonda Tak, Surghan | Closed | 99900 | 0 | 2022-05-20
BHIND / RON | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005038/FP/22012034630696 — Nala nirman P.school se khel maidan tak ahroli | Closed | 0 | 0 | 2022-10-02
BHIND / RON | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702005038/FP/22012034633358 — kachcha nala nirman PS se talab tak Ahroli | Closed | 309173.4 | 0 | 2023-04-14
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702005038/IF/22012034304634 — Nadep tanka Harcharn/Balkishan | Deleted | 12000 | 0 | 2016-12-01
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702005038/IF/22012034304635 — Nadep tanka Ramnaresh/Madhosingh | Deleted | 12000 | 0 | 2016-12-08
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702005038/IF/22012034304649 — Nadep taka rajkumar/dwarka prasad surghan | Deleted | 12000 | 0 | 2016-12-15
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005038/IF/22012034347818 — vriksharopan road side surghan se guda ki or surghan | Completed | 335000 | 23880 | 2017-06-22 | 2021-05-11
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005038/IF/22012034354643 — VRIKSHAROPAN ROAD SIDE | Completed | 335000 | 23880 | 2017-07-13 | 2021-05-11
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005038/IF/22012034354646 — VRIKSHAROPAN ROAD SIDE AHROLI MARG | Completed | 335000 | 23880 | 2017-07-13 | 2021-05-11
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702005038/IF/22012034354649 — VRIKSHAROPAN SADAK KINARE SCHOOL KE PASS | Completed | 335000 | 18032 | 2017-07-27 | 2021-05-11
BHIND / RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1702005038/IF/22012034571335 — khet talab girjesh kumar surgan | Completed | 332572.21 | 157338 | 2020-07-11 | 2021-05-11
BHIND / RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1702005038/IF/22012034571336 — khet talab ramswaroop surghan | Completed | 332572.21 | 224580 | 2020-07-11 | 2021-05-11
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/22012034596218 — pashused mulchandra/ramswaroop | Completed | 101273.16 | 84420.62 | 2020-09-20 | 2025-05-19
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/22012034596219 — pashused atul/mulchandra | Completed | 101273.16 | 83280.62 | 2020-09-20 | 2023-05-25
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/22012034596221 — pashused pankaj/mulchandra | Closed | 0 | 0 | 2020-04-14
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/22012034596224 — pashused sarvesh/ramswaroop | Closed | 101273.16 | 0 | 2020-04-14
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/22012034596225 — pashused girjeshkumar/madhoveni | Closed | 101273.16 | 0 | 2020-04-14
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/22012034596226 — pashused chanda devi/ramnaresh | Closed | 101273.16 | 0 | 2020-04-14
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727865 — med bnadhan manna singh/ochelal | Completed | 45223.33 | 34740 | 2021-06-06 | 2022-11-22
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727874 — med bnadhan lal singh/hardyal | Ongoing | 43447.88 | 20844 | 2021-05-29
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727882 — med bnadhan suresh /chotelal | Completed | 43955.15 | 35496 | 2022-06-30 | 2023-05-24
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727890 — med bnadhan suneta devi/gajendra | Completed | 44124.24 | 40392 | 2022-05-27 | 2022-11-22
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727895 — med bnadhan ranibai mulchand | Completed | 44462.42 | 36720 | 2022-05-27 | 2023-05-25
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727905 — med bnadhan baburam/sukhbasi | Completed | 44631.51 | 33582 | 2021-06-25 | 2025-05-13
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727909 — med bnadhan ramsanehi/jaylal | Completed | 43278.79 | 36720 | 2021-06-24 | 2025-05-13
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727921 — med bnadhan panna lal /kashiram | Physically Completed | 44631.51 | 35898 | 2021-06-14 | 2021-11-15
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of pebble peripheral bund for indiv / Construction of Pebble peripheral/farm/field Bund for Individuals | Construction of Bund | 1702005038/IF/22012034727922 — med bnadhan malkhan/gangu | Physically Completed | 44293.32 | 34740 | 2021-06-14 | 2021-11-15
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012034996559 — khet talab Rajesh/Ochhelal | Closed | 0 | 0 | 2022-04-14
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012034996566 — khet talab mamta/Ochhelal | Ongoing | 356340.1 | 184620 | 2022-11-24
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012034996576 — Khet talab Mataprasad/Ramdayal | Closed | 0 | 0 | 2022-04-14
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012034996578 — khet talab Punu/ramdayal | Completed | 356340.1 | 281724 | 2022-12-03 | 2024-02-20
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012034996583 — Khet talab Harwa/Phool singh | Closed | 0 | 0 | 2022-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035503291 — khet talab Ashok kumar/ramnaresh surghan | Ongoing | 147621.16 | 98919 | 2025-05-19
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035503337 — khet talab ramesh/badalu surghan | Ongoing | 147621.16 | 261 | 2025-05-19
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538349 — khet talab kishunlal/nathu surghan | Ongoing | 147621.16 | 3132 | 2025-06-05
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538359 — khet talab umesh/raghuveer ahrolee | Ongoing | 147621.16 | 4698 | 2025-06-05
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538368 — khet talab parashuram/baldhari ahrolee | Ongoing | 147621.16 | 3132 | 2025-06-05
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538392 — khet talab ramsiya/baldhari ahroli | Ongoing | 147621.16 | 3132 | 2025-06-05
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538589 — khet talalb vinod/baldhari ahroli | Ongoing | 147621.16 | 3132 | 2025-06-05
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538607 — khet talab nagendra singh/babusingh ahroli | Ongoing | 147621.16 | 3132 | 2025-06-29
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035538617 — khet talalb udaypratap/vishram singh ahroli | Ongoing | 147621.16 | 6264 | 2025-06-05
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702005038/IF/22012035574270 — Plantation of priyanka farm | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1702005038/IF/22012035574714 — dugwell girjesh kumar ke kua par | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574728 — khet talab nirman suresh/chhote surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574736 — khet talalb nirman kanchhidde/rajaram surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574739 — khet talab nirman chandan/pokhan surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574750 — khet talab nirman manna singh/ochhe surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574756 — khet talab nirman Megh singh/vijay singh surghan | New | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574757 — khet talab nirman Megh singh/vijay singh surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574767 — khet talab nirman bhagwan singh/maniram surgan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574771 — khet talab nirman arvind/majboot surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574777 — khet talab nirman suneel/babu singh surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574778 — khet talab nirman budhabai/vijay singh surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574783 — khet talab nirman malkhan singh/babu singh surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574796 — khet talab nirman brajesh/udayram surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574805 — khet talab nirman Loksingh/Ochhe surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574809 — khet talab niran raju/baljeet surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/IF/22012035574817 — khet talab sunita/gajendra singh surghan | Approved | 0 | 0 | 2025-04-14
BHIND / RON | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/9926701963 — mabeshi sed Kadore/mani | Deleted | 89000 | 0 | 2014-02-15
BHIND / RON | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/9926714140 — mabeshi sed rambahadur/ghamandi Ahroli surghan | Deleted | 89000 | 0 | 2014-01-26
BHIND / RON | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1702005038/IF/9926714149 — mabeshi sed Ghamndi/ganpat Ahroli surghan | Deleted | 89000 | 0 | 2014-01-26
BHIND / RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/9993704806 — pashushed nirman puttulal/hardyal surghan | Deleted | 122000 | 0 | 2016-01-14
BHIND / RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/9993704809 — pashushed nirman ashok / bedri surghan | Completed | 122000 | 97558.35 | 2016-01-28 | 2017-12-05
BHIND / RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/9993708359 — pashu shed nirman longadevi/devidyal surghan | Completed | 122000 | 101704.82 | 2016-02-04 | 2017-12-05
BHIND / RON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702005038/IF/9993708361 — pashu shed nirman sarnam/hariram surghan | Deleted | 122000 | 0 | 2015-08-15
BHIND / RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/121532 — Construction of IAY House -IAY REG. NO. MP-02-005-038-002/100 | Completed | 14310 | 14490 | 2016-08-11 | 2018-12-29
BHIND / RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/121533 — Construction of IAY House -IAY REG. NO. MP-02-005-038-002/92 | Completed | 14310 | 15492 | 2016-08-04 | 2018-12-14
BHIND / RON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2278581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5315150 | Physically Completed | 17100 | 16308 | 2020-04-24 | 2024-11-21
BHIND / RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2295961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5314836 | Approved | 27000 | 0 | 2019-07-31
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2295990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5364380 | Completed | 17100 | 15147 | 2022-03-09 | 2024-02-20
BHIND / RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2296106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5621606 | Approved | 27000 | 0 | 2019-07-31
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2296185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5320510 | Completed | 17100 | 16840 | 2022-03-09 | 2024-02-20
BHIND / RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2296230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5403291 | Approved | 27000 | 0 | 2019-07-31
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2296286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5413490 | Completed | 17100 | 15310 | 2022-03-16 | 2024-02-20
BHIND / RON | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2317174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5377506 | Approved | 27000 | 0 | 2019-08-20
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/2330529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5331409 | Completed | 17100 | 15912 | 2022-03-19 | 2024-02-20
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3258857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3741243 | Completed | 17370 | 17238 | 2022-03-09 | 2024-02-20
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3267190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4765443 | Completed | 17370 | 16872 | 2022-03-09 | 2024-02-20
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3267239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4769179 | Completed | 17370 | 17070 | 2022-03-09 | 2024-02-20
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3276942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5425378 | Physically Completed | 17370 | 16541 | 2022-03-09 | 2024-11-21
BHIND / RON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3276949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5425622 | Completed | 17370 | 16616 | 2022-03-09 | 2024-02-20
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3690795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100656254 | Closed | 18360 | 0 | 2022-05-03
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3714563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684605 | Approved | 27000 | 0 | 2022-04-30
BHIND / RON | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/375746 — Construction of IAY House -IAY REG. NO. MP1448951 | Completed | 15030 | 16032 | 2017-02-02 | 2017-12-07
BHIND / RON | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/3771828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120578785 | Closed | 18360 | 0 | 2022-05-04
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/4735661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100656297 | Ongoing | 27000 | 23490 | 2025-04-21
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/4739511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683821 | Ongoing | 27000 | 23130 | 2025-03-21
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/4761971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120561255 | Ongoing | 27000 | 23490 | 2025-04-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5570552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683501 | Ongoing | 27000 | 22968 | 2025-09-27
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5570553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683546 | Approved | 27000 | 0 | 2025-03-25
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5570554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683614 | Ongoing | 27000 | 1566 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5571060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120805832 | Ongoing | 27000 | 1305 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5571347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106810638 | Physically Completed | 23490 | 22446 | 2025-09-27 | 2026-08-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5572565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118380618 | Ongoing | 27000 | 2610 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5572653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120574086 | Ongoing | 27000 | 21924 | 2025-12-17
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5572746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684004 | Ongoing | 27000 | 4698 | 2025-09-27
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5572747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684234 | Physically Completed | 23490 | 22968 | 2025-09-27 | 2026-08-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5572748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684318 | Physically Completed | 23490 | 22446 | 2026-01-18 | 2026-07-12
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5572827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120561019 | Ongoing | 27000 | 18792 | 2025-12-07
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120565349 | Ongoing | 27000 | 3132 | 2026-01-18
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683449 | Approved | 27000 | 0 | 2025-03-25
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684364 | Ongoing | 27000 | 9396 | 2025-09-27
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684422 | Ongoing | 27000 | 12528 | 2025-12-07
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684519 | Ongoing | 27000 | 9918 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684579 | Ongoing | 27000 | 1566 | 2026-01-18
BHIND / RON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120562964 | Approved | 27000 | 0 | 2025-03-25
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5706962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126429839 | Ongoing | 27000 | 1305 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683577 | Ongoing | 27000 | 22707 | 2025-12-07
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683712 | Ongoing | 27000 | 12528 | 2025-12-07
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683782 | Ongoing | 27000 | 12528 | 2025-12-07
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105683893 | Ongoing | 27000 | 12528 | 2025-12-07
BHIND / RON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684198 | Physically Completed | 23490 | 23490 | 2026-06-06 | 2026-08-02
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100656262 | Ongoing | 27000 | 9396 | 2025-09-27
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120564978 | Ongoing | 27000 | 9918 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118539554 | Physically Completed | 23490 | 22446 | 2026-01-18 | 2026-07-12
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126318672 | Ongoing | 27000 | 1305 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5707950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126513711 | Ongoing | 27000 | 4176 | 2025-09-27
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/5776561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684682 | Ongoing | 27000 | 2610 | 2026-01-18
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/6237550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105684101 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/6237910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118554850 | Approved | 27000 | 0 | 2026-02-10
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/744524 — Construction of IAY House -IAY REG. NO. MP2359632 | Completed | 15030 | 14448 | 2017-09-14 | 2018-05-18
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/761836 — Construction of IAY House -IAY REG. NO. MP3044647 | Completed | 15030 | 15576 | 2017-09-14 | 2018-06-30
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/775775 — Construction of IAY House -IAY REG. NO. MP3720455 | Completed | 15030 | 14706 | 2017-09-14 | 2018-07-31
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/925650 — Construction of IAY House -IAY REG. NO. MP2513420 | Completed | 15480 | 15480 | 2017-07-27 | 2018-04-10
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/926341 — Construction of IAY House -IAY REG. NO. MP2529002 | Completed | 15480 | 14568 | 2017-09-14 | 2018-08-25
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/975514 — Construction of IAY House -IAY REG. NO. MP3705045 | Completed | 15480 | 15588 | 2017-07-27 | 2018-06-30
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/975867 — Construction of IAY House -IAY REG. NO. MP3719336 | Completed | 15480 | 15576 | 2017-07-27 | 2018-07-02
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702005038/IF/IAY/976970 — Construction of IAY House -IAY REG. NO. MP3760942 | Completed | 15480 | 16584 | 2017-06-22 | 2018-06-30
BHIND / RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/168 — मेडबन्‍धान ज्‍वाली/ जालिम | Completed | 15662 | 0 | 2009-10-25 | 2013-12-14
BHIND / RON | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/169 — मेडबन्‍धान मंगली / धनपाल | Completed | 15662 | 0 | 2009-10-11 | 2013-12-14
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034227965 — medbandhan chhutkan/ patiram surghan | Completed | 21200 | 15900 | 2015-08-20 | 2015-09-02
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034227966 — medbandhan mansingh/ ochhelal surghan | Completed | 21200 | 14310 | 2015-08-27 | 2016-02-07
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034227967 — medbandhan sitaram/ raghuwar surghan | Completed | 28000 | 16218 | 2015-08-27 | 2016-01-07
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034228092 — medbandhan baburam / sukhwasi surghan | Completed | 21200 | 9699 | 2015-08-27 | 2015-11-07
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034228096 — medbandhan pradeep/patiram surghan | Completed | 28000 | 9858 | 2015-08-27 | 2016-01-08
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034228282 — medbandhan kadore/mojilal surghan | Completed | 24600 | 18126 | 2015-09-10 | 2015-12-23
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034229207 — MRDBANDHAN SANTRAM/ SHRIPAL SURGHAN | Completed | 21200 | 12402 | 2015-10-15 | 2015-12-15
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034229209 — MEDBANDHAN RAJENDRA/ ASHARAM SURGHAN | Deleted | 14500 | 0 | 2015-04-01
BHIND / RON | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/22012034229286 — medbandhan bharat/ harkishun surghan | Deleted | 17200 | 0 | 2015-04-01
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005038/LD/22012034239674 — medbandhan dharmjeet/rambharose | Completed | 38054 | 14310 | 2015-12-17 | 2015-12-22
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005038/LD/22012034239677 — medbandhan ramsiya/baldhari | Completed | 38054 | 34821 | 2015-12-03 | 2016-02-01
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005038/LD/22012034239680 — medbandhan rambahadur/ghamandhi | Completed | 34570 | 15264 | 2015-12-03 | 2016-01-12
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1702005038/LD/22012034262089 — med bandhan punu/ramdayal | Deleted | 0 | 0 | 2016-01-26
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005038/LD/22012034296234 — SHANTIDHAM NIRMAN SURGHAN | Deleted | 245000 | 0 | 2017-01-05
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702005038/LD/22012034296235 — SHANTIDHAM NIRMAN KARMARA RASTE AHROLI | Deleted | 180000 | 0 | 2016-12-01
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702005038/LD/22012034316578 — शांति धाम निर्माण ग्राम कन्हाई पुरा | Ongoing | 245000 | 232192.07 | 2019-01-13
BHIND / RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/3799403146 — Medbandhan Jandel/muloo surghan | Completed | 30700 | 584 | 2014-03-06 | 2014-05-28
BHIND / RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/3799403147 — Medbandhan Kishunlal/nathuram surghan | Completed | 29500 | 27156 | 2013-09-28 | 2013-12-12
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/427 — मेड्बंधान रमेश/बदलू सुरघान | Completed | 23842 | 14400 | 2010-08-28 | 2010-09-10
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/428 — मेड्बंधान धर्मजीत/धनपाल सुरघान | Completed | 23150 | 14400 | 2010-09-11 | 2010-09-23
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/429 — मेड्बंधान मुन्‍नालाल/पुत्‍तु सुरघान | Deleted | 21766 | 0 | 2010-08-21
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/455 — मेड्बंधान विजयराम/बद्री सुरघान | Completed | 15692 | 14400 | 2010-07-01 | 2010-07-13
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/456 — मेड्बंधान खरगो/बेबा सुरघान | Completed | 15662 | 14400 | 2010-07-15 | 2010-07-27
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/457 — मेड्बंधान रघुवर/परमसुख सुरघान | Completed | 15662 | 12000 | 2010-08-01 | 2010-08-07
BHIND / RON | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/458 — मेड्बंधान राजाराम/धनीराम सुरघान | Deleted | 0 | 0 | 2010-08-08
BHIND / RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/567 — मेड्बंधान मंटाई/रामचरन सुरघान | Completed | 24748 | 9272 | 2011-08-09 | 2011-08-23
BHIND / RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/568 — मेड्बंधान बुद्वसिंह/खुशाली सुरघान | Completed | 30697 | 12200 | 2011-08-02 | 2011-08-23
BHIND / RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/569 — मेड्बंधान भुवनदेवी/हरीराम सुरघान | Completed | 40596 | 30796 | 2011-08-16 | 2015-05-30
BHIND / RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/674 — मेड्बंधान शारदा देवी /बेबा परमसुख सुरघान | Completed | 33660 | 19642 | 2011-09-08 | 2011-12-05
BHIND / RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/699 — मेड्बंधान शोभाराम/श्री रामदीन सुरघान | Completed | 22279 | 9394 | 2011-09-22 | 2011-12-05
BHIND / RON | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702005038/LD/700 — मेड्बंधान हंसादेवी/दौलत सिंह सुरघान | Completed | 24748 | 14274 | 2011-09-30 | 2011-12-05
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702005038/PG/9425891835 — khel maidan karmara wale raste ahroli | Completed | 353000 | 227623.24 | 2017-02-16 | 2021-05-11
BHIND / RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034186233 — cc road panchparmeswar majbbot singh ke ghar se ma | Completed | 129500 | 84370 | 2013-12-07 | 2016-05-30
BHIND / RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034186237 — cc road panchparmeswar dhanpal baghel ke ghar phun | Completed | 125800 | 105534 | 2013-12-07 | 2016-02-02
BHIND / RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034200751 — cc road panchparmeswar talab se ramsiya ke makan t | Completed | 98600 | 60096 | 2014-02-01 | 2016-02-02
BHIND / RON | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702005038/RC/22012034209516 — CCROAD KACCHA PAUNCH MARG CHAUHAN KE TUBEL TAK SU | Deleted | 1124000 | 0 | 2014-03-06
BHIND / RON | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034225534 — cc road panchparmeswar prathvipal ke makan se dine | Completed | 128800 | 63748 | 2014-09-30 | 2016-02-02
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034266372 — cc road panchparmeswar kua se mata mandir tak surghan | Completed | 36300 | 19451 | 2015-07-08 | 2015-08-05
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034266373 — cc road panchparmeswar ramsiya baghel ke makan se lakharam ke goda tak surghan | Deleted | 0 | 0 | 2015-04-01
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034266374 — cc road panchparmeswar ramsiya baghel ke makan se lakharam ke goda tak surghan | Completed | 70600 | 65084 | 2015-07-09 | 2015-08-02
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034284671 — cc road rameswar ke makan se malkhan singh ke ghar tak surghan | Completed | 83400 | 74647 | 2016-01-28 | 2018-06-08
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034284928 — cc road panchparmeswar ramprakash ke ghar se talab tak surghan | Completed | 99800 | 96680 | 2015-12-17 | 2018-05-09
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034292813 — cc road panchparmeswar chhoto ke makan se talab ki or surghan | Completed | 37700 | 36299 | 2016-01-14 | 2018-08-06
BHIND / RON | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034305459 — cc road chemku mata se vijay singh ke makan tak surghan | Deleted | 0 | 0 | 2016-01-26
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034328402 — cc road panchparmeswar darbari ke makan se panchayat bhawan ki or surghan | Completed | 161000 | 131352 | 2017-03-09 | 2018-05-30
BHIND / RON | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034334695 — CC ROAD PANCHPARMESWAR PRI.SCHOOL SE PRI.SCHOOL KANHAIPURA KI OR SURGHAN | Closed | 159300 | 0 | 2017-01-01
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702005038/RC/22012034351787 — sudur sampark sadak kanahaipura se bhakoti mukhya margya tak | Completed | 980000 | 923557.7 | 2017-09-14 | 2021-04-05
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034365788 — cc road nirman karya sevaram baghel ke makan se devi baba ke sthan ki or | Completed | 44250 | 44032 | 2017-11-02 | 2018-04-20
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034373049 — CC raod | Closed | 0 | 0 | 2017-10-02
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034380637 — cc road dwarka prasad ke makan se prathvi pal ke makan ki or surghan | Physically Completed | 37687 | 37392 | 2018-08-15 | 2021-11-15
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034380638 — cc road gyadeen ke makan se gangaram ke makan ki or kadhaipura surghan | Completed | 44250 | 43932 | 2018-01-11 | 2019-02-08
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034380639 — cc road babu ke makan se mata ke mandir ki or kadhaipura surghan | Completed | 33150 | 29316 | 2018-01-11 | 2021-04-06
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034380640 — cc road ramveer ke makan se janved ke bada ki or kadhaipura surghan | Completed | 61950 | 60726 | 2018-01-11 | 2019-02-08
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034380641 — cc road sateesh ke makan se chhote ke makan ki or ahroli | Completed | 79650 | 79764 | 2018-01-25 | 2019-02-08
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387631 — cc road asharam rathor ke makan se puran ke makan ke pichhe tak | Completed | 19000 | 16704 | 2018-08-07 | 2019-02-08
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387632 — cc road gotiram ke makan se shishupal ke makan tak | Completed | 47000 | 43848 | 2018-07-03 | 2019-02-08
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387633 — cc road asharam ke makan se asharfi ke makan tak | Completed | 47000 | 36018 | 2018-07-10 | 2019-02-08
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387634 — cc road maniram ke makan se jagmohan ke makan tak | Completed | 84000 | 79008 | 2018-08-07 | 2020-08-21
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387635 — cc road malkhan ke makan se pahuj nadi ki or | Completed | 23000 | 21228 | 2018-09-28 | 2019-02-08
BHIND / RON | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387636 — cc road batai ke ghar se school tak | Closed | 0 | 0 | 2017-04-01
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034387745 — cc road batai ke ghar se latore ke makan tak surghan | Completed | 142000 | 102174 | 2018-08-15 | 2022-02-16
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034434956 — Panch Parmeshwar CC Road May Nali Nirman Hargovind Ke Makan Se Munni Ke Makan Ki Ore | Completed | 38595 | 21924 | 2019-01-27 | 2020-08-21
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034434957 — Panch Parmeshwar CC Road May Nali Nirman Babu Singh Ke Makan Se Raje Ke Makan Ki Ore | Physically Completed | 20460 | 17370 | 2021-05-20 | 2021-11-15
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034434958 — Panch Parmeshwar CC Road May Nali Nirman Nandram Ke Makan Se Puttu Lal Ke Makan Ki Ore | Ongoing | 6975 | 4614 | 2020-09-25
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034434959 — Panch Parmeshwar CC Road May Nali Nirman Baba Ke Sthan Se Sitaram Ke Ghar Ki ore | Ongoing | 6975 | 8088 | 2020-09-25
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034434960 — Panch Parmeshwar CC Road May Nali Nirman Chhutkan Ke Ghar Se Matadin Ke Makan Ki Ore | Ongoing | 6975 | 4614 | 2020-09-25
BHIND / RON | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034442304 — cc road | Closed | 0 | 0 | 2019-01-26
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034536556 — cc road dolti ke goda s uday singh ke makan tak kanahi ka pura | Ongoing | 49500 | 47850 | 2020-09-25
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034536560 — cc road dasrath ke makan se lakhan ke makan tak surghan | Ongoing | 34800 | 32028 | 2020-12-02
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034536562 — cc road dhanpal ke makan se jayprakash ke bade ki or surghan | Ongoing | 34800 | 33330 | 2020-09-25
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034541165 — cc road matadin ke ghar se rajesh ke bada ki or | Physically Completed | 39600 | 22800 | 2020-09-29 | 2021-11-15
BHIND / RON | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034541173 — cc raod mata mandir se pujari ke bada tak surghan | Ongoing | 80550 | 80130 | 2020-09-25
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034562342 — cc road kanahi k apura se panchatb bhwan ki or surghan | Physically Completed | 30000 | 13896 | 2021-05-29 | 2021-11-15
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034566264 — cc roa jabar singh ke makan se nirpat ke makan ki or surghan | Ongoing | 50250 | 39372 | 2021-12-04
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702005038/RC/22012034606559 — C.C.Road Mai Nali Nirman Bhagwan Singh Ke Makan Se Buddh Singh Ke Kunya Tak, Surghan | Ongoing | 59850 | 59304 | 2022-02-27
BHIND / RON | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1702005038/RS/22012034493845 — nali nirman rajendra singh ke ghar se darwari ke makan ki or surghan | Ongoing | 40200 | 22002 | 2021-04-05
BHIND / RON | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702005038/WC/22012034293860 — talab gahrikaran shankarji ke mandir pass surghan | Deleted | 99000 | 0 | 2016-04-01
BHIND / RON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702005038/WC/22012034384020 — NAVEEN TALAB NIRMAN | Closed | 0 | 0 | 2017-10-02
BHIND / RON | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005038/WC/22012034560591 — Naveen talab Budi mata mandir ke pass surghan | Completed | 1379555.46 | 603060 | 2020-06-19 | 2021-05-11
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005038/WC/22012034791503 — Naveen talab sarve no 23 Ahroli | Closed | 1472192.52 | 0 | 2021-04-14
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005038/WC/22012034791507 — Naveen talab nirman no 1 sarve no 1038 surghan | Ongoing | 1477259.82 | 418224 | 2021-10-05
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005038/WC/22012034791509 — Naveen talab no 2 sarve no 1039 surghan | Closed | 1467591.94 | 0 | 2021-04-14
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035005865 — Eardhan Check dem Budi mata mandir ke pass surghan | Closed | 0 | 0 | 2022-08-15
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035005866 — Eardhan check dem god baba ke pass surghan | Closed | 0 | 0 | 2022-08-15
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035005869 — Eardhan check dem ramsiya ke khet ke pass ahroli | Closed | 0 | 0 | 2022-08-15
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035005870 — Eardhan check dem puliya ke pass ahroli | Closed | 0 | 0 | 2022-08-15
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035014550 — Earthan check dem shiddh baba ke pass (kharaua) ahroli | Ongoing | 1445275.76 | 692097.24 | 2023-07-28
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702005038/WC/22012035025590 — Naveen talab nirman school ke pass banuapura surghan | Closed | 0 | 0 | 2022-10-02
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702005038/WC/22012035025591 — amrisarovar dub pock point talab Ahroli | Closed | 0 | 0 | 2022-10-02
BHIND / RON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035050504 — Eardhan check dem siddhbaba ke pass surghan | Closed | 0 | 0 | 2023-01-26
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035080524 — ardhan check dem puliya ke aage Ahroli | Closed | 1497486.18 | 0 | 2023-04-14
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702005038/WC/22012035080526 — Ardhan check dem ramsiya ke khet ke pass ahroli | Closed | 1429932.41 | 0 | 2023-04-14
BHIND / RON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702005038/WC/22012035080531 — Amart sarovar talab dab point tagar ke pass surghan | Closed | 1482720.94 | 0 | 2023-04-14
BHIND / RON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702005038/WC/22012035300016 — Dugwell Recharge Rupendra Baghel Ke Darwaje Ke Samne Gram Ahroli Surghan | Physically Completed | 25899.46 | 22090 | 2025-05-13 | 2026-04-25
BHIND / RON | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702005038/WC/9993646148 — talab ghrikaran awam vistar karya surghan | Completed | 221500 | 149986 | 2014-02-27 | 2016-01-26
BHIND / RON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702005038/WH/19959083 — talab bandh sudrikaran bagiche ke pass surghan | Completed | 86500 | 86344 | 2017-05-12 | 2018-01-20
BHIND / RON | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702005038/WH/19959178 — talab bandh sudrikaran karmara ke raste ahroli | Completed | 77500 | 77400 | 2017-06-01 | 2018-01-20
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005038/WH/22012034457009 — talab shantidham ke pass ahroli | Completed | 49940.51 | 44064 | 2022-03-26 | 2023-05-25
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005038/WH/22012034457010 — talab pareet baba ke pass surghan | Completed | 49893.19 | 46116 | 2022-03-16 | 2023-05-25
BHIND / RON | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702005038/WH/22012034457011 — talab mandir ke pass surghan | Completed | 49976.37 | 43800 | 2022-03-09 | 2023-05-25
BHIND / RON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1702005/DP/22012034627228 — Samudhayak vraksharopan hanumanji mandir ke peeche surghan | Approved | 0 | 0 | 2024-06-08