## Work List
Exported on: 2026-10-11 03:04:28
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: LAPVAHHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1702006007/FP/22012034642014 — आगनबाड़ी भवन से भुजरिया तालाब की ओर (जिला पंचायत मद 15 वाॅ वित्त से निर्मित नाले के आगे से) | Approved | 23000 | 0 | 2024-04-14
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4754744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118299302 | Ongoing | 27000 | 0 | 2025-01-28
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4754756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118301291 | Ongoing | 27000 | 0 | 2024-12-13
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4760773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120799758 | Ongoing | 27000 | 0 | 2024-12-13
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4763331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121363058 | Ongoing | 27000 | 0 | 2024-12-13
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4781148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128827957 | Ongoing | 27000 | 0 | 2024-12-13
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4785666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129838085 | Ongoing | 27000 | 0 | 2025-01-28
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4888973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121350976 | Ongoing | 27000 | 0 | 2025-02-22
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/4888974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121351509 | Ongoing | 27000 | 0 | 2025-02-22
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129000213 | Ongoing | 27000 | 3600 | 2025-12-26
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129000467 | Ongoing | 27000 | 3600 | 2026-05-02
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126592978 | Ongoing | 27000 | 9000 | 2026-02-24
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123368421 | Physically Completed | 23490 | 0 | 2025-12-13 | 2026-08-02
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126591821 | Ongoing | 27000 | 0 | 2025-09-17
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133743919 | Ongoing | 27000 | 7200 | 2025-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118041624 | Ongoing | 27000 | 0 | 2025-12-26
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151563407 | Ongoing | 27000 | 1800 | 2026-05-02
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126081602 | Ongoing | 27000 | 7200 | 2025-09-13
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121363795 | Ongoing | 27000 | 0 | 2026-04-23
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121348124 | Ongoing | 27000 | 3600 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125844540 | Ongoing | 27000 | 0 | 2025-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128995538 | Ongoing | 27000 | 5400 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128995701 | Ongoing | 27000 | 0 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143320967 | Ongoing | 27000 | 7200 | 2025-10-04
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129003422 | Ongoing | 27000 | 9000 | 2026-07-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128991208 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122889140 | Ongoing | 27000 | 3600 | 2025-12-26
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125845682 | Ongoing | 27000 | 10800 | 2026-05-11
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121346399 | Ongoing | 27000 | 0 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129004130 | Ongoing | 27000 | 7200 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125849243 | Ongoing | 27000 | 3600 | 2025-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118505179 | Ongoing | 27000 | 1800 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118511864 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120799592 | Ongoing | 27000 | 3600 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123049601 | Ongoing | 27000 | 0 | 2025-12-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128998473 | Ongoing | 27000 | 0 | 2025-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125025341 | Ongoing | 27000 | 0 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123050739 | Ongoing | 27000 | 3600 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127331967 | Ongoing | 27000 | 5400 | 2025-12-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121434521 | Physically Completed | 23490 | 3600 | 2025-09-17 | 2026-08-02
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121435625 | Ongoing | 27000 | 0 | 2025-09-13
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121361471 | Ongoing | 27000 | 5400 | 2026-07-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127329736 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118303621 | Ongoing | 27000 | 3600 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128990605 | Ongoing | 27000 | 3600 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685567 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128990732 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118496831 | Ongoing | 27000 | 7200 | 2026-02-24
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128988597 | Ongoing | 27000 | 0 | 2025-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128988787 | Ongoing | 27000 | 3600 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128990905 | Ongoing | 27000 | 0 | 2025-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128991128 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129001621 | Ongoing | 27000 | 0 | 2026-05-02
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129001855 | Ongoing | 27000 | 10800 | 2026-07-03
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129002024 | Ongoing | 27000 | 10800 | 2026-07-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128987940 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118516371 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5685637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118529962 | Ongoing | 27000 | 0 | 2025-12-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5721389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129000716 | Ongoing | 27000 | 7200 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5721390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129003204 | Ongoing | 27000 | 3600 | 2025-12-13
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5721391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129004611 | Ongoing | 27000 | 7200 | 2026-07-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5723643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127330080 | Ongoing | 27000 | 0 | 2025-12-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5723645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127332443 | Approved | 27000 | 0 | 2025-05-09
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5724079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128995866 | Physically Completed | 23490 | 0 | 2025-10-04 | 2026-08-02
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5725213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125808382 | Ongoing | 27000 | 10800 | 2026-05-02
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5727024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119086395 | Ongoing | 27000 | 3600 | 2025-10-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5727657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128988081 | Ongoing | 27000 | 7200 | 2026-02-24
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5727753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126064127 | Ongoing | 27000 | 7200 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5727961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129002413 | Ongoing | 27000 | 10800 | 2025-12-26
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5728870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118531364 | Ongoing | 27000 | 10800 | 2026-05-02
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5730150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121436193 | Approved | 27000 | 0 | 2025-05-09
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5882709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128186291 | Ongoing | 27000 | 7200 | 2026-07-03
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5885842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128999495 | Ongoing | 27000 | 12600 | 2026-07-03
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/5885889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126517728 | Ongoing | 27000 | 9000 | 2026-07-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/6330717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129004783 | Approved | 27000 | 0 | 2026-02-10
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/6331778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118522962 | Approved | 27000 | 0 | 2026-02-10
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/6332635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129005671 | Approved | 27000 | 0 | 2026-02-10
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/6386775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125309451 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/6387030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125158013 | Approved | 27000 | 0 | 2025-05-03
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006007/IF/IAY/6387515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121350223 | Approved | 27000 | 0 | 2026-06-15
BHIND / LAHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1702006007/LD/22012034587819 — बाउन्ड्रीबाॅल निर्माण कार्य नलकूप भवन व शंकर जी मंदिर परिसर ग्राम लपवाहा | Ongoing | 1391000 | 0 | 2023-03-14
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006007/RC/22012034618448 — पेवर ब्लाक निर्माण कार्य शा. प्रा. कन्या / बालक विद्यालय परिसर में ग्राम लपवाहा | Ongoing | 1397000 | 0 | 2023-01-09