## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006028/AV/22012034368760 — शांति धाम निसार ग्राम पंचायत करियबली | Completed | 245000 | 179859.16 | 2017-09-30 - 2019-04-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006028/AV/22012034368761 — शांति धाम निमार्ण ग्राम पंचायत करियबली | Ongoing | 245000 | 147032.8 | 2017-09-30 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702006028/AV/22012034509588 — खेल मैदान निमार्ण कार्य ग्राम करियबली ग्राम पंचायत करियबली | Ongoing | 864416.02 | 1140 | 2021-03-10 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1702006028/AV/22012034509700 — खेल मैदान निसार | Closed | 0 | 0 | 2020-04-04 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702006028/AV/4188 — Aanganbadi/Other Rural Infrastructure,KARIYAWALI | Completed | 330000 | 329990 | 2015-12-18 - 2018-04-04
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006028/DP/2 — व़क्षारोपण एवं तार फेसिंग सिद्वगुरू के स्‍थान पर निसार | Completed | 412000 | 141284 | 2009-01-22 - 2016-09-28
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006028/FP/22012034634023 — सी सी नाला निर्माण कार्य जगराम के मकान से पुलिया तक | Completed | 159000 | 154479 | 2023-09-04 - 2024-04-21
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006028/FP/22012034635202 — सी सी नाला निर्माण कार्य अवधेश के मकान से कंडई नाले की ओर | Ongoing | 43000 | 37246 | 2024-03-09 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006028/FP/22012034636295 — कच्चा नाला निर्माण कार्य महावीर बब्बा के स्थान से कंडई नाले तक ग्राम करियावली | Closed | 502908.41 | 0 | 2023-04-14 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006028/FP/22012034639135 — सी सी नाला निर्माण कार्य हनुमान जी के मंदिर से नरिया की ओर ग्राम करियावली | Ongoing | 29000 | 17474 | 2024-03-10 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006028/IF/1000034190 — MEDHBANDHAN KASHIRAM,LALLU,KAMALKISHRRE,RAMSAHAY | Completed | 89548 | 82198 | 2013-09-08 - 2014-02-06
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006028/IF/1000045257 — MEDHBANDHAN MOTILAL/NATHU | Completed | 89548 | 73292 | 2013-10-08 - 2014-02-06
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/22012034295674 — Shri ram / munga ram aadi | Closed | 45420 | 0 | 2016-04-14 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/22012034295677 — Raja veti / chhotelal | Deleted | 20650 | 0 | 2016-08-06 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034305193 — Nadip taka vishivnath s/o ram prasad | Completed | 12000 | 11282.4 | 2016-12-01 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034317833 — NADEP TANKA CHANDRARUP S/O RAGHUNANDAN | Completed | 12000 | 11187.4 | 2017-02-02 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034317858 — NADEP TANKA HARISINGH S/O RAGHUNANDAN | Completed | 12000 | 11187.4 | 2017-02-09 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034321000 — नाडेप टांका निर्माण करन सिंह / मनीराम कुशवाह | Completed | 12000 | 11187.4 | 2017-02-18 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034328843 — नाडिप टाका माता प्रसाद S/o श्री कामता काछी।सिकरी | Closed | 12000 | 0 | 2017-02-12 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034328845 — नाडिप टाका लक्षछी s/o श्री हीरा लाल जाटब् | Completed | 12000 | 11473 | 2017-03-26 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034328848 — नाडिप टाका फूल सिंह s/o श्री मनीराम कुशबहा करियबली | Closed | 12000 | 0 | 2017-02-12 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034336881 — नाडिप टाका जयराम S/O श्री गोकली | Completed | 12000 | 11568 | 2017-05-10 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034336884 — नाडिप टाका गोबिद दास S/O श्री रतिराम | Completed | 12000 | 11568 | 2017-05-17 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006028/IF/22012034370834 — PLATATION WORK ON ROAD SIDE GRAM KARIYABLI | Completed | 335000 | 19160 | 2017-08-09 - 2020-01-05
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374398 — नाडिप टाका विजोले s/o श्री सुखराम | Closed | 12000 | 0 | 2017-08-15 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374400 — नाडिप टाका घसीटे s/o श्री धन सिंह | Completed | 12000 | 11568 | 2017-08-29 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374401 — नाडिप टाका मनीराम s/o श्री रामधर | Completed | 12000 | 11568 | 2017-08-26 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374402 — नाडिप टाका बसनते s/o श्री डबू | Completed | 12000 | 11568 | 2017-08-26 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374403 — नाडिप टाका शिव नारायण s/o श्री पहलू | Completed | 12000 | 11568 | 2017-08-26 - 2018-02-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374404 — नाडिप टाका आशाराम s/o श्री मनफुले | Closed | 12000 | 0 | 2017-08-15 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374405 — नाडिप टाका उमाशंकर s/o श्री छोटे लाल | Closed | 12000 | 0 | 2017-08-15 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006028/IF/22012034374406 — नाडिप टाका अरबिन्द्र s/o श्री सरमन | Closed | 12000 | 0 | 2017-08-15 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/22012034608089 — पशु शेड निर्माण कार्य मनीराम / राजधर | Completed | 101273.16 | 92729.75 | 2021-09-08 - 2023-12-02
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006028/IF/22012034608090 — पशु शेड निर्माण कार्य मैहरवान / रघुवीर | Completed | 101273.16 | 92729.75 | 2021-11-11 - 2023-02-25
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006028/IF/22012034608091 — पशु शेड निर्माण कार्य फूल सिंह / नेकसाई | Completed | 101273.16 | 92729.75 | 2021-11-30 - 2022-10-29
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/22012034608092 — पशु शेड निर्माण कार्य कालीचरन / नेकसाईं | Completed | 101273.16 | 92729.75 | 2021-11-30 - 2022-10-29
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/22012034608093 — पशु शेड निर्माण कार्य सुरेश / रामाधार | Ongoing | 101273.16 | 85425.75 | 2021-12-04 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/22012034611264 — पशु शेड निर्माण कार्य वीर सिंह / भगवन सिंह | Completed | 101273.16 | 92952.75 | 2021-07-03 - 2023-12-02
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/22012034611265 — पशु शेड निर्माण कार्य आनंद / मान सिंह | Closed | 0 | 0 | 2020-04-14 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/22012034616544 — PASHU SHED NIRMAN KARY RADHELAL / GOLAI | Closed | 0 | 0 | 2020-04-14 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006028/IF/22012034776797 — मेड बन्धान राजेन्द s/o श्री डुलि चंद्र | Closed | 0 | 0 | 2021-04-14 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9926712299 — MEDHBANDAN HARMUKH MAHAL SINGH/MANGLI | Completed | 67000 | 27740 | 2014-03-03 - 2014-03-28
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006028/IF/9993650279 — MEDBANDHAN PARSHURAM S/O MANOHAR | Completed | 79289 | 89490 | 2014-08-19 - 2016-06-22
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993692172 — Madha bandhan Fadali S/OShri Chotelal | Completed | 63230 | 53901 | 2015-12-04 - 2017-12-30
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/9993725033 — PASHU SHED NIRMAN SURESH / RAMADHAR | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/9993725034 — PASHU SHED NIRMAN MULCHANDRA / CHATURBHUJ | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/9993725035 — PASHU SHED NIRMAN CHATURBHUJ / GOLAI | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/9993725036 — PASHU SHED NIRMAN ISHWAR DAYAL / ATAR SINGH | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006028/IF/9993725037 — PASHU SHED NIRMAN VISHWANATH / RAMPRASAD | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725039 — MED BANDHAN NARESH / CHHOTE | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725040 — MED BANDHAN SHRIRAM / MUNGARAM | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725041 — MED BANDHAN MUKESH / KISHOR SINGH | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725042 — MED BANDHAN DASHRATH / MUNNI LAL | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725043 — MED BANDHAN RAMBABU / PARSHURAM | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725045 — MED BANDHAN BRAJESH / RAJARAM | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725046 — MED BANDHAN POORAN SINGH / SHOBHRAN SINGH | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725047 — MED BANDHAN RAMESHWAR / RAJARAM | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725048 — MED BANDHAN LAXMINARAYAN / SHOBHRAN SINGH | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725049 — MED BANDHAN RAKESH / KALKA PRASAD | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725050 — MED BANDHAN LALSINGH / PARSHURAM | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006028/IF/9993725051 — MED BANDHAN MAHENDRA SINGH / PRAN SINGH | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/115242 — Construction of IAY House -IAY REG. NO. MP-02-006-028-003/10 | Completed | 14310 | 15030 | 2016-07-26 - 2017-12-30
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1184614 — Construction of IAY House -IAY REG. NO. MP3875188 | Completed | 15480 | 15480 | 2017-09-30 - 2018-04-04
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1758081 — Construction of IAY House -IAY REG. NO. MP2636132 | Completed | 15660 | 15660 | 2018-08-29 - 2018-09-24
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1895012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5704451 | Completed | 15660 | 14976 | 2018-10-03 - 2019-12-20
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1895021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5717434 | Completed | 17100 | 15744 | 2018-10-06 - 2024-10-10
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1895030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5723475 | Completed | 15660 | 15174 | 2018-10-06 - 2019-08-12
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1895035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5726442 | Completed | 15660 | 15162 | 2018-10-06 - 2019-12-20
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/1895049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5733518 | Completed | 15660 | 15672 | 2018-10-06 - 2019-12-20
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/2328609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5737935 | Completed | 15840 | 15960 | 2020-04-27 - 2020-07-19
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/3766407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125679021 | Completed | 18360 | 15249 | 2023-04-24 - 2025-09-20
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/3782532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126728015 | Ongoing | 23490 | 15990 | 2023-12-11 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/3847281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131201999 | Approved | 23490 | 0 | 2023-09-11 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/3881322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131750857 | Physically Completed | 18360 | 5304 | 2023-12-11 - 2024-11-21
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/4015532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126184051 | Completed | 18360 | 18173 | 2023-01-10 - 2023-10-02
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/4326077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131754197 | Completed | 18360 | 18122 | 2023-09-29 - 2024-04-16
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/4523696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120993311 | Ongoing | 23490 | 13140 | 2025-02-15 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/4526045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123189890 | Ongoing | 23490 | 16578 | 2025-02-07 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/4530300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148464576 | Ongoing | 23490 | 7290 | 2025-02-07 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/524105 — Construction of IAY House -IAY REG. NO. MP2644096 | Completed | 15030 | 15639 | 2017-02-12 - 2018-10-06
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/526726 — Construction of IAY House -IAY REG. NO. MP2717106 | Completed | 15030 | 15577 | 2017-02-12 - 2019-01-06
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5719802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125661801 | Ongoing | 23490 | 1566 | 2026-02-20 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5720095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125665635 | Ongoing | 23490 | 5742 | 2026-02-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5721561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131313974 | Ongoing | 23490 | 1566 | 2026-04-22 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5721640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120880548 | Ongoing | 23490 | 6003 | 2025-09-27 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5721768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125680958 | Ongoing | 23490 | 6786 | 2025-09-27 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5721771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125682533 | Ongoing | 23490 | 4176 | 2026-02-20 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5721772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125683536 | Ongoing | 23490 | 14616 | 2025-09-27 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5723430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125674424 | Ongoing | 23490 | 1305 | 2026-04-22 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5724642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123213298 | Ongoing | 23490 | 6003 | 2025-09-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5724798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126731630 | Ongoing | 23490 | 1566 | 2026-02-20 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5725184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126201811 | Ongoing | 23490 | 2871 | 2026-03-18 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5725314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122192771 | Ongoing | 23490 | 7308 | 2025-09-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5725452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128205640 | Ongoing | 23490 | 2610 | 2026-03-26 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5725990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131751136 | Completed | 23490 | 21663 | 2025-09-13 - 2026-05-11
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5726058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126729632 | Ongoing | 23490 | 5742 | 2026-03-18 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5726835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131755526 | Completed | 23490 | 22968 | 2025-09-27 - 2026-05-11
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5726927 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123602782 | Ongoing | 23490 | 10440 | 2025-09-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5728267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125980881 | Ongoing | 23490 | 2871 | 2026-03-18 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5728813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125676120 | Ongoing | 23490 | 18009 | 2026-02-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5728940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123600809 | Ongoing | 23490 | 1566 | 2026-02-20 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5729703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124425234 | Ongoing | 23490 | 10701 | 2025-09-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5731261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125270443 | Ongoing | 23490 | 1305 | 2026-03-26 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5731607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125677494 | Ongoing | 23490 | 1566 | 2026-02-20 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5732287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128212428 | Ongoing | 23490 | 5742 | 2026-02-13 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/5732941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126179860 | Ongoing | 23490 | 3132 | 2026-02-20 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006028/IF/IAY/931594 — Construction of IAY House -IAY REG. NO. MP2644037 | Completed | 15480 | 15480 | 2017-05-20 - 2018-04-04
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006028/LD/22012034265067 — MITTI BHARAW MANDIR SE KANDAI | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006028/LD/22012034265073 — NALA NIRMAN BHAGWAN DAS MISTRI KE YAHA SE HARDAYAL KUSHWAH KE YAHA TAK | Closed | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006028/LD/22012034309836 — शांति धाम निर्माण ग्राम शिकरी | Completed | 180000 | 179711.5 | 2017-04-10 - 2018-01-20
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1702006028/LD/22012034560160 — मिटटी भराव कार्य शाला भवन पर ग्राम निसार | Completed | 689628 | 660083.38 | 2021-06-12 - 2024-04-22
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702006028/PG/22012034365850 — खेल मैदान ग्राम पंचयत क्रियाबली | Closed | 0 | 0 | 2018-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006028/RC/1 — करियावली से लोटमपुरा की सीमा तक पहुंच मार्ग | Completed | 28000 | 163179 | 2008-07-16 - 2008-07-16
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006028/RC/190 — panch parmeswar raju moliya ke ghar budhu ke makan | Completed | 110000 | 81604 | 2012-05-16 - 2013-06-29
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034164964 — C.C.ROAD NALI NIRMAN BRAJNAND KE MAKAN SE HENDPAMP | Completed | 106080 | 106667 | 2013-05-06 - 2013-07-29
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034164967 — C.C.ROAD NILI NIRMAN MUKESH KE MAKAN SE SCHOOL TAK | Completed | 93915 | 87539.64 | 2013-05-06 - 2013-07-29
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034179018 — पंच परमेश्‍वर सीसी रोड मानसिंह बघेल के यहां से सिद | Completed | 108063 | 112776 | 2013-08-24 - 2014-05-20
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034197088 — विधायक निधि सीसी रोड मय नाली निर्माण प्रभुदयाल के | Completed | 17843 | 11972 | 2014-01-02 - 2014-01-31
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034200749 — पंच परमेश्‍वर माता के मंदिर से मुन्‍ना पटवा के मका | Completed | 37091 | 37032 | 2014-01-25 - 2015-09-16
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034210848 — पंच परमेश्‍वर सीसी रोड देवा तिरवेणी के यहां से हरन | Completed | 207010 | 161813 | 2014-03-03 - 2015-09-16
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/22012034211519 — SHUDUR SAMPARK MARGGRAM SHIKRI C KARIYAWALI SCHOOL | Completed | 340000 | 1752 | 2014-03-04 - 2016-09-28
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/22012034211566 — SHUDUR SAMPARAK MARG PUKHARIYA SE RAM PRAKASH KI KOT | Completed | 1371300 | 370023.1 | 2014-03-04 - 2016-05-30
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034230047 — पंच परमेश्‍वर सीसी रोड कन्‍हैलाल बाबा के घर से ब्रजनंदन के मकान होते हुये सि‍दध महाराज की ओर | Completed | 148177 | 124463 | 2014-09-23 - 2016-09-28
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034267033 — पंच परमेश्‍वर सीसी रोड विश्‍वनाथ धोबी के यहां से रामनारायण के मकान तक | Completed | 97626 | 97237.71 | 2015-07-07 - 2016-06-04
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034292532 — सी सी राेड मय नाली निर्माण अतर सिंह के मकान से देवसिंह के मकान होते हुये हरीशचन्‍द्र के मकान तक | Completed | 78178 | 106288 | 2016-02-03 - 2017-01-09
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034307420 — CC ROAD MAY NALI NIRMAN SIROMAN PARIHAR KE MAKAN SE SHASKIY SCHOOL TAK | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034307421 — CC ROAD NIRMAN SHRI RAM KE GHAR SE MATHURI KE GHAR KI OR | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034307430 — NALI NIRMAN NARAYAN DAS KE DARWAJE SE HANUMAN JI KE MANDIR TAK | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034307431 — CC ROAD MAY NALI NIRMAN PHADALI KE DARWAJE SE HENDPAMP TAK | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034307432 — CC ROAD MAY NALI NIRMAN MALKHAN BAGHEL KE YAHA SE LAXMINARAYAN KE GHAR TAK | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034307434 — CC ROAD MAY NALI NIRMAN MOTILAL KE DARWAJE SE AASHARAM KE GHAR KI OR | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/22012034307435 — SUDUR SAMPARK SIDDH BABA SE RAJARAM MASTAR KE KHET KI OR | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/22012034307436 — SUDUR SAMPARK MAIN SADAK SE PRAN SINGH KE KHET TAK SIKRI MARG | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/22012034307437 — SUDUR SAMPARK SHALA BHAWAN SE SIDDH MAHARAJ TAK | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034312007 — सी सी रोड मय नाली निर्माण रघुबंशी के द्वारे से भसोले के द्वारे तक | Completed | 20975 | 20965 | 2016-05-01 - 2017-05-24
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034312010 — सी सी रोड मय नाली निर्माण कमलेश के द्वारे से राजाराम मास्‍टर के द्वारे तक | Completed | 57203 | 57191 | 2016-04-23 - 2017-05-24
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034330999 — CC ROAD MAY NALI NIRMAN SHREE RAM KE MAKAN SE MATHURI KE MAKAN TAK | Completed | 96000 | 58000 | 2017-03-19 - 2017-12-30
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034362391 — पच परमेश्वर सी सी रॉड मय नाली निमार्ण राम किशोर के मकान से हरनारायण के मकान तक | Completed | 162500 | 51600 | 2017-09-30 - 2018-08-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034362394 — पच परमेश्वर सी सी रॉड मय नाली निमार्ण सेबा जाटव के मकान से आनंद तिबारी के मकान तक करियबली | Completed | 95000 | 42140 | 2017-09-30 - 2018-08-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034362396 — पच परमेश्वर सी सी रॉड मय नाली निर्माण पाठक से राजू बुधौलिया के मकान तक करियबली | Completed | 162500 | 59512 | 2017-09-30 - 2018-08-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034376521 — C.C.Raod | Closed | 0 | 0 | 2018-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034382139 — सी सी नाली निमार्ण रोड पंच परमेश्वर रामहेत बरार के मकान से छोटे प्रजापति के मकान से होते हुए गबड़ू के | Completed | 145000 | 92916 | 2018-04-07 - 2018-08-26
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034382141 — सी सी रोड नाली निमार्ण सुनील के मकान से रंगीला के मकान की ओर ग्राम सीकरी | Completed | 77000 | 25752 | 2018-07-11 - 2019-03-27
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034389246 — पंच परमेशर सी सी रोड़ मय नाली निमार्ण अबध कुँअर के मकान से मनफुले के मकान तक | Deleted | 0 | 0 | 2017-10-02 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034389349 — पंच परमेश्वर सी सी रोड़ मय नाली निमार्ण अबध कुँअर के मकान से मनफुले के मकान तक | Completed | 41000 | 18966 | 2018-07-20 - 2018-08-15
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034396628 — पंच परमेश्वर सी सी रोड़ मय नाली निमार्ण शिरोबन खगर के मकान से छोटे जाटव के मकान तक | Ongoing | 83000 | 2088 | 2018-10-05 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034396645 — पंच परमेश्र्वर सी सी रोड मय नाली निमार्ण लाल सिंह के मकान से तेज सिंह कुशबहा के मकान तक | Completed | 40000 | 27840 | 2018-10-05 - 2019-01-20
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034396648 — पंच परमेश्वर सी सी रॉड मय नाली निमार्ण मेबलाल के मकान से फदली के मकान तक | Completed | 43000 | 32538 | 2018-10-05 - 2019-02-15
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034396651 — पंच परमेश्वर सी सी रोड़ मय नाली निमार्ण शिरोबन के मकान से शाला भवन तक | Ongoing | 43000 | 2088 | 2018-10-05 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034396655 — पंच परमेश्वर सी सी रॉड मय नाली निमार्ण विजय सिंह के मकान से हरजू के मकान तक | Completed | 33000 | 23142 | 2018-10-05 - 2019-01-25
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034396657 — पंच परमेश्वर सी सी रॉड मय नाली निमार्ण मोती लाल जाटव के मकान से काशी राम कुशबहा के मकान तक | Completed | 100000 | 85956 | 2018-10-05 - 2018-11-03
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034435898 — पंच परमेश्वर सी 0 सी0 रोड़ निमार्ण कार्य रामेश्वर के मकान से भारत के मकान तक निशार रोड़ | Deleted | 0 | 0 | 2018-08-16 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034435901 — पंच परमेश्वर सी0 सी0 रोड़ निमार्ण कार्य प्राण सिंह के मकान से मेंन रॉड तक निशार | Completed | 46000 | 34800 | 2019-02-17 - 2019-03-16
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034435902 — पंच परमेश्वर सी0 सी0 रॉड निमार्ण कार्य कल्लू जाटव के मकान से कृष्ण जाटव के मकान तक | Completed | 56000 | 46440 | 2019-02-10 - 2019-09-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034435919 — पंच परमेश्वर सी0 सी 0 रोड़ निमार्ण कार्य रामेश्वर के मकान से भारत के मकान तक | Completed | 46000 | 34800 | 2019-02-10 - 2019-03-16
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034440530 — पंच परमेश्वर सी सी रोड़ हरदास के मकान से कांडई नाले की ओर करियाबली | Completed | 69000 | 57704 | 2019-02-10 - 2019-10-28
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034440533 — पंच परमेश्वर सी सी रॉड नाली निमार्ण फूल सिह के मकान से मनफूले के मकान तक | Completed | 34000 | 23208 | 2019-02-10 - 2019-09-10
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034447310 — पंच परमेश्वर सी सी रोड मय नाली निमार्ण हमीर सिह के मकान से प्राण सिह के मकान की ओर | Completed | 12000 | 6786 | 2019-03-06 - 2019-04-15
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034447312 — पंच परमेश्वर सी सी रोड मय नाली निमार्णलल्लू कुशबहा के मकान से धनीराम कुशबहा के मकान तक | Completed | 36000 | 22396 | 2019-03-06 - 2019-09-01
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034474703 — C.C. ROAD NALI NIRAMAN KARY RAMJEEVAN KE MAKAN SE KANDAI NALE KI OR GRAM KARIYAWALI | Completed | 46000 | 46464 | 2019-09-16 - 2019-10-05
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/22012034481365 — सुदर सम्पर्क सड़क निसार से महराज पुरा की सीमा तक | Completed | 880000 | 828698.06 | 2019-10-10 - 2020-06-15
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034528039 — C.C. ROAD NALI NIRMAN KARY P M SADAK SE PRADEEP TIWARI KE MAKAN KI OR | Completed | 113000 | 107160 | 2020-07-07 - 2020-07-28
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034532461 — सी सी रोड नाली निर्माण जसमंत कुशवाह के मकान से डी. पी.(ट्रांसफार्मर) की ओर | Completed | 14000 | 13870 | 2020-08-18 - 2020-09-06
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034541936 — सीसी रोड मय नाली निर्माण बीर सिंह के मकान से तालाब तक ग्राम निसार | Completed | 12443 | 12350 | 2020-09-27 - 2021-02-28
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034541939 — सीसी रोड निर्माण घटोई बाबा से मन्दिर की ओर ग्राम करियावली | Completed | 76500 | 76380 | 2020-09-27 - 2021-01-29
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034567029 — सीसी रोड मय नाली निर्माण कार्य मैन रोड से राममिलन बराहर के मकान की ओर ग्राम करियावली | Completed | 32550 | 32424 | 2021-04-15 - 2021-07-11
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034586928 — सी सी फर्श निर्माण कार्य सिद्ध बाबा के स्थान पर | Completed | 257000 | 64740 | 2021-11-15 - 2024-04-25
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034586929 — सी सी रोड नाली निर्माण कार्य कमल राठौर के मकान से सेवा जाटव के मकान तक | Completed | 108000 | 104640 | 2022-04-05 - 2023-02-25
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034615193 — पुलिया निर्माण कार्य कंडई नाले पर (देवरी रास्ता) ग्राम सिकरी | Completed | 135000 | 134300 | 2022-05-27 - 2024-02-27
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034644049 — सी सी रोड निर्माण कार्य मंदिर प्रागंण में | Completed | 129000 | 112047 | 2023-07-17 - 2025-09-20
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034681177 — पुलिया निर्माण कार्य कंडई नाला पर | Ongoing | 115000 | 27748 | 2024-03-10 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/22012034843498 — सी सी सड़क एवं नाली निर्माण कार्य सुन्नू के मकान से रामशरण कुशवाह के मकान की ओर ग्राम करियावली | Approved | 47000 | 0 | 2025-04-14 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006028/RC/24 — पहुंच मार्ग बजरीक्रत मार्ग रूरई की ओर पहुंच मार्ग | Completed | 483000 | 80899 | 2009-09-24 - 2009-09-24
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006028/RC/277 — Vidhayak Nidhi Rupa Dhobi Ke Makan Se Mata Mandir | Completed | 32741 | 22308 | 2012-12-18 - 2013-04-02
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006028/RC/50 — ि‍मटटी पहुचमार्ग ग्राम ि‍नसार से महाराजपुरा की ओर | Completed | 360378 | 19700 | 2010-09-12 - 2014-01-30
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006028/RC/61 — मिटटी पहुचमाग करियावली से ररइ की ओर | Completed | 482772 | 47625 | 2010-07-08 - 2014-01-30
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Soakage Channel/Pit / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034294357 — SHANTI DHAM NIRMAN GRAM SIKRI | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Soakage Channel/Pit / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034294358 — SHANTI DHAM NIRMAN GRAM KARIYAWALI | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Drainage Channel / Construction of Flood/ Diversion Channel for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034294359 — SHANTI DHAM NIRMAN GRAM NISAR | Deleted | 0 | 0 | 2016-04-01 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034657803 — सामुदायिक सोकपिट निर्माण कार्य माध्यमिक शाला भवन पर निसार | Ongoing | 6600 | 3672 | 2022-05-27 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034657805 — सामुदायिक सोकपित निर्माण कार्य पुलिया के पास करियावली | Ongoing | 6600 | 3672 | 2022-05-27 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006028/RS/22012034657868 — सामुदायिक नाडेप निर्माण कार्य सिद्ध महाराज के पास निसार | Ongoing | 2000 | 1224 | 2022-05-27 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006028/RS/22012034657876 — सामुदायिक नाडेप निर्माण कार्य कडई पुलिया के पास करियावली | Ongoing | 2000 | 1224 | 2022-05-27 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034688857 — सामुदायिक सोख्ता गड्डा निर्माण कार्य हनुमान जी मंदिर के पास | Completed | 8000 | 7344 | 2023-02-14 - 2023-03-18
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034688858 — सामुदायिक सोख्ता गड्डा निर्माण कार्य शाला भवन के पास | Completed | 8000 | 7956 | 2023-02-14 - 2023-03-05
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034696031 — सामुदायिक सोख्ता गड्डा निर्माण कार्य रामसहाय भगत के मकान के पास | Completed | 8000 | 7956 | 2023-05-25 - 2023-07-05
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006028/RS/22012034696032 — सामुदायिक सोख्ता गड्डा निर्माण कार्य रामाधार दोहरे के मकान के पास ग्राम करियावली | Completed | 8000 | 7956 | 2023-05-25 - 2023-07-05
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006028/WC/2 — तालाब गहरीकरण करियावली | Completed | 0 | 24752 | 2009-01-22 - 2009-01-22
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006028/WC/22012034293807 — पुखरिया तालाब गहरीकरण | Deleted | 97000 | 0 | 2016-05-22 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702006028/WC/22012034324049 — Talab Ki Bund Sudrikaran | Deleted | 77000 | 0 | 2017-04-14 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702006028/WC/22012034384109 — Talab Nirman | Closed | 0 | 0 | 2018-04-01 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006028/WC/22012034437651 — Talab Nirman | Closed | 0 | 0 | 2019-04-01 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006028/WC/22012034621796 — डग पौंड निर्माण कार्य ग्राम सिकरी ग्राम पंचायत करियावली | Ongoing | 992692.74 | 3474 | 2021-04-08 -
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702006028/WC/22012034738725 — तालाब जीर्णोद्वार कार्य बाग के पास ग्राम करियावली | Completed | 900782.39 | 769011.82 | 2021-06-12 - 2024-02-21
BHIND / LAHAR / KARIYAWALI | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702006028/WC/22012034738731 — तालाब जीर्णोद्वार कार्य ग्राम निसार | Closed | 0 | 0 | 2021-04-14 -
BHIND / LAHAR / KARIYAWALI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702006028/WC/22012034750012 — वेस्ट वियर निर्माण बाग बाला तालाब ग्राम एवं ग्राम पंचायत करियावली | Ongoing | 449766.61 | 2316 | 2021-06-12 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/296 — मेढवंधान मोतीलाल/गुन्‍दे ग्राम पंचायत करि‍यावली | Deleted | 19452 | 0 | 2010-08-31 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/297 — मेढवंधान घनश्‍याम/गुन्‍दे ग्राम पंचायत करि‍यावली | Deleted | 19452 | 0 | 2010-08-04 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/298 — मेढवंधान कालीचरण/रामकि‍शुन ग्राम पंचायत करि‍यावली | Deleted | 17831 | 0 | 2010-09-08 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/299 — मेढवंधान मि‍ठू/मातादीन ग्राम पंचायत करि‍यावली | Deleted | 11346 | 0 | 2010-08-26 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/300 — मेढवंधान रामस्‍वरूप/तुलई ग्राम पंचायत करि‍यावली | Deleted | 22694 | 0 | 2010-08-19 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/301 — मेढवंधान लखन/चि‍टू ग्राम पंचायत करि‍यावली | Deleted | 29178 | 0 | 2010-05-05 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/302 — मेढबंधान भोगीराम/रमजू ग्राम पंचायत करियावली | Deleted | 29178 | 0 | 2010-04-29 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/303 — मेढबंधान कासीराम/चिनू ग्राम पंचायत करियावली | Deleted | 8105 | 0 | 2010-08-12 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/304 — मेढबंधान दीनदयाल/लक्ष्‍मण ग्राम पंचायत करियावली | Deleted | 11346 | 0 | 2010-04-22 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/513 — मेढबंधान दौलतसिंह/रामसहाय ग्राम पंचायत करियावली | Completed | 26000 | 14762 | 2011-06-24 - 2011-06-29
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/514 — मेढबंधान दीनानाथ/हरकिशुन ग्राम पंचायत करियावली वर्ष 2011 | Completed | 57000 | 41236 | 2011-06-12 - 2011-06-17
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/515 — मेढबंधान जनवेद/रामसहाय ग्राम पंचायत करियावली वर्ष 2011 | Completed | 26000 | 17080 | 2011-07-01 - 2012-04-18
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/816 — मेढबंधान प्रीतम/भदोले ग्राम पंचायत करियावली वर्ष 1 | Completed | 40373 | 29964 | 2012-10-02 - 2012-10-08
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/817 — मेढबंधान मोहरसिंह/रामचन्‍द्र ग्राम पंचायत करियावली | Completed | 25023 | 18348 | 2012-10-25 - 2013-01-25
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/818 — मेढबंधान गोविंदसिंह/रामनाथ ग्राम पंचायत करियावली व | Completed | 41088 | 35508 | 2012-10-13 - 2013-01-25
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/886 — Medhbandhan Basante / Dabu | Completed | 50442 | 35904 | 2013-01-06 - 2013-01-12
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/9993649095 — नाली निर्माण हरदास कुशवाहा के यहां से कधई तक | Completed | 164376 | 129817.59 | 2014-03-04 - 2016-06-22
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/9993649102 — नाली निर्माण मथुरी के यहां से कारसदेव तक | Completed | 321219 | 271644.46 | 2014-03-04 - 2016-06-22
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006028/WC/9993649106 — नाली निर्माण मूलचन्‍द्र पाठक के यहां से पुखरिया तक | Completed | 295785 | 253273.52 | 2014-03-04 - 2016-06-22
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702006028/WH/19959101 — Talab Ki Bund Sudrikaran | Completed | 77000 | 74304 | 2017-05-11 - 2018-01-20
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1702006028/WH/22012034450190 — तालाब जीर्णोद्वार कार्य ग्राम निसार ग्राम पंचायत करियावली | Closed | 0 | 0 | 2021-04-14 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702006028/WH/22012034456811 — तालाब जीर्णोद्वार कार्य पुखरिया सिकरी (करियावली) | Ongoing | 48916.89 | 2448 | 2022-05-27 -
BHIND / LAHAR / KARIYAWALI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702006028/WH/22012034456812 — तालाब जीर्णोद्वार कार्य सिद्ध बाबा के पास निसार (करियावली) | Closed | 47690.14 | 0 | 2021-04-14 -