## Work List
Exported on: 2026-08-20 05:21:51
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: FARDUA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702006040/AV/22012034399360 — Aaganwadi Bhawan-Phardua | Physically Completed | 312000 | 191336 | 2019-02-25 | 2020-05-15
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1702006040/AV/22012034399361 — Punchayat Bhawan- Phardua | Ongoing | 579200 | 515999 | 2019-02-25
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1702006040/AV/22012034535208 — रसोई एवं भंडार गृह सह डायनिंग हाल माध्यमिक शाला फरदुआ | Ongoing | 425000 | 27594 | 2021-03-04
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006040/AV/22012034631958 — नवीन समशान घाट निर्माण कार्य ग्राम फरदुआ | Closed | 223993.09 | 0 | 2022-08-16
BHIND / LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702006040/AV/4114 — Aanganbadi/Other Rural Infrastructure,LAHAR | Ongoing | 330000 | 258317 | 2015-12-07
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/35 — मेढवंधान रोशन ि‍संह नंद ि‍कशोर ग्राम फरदुआ | Completed | 31000 | 28800 | 2010-09-08 | 2010-09-14
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/36 — मेढ्वंधान वेनी रामि‍कशुन फरदुआ | Completed | 32000 | 30000 | 2010-08-11 | 2010-08-17
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/37 — मेढबंधान डालचन्‍द्र/डरू | Completed | 30000 | 27000 | 2010-07-22 | 2010-07-28
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/38 — मेढबंधान घासीराम/डरू | Completed | 29000 | 26600 | 2010-07-29 | 2010-08-04
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/39 — मेढबंधान लक्ष्‍मन/डरू | Completed | 11000 | 9600 | 2010-07-29 | 2010-08-04
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/40 — मेढबंधान रामाधर/रामि‍कसुन | Completed | 0 | 24000 | 2010-08-13 | 2010-08-19
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1702006040/DP/41 — मेढबंधान करन ि‍संह/ज्ञान ि‍संह | Completed | 0 | 9000 | 2010-09-01 | 2010-09-07
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1702006040/FP/22012034363044 — नबीन नाला निमार्ण कार्य अतर सिह बघेल के मकान से राम सिया दोहरे के मकान तक | Completed | 256000 | 270214 | 2019-03-12 | 2021-12-15
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702006040/FP/22012034625940 — नवीन नाला निर्माण कार्य मुन्नालाल कुशवाह के खेत से खजराह नाला तक | Completed | 585415.12 | 493115 | 2021-06-30 | 2021-12-25
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006040/FP/22012034625941 — नवीन नाला निर्माण कार्य किशोर दोहरे के खेत से मैंन रोड की पुलिया की ओर नरिया पर | Physically Completed | 613964.94 | 497940 | 2021-06-25 | 2026-04-20
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006040/FP/22012034632150 — सी सी नाला निर्माण कार्य श्री ईश्वर शाक्य के मकान से श्री रामजी शाक्य के मकान तक | Closed | 47000 | 0 | 2023-08-14
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006040/FP/22012034632269 — कच्चा नाला निर्माण कार्य गौड़ बाबा के चबूतरा से बड़ी माता मंदिर की ओर | Closed | 43809.85 | 0 | 2022-08-16
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006040/IF/22012034297979 — med bandhanrameswar/bhawani | Completed | 5933400000 | 29893 | 2016-09-08 | 2017-05-24
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034306226 — नाडेप टांका निर्माण खेतराम / गेंदालाल | Completed | 12000 | 10453 | 2016-12-06 | 2019-02-10
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034306228 — नाडेप टांका निर्माण बहादुर / धनसिंह | Completed | 12000 | 11770 | 2016-12-06 | 2018-01-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034306233 — नाडेप टांका निर्माण बादाम सिंह / रघुबर | Completed | 12000 | 11598 | 2016-12-06 | 2018-01-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034314610 — नाडेप टांका निर्माण कृष्णवीर / राघवराम | Completed | 12000 | 11805 | 2017-02-04 | 2018-01-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034314612 — नाडेप टांका निर्माण बेनीप्रसाद / रामकिशन | Completed | 12000 | 11872 | 2017-03-02 | 2018-01-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324090 — nadep tanka nirman amar singh s/o munnilal | Completed | 12000 | 11705 | 2017-03-02 | 2018-01-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324095 — nadep tanka nirman tulsiram s/o shyamlal | Completed | 12000 | 10369 | 2017-03-02 | 2018-01-20
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324098 — nadep tanka nirman karya chandra prakash s/o daruprasad shakya | Completed | 12000 | 11497 | 2017-07-28 | 2019-02-10
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324100 — NADEP TANKA NIRMAN KARYA VIMLESH W/O RAGHAVRAO | Completed | 12000 | 11872 | 2017-03-02 | 2018-01-20
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324103 — NADEP TANKA NIRMAN KARYA RAMESHWAR S/O BHAWANI | Completed | 12000 | 11805 | 2017-06-11 | 2018-01-20
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324105 — nadep tanka nirman karya lalluram s/o sadole | Completed | 12000 | 11805 | 2017-06-18 | 2018-01-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1702006040/IF/22012034324109 — nadep tanka nirman karya deshraj s/o dayaram | Completed | 12000 | 11872 | 2017-03-17 | 2018-01-20
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006040/IF/22012034352048 — Braksharopan pradhanmantri sadak ke kinare | Completed | 335000 | 31188 | 2017-07-28 | 2020-01-05
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006040/IF/22012034353833 — plantation work in campus of pradhanmantri sadak ke kinare | Completed | 335000 | 49538 | 2017-07-28 | 2020-01-05
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006040/IF/22012034718351 — मेड बंधान निर्माण कार्य कडोरे / रामजू कुशवाह | Completed | 69232.81 | 46320 | 2021-05-19 | 2021-12-25
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006040/IF/22012034718352 — मेड बंधान निर्माण कार्य घासीराम / डलू | Completed | 67203.38 | 44004 | 2021-04-27 | 2022-02-16
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006040/IF/22012034718353 — मेड बंधान निर्माण कार्य सरोजना / घासीराम | Completed | 65173.95 | 58286 | 2021-04-22 | 2021-05-29
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006040/IF/22012034718354 — मेड बंधान निर्माण कार्य जयनारायण / रामगोपाल | Completed | 63144.52 | 40530 | 2021-04-27 | 2021-09-16
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1702006040/IF/22012034718355 — मेड बंधान निर्माण कार्य सावित्री देवी / ठाकुरदास | Completed | 61115.09 | 52110 | 2021-05-19 | 2021-06-20
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006040/IF/22012034718356 — खेत तालाब निर्माण कार्य राघवराम / लालसहाय | Ongoing | 337715.44 | 17370 | 2021-05-20
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006040/IF/22012034990747 — खेत तालाब निर्माण कार्य रामेश्वर दोहरे / भवानी ग्राम फरदुआ | Closed | 356340.1 | 0 | 2022-04-14
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006040/IF/22012035125858 — खेत तालाब निर्माण कार्य जगमोहन पुत्र प्रभुदयाल ग्राम फरदुआ | Closed | 0 | 0 | 2023-04-14
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006040/IF/22012035125859 — खेत तालाब निर्माण कार्य भगवती पुत्र प्रभुदयाल | Closed | 0 | 0 | 2023-04-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006040/IF/22012035654630 — Ek bagiya maa ke naam vraksharopan pooja/mannulal gram larsa fardua | Approved | 266578.64 | 0 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006040/IF/22012035654631 — Ek bagiya maa ke naam vraksharopan meera/hardayal badagaon n2 | New | 0 | 0 | 2025-12-26
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006040/IF/22012035654632 — Ek bagiya maa ke naam vraksharopan meena/dwarkaprashad gram larsa fardua | Approved | 266578.64 | 0 | 2025-12-26
BHIND / LAHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1702006040/IF/9926709975 — पशु शेड दिलीप/शिरोवन | Completed | 89000 | 13578 | 2014-02-28 | 2014-12-30
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Soil Cover on Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006040/IF/9993714149 — मेढवंधान मानसिंह | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006040/IF/9993714150 — मेढवंधान किशोर प्रसाद | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006040/IF/9993714151 — मेढवंधान हरपाल | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006040/IF/9993714152 — मेढवंधान कढोरे | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006040/IF/9993714154 — मेढवंधान छोटेलाल | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/115271 — Construction of IAY House -IAY REG. NO. MP-02-006-040-001/08 | Completed | 14310 | 15528 | 2017-01-02 | 2019-01-12
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/133868 — Construction of IAY House -IAY REG. NO. MP-02-006-040-001/41 | Completed | 14310 | 15660 | 2017-01-02 | 2019-01-19
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/1912143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4982074 | Completed | 15660 | 15660 | 2018-11-09 | 2018-12-10
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/1912193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5166296 | Completed | 15660 | 15660 | 2018-10-25 | 2019-01-12
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/1912294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5533831 | Completed | 15660 | 15660 | 2018-10-11 | 2018-12-23
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/196848 — Construction of IAY House -IAY REG. NO. MP-02-006-040-001/25 | Completed | 14310 | 14520 | 2017-07-13 | 2018-12-30
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/202966 — Construction of IAY House -IAY REG. NO. MP-02-006-040-001/11 | Completed | 15030 | 14544 | 2017-06-29 | 2019-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/278976 — Construction of IAY House -IAY REG. NO. MP3905813 | Completed | 15030 | 16212 | 2017-02-14 | 2018-01-20
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3750896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124647877 | Completed | 18360 | 14382 | 2022-11-14 | 2024-05-15
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3750900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124648757 | Physically Completed | 18360 | 12198 | 2023-10-27 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3769071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124905355 | Physically Completed | 18360 | 10740 | 2023-10-27 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3769100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124913483 | Physically Completed | 18360 | 14052 | 2023-12-12 | 2024-11-21
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3774667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125004931 | Physically Completed | 18360 | 13116 | 2022-11-14 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3777472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130548076 | Physically Completed | 18360 | 18030 | 2023-12-05 | 2024-11-21
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3787917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130808184 | Physically Completed | 18360 | 12942 | 2022-11-14 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3787919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130808268 | Physically Completed | 18360 | 8220 | 2023-10-27 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/3989841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124906883 | Physically Completed | 18360 | 2784 | 2023-11-24 | 2024-11-21
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4020702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130692929 | Physically Completed | 18360 | 11556 | 2022-11-30 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4020703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130693066 | Completed | 18360 | 17238 | 2023-06-08 | 2023-10-14
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4020707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130697294 | Completed | 18360 | 17238 | 2023-06-08 | 2024-01-26
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4325682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127964957 | Completed | 18360 | 17238 | 2023-06-08 | 2024-05-15
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4326154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130698185 | Physically Completed | 18360 | 8220 | 2023-11-24 | 2024-11-21
BHIND / LAHAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4326155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130698475 | Completed | 18360 | 18122 | 2023-05-30 | 2024-05-09
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4526837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129723571 | Physically Completed | 23490 | 20358 | 2025-06-16 | 2026-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4526871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125007964 | Ongoing | 23490 | 1566 | 2026-01-13
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4779295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127952388 | Ongoing | 23490 | 3132 | 2026-04-23
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4780614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128085547 | Ongoing | 23490 | 17226 | 2025-06-16
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4785228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130808855 | Ongoing | 23490 | 0 | 2025-12-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/4890421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130699633 | Physically Completed | 23490 | 3132 | 2025-06-16 | 2026-08-16
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5608677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141308558 | Physically Completed | 23490 | 7830 | 2025-06-16 | 2026-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5608706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130808284 | Ongoing | 23490 | 0 | 2025-12-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5608794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130698266 | Physically Completed | 23490 | 3132 | 2025-06-16 | 2026-08-16
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130694657 | Ongoing | 23490 | 3132 | 2026-04-14
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130694800 | Ongoing | 23490 | 3132 | 2026-04-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130696676 | Ongoing | 23490 | 3132 | 2026-03-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124905117 | Ongoing | 23490 | 1566 | 2026-03-14
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125142800 | Ongoing | 23490 | 1566 | 2026-04-22
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130699810 | Ongoing | 23490 | 3132 | 2026-03-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127949112 | Ongoing | 23490 | 4698 | 2026-03-14
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5685508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130699413 | Ongoing | 23490 | 1566 | 2026-04-23
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5719841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127878981 | Ongoing | 23490 | 1566 | 2026-04-23
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5722476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130697427 | Ongoing | 23490 | 0 | 2025-10-15
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5723102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132044952 | Ongoing | 23490 | 6264 | 2026-03-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5724245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130695679 | Ongoing | 23490 | 9396 | 2026-03-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5730092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131857924 | Ongoing | 23490 | 3132 | 2026-03-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5730488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124647647 | Ongoing | 23490 | 0 | 2026-03-14
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5882740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131869962 | Ongoing | 23490 | 4698 | 2026-02-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5885395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128122088 | Ongoing | 23490 | 3132 | 2026-02-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5885466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130068508 | Ongoing | 23490 | 3132 | 2026-02-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006040/IF/IAY/5885633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129722360 | Ongoing | 23490 | 3132 | 2026-02-13
BHIND / LAHAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006040/LD/119 — SHANTiDHAM G.p. FARDuA YEAR 2011-12 | Completed | 356000 | 82319.42 | 2012-05-01 | 2014-08-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006040/LD/22012034307616 — Shantidhaam gram panchayat fardua | Completed | 180000 | 181384.46 | 2017-03-25 | 2019-04-24
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702006040/LD/22012034307619 — Khel maidan gram panchayat fardua | Ongoing | 0 | 14448 | 2017-07-24
BHIND / LAHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006040/LD/22012034307622 — shantidham gram panchayat fardua | Closed | 0 | 0 | 2016-12-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006040/LD/22012034307628 — shanti dham nirman karya gram fardua | Deleted | 0 | 0 | 2016-10-02
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006040/LD/22012034567488 — खेत समतलीकरण कार्य सर्वे क्रमांक 209,214,370 आज्ञाराम s/o स्वर्गीय किशोरी शरण लरसा (फरदुआ) | Physically Completed | 349862.16 | 119556 | 2021-11-24 | 2026-06-11
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006040/LD/22012034567489 — खेत समतलीकरण कार्य सर्वे क्रमांक 502.503 राजीव s/o आज्ञाराम लरसा (फरदुआ) | Physically Completed | 322496.13 | 128562 | 2021-11-10 | 2026-06-10
BHIND / LAHAR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006040/LD/9926713705 — पंच परमेश्‍वर सीसी रोड शाक्‍य मौहल्‍ला से दुर्गा क | Completed | 137148 | 73476 | 2014-07-29 | 2016-09-30
BHIND / LAHAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006040/RC/115 — ि‍मटटी पहुचमार्ग कांक्‍सी तालाब के आगे से हार की ओर ग्राम पंचायत | Completed | 405000 | 118826.2 | 2010-10-14 | 2016-09-14
BHIND / LAHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006040/RC/131 — मिटटी पहुचमार्ग जगमोहन के खेत से गांव की ओर ग्राम पंचायत फरदुआ वर्ष 2011 | Completed | 104000 | 119552.18 | 2011-09-03 | 2011-11-23
BHIND / LAHAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006040/RC/18 — ग्राम पंचायत फरदुआ में पहुचमार्ग | Completed | 0 | 100008 | 2009-07-27 | 2009-07-29
BHIND / LAHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/182 — panch parmeshwar prathmik vidhyalaya se ishwar ke | Completed | 153000 | 49284 | 2012-05-25 | 2012-08-03
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034199464 — सी सी नाली निर्माण ध्रुव के मकान से मुख्‍य मार्ग क | Completed | 133230 | 128048 | 2014-01-18 | 2014-02-20
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034209608 — पंच परमेश्‍वर सीसी रोड बघेल मौहल्‍ला से राठौर मौहल | Completed | 130558 | 118188 | 2014-02-28 | 2014-03-20
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006040/RC/22012034213172 — खेत सड्क पुलिया से कल्‍लन के खेत की ओर | Completed | 1399000 | 343554 | 2014-03-07 | 2016-09-11
BHIND / LAHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034219322 — पंच परमेश्‍वर सीसी रोड राठौर मौहल्‍ला से मैन रोड क | Completed | 138068 | 128429 | 2014-05-27 | 2016-10-19
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034226219 — पंच परमेश्‍वर सीसी रोड शाक्‍य मौहल्‍ला से दुगौ के मकान तक | Deleted | 0 | 0 | 2014-01-26
BHIND / LAHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034226220 — पंच परमेश्‍वर सीसी रोड शाक्‍य मौहल्‍ला से दुर्गा के मकान तक | Deleted | 0 | 0 | 2013-01-26
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034226221 — पंच परमेश्‍वर सीसी रोड शाक्‍य मौहल्‍ला से दुर्गा के मकान तक | Deleted | 0 | 0 | 2014-01-26
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034226222 — panch parmeshwar cc road | Deleted | 0 | 0 | 2014-01-26
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006040/RC/22012034226223 — road | Deleted | 0 | 0 | 2014-01-26
BHIND / LAHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Tiles / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1702006040/RC/22012034226224 — पंच परमेश्‍वर सीसी रोड शाक्‍य मौहल्‍ला से दुर्गा के मकान तक | Deleted | 0 | 0 | 2014-04-01
BHIND / LAHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034231348 — पेच परमेश्‍वर सीसी रोड शाक्‍य मौहल्‍ला से चौक मौहल | Completed | 180000 | 47706 | 2014-10-08 | 2016-09-11
BHIND / LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034288289 — पंच परमेश्‍वर सीसी रोड मय नाली निर्माण रामजीलाल राठौर के मकान से प्रधानमंत्री रोड तक | Completed | 263675 | 172026 | 2015-11-03 | 2017-11-11
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034318346 — सी सी रोड मय नाली निर्माण राजबहादुर के मकान से प्रा. शा. भवन की ओर | Completed | 91790 | 50066 | 2017-01-03 | 2018-12-30
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034365668 — cc road & nali nirman karya pradhanmantri road se beni prasad ke makan ki or | Completed | 89467 | 91848 | 2017-10-31 | 2020-01-05
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034365672 — cc road & nali nirman karya baini prasad ke makan se ashok dohre ke makan ki or | Completed | 59842 | 56180 | 2017-10-31 | 2020-01-05
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034365680 — cc road & nali nirman karya pradhanmantri sadak se shripal kushwah ke makan tak | Completed | 205000 | 124872 | 2017-10-31 | 2018-12-30
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006040/RC/22012034373454 — सुदूर संपर्क सड़क निर्मन | Closed | 0 | 0 | 2018-04-01
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034376499 — C.C.Road | Closed | 0 | 0 | 2017-04-01
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034448178 — पंच परमेश्वर सी सी रोड मय नाली निमार्ण प्रभु दयाल शर्मा के मकान से हर सेबक मिश्रा के मकान तक | Completed | 65000 | 70740 | 2019-03-13 | 2020-08-21
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034448180 — पंच परमेश्वर सी सी रोड मय नाली निमार्णभगवती शर्मा के मकान से राजू शर्मा के मकान तक | Completed | 49000 | 45008 | 2019-03-13 | 2020-08-21
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034448182 — पंच परमेश्वर पप्पू शर्मा के मकान से प्रभु दयाल शर्मा के मकान तक | Completed | 38000 | 31656 | 2019-03-13 | 2020-08-03
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034517707 — सीसी रोड मय नाली निर्माण आंगनवाडी भवन से बडी माता मंदिर तक | Completed | 63562 | 53328 | 2020-02-24 | 2021-12-15
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034517709 — सीसी रोड मय नाली निर्माण श्रीपाल कुशवाह के मकान से किसमानी के मकान तक | Completed | 63292 | 68936 | 2020-02-24 | 2021-12-12
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034563959 — सी सी निर्माण कार्य पंचायत भवन एवं आगनवाडी परिसर में ग्राम फरदुआ | Completed | 51000 | 44004 | 2021-04-06 | 2022-02-16
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034565512 — सी सी रोड नाली निर्माण कार्य रघुवंशी शाक्य के मकान से रामस्वरूप परिहार के मकान की ओर ग्राम फरदुआ | Completed | 89000 | 67936 | 2021-10-27 | 2023-04-26
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034614224 — सी सी रोड नाली निर्माण कार्य गब्बर सिंह के मकान से सतीमाता चबूतरा की ओर | Closed | 54000 | 0 | 2022-04-14
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006040/RC/22012034629289 — सी सी सडक निर्माण कार्य पिंटू बाजपेई के मकान से सतीश वाजपेई के मकान की ओर | Closed | 17000 | 0 | 2023-07-17
BHIND / LAHAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006040/RC/28 — पहुॅच मार्ग निर्माण मिटटी काय्र ग्राम फरदुआ | Deleted | 180000 | 0 | 2008-08-15
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1702006040/RS/22012034493699 — नवीन सामुदायिक स्वछता परिसर निर्माण कार्य ग्राम कांक्सी ग्राम पंचायत फरदुआ | Ongoing | 43000 | 27740 | 2020-09-19
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006040/RS/22012034553317 — samudayik sokhta gadda school parisar | Ongoing | 8780 | 5790 | 2021-09-04
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006040/WC/22012034325716 — TALAB JIRDODHAR FARDUA TALAB | Completed | 706000 | 351139.37 | 2017-05-21 | 2020-08-21
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1702006040/WC/22012034357038 — Bori bandhan karya mirga Nadi par | Completed | 139000 | 7224 | 2017-10-06 | 2020-01-05
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702006040/WC/22012034357040 — Bori bandhan karya mirga Nadi par | Completed | 4950000000 | 8256 | 2017-10-06 | 2019-07-02
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1702006040/WC/22012034357041 — Bori bandhan karya mirga Nadi par | Completed | 6090000000 | 11352 | 2017-10-06 | 2019-07-02
BHIND / LAHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702006040/WC/22012034384006 — Talab Nirman | Closed | 0 | 0 | 2018-04-01
BHIND / LAHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702006040/WC/22012034384101 — Talab Nirman | Closed | 0 | 0 | 2018-04-01
BHIND / LAHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006040/WC/22012034435554 — Talab Nirman | Closed | 0 | 0 | 2019-04-01
BHIND / LAHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006040/WC/22012034510742 — चेक डेम निमार्ण कार्य खजराह नाले पर ग्राम लरसा ग्राम पंचायत फरदुआ | Closed | 0 | 0 | 2019-10-02
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702006040/WC/22012034755404 — रूफ वाटर हार्वेस्टिंग पंचायत भवन फरदुआ | Closed | 0 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702006040/WC/22012034755487 — रूफ वाटर हार्वेस्टिंग पंचायत भवन फरदुआ | Completed | 22173.14 | 4632 | 2021-06-07 | 2021-12-25
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702006040/WC/22012034792853 — परकोलेशन तालाब निर्माण कार्य (गनपत के खेत के पास खजराह नाले पर ) लरसा | Physically Completed | 1488809.37 | 559121 | 2021-07-09 | 2026-06-13
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702006040/WC/22012034966574 — नवीन तालाब निर्माण कार्य सर्वे न. 263 रामेश्वर दोहरे के खेत के पास ग्राम फरदुआ | Closed | 0 | 0 | 2022-04-14
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702006040/WC/22012034970222 — अमृत सरोवर तालाब निर्माण कार्य रामेश्वर दोहरे के खेत के पास ग्राम फरदुआ | Ongoing | 2544000 | 233055 | 2022-05-17
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1702006040/WC/22012034970227 — अमृत सरोवर तालाब निर्माण कार्य रामेश्वर दोहरे के खेत के पास ग्राम फरदुआ | Closed | 2544000 | 0 | 2022-04-14
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/388 — मेढबंधान नारायण्/नंदि‍कशोर ग्राम पंचायत फरदुआ | Completed | 31000 | 0 | 2010-09-08 | 2016-08-08
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/389 — मेढबंधान बद्री/पारीछत ग्राम पंचायत फरदुआ | Completed | 18000 | 0 | 2010-09-25 | 2010-09-30
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/390 — मेढबंधान बीर ि‍संह/ज्ञान ि‍संह ग्राम पंचायत फरदुआ | Completed | 11000 | 0 | 2010-09-08 | 2010-09-13
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/391 — मेढबंधान ि‍सरोबन/ज्ञान ि‍संह ग्राम पंचायत फरदुआ | Completed | 11000 | 0 | 2010-09-18 | 2010-09-23
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/407 — मेढबंधान मुन्‍ना/हरचरण ग्राम पंचायत फरदुआ | Deleted | 24000 | 0 | 2010-09-18
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/408 — मेढबंधान मुन्‍नावती/गोि‍वंददास ग्राम पंचायत फरदुआ | Deleted | 36000 | 0 | 2010-07-22
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/409 — मेढबंधान देवप्रसाद/बलदेव ग्राम पंचायत फरदुआ | Deleted | 18000 | 0 | 2010-09-25
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/410 — मेढबंधान कामता/दानसाह ग्राम पंचायत फरदुआ | Deleted | 23000 | 0 | 2010-09-18
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/461 — मेढबंधान करनसिंह/ज्ञानसिंह ग्राम पंचायत फरदुआ | Deleted | 11000 | 0 | 2010-04-01
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006040/WC/463 — मेढबंधान रोशन/नंदकिशोर ग्राम पंचायत फरदुआ | Deleted | 31000 | 0 | 2010-04-01
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702006040/WH/19962296 — Talab Jirdodhar Kanksi | Completed | 871000 | 323712.49 | 2017-05-31 | 2021-10-15
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702006040/WH/22012034456737 — तालाब जीर्णोद्वार कार्य फरदुआ | Closed | 48916.89 | 0 | 2021-04-14
BHIND / LAHAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006041/RC/121 — मिटटी पहुचमार्ग जगदीशपुरा से बडे तालाब से दबोह की ओर | Deleted | 0 | 0 | 2010-04-10
BHIND / LAHAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702/RC/22012034152377 — ग्राम संपर्क सड्क योजना | Completed | 1177000 | 12700 | 2010-06-03 | 2016-09-12