## Work List
Exported on: 2026-10-11 10:28:30
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: SHAHPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034509560 — shantidham nirman shahpura | Closed | 194312.08 | 0 | 2020-04-14
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034509561 — shantidham nirman chadhraua | Closed | 0 | 0 | 2020-04-15
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034509932 — SHANTIDHAM NIRMAN KARY CHADRAUA GRAM PANCHYAT SHAHPURA | Closed | 194312.08 | 0 | 2020-04-05
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034565931 — शान्तिधाम निर्माण शाहपुरा न 2 | Closed | 195934.71 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034565932 — शान्तिधाम निर्माण चढ़रउआ | Closed | 195934.71 | 0 | 2021-04-15
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034621211 — शांतिधाम निर्माण कार्य ग्राम चढ़रौआ ग्राम पंचायत शाहपुरा न. 2 | Closed | 0 | 0 | 2022-08-16
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034621214 — शांतिधाम निर्माण कार्य ग्राम शाहपुरा ग्राम पंचायत शाहपुरा न. 2 | Closed | 0 | 0 | 2022-08-16
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034662981 — शान्तिधाम निर्माण कार्य सदोले प्रजापति के मकान के पास ग्राम चढ़रौआ | Closed | 235393.34 | 0 | 2024-04-14
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/AV/22012034662982 — शान्तिधाम निर्माण कार्य मुख्यमंत्री सड़क के पास ग्राम शाहपुरा न. 2 | Closed | 235393.34 | 0 | 2024-04-14
BHIND / LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702006042/AV/4097 — Aanganbadi/Other Rural Infrastructure,LAHAR | Completed | 330000 | 326860 | 2015-12-10 | 2021-12-15
BHIND / LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1702006042/AV/4098 — Aanganbadi/Other Rural Infrastructure,LAHAR | Completed | 330000 | 326445 | 2015-12-24 | 2021-12-15
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702006042/FP/22012034362173 — C.C.Nali Nirman Fhool Singh Gaur Ke Makan Se Talab Ki or, Shahpura | Completed | 5115 | 5080 | 2019-03-01 | 2019-07-08
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702006042/FP/22012034365081 — baadh niyantran channenl sudur sadak se khajraha nala tak chadhraua | Closed | 987269.01 | 0 | 2021-04-03
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1702006042/FP/22012034629735 — सी सी नाला निर्माण कार्य माताप्रसाद बघेल के मकान से नरिया की ओर | Physically Completed | 181000 | 177769 | 2022-12-13 | 2026-04-22
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1702006042/FP/22012034641261 — जल निकासी नाली निर्माण कार्य माता मंदिर से मरघट की ओर ग्राम शाहपुरा न. 02 | Approved | 11000 | 0 | 2024-06-08
BHIND / LAHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006042/IF/1000032172 — MEDHBANDHAN PREMA DEVI BEBA/DHANIRAM | Deleted | 24771 | 0 | 2013-08-23
BHIND / LAHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006042/IF/1000032174 — MEDHBANDHAN NATHU RAMSWAROOP/BHAROSE | Deleted | 24771 | 0 | 2013-08-23
BHIND / LAHAR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1702006042/IF/14 — शाहपुरा न;ं 2 में कुननिमार्ण हरचरण | Completed | 0 | 73551 | 2009-06-17 | 2009-06-17
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006042/IF/22012034346902 — Plantation work in campus of School etc. | Deleted | 335200 | 0 | 2017-06-16
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006042/IF/22012034346904 — Plantation work in Road side | Completed | 335200 | 17784 | 2017-06-25 | 2020-01-05
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1702006042/IF/22012034352804 — Braksharopan gram chadraua se shahpura no.2 ki ore | Deleted | 500000 | 0 | 2017-06-15
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1702006042/IF/22012034353859 — plantation wori in campus of shala bhavan se balbir kourav ki kothi ki ore | Completed | 335200 | 25600 | 2017-06-25 | 2019-01-05
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727787 — Med Bandhan Nirman rames/neksai shahpura | Closed | 69977.12 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727797 — Med Bandhan Nirman puspendra/keskumar shahpura | Closed | 71151.63 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727803 — Med Bandhan Nirman maharaj singh/ghanshyam shahpura | Closed | 80547.36 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727809 — Med Bandhan Nirman gyaprasad/ratiram shahpura | Closed | 72326.14 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727816 — Med Bandhan Nirman gyaprasad/ratiram shahpura | Closed | 0 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727825 — Med Bandhan Nirman atalbihari/ratu shahpura | Closed | 73500.65 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727830 — Med Bandhan Nirman puran singh/ matadin shahpura | Closed | 74674.98 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727855 — Med Bandhan Nirman mevalal/sukhlal chadhraua | Ongoing | 75849.5 | 12738 | 2021-06-11
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727858 — Med Bandhan Nirman chunnilal/harprasad chadhraua shahpura | Closed | 77024 | 0 | 2021-04-15
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727863 — Med Bandhan Nirman chhotelal/gajai chadhraua | Closed | 0 | 0 | 2021-04-15
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727870 — Med Bandhan Nirman ghanaram/gajai chadhraua | Ongoing | 78198.51 | 1158 | 2021-06-11
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034727878 — Med Bandhan Nirman narayan/neksai chadhraua | Closed | 79372.85 | 0 | 2021-04-15
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034728083 — Med Bandhan Nirman mangli/pehalwan chadhraua | Closed | 69977.12 | 0 | 2021-04-15
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034728086 — Med Bandhan Nirman rajaram/dharajit chadhraua | Ongoing | 71151.63 | 1158 | 2021-06-11
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034728088 — Med Bandhan Nirman mitthulal/darele chadhraua | Ongoing | 72326.14 | 1158 | 2021-06-11
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034728092 — Med Bandhan Nirman maniram/ajuddhi chadhraua | Closed | 73500.65 | 0 | 2021-04-15
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1702006042/IF/22012034728095 — Med Bandhan Nirman harkishun mahore/halke chadhraua | Ongoing | 74674.98 | 1158 | 2021-06-11
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1702006042/IF/22012034834314 — खेत तालाब निर्माण कार्य कमलेश / हरजूप्रसाद प्रजापति | Closed | 111248.93 | 0 | 2021-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993714133 — मेढवंधान नाथू / रामसहाय | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Soil Cover on Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993714134 — मेढवंधान हरचरन | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993714135 — मेढवंधान रामप्रसाद | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993714136 — मेढवंधान सियाशरण | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Soil Cover on Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993714137 — मेढवंधान शेरसिंह | Closed | 0 | 0 | 2016-04-14
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993716042 — med bandhan nirman munnalal / neksai kaurav | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993716043 — med bandhan nirman sahavsingh / jagdeesh | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716044 — med bandhan nirman munnalal / neksai kaurav | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716045 — med bandhan nirman sahav singh / jagdeesh | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993716046 — med bandhan nirman ratiram / chandrabhan | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716047 — pashu shaid narendra / poran singh | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716048 — pashu shaid kesh kumar / badri | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716049 — pashu shaid pahlvan parihar | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716050 — pashu shaid hari singh rathor | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716051 — pashu shaid pooran vanskar | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Piggery shed / Construction of Piggery Shelter for Individuals | Piggery Shelter | 1702006042/IF/9993716052 — pashu shaid rustaum kaurav | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993716053 — med bandhan keshkumar | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1702006042/IF/9993716054 — med bandhan pooran vanshkar | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/1142416 — Construction of IAY House -IAY REG. NO. MP-02-006-042-002/24 | Approved | 23490 | 0 | 2016-02-19
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/115272 — Construction of IAY House -IAY REG. NO. MP-02-006-042-001/15 | Completed | 14310 | 14268 | 2016-12-07 | 2018-12-10
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/115273 — Construction of IAY House -IAY REG. NO. MP-02-006-042-002/019 | Completed | 14310 | 14448 | 2017-08-02 | 2018-05-20
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/115274 — Construction of IAY House -IAY REG. NO. MP-02-006-042-002/10 | Completed | 14310 | 14232 | 2016-10-21 | 2018-12-10
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/115275 — Construction of IAY House -IAY REG. NO. MP-02-006-042-002/23 | Completed | 14310 | 14328 | 2016-10-21 | 2018-05-30
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/1892983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4460736 | Completed | 15660 | 15660 | 2018-09-20 | 2018-12-10
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/1894095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5028853 | Completed | 15660 | 15660 | 2018-09-01 | 2019-01-06
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/1894647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5433496 | Completed | 15660 | 15660 | 2018-08-22 | 2018-12-25
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/1897632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5530574 | Completed | 15660 | 15660 | 2018-09-11 | 2019-01-06
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/192869 — Construction of IAY House -IAY REG. NO. MP-02-006-042-002/025 | Completed | 14310 | 15030 | 2016-10-21 | 2018-05-30
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/192870 — Construction of IAY House -IAY REG. NO. MP-02-006-042-002/28 | Completed | 14310 | 15030 | 2016-10-19 | 2018-05-30
BHIND / LAHAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/1943135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5028330 | Completed | 15660 | 15582 | 2019-03-06 | 2019-06-12
BHIND / LAHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/2157595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5450823 | Completed | 17100 | 16567 | 2020-06-26 | 2022-10-29
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/2157606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5451073 | Ongoing | 23490 | 9264 | 2021-06-23
BHIND / LAHAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/2161268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5548609 | Completed | 17100 | 16677 | 2020-02-14 | 2021-05-07
BHIND / LAHAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/2188216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5273687 | Completed | 17100 | 16406 | 2020-01-22 | 2021-05-07
BHIND / LAHAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/2346214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5544075 | Completed | 15840 | 16300 | 2020-03-19 | 2020-08-10
BHIND / LAHAR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/2346215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5558268 | Completed | 15840 | 16008 | 2020-02-02 | 2020-05-13
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/260316 — Construction of IAY House -IAY REG. NO. MP2405073 | Completed | 15030 | 15480 | 2017-11-16 | 2018-04-20
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/261718 — Construction of IAY House -IAY REG. NO. MP2627251 | Completed | 15030 | 15330 | 2017-03-08 | 2018-04-20
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/270503 — Construction of IAY House -IAY REG. NO. MP2664301 | Completed | 15030 | 15020 | 2017-01-27 | 2018-05-20
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/270623 — Construction of IAY House -IAY REG. NO. MP2678086 | Completed | 15030 | 15340 | 2017-01-27 | 2018-04-20
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/278331 — Construction of IAY House -IAY REG. NO. MP3754659 | Completed | 15030 | 14532 | 2017-01-27 | 2018-09-19
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/3278860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5569356 | Completed | 17370 | 17280 | 2021-12-30 | 2022-10-28
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/3702636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115947393 | Completed | 18360 | 18360 | 2022-06-19 | 2022-10-28
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/3777657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125043659 | Completed | 18360 | 18360 | 2022-09-20 | 2023-06-27
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/3915174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148880696 | Completed | 18360 | 16932 | 2022-06-03 | 2022-10-29
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/4326158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144284290 | Completed | 18360 | 18360 | 2022-09-15 | 2023-06-27
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/4520932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115277154 | Ongoing | 23490 | 21942 | 2024-11-28
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/4773189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125041742 | Ongoing | 23490 | 21942 | 2024-11-28
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/4775325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122698490 | Ongoing | 23490 | 22194 | 2025-02-12
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5573780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115946892 | Ongoing | 23490 | 23229 | 2025-06-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5573781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115947045 | Physically Completed | 23490 | 23490 | 2025-05-29 | 2026-05-24
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5574150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116984310 | Physically Completed | 23490 | 23229 | 2025-09-20 | 2026-05-31
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5574195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129227928 | Physically Completed | 23490 | 23229 | 2025-06-01 | 2026-05-17
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5574197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129228139 | Physically Completed | 23490 | 17226 | 2025-06-05 | 2026-06-07
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5719658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124971174 | Physically Completed | 23490 | 23490 | 2025-09-29 | 2026-05-03
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5858305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129227992 | Ongoing | 23490 | 23490 | 2025-11-28
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/5864240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116984243 | Ongoing | 23490 | 23490 | 2026-02-25
BHIND / LAHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1702006042/IF/IAY/586660 — Construction of IAY House -IAY REG. NO. MP2731876 | Completed | 15030 | 15434 | 2017-03-09 | 2018-05-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/LD/22012034257814 — samshan ghat shaypura | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/LD/22012034257815 — samshan ghat chadrouaa | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006042/LD/22012034257816 — vaundri wall m.s.shaypura | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006042/LD/22012034257817 — talab gehrikaran shaypura | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1702006042/LD/22012034257818 — talab gehrikaran chadroua | Closed | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1702006042/LD/22012034309556 — shanti dham nirman shahpura n.2 | Deleted | 180000 | 0 | 2017-06-28
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702006042/LD/22012034943526 — JAL NIKASI NALI NIRMAN KARY MATA MANDIR SE MARGHAT KI OR GRAM SHAHPURA NO 2 | Approved | 11000 | 0 | 2024-04-14
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702006042/LD/22012034943527 — JAL NIKARI NALI NIRMAN KARY GANDHARV SINGH BAGHEL KE MAKAN SHALA BHAVAN KI OR | Approved | 18000 | 0 | 2024-04-14
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1702006042/LD/22012034943528 — JAL NIKASI NALI NIRMAN KARY RAMSHANKAR RATHAUR KE MAKAN SE MAIN ROAD TAK GRAM SHAHPURA NO 2 | Approved | 21000 | 0 | 2024-04-14
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1702006042/PG/22012034365830 — खेल मैदान ग्राम पंचयत शाह पुरा | Closed | 0 | 0 | 2018-04-01
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034195912 — पंच परमेश्‍वर सीसी रोड कल्‍लू वंशकार के मकान से गे | Completed | 113654 | 102199.9 | 2013-12-26 | 2014-02-24
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034201799 — पंच परमेश्‍वर सीसी रोड मानसिंह बघेल के मकान से पुल | Completed | 113603 | 98823.8 | 2014-01-31 | 2014-03-19
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034212838 — पंच परमेश्‍वर सीसी रोड भगवत कौरव के मकान से बाटर श | Completed | 173834 | 142946.6 | 2014-03-06 | 2015-09-18
BHIND / LAHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034212844 — पंच परमेश्‍वर सीसी रोड ज्ञान सिंह कौरव के मकान से | Completed | 131263 | 117059 | 2014-03-06 | 2016-05-06
BHIND / LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034288375 — सीसी रोड मय नाली निर्माण हनुमान जी के मंदिर से लेकर केशकुमार कौरव के मकान से होेते हुुए रामेश्‍वर तक | Completed | 62374 | 61956 | 2015-11-04 | 2017-11-12
BHIND / LAHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034296089 — सी सी रोड मय नाली निर्माण परमानन्‍द राठौर के मकान से गुजरते हुये बम्‍बा की ओर | Completed | 153666 | 103532 | 2016-02-15 | 2016-04-20
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034301604 — c.c. rod may nali ke ramjanki mandir se bamba ki or | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034301605 — c.c. rod may nali ke ramjanki mandir se ramji kaurav ki or | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034301606 — c.c. rod may nali ke gende parihar se rma sankar vanshkar ki or | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006042/RC/22012034301608 — sudur sampark rod bamba ki puliya se rameswr udainiya ke khet tak | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006042/RC/22012034301609 — sudur sampark rod balveer kaurav ke khet se siya kaurav ke khet tak | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1702006042/RC/22012034301612 — sudur sampark rod sanman ke khet se birjbhan ke khet tak | Deleted | 0 | 0 | 2016-04-01
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034334625 — C.C ROAD MAY NALI NIRMAN MAIN ROAD SE KANHAIYALAL UDAINIYA KE MAKAN KI OUR GRAM SHAHPURA N. 2. | Completed | 56250 | 44548 | 2017-04-10 | 2018-01-30
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034361279 — C.C.ROAD.& NALI NIRMAN , MAIN ROAD SE MALKHAN GOUR KE MAKAN KI OR | Completed | 135000 | 119196 | 2017-09-29 | 2018-01-20
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006042/RC/22012034366952 — Sudur Samprak Sadak Chadrauaa se barthara P.M.G.S.Y raod tak, Shahpura | Physically Completed | 1844000 | 1677194.8 | 2017-11-18 | 2021-06-18
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034376545 — C.C.Raod | Deleted | 0 | 0 | 2018-04-01
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034440268 — C.C.Road Mai Nali Chunnilal Baghel Ke Makan Se Hakim Singh Baghel Ke Makan Ki Or, shahpura | Closed | 93000 | 0 | 2018-12-29
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034441203 — C.C.Road | Closed | 0 | 0 | 2019-04-01
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034443708 — सी.सी.रोड मय नाली चुन्नी लाल बघेल के मकान से हाकिम सिंह के मकान की ओर , शाहपुरा | Completed | 93000 | 84880 | 2019-02-26 | 2019-09-01
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034446860 — सीसी रोड मय नाली निर्माण राजेंद्र सिंह गोर के मकान से छोटे कुशवाह के मकान से होते हुये मुन्ना लाल सव | Completed | 100750 | 58384 | 2019-03-05 | 2019-09-01
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034446864 — सीसी रोड मय नाली निर्माण राधाचरन कौरव से सुखसिंह कौरव के मकान की ओर | Completed | 38750 | 22996 | 2019-03-05 | 2019-09-01
BHIND / LAHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034446936 — सीसी रोड मय नाली निर्माण धनीराम परिहार के मकान से पहलवान परिहार के मकान की ओर | Completed | 38750 | 18056 | 2019-03-05 | 2020-01-05
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034476688 — सी सी रोड एवं नाली निर्माण 14 व वित सरजू शरण जाटव के मकान से पी एम जी एस रोड तक | Closed | 21000 | 0 | 2019-08-15
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034476759 — सी सी रोड निमार्ण कार्य 14 वा वित्त परमानंद राठोर के मकान से पी एम जी रोड तक | Closed | 68000 | 0 | 2019-08-15
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034476762 — सी सी रोड़ nili nirana 14 वित्त रामकुमार बशकार के मकान से | Closed | 21000 | 0 | 2019-08-15
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034477828 — C.C. ROAD NALI NIRMAN KARY PARMANAND RATHAUR KE MAKAN SE P M SADAK KI OR | Completed | 70000 | 55616 | 2019-10-25 | 2020-03-17
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034477829 — C.C. ROAD NALI NIRMAN KARY KAMTA PRASAD JATAV EVM SARJUSHRAN JATAV KE MAKAN SE P M SADAK KI OR | Completed | 20000 | 17248 | 2019-11-01 | 2020-02-17
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034477830 — C.C. ROAD NALI NIRMAN KARY RAJKUMAR BANSKAR KE MAKAN SE AGANWADI BHAVAN KI OR | Completed | 22000 | 21648 | 2019-11-04 | 2020-02-10
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034534831 — सी सी रोड नाली निर्माण कार्य सुनील बघेल के मकान से धन सिंह बघेल के मकान की ओर | Completed | 37200 | 32213 | 2020-09-16 | 2021-12-11
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034534832 — सी सी रोड नाली निर्माण कार्य अशोक प्रजापति के मकान से चतुर सिंह माहौर के मकान की ओर | Completed | 32500 | 32406 | 2020-09-14 | 2021-12-13
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034540395 — सीसी रोड मय नाली निर्माण हरिओम प्रजापति के मकान से मातादीन रजक के मकान तक ग्राम चढ़रौआ | Completed | 23250 | 17545 | 2020-09-25 | 2021-12-11
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034540397 — सीसी रोड मय नाली निर्माण लाखन सिंह बघेल के मकान से रामफल बघेल के मकान ओर ग्राम चढ़रौआ | Closed | 46500 | 0 | 2020-04-27
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034540399 — सीसी रोड मय नाली निर्माण रामजानकी मंदिर से चतुर सिंह बघेल के मकान तक ग्राम चढ़रौआ | Completed | 44888 | 26417 | 2020-09-24 | 2021-12-11
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034540402 — सीसी रोड मय नाली निर्माण राजाराम कुशवाह के मकान से विजय सिंह बघेल के मकान तक ग्राम चढ़रौआ | Completed | 13950 | 10398 | 2020-09-24 | 2021-12-11
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034585661 — सीसी रोड एवं नाली निर्माण कार्य लाखन सिंह बघेल के मकान से रामफल बघेल के मकान की ओर ग्राम चढ़रौआ | Closed | 85000 | 0 | 2021-04-15
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034591410 — सी सी रोड नाली निर्माण कार्य लाखन सिंह बघेल के मकान से रामफल बघेल के मकान की और | Completed | 85000 | 63304 | 2021-11-03 | 2023-04-26
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034616786 — सी सी सडक एवं नाली निर्माण कार्य हाकिम सिंह बघेल के मकान से गौरीशंकर बघेल के मकान तक | Ongoing | 48000 | 30600 | 2022-11-24
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034629004 — सी सी रोड नाली निर्माण कार्य सनमान कौरव के बाहरी मकान से कमलेश परिहार के मकान की ओर | Completed | 59000 | 54145 | 2023-05-04 | 2024-05-20
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034629005 — सी सी सड़क एवं नाली निर्माण कार्य राजीव पांडे के मकान से रघुवंशी कौरव के मकान तक | Completed | 24000 | 20995 | 2023-05-28 | 2024-05-20
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034629006 — सी सी सड़क एवं नाली निर्माण कार्य रतनलाल प्रजापति के मकान से रामस्वरूप के मकान की ओर | Completed | 40000 | 29172 | 2023-07-23 | 2024-05-20
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034642453 — सी सी रोड एवं नाली निर्माण कार्य मैंन रोड से परमानन्द राठौर के मकान की ओर | Completed | 360000 | 58785 | 2023-10-01 | 2024-11-22
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034642454 — सी सी रोड एवं नाली निर्माण कार्य मंगल सिंह कौरव के मकान से गुलाब सिंह कौरव के मकान की ओर | Completed | 48000 | 35360 | 2023-09-03 | 2024-05-20
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1702006042/RC/22012034824074 — C C ROAD NIRMAN KARY MAIN ROAD SE MARGHAT KI OR | Approved | 37000 | 0 | 2024-04-14
BHIND / LAHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1702006042/RC/291 — 1702006042/RC/291 | Completed | 0 | 25956 | 2012-10-04 | 2014-02-25
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006042/RS/22012034685253 — सामुदायिक सोख्ता गड्डा निर्माण कार्य शाला भवन के हैण्ड पम्प पर ग्राम शाहपुरा न. 2 | Closed | 6600 | 0 | 2022-08-16
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006042/RS/22012034685255 — सामुदायिक सोख्ता गड्डा निर्माण कार्य माता मंदिर के हैण्ड पम्प पर ग्राम शाहपुरा न.2 | Closed | 6600 | 0 | 2022-08-16
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1702006042/RS/22012034685256 — सामुदायिक सोख्ता गड्डा निर्माण कार्य शाला भवन के हैण्डपम्प पर ग्राम चढ़रौआ | Closed | 6600 | 0 | 2022-08-16
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012034685257 — सामुदायिक निर्माण कार्य हरदान सिंह राजावत के मकान के पास ग्राम शाहपुरा न. 2 | Ongoing | 1900 | 1458 | 2024-06-08
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012034685259 — सामुदायिक नाडेप निर्माण कार्य शंकर राठौर की जगह पर ग्राम शाहपुरा न. 2 | Completed | 1900 | 884 | 2023-08-09 | 2023-09-09
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012035134412 — सामुदायिक नाडेप निर्माण कार्य रामफल बघेल के बाहरी मकान के पास ग्राम चढ़रौआ | Closed | 2000 | 0 | 2025-01-28
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012035134413 — सामुदायिक नाडेप निर्माण कार्य बालकिशुन बघेल के खेत के पास ग्राम चढ़रौआ | Closed | 2000 | 0 | 2025-01-28
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012035134420 — सामुदायिक नाडेप निर्माण कार्य PWD रोड के पास ग्राम शाहपुरा न. 2 | Closed | 2000 | 0 | 2025-01-27
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012035134480 — सामुदायिक नाडेप निर्माण कार्य सुरेन्द्र सिंह वैश के बाहरी मकान के पास ग्राम शाहपुरा न. 2 | Closed | 2000 | 0 | 2025-01-27
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1702006042/RS/22012035134481 — सामुदायिक नाडेप निर्माण कार्य शाला भवन पर ग्राम चढ़रौआ | Closed | 2000 | 0 | 2025-01-28
BHIND / LAHAR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006042/WC/196 — मेढ्वंधान नि‍रपाल/हाकि‍म सि‍ह ग्राम पंचायत शाहपुरा नं2 | Completed | 7000 | 0 | 2009-08-24 | 2009-08-24
BHIND / LAHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702006042/WC/22012034293702 — शा.प्रा.वि.भवन के पास तालाब | Deleted | 81000 | 0 | 2016-05-20
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702006042/WC/22012034324059 — Talab Ki Bund Sudrikaran Aganbadi Bhavan Ke Pass | Deleted | 68000 | 0 | 2017-04-14
BHIND / LAHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1702006042/WC/22012034384055 — NEW TALAB NIRMAN | Closed | 0 | 0 | 2017-10-02
BHIND / LAHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1702006042/WC/22012034384134 — Talab Nirman | Closed | 0 | 0 | 2018-04-01
BHIND / LAHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006042/WC/22012034437663 — Talab Nirman | Closed | 0 | 0 | 2019-04-01
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1702006042/WC/22012034670060 — dag pond nirman chadhraua | Ongoing | 1496404.18 | 1158 | 2021-06-10
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1702006042/WC/22012034765653 — रूफ वाटर हार्वेस्टिंग पंचायत भवन शाहपुरा न 2 | Closed | 0 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1702006042/WC/22012034813936 — चैक डेम निर्माण खजराहा नाले पर ग्राम चढ़रौआ ग्रा. प. शाहपुरा न 2 | Ongoing | 1130000 | 579 | 2021-10-27
BHIND / LAHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1702006042/WC/22012035055128 — रिटेनिंग वाल निर्माण कार्य माता मंदिर मुख्यमंत्री रोड तालाब के आस पास | Physically Completed | 1382000 | 1375702.98 | 2023-06-24 | 2026-06-11
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006042/WC/457 — मेढबंधान सदोले/खन्‍जू ग्राम पंचायत शाहपुरा नं02 | Deleted | 24000 | 0 | 2010-07-14
BHIND / LAHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1702006042/WC/458 — मेढबंधान हरचरण/तिजोल यादव ग्राम पंचायत शाहपुरा नं02 | Deleted | 24000 | 0 | 2010-05-09
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702006042/WH/19959120 — Talab Ki Bund Sudrikaran Aganbadi Bhavan Ke Pass | Completed | 68000 | 57792 | 2017-05-18 | 2018-01-20
BHIND / LAHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1702006042/WH/22012034325324 — Talab jirdodhar gram chadraua | Completed | 46000 | 32364 | 2017-07-13 | 2020-01-05
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702006042/WH/22012034456614 — तालाब जीर्णोद्वार कार्य गाँव के पास शाहपुरा न 2 | Closed | 21740.84 | 0 | 2021-04-14
BHIND / LAHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1702006042/WH/22012034456618 — तालाब जीर्णोद्वार कार्य चढ़रौआ (शाहपुरा न 2) | Closed | 26306.42 | 0 | 2021-04-14