## Work List
Exported on: 2026-10-10 11:24:10
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BARTHARA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006047/AV/22012034509635 — kabrastan nirman barthra | Ongoing | 358565.66 | 0 | 2020-06-04
BHIND / LAHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1702006047/AV/22012034552160 — शांति धाम निर्माण कार्य ग्राम पंचायत बरथरा | Ongoing | 195535.43 | 0 | 2021-04-04
BHIND / LAHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for Community | Construction of Embankment | 1702006047/FP/22012034363036 — नवीन नाला निमार्ण संतोष कौरव के मकान से सन्ति कौरव के मकान की ओर | Ongoing | 500000 | 0 | 2019-04-03
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702006047/FP/22012034633902 — सी सी नाला निर्माण कार्य शंकर जी के मंदिर से राय सिंह कुशवाह के मकान की ओर ग्राम बरथरा | Ongoing | 174000 | 0 | 2023-08-03
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Flood Diversion Drain for Community | Works for Flood Control and Protection | 1702006047/FP/22012034636763 — सी सी नाला निर्माण कार्य हरिराम के घर से पुलिया की ओर | Ongoing | 111000 | 0 | 2023-10-09
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702006047/IF/22012034818700 — KHET TALAB NIRMAN KARY ABADHKISHOR / BANSHGOPAL | Ongoing | 338902.57 | 0 | 2021-07-01
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702006047/IF/22012034941987 — खेत तालाब निर्माण कार्य विजय उदैनिया/मंगल प्रसाद ग्राम बरथरा | Ongoing | 338902.57 | 0 | 2022-03-04
BHIND / LAHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1702006047/IF/22012034941988 — खेत तालाब निर्माण कार्य वेवा देवकुंवर / जानकीशरण ग्राम बरथरा | Ongoing | 338902.57 | 0 | 2022-03-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006047/IF/22012035608032 — Ek bagiya maa ke naam vraksharopan mamta w/o ramprakash | New | 0 | 0 | 2025-08-01
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006047/IF/22012035608166 — Ek bagiya maa ke naam vraksharopan mamta w/o ramprakash | Ongoing | 266577.25 | 0 | 2025-09-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006047/IF/22012035610861 — Ek bagiya maa ke naam vraksharopan vimla devi w/o arjun singh | Ongoing | 266577.25 | 0 | 2025-12-29
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006047/IF/22012035613150 — Ek bagiya maa ke naam vraksharopan keshwati w/o dashrath singh | Ongoing | 266577.25 | 0 | 2025-12-29
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1702006047/IF/22012035626524 — Ek bagiya maa ke naam vraksharopan rammurti/thakurprasad barthara gora | Approved | 199129.33 | 0 | 2025-08-15
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/3971670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114978681 | Ongoing | 27000 | 0 | 2022-11-12
BHIND / LAHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/3977773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117776777 | Ongoing | 27000 | 0 | 2022-10-22
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4519688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114207140 | Ongoing | 27000 | 0 | 2025-01-29
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4519689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114210481 | Ongoing | 27000 | 0 | 2025-01-29
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4520213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115175801 | Ongoing | 27000 | 0 | 2025-04-07
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4521167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675220 | Ongoing | 27000 | 0 | 2025-05-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4521681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117392143 | Ongoing | 27000 | 0 | 2025-04-11
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4523999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123688902 | Ongoing | 27000 | 0 | 2025-04-07
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4528180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129882752 | Approved | 27000 | 0 | 2024-09-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4746508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114997516 | Ongoing | 27000 | 0 | 2025-04-07
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4747612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115178118 | Ongoing | 27000 | 0 | 2025-04-11
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4748186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115250899 | Ongoing | 27000 | 0 | 2025-04-07
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4765869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115795851 | Ongoing | 27000 | 0 | 2025-04-07
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4768181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123689062 | Ongoing | 27000 | 0 | 2025-04-07
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4773817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675270 | Ongoing | 27000 | 0 | 2025-05-27
BHIND / LAHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/4782063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129875399 | Ongoing | 27000 | 0 | 2025-01-29
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129876079 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117765527 | Approved | 27000 | 0 | 2025-04-06
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115018719 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129878195 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129880750 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115863068 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129874146 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129878038 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117760379 | Approved | 27000 | 0 | 2025-05-01
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129876228 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117392030 | Approved | 27000 | 0 | 2025-04-11
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116100667 | Approved | 27000 | 0 | 2025-04-11
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129875239 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115643197 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129878482 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123687558 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115749539 | Ongoing | 27000 | 3600 | 2026-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150097058 | Approved | 27000 | 0 | 2025-05-01
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114809653 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117392034 | Approved | 27000 | 0 | 2025-05-01
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117397304 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123790587 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132771676 | Approved | 27000 | 0 | 2025-04-06
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123688824 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115870414 | Ongoing | 27000 | 0 | 2026-09-28
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675380 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117395246 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115187226 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5882790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117395259 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5935606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123800134 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5935758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139999630 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5936097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115248723 | Approved | 27000 | 0 | 2025-04-04
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5936564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150101317 | Ongoing | 27000 | 0 | 2026-07-12
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5936957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150096658 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5937691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129880639 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5938006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129874532 | Approved | 27000 | 0 | 2025-04-06
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5939192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117765462 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5939193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117765511 | Ongoing | 27000 | 0 | 2026-07-12
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5940211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114979871 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5940828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114780929 | Ongoing | 27000 | 0 | 2026-08-10
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5941364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115008814 | Approved | 27000 | 0 | 2025-04-04
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5941385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129872320 | Ongoing | 27000 | 0 | 2026-07-12
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5941386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117766430 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5942308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115250878 | Approved | 27000 | 0 | 2025-04-06
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5942590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129879123 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5942868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150247158 | Ongoing | 27000 | 3600 | 2026-05-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5942900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115194697 | Approved | 27000 | 0 | 2025-04-06
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/5943203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114787210 | Approved | 27000 | 0 | 2025-04-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115250850 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114783311 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115863058 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140048903 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132778186 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115043012 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129876878 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242752 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124071411 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129870996 | Approved | 27000 | 0 | 2025-04-06
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132778193 | Approved | 27000 | 0 | 2026-03-09
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117392157 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675360 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802335 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410055 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123687071 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115863080 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115753031 | Ongoing | 27000 | 0 | 2026-08-19
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115872397 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122940408 | Approved | 27000 | 0 | 2025-04-13
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115248692 | Approved | 27000 | 0 | 2025-04-04
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675418 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675352 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115795830 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125276333 | Approved | 27000 | 0 | 2025-04-11
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6242959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675400 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6351762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115870444 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6354326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129873969 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6354554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114762660 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6386648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115410012 | Approved | 27000 | 0 | 2025-05-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6386836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115675430 | Approved | 27000 | 0 | 2025-04-08
BHIND / LAHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1702006047/IF/IAY/6386894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117392014 | Approved | 27000 | 0 | 2025-04-05
BHIND / LAHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006047/RC/22012034360387 — C.C.ROAD & NALI NIRMAN MAHATAB KAURAV KE MAKAN SE SANJAY KAURAV KE MAKAN TAK | Ongoing | 0 | 0 | 2017-09-18
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1702006047/RC/22012034525972 — sudur sampark khet sadak nirman vanshi kaurav ke khet se belma ki or gram barthara | Ongoing | 2497458.48 | 0 | 2020-06-26
BHIND / LAHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006047/RC/22012034610355 — सी सी रोड निर्माण उदय सिंह के मकान से मुन्नालाल वाल्मीक के मकान तक | Ongoing | 57000 | 0 | 2022-06-06
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006047/RC/22012034616750 — सी सी रोड एवं नाली निर्माण कार्य भिंड भांडेर रोड से छदामी कुशवाह के मकान तक | Ongoing | 274000 | 0 | 2023-05-16
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006047/RC/22012034644247 — सी सी रोड एवं नाली निर्माण कार्य रणवीर सिंह कौरव के मकान से माता जी के मंदिर तक ग्राम बरथरा | Ongoing | 92000 | 0 | 2023-07-13
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006047/RC/22012034664404 — सी सी रोड एवं नाली निर्माण कार्य चन्द्रप्रकाश कुशवाह के मकान से राजकुमार अहिरवार के मकान तक | Ongoing | 247000 | 0 | 2023-10-09
BHIND / LAHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1702006047/RC/22012034822899 — सी सी रोड़ निर्माण कार्य मैंन रोड से लक्ष्मण जी मंदिर की ओर | Approved | 67000 | 0 | 2024-04-14
BHIND / LAHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex for Community | Community Sanitary Complex | 1702006047/RS/22012034493920 — नवीन सामुदायिक स्वच्छता परिसर निर्माण कार्य ग्राम गोरा ग्राम पंचायत बरथरा | Ongoing | 43000 | 0 | 2020-09-21
BHIND / LAHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for Community | Construction of Embankment | 1702006047/WC/22012035108405 — नवीन तालाब निर्माण ग्राम बरथरा फेज 1 | Ongoing | 1496801.42 | 0 | 2023-10-05