## Work List
Exported on: 2026-10-21 05:10:22
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JHADOLI(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GWALIOR / DABRA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1703003032/DP/22012034586792 — amrat vatika nirman govt midil prathmik vidhyalay jhadoli | Ongoing | 55847.4 | 2100 | 2024-07-25
GWALIOR / DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/42574 — Construction of IAY House -IAY REG. NO. MP-03-003-032-001/17 | Approved | 27000 | 0 | 2015-06-01
GWALIOR / DABRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4745662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114078245 | Ongoing | 27000 | 3600 | 2025-03-19
GWALIOR / DABRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4745700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114083138 | Ongoing | 27000 | 0 | 2025-02-15
GWALIOR / DABRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4746940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114137267 | Ongoing | 27000 | 0 | 2025-02-15
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4942308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114120595 | Ongoing | 27000 | 0 | 2025-08-06
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4942317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114123356 | Ongoing | 27000 | 6300 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4942344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114129371 | Physically Completed | 27000 | 0 | 2025-09-24 | 2026-10-18
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4942999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114094116 | Physically Completed | 27000 | 3600 | 2025-05-21 | 2026-09-13
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4943006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114095996 | Physically Completed | 23490 | 0 | 2025-06-11 | 2026-08-16
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4943013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114098658 | Physically Completed | 23490 | 0 | 2025-07-02 | 2026-08-16
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4945385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114737519 | Ongoing | 27000 | 0 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4945427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114750303 | Ongoing | 27000 | 0 | 2025-10-15
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4945432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114752112 | Ongoing | 27000 | 0 | 2025-09-24
GWALIOR / DABRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4946179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115926974 | Approved | 27000 | 0 | 2025-02-14
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4954401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114079519 | Physically Completed | 23490 | 3600 | 2025-08-06 | 2026-08-16
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4954418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114084285 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-16
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/4954430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114087422 | Ongoing | 27000 | 1800 | 2025-05-21
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5342268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115927096 | Ongoing | 27000 | 6600 | 2026-09-02
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5423238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114749008 | Physically Completed | 23490 | 0 | 2025-10-15 | 2026-08-23
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5431022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115925861 | Ongoing | 27000 | 0 | 2025-10-08
GWALIOR / DABRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5431023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115926628 | Approved | 27000 | 0 | 2025-02-14
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5433899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114744921 | Ongoing | 27000 | 0 | 2025-10-15
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5597192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115925700 | Ongoing | 27000 | 0 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5597193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115926013 | Ongoing | 27000 | 0 | 2025-10-15
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5598082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115927047 | Ongoing | 27000 | 0 | 2025-07-02
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5603512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121702972 | Approved | 27000 | 0 | 2025-04-29
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5604101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115926182 | Ongoing | 27000 | 0 | 2025-10-15
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5604653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114742019 | Ongoing | 27000 | 0 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5670657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152078690 | Physically Completed | 27000 | 0 | 2025-09-03 | 2026-09-20
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5670658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152078695 | Physically Completed | 27000 | 0 | 2025-09-24 | 2026-09-06
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5670693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152086799 | Physically Completed | 23490 | 0 | 2025-09-24 | 2026-08-02
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5671026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152079467 | Physically Completed | 27000 | 0 | 2025-09-03 | 2026-08-30
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5671112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076480 | Physically Completed | 23490 | 0 | 2025-09-03 | 2026-08-16
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5671317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152081775 | Physically Completed | 27000 | 0 | 2025-09-03 | 2026-09-20
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5671377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152084717 | Physically Completed | 23490 | 0 | 2025-09-03 | 2026-08-16
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5702031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115925941 | Ongoing | 27000 | 3300 | 2026-09-02
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5702546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114734213 | Ongoing | 27000 | 10800 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5702547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114739709 | Ongoing | 27000 | 0 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5702579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114709120 | Approved | 27000 | 0 | 2025-05-23
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5702643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114127348 | Ongoing | 27000 | 15600 | 2026-05-13
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5703022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114735417 | Ongoing | 27000 | 3600 | 2025-09-24
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5796966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115926494 | Ongoing | 27000 | 10800 | 2026-01-13
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5797695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114081561 | Ongoing | 27000 | 1800 | 2025-10-01
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/5797949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114125573 | Approved | 27000 | 0 | 2025-04-15
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6051047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076709 | Ongoing | 27000 | 0 | 2026-09-17
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6051456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076710 | Ongoing | 27000 | 6900 | 2026-07-22
GWALIOR / DABRA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6055820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152078691 | Approved | 27000 | 0 | 2026-02-26
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6055908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152076537 | Ongoing | 27000 | 8400 | 2026-07-22
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6055909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152090612 | Ongoing | 27000 | 6900 | 2026-07-22
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6060647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152086826 | Ongoing | 27000 | 6900 | 2026-07-22
GWALIOR / DABRA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6066398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114080263 | Approved | 27000 | 0 | 2025-02-14
GWALIOR / DABRA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/6237952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152084737 | Ongoing | 27000 | 12000 | 2026-07-22
GWALIOR / DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/71569 — Construction of IAY House -IAY REG. NO. MP-03-003-032-001/57 | Approved | 27000 | 0 | 2015-06-01
GWALIOR / DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/71570 — Construction of IAY House -IAY REG. NO. MP-03-003-032-001/67 | Approved | 27000 | 0 | 2015-06-01
GWALIOR / DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/71571 — Construction of IAY House -IAY REG. NO. MP-03-003-032-001/69 | Approved | 27000 | 0 | 2015-06-01
GWALIOR / DABRA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703003032/IF/IAY/71572 — Construction of IAY House -IAY REG. NO. MP-03-003-032-001/74 | Approved | 27000 | 0 | 2015-06-01
GWALIOR / DABRA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1703003032/RC/22012034540979 — GRAVAL ROAD NIRMAN JHADOLI SE SAMCHOLI KI OR JHADOLI KI OR | Ongoing | 2849351.95 | 0 | 2020-09-29
GWALIOR / DABRA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1703003032/RC/22012034818945 — RCC Nala Nirman Main Road Se Society Ki Puliya Tak Jhadoli | New | 0 | 0 | 2024-04-14
GWALIOR / DABRA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1703003032/RC/22012034840125 — C C ROAD NIRMAN BHEEKAM SINGH KE MAKAN SE RAMSWROOP KE MAKAN KI OR | Approved | 103000 | 0 | 2025-01-27
GWALIOR / DABRA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Toilet for Community | Construction of Toilets | 1703003032/RS/22012034636198 — NAVEEN SWACHHTA PARISAR GRAM PANCHAYAT JHADOLI ME SAMUDAYIK SWACHHTAN PARISAR NIRMAN KARY | Ongoing | 61000 | 0 | 2022-03-16
GWALIOR / DABRA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Repair & Maintenance of Fishery Pond for Community | Repair & maint of Pond/ Tank | 1703003032/WC/22012034664040 — CTR KHET TALAB GOPAL S/O GILLU RAM KE KHET PAR JHADOLI | Ongoing | 337715.44 | 0 | 2021-06-09
GWALIOR / DABRA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1703003032/WC/22012034742452 — CTR KHET TALAB RANVEER S/O HARIKISHAN KE KHET PAR | Ongoing | 110516.06 | 0 | 2021-11-03
GWALIOR / DABRA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1703003032/WC/22012034742458 — C T R KHET TALAB LALCHANDRA S/O FODARAM JHADOLI | Ongoing | 110516.06 | 0 | 2021-11-03