## Work List
Exported on: 2026-10-24 19:49:37
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: ADAMPUR(P)
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GWALIOR / BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of minor Canal for Community / Construction of Branch Canal for Community | Construction of Canal | 1703004003/IC/22012034883827 — Water Channel Nirman Penta se Ramras rawat ke khet se man singh jatav ke khet ki or | Ongoing | 701152.89 | 0 | 2024-02-26
GWALIOR / BHITARWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1703004003/IF/22012035008879 — Khet ki med per vrachharopan bhupendra jatav najarpur | Ongoing | 395825.29 | 0 | 2022-09-27
GWALIOR / BHITARWAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1703004003/IF/22012035008883 — Khet ki med per vrachharopan karan singh jatav adampur | Ongoing | 395825.29 | 7200 | 2022-08-30
GWALIOR / BHITARWAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1703004003/IF/22012035091069 — Vrachharopan Khere ke ghat se khiriya ki or najarpur | Ongoing | 431281.07 | 0 | 2023-08-08
GWALIOR / BHITARWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1703004003/IF/22012035239552 — Khet Ki Med Par Plantation Mukesh Rawat Adampur | Ongoing | 173308.58 | 9000 | 2024-08-13
GWALIOR / BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1703004003/IF/22012035456144 — Jal ganga samardhan jgsa 2025 dug wel shaskiya kuya school ke pas adampur | New | 0 | 0 | 2025-04-02
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1703004003/IF/22012035624721 — Maa ki bagiya Jamuna bai/ramesh batham najarpur 1703004003/002/07 | New | 0 | 0 | 2025-08-15
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035624731 — Maa ki bagiya Jamuna bai/ramesh batham najarpur 1703004003/002/07 | New | 0 | 0 | 2025-08-15
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035624736 — Maa ki bagiya Jamuna bai/ramesh batham najarpur 1703004003/002/07 | New | 0 | 0 | 2025-08-15
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035624742 — Maa ki bagiya Jamuna bai/ramesh batham najarpur 1703004003/002/07 | Ongoing | 261748.57 | 7200 | 2025-11-05
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035624891 — Maa ki bagiya geeta bai/amar singh jatav mp03004003249 | Ongoing | 261748.57 | 0 | 2025-11-05
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035624906 — Maa ki bagiya laxmi bai /ramsingh jatav adampur mp03004003119 | New | 0 | 0 | 2025-08-15
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035626272 — Maa ki bagiya Shanti bai jatav /sughar singh adampur mp00300400300261 | Ongoing | 261748.57 | 0 | 2025-11-05
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035626287 — Maa ki bagiya basanti rawat/sultan najarpur mp03004003001265 | Ongoing | 261748.57 | 0 | 2025-11-05
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035626289 — Maa ki bagiya pooja rawat/rajeevnajarpur mp03004003001322 | Ongoing | 261748.57 | 0 | 2025-11-05
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Biodrainage in Fields-Individuals / Bio-drainage Plantation for Individual | Plantation | 1703004003/IF/22012035639130 — Maa ki bagiya shimla rawat/vichitra singh najarpur 1703004003/001/396 | New | 0 | 0 | 2025-08-15
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035639207 — Maa ki bagiya rakhi raje adampur 1703004003/002/08 | Ongoing | 262863.2 | 0 | 2025-11-13
GWALIOR / BHITARWAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1703004003/IF/22012035639223 — Maa ki bagiya simla rawat /vichitra najarpur 1703004003/002/07 | Ongoing | 262863.2 | 0 | 2025-11-13
GWALIOR / BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703004003/IF/IAY/71744 — Construction of IAY House -IAY REG. NO. MP-03-004-003-001/2 | Approved | 27000 | 0 | 2015-06-23
GWALIOR / BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703004003/IF/IAY/71745 — Construction of IAY House -IAY REG. NO. MP-03-004-003-001/79 | Approved | 27000 | 0 | 2015-06-23
GWALIOR / BHITARWAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1703004003/IF/IAY/71746 — Construction of IAY House -IAY REG. NO. MP-03-004-003-002/47 | Approved | 27000 | 0 | 2015-06-23
GWALIOR / BHITARWAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1703004003/RS/22012034682768 — Samudayik Nadep Nirman Baghel Mohalla Adampur | Closed | 41600 | 0 | 2023-01-24
GWALIOR / BHITARWAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1703004003/WC/22012034710170 — Ctr sok pit baghel mohalla head pump adampur | Ongoing | 20874 | 0 | 2021-06-08
GWALIOR / BHITARWAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1703004003/WC/22012035212314 — Talab Nirman Kotwar Ke Khet Ke Neeche Adampur | Approved | 0 | 0 | 2024-06-08
GWALIOR / BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1703004003/WC/22012035293688 — Jal ganga samardhan jgsa 2025 dug wel shaskiya kuya school ke pas adampur | New | 0 | 0 | 2025-04-02
GWALIOR / BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1703004003/WC/22012035294347 — Jal ganga samvardhan abhiyan jgsa 2025 takhat singh ke samne Wala kuya najarpur | New | 0 | 0 | 2025-04-02
GWALIOR / BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1703004003/WC/22012035294600 — Jal ganga samardhan jgsa 2025 dug wel man singh jatat ke liye ke pas najarpur | New | 0 | 0 | 2025-04-02
GWALIOR / BHITARWAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1703004003/WC/22012035295300 — Jal ganga samvardhan abhiyan jgsa 2025 takhat singh ke samne Wala kuya najarpur | New | 0 | 0 | 2025-04-02