## Work List
Exported on: 2026-10-07 04:24:30
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: RUBAHA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Repair & maint of Cattle Shelter for Comm / Repair and maintenance of Cattle Shelter for Community | Repair & Maint of Community infrastructure | 1704001027/AV/22012034467123 — Shantidham Nirman Basaijeev | Closed | 0 | 0 | 2019-06-22
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1704001027/AV/22012034467124 — Shantidham nirman Rubaha | Closed | 283566.25 | 0 | 2019-06-22
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1704001027/AV/22012034467125 — Shantidham nirman Dhorra | Closed | 285409.48 | 0 | 2019-06-22
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704001027/AV/22012034547992 — SAMUDAYIK SHOCHALAY GRAM ROORA | Closed | 0 | 0 | 2020-10-02
DATIA / SEONDHA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1704001027/AV/22012034627233 — BAUNDRIBALL NIRMAN MELA PARISAR RUBAHA | Closed | 0 | 0 | 2022-10-02
DATIA / SEONDHA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/AV/22012034627474 — BAUNDRIBALL NIRMAN MELA PARISAR RUBAHA | Completed | 88000 | 82484 | 2022-12-26 | 2023-09-05
DATIA / SEONDHA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1704001027/AV/22012034643035 — boundry ball nirman karya mela parisar me | Completed | 44000 | 42282 | 2024-04-22 | 2025-12-20
DATIA / SEONDHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1704001027/DP/22012034229687 — नाली निर्माण कार्य | Deleted | 0 | 0 | 2016-01-27
DATIA / SEONDHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1704001027/DP/22012034484779 — नाला निर्माण कार्य आंगनवाडी से शांतिधाम की ओर रूवाहा | Closed | 0 | 0 | 2019-04-14
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034532105 — NALA NIRMAN KARY PRATAP YADAV KE MAKAN SE BDRI BADAI KE MAKAN KI OR | Completed | 98000 | 93798 | 2021-09-13 | 2023-07-10
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Repair & Maint of distributary Canal for Community / Repair and Maintenance of distributary Canal for Community | Repair & Maint of Canal | 1704001027/DP/22012034532710 — NALA NIRMAN KARY AGANBADI SE SHANTIDHAM KI OR | Closed | 528877.22 | 0 | 2021-04-15
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034532711 — AVRODHAK DIVAL NIRMAN SADAK KINARE ROORA | Completed | 946636.12 | 941969.64 | 2021-08-16 | 2023-07-10
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034539252 — NALA NIRMAN KARY UDAYRAJ YADAV KE MAKAN SESITA YADAV KE MAKAN KI OR | Completed | 1142261.29 | 754370.9 | 2021-11-08 | 2023-07-10
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034539253 — NALA NIRMAN KARY RAMRAJA YADAV KE MAKAN SE BARIYA KI OR | Ongoing | 999947.49 | 1158 | 2021-11-08
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034539872 — nala nirman kary udayvir ke makan | Completed | 38000 | 22002 | 2021-12-13 | 2022-08-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034539891 — nali nirman karya rajiv baghel ke makan se ramsingh jamadar ki or | Closed | 24000 | 0 | 2021-08-15
DATIA / SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/DP/22012034578530 — NALA NIRMAN MANGAL YADAV KE MAKAN SE NAHAR KI OR | Completed | 57000 | 56797 | 2023-07-17 | 2024-05-31
DATIA / SEONDHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1704001027/DP/9993630905 — जल निकासी निर्माण शा0मा0वि0से सरनृाम यादव के मकान की ओर | Completed | 193000 | 189968.82 | 2015-11-02 | 2018-08-14
DATIA / SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/1000016940 — BUMISILP VINDRAWAN/NARAYAN NAI | Completed | 25000 | 23798 | 2013-06-10 | 2014-11-15
DATIA / SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/1000050274 — BUMISILP RAMSINGH/SHAYAM JAMADAR | Completed | 22500 | 18688 | 2013-11-11 | 2014-11-10
DATIA / SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001027/IF/22012034353968 — vircharopan hanumanmandir dhorra | Completed | 335000 | 5575 | 2017-06-26 | 2021-01-27
DATIA / SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001027/IF/22012034363705 — Plantation Sadak kinare CC road par Rubaha | Completed | 335000 | 10600 | 2017-08-02 | 2023-05-05
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704001027/IF/22012034369386 — pilantesan bagiya giram roora | Closed | 335000 | 0 | 2019-08-05
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012034548637 — KHET TALAB MULAYAM SINGH / RATTI | Completed | 332572.21 | 261060 | 2020-05-11 | 2021-01-27
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012034548641 — KHET TALAB MOTI BAGHEL | Closed | 332572.21 | 0 | 2020-04-20
DATIA / SEONDHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Biodrainage-Individuals / Bio-drainage Plantation for Individual | Plantation | 1704001027/IF/22012034593331 — Braksharopan Kary khet ki med or Gopal Yadav ke khet pr | Ongoing | 116265.03 | 21660 | 2020-08-17
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012034649957 — KHET TALAB HARVILAS YADAV | Completed | 332962.02 | 268650 | 2021-02-15 | 2021-08-30
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012034666898 — khet talab mangal jatav | Completed | 332962.02 | 247794 | 2021-03-22 | 2021-08-30
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012034666899 — khet talab syamsundar | Completed | 332962.02 | 273234 | 2021-03-22 | 2021-08-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012034754752 — CTR KHET TALAB RAKWSH YADAV | Completed | 337715.44 | 173893 | 2021-06-28 | 2023-05-05
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780752 — CTR MEDBADHAN KARY DWARKAPRASAD/BALADEEN | Completed | 48631.19 | 44004 | 2021-06-14 | 2021-08-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780759 — CTR MEDBADHAN KARY LAXMINARAYAN /KUNDAN | Completed | 29719.13 | 24318 | 2021-06-14 | 2021-08-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780766 — CTR MEDBADHAN KARY RAMRAJA/ALBEL SINGH | Completed | 47730.68 | 41688 | 2021-06-14 | 2021-08-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780778 — CTR MEDBADHAN KARY MAHENDRA /PRATAP | Completed | 45028.87 | 35898 | 2021-06-14 | 2021-08-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780792 — CTR MEDBADHAN KARY HARVILAS /SUGHAR SINGH | Completed | 50432.34 | 40530 | 2021-06-14 | 2022-08-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780796 — CTR MEDBADHAN KARY KITABSINGH/KASHIRAM | Completed | 46830.03 | 34740 | 2021-06-14 | 2021-08-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Upland Bench Terrace for Individual / Construction of Upland Bench Terrace for Individual | Terracing | 1704001027/IF/22012034780805 — CTR MEDBADHAN KARY TULSIRAM/VIJAYRAM | Completed | 46830.03 | 37056 | 2021-06-14 | 2021-08-30
DATIA / SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012035045640 — KHET TALAB NIRMAN BHAGIRATH AHIRVAR KE KHET KE PAR | Closed | 0 | 0 | 2022-10-02
DATIA / SEONDHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1704001027/IF/22012035045643 — KHET TALAB NIRMAN RAMDEEN AHIRVAR KE MAKAN KE PAS | Completed | 360853.32 | 210834 | 2023-04-24 | 2024-05-31
DATIA / SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/22012035406137 — khet talab nirman kary kallu/sure gram badai jeev | Deleted | 0 | 0 | 2025-04-14
DATIA / SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/22012035406218 — khet talab nirman kary kallu/sure gram badai jeev | Deleted | 199457.43 | 261 | 2025-05-02
DATIA / SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/22012035406259 — khet talab nirman kary bhogiram/sure | Physically Completed | 199457.43 | 127629 | 2025-05-02 | 2026-06-10
DATIA / SEONDHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/22012035495074 — khet talab nirman kary fundi/badri gram basaijeev | Completed | 195703.54 | 125019 | 2025-05-15 | 2026-06-08
DATIA / SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704001027/IF/9926700265 — पशु सेड निर्माण कार्य विन्‍द्रावन/नारान नाई | Completed | 84000 | 41313.55 | 2014-02-10 | 2018-08-26
DATIA / SEONDHA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704001027/IF/9926702723 — मेढबंधान कार्य निरंजन सिंह/प्रेमसिंह यादव | Completed | 56000 | 40056 | 2014-02-17 | 2014-11-10
DATIA / SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704001027/IF/9993689946 — नाडेप टांका निर्माण मंगलसिंह जाटव | Completed | 26000 | 18367.53 | 2015-11-23 | 2016-08-09
DATIA / SEONDHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001027/IF/9993699113 — नाडेप टांका निर्माण कार्य भगवानसिंह यादव | Completed | 26000 | 23185 | 2015-12-21 | 2017-01-30
DATIA / SEONDHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704001027/IF/9993699116 — नाडेप टांका निर्माण आज्ञाराम यादव | Completed | 26000 | 22649.85 | 2015-12-21 | 2016-07-01
DATIA / SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704001027/IF/9993718706 — nadep tanka-agyaram/ramsevak | Deleted | 0 | 0 | 2016-01-26
DATIA / SEONDHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1704001027/IF/9993723452 — भूमिशिल्‍प निर्माण कार्य | Deleted | 0 | 0 | 2016-01-26
DATIA / SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/1898895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4244079 | Completed | 15660 | 15486 | 2018-08-06 | 2018-12-12
DATIA / SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/1899916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5416812 | Completed | 15660 | 15660 | 2018-08-06 | 2019-01-05
DATIA / SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/1899994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5119926 | Completed | 15660 | 15486 | 2018-08-06 | 2019-03-01
DATIA / SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/1900003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5124365 | Completed | 15660 | 15660 | 2018-08-13 | 2019-01-05
DATIA / SEONDHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/1904140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5177299 | Completed | 15660 | 14268 | 2018-08-06 | 2019-03-01
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2169858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1785561 | Completed | 15840 | 15086 | 2019-11-25 | 2020-05-07
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2191305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4240384 | Completed | 15840 | 16008 | 2019-11-04 | 2020-05-10
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2338162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5304537 | Completed | 15840 | 15558 | 2019-11-04 | 2020-05-10
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2338163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5351846 | Completed | 15840 | 15924 | 2019-11-04 | 2020-05-10
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2338172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5363375 | Completed | 15840 | 16190 | 2019-11-25 | 2020-05-23
DATIA / SEONDHA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2338205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4321556 | Completed | 15840 | 15734 | 2019-11-04 | 2020-05-10
DATIA / SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2903972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3137105 | Completed | 17100 | 16212 | 2021-05-03 | 2021-11-12
DATIA / SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2903973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3158056 | Completed | 17100 | 16212 | 2021-05-03 | 2021-11-12
DATIA / SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2903985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3689047 | Completed | 17100 | 16212 | 2021-05-03 | 2022-08-02
DATIA / SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2904975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3689556 | Completed | 17100 | 15054 | 2021-05-10 | 2021-11-12
DATIA / SEONDHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/2904976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3711823 | Completed | 17100 | 11580 | 2021-05-10 | 2022-08-02
DATIA / SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/3717311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120908494 | Completed | 18360 | 17952 | 2022-07-18 | 2023-05-02
DATIA / SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/3774761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130378685 | Completed | 18360 | 17748 | 2022-07-18 | 2022-10-17
DATIA / SEONDHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/3864152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146547451 | Completed | 18360 | 17748 | 2022-07-18 | 2022-10-17
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/420660 — Construction of IAY House -IAY REG. NO. MP1331486 | Completed | 15030 | 15498 | 2017-02-13 | 2018-06-23
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4527911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130324303 | Completed | 23490 | 22626 | 2025-01-14 | 2025-07-09
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4527918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130387839 | Completed | 23490 | 20412 | 2025-01-14 | 2025-12-20
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4528897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149780559 | Completed | 23490 | 20628 | 2025-01-21 | 2026-02-14
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4528900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149790704 | Completed | 23490 | 20520 | 2025-01-14 | 2025-07-09
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4528901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149792129 | Completed | 23490 | 22626 | 2025-01-14 | 2025-07-09
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4530052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150426769 | Completed | 23490 | 22104 | 2025-01-14 | 2025-12-20
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/475149 — Construction of IAY House -IAY REG. NO. MP1902351 | Completed | 15030 | 14538 | 2017-02-20 | 2018-07-10
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/477214 — Construction of IAY House -IAY REG. NO. MP1934312 | Completed | 15030 | 15402 | 2017-01-30 | 2018-08-25
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/478046 — Construction of IAY House -IAY REG. NO. MP1948459 | Completed | 15030 | 14720 | 2017-01-30 | 2018-05-08
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4782571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130388449 | Completed | 23490 | 20412 | 2025-01-14 | 2025-06-04
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4782576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130391342 | Completed | 23490 | 20412 | 2025-01-14 | 2026-02-14
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4800239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149788707 | Completed | 23490 | 20520 | 2025-01-14 | 2025-07-09
DATIA / SEONDHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/4869601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150594152 | Completed | 23490 | 20412 | 2025-02-04 | 2025-06-04
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/559293 — Construction of IAY House -IAY REG. NO. MP3633419 | Completed | 15030 | 14496 | 2017-01-30 | 2018-08-01
DATIA / SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/600324 — Construction of IAY House -IAY REG. NO. MP1770167 | Completed | 15030 | 15450 | 2018-02-19 | 2018-08-25
DATIA / SEONDHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/600435 — Construction of IAY House -IAY REG. NO. MP3071066 | Completed | 15030 | 15244 | 2017-06-19 | 2018-06-23
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/72063 — Construction of IAY House -IAY REG. NO. MP-04-001-027-002/1 | Completed | 14310 | 8684 | 2016-06-06 | 2018-07-10
DATIA / SEONDHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704001027/IF/IAY/72064 — Construction of IAY House -IAY REG. NO. MP-04-001-027-004/5 | Completed | 14310 | 8684 | 2016-06-06 | 2018-07-10
DATIA / SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1704001027/LD/22012034232404 — शांति‍धाम शेड निर्माण कार्य रूरा | Completed | 180000 | 134095.85 | 2015-10-12 | 2018-10-06
DATIA / SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001027/LD/22012034310548 — Shanti dham gram rubaha | Deleted | 180000 | 0 | 2017-04-24
DATIA / SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704001027/LD/22012034310736 — Shanti Dham Nirman Basai jeev | Deleted | 180000 | 0 | 2017-04-24
DATIA / SEONDHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1704001027/LD/22012034310769 — Shantidham KaryNirman Dhorra | Deleted | 0 | 0 | 2016-08-15
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001027/PG/22012034305342 — Khel maidan Basaijeev | Deleted | 186600 | 0 | 2016-10-02
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001027/PG/22012034305344 — Khel maidan Rura | Deleted | 186600 | 0 | 2016-10-02
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001027/PG/22012034305349 — Khel maidan Dhorra | Deleted | 186600 | 0 | 2016-10-02
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704001027/PG/22012034305360 — khel maidan Rubaha | Deleted | 186600 | 0 | 2016-10-02
DATIA / SEONDHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/1050 — सीमेन्‍ट कंक्रीट रोड निर्माण कार्य श्‍यामसुन्‍दर यादव के मकान से मंगलसिंह जाटव के मकान की ओर | Completed | 67000 | 54846 | 2012-07-03 | 2012-12-03
DATIA / SEONDHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034198825 — C.C.ROAD NILI NIRMAN KALLU KE MAKAN SE BHAI LAL YA | Completed | 88000 | 68934 | 2014-01-13 | 2014-04-02
DATIA / SEONDHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034203894 — सी0सी0रोड नाली सहित मोहनसिंह यादव के मकान से कन्‍ह | Completed | 41000 | 22747 | 2014-02-10 | 2014-06-29
DATIA / SEONDHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034203895 — सी0सी0रोड नाली सहित माता मंदिर से उदयभान बघेल के म | Completed | 113000 | 63473 | 2014-02-17 | 2016-09-18
DATIA / SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034223589 — सी0सी0रोड नाली निर्माण कार्य मुन्‍शी यादव के मकान | Completed | 40500 | 16485 | 2014-06-30 | 2016-11-10
DATIA / SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034226135 — सी0सी0रोड नाली न‍िर्माण रामचरन धाकड के मकान से अलव | Completed | 44000 | 4396 | 2014-08-04 | 2016-09-18
DATIA / SEONDHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034289774 — सी0सी0रोड सह नाली निर्माण सुरेन्‍द्र यादव पटेल के मकान से तिलक यादव के मकान की ओर बसईजीव | Completed | 133000 | 87662 | 2015-11-23 | 2016-01-29
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001027/RC/22012034306526 — सुदूर सम्‍पर्क रोड नहर से बसईमलक की ओर | Deleted | 1291000 | 0 | 2016-12-26
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034322544 — CC road nali nirman | Closed | 0 | 0 | 2016-10-02
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001027/RC/22012034327896 — SUDUR GRAM SADAK SADAK SADAK YOJNA GRAM RUDI SE HANUMAN JI MANDIR KI OR | Completed | 1463000 | 96237 | 2017-02-21 | 2019-02-07
DATIA / SEONDHA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034330822 — सी0सी0रोड सह नाली निर्माण आंगनवाडी भवन से सुघर सिंह के मकान तक वाया रामजीशरण यादव के मकान तक | Completed | 87000 | 71144 | 2017-03-13 | 2019-02-06
DATIA / SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034360575 — c.croad with drain shyam sundar ke makan se raghuvir singh yadav ke makan baya kamal singh se rakesh | Completed | 84000 | 83936 | 2017-09-18 | 2018-04-01
DATIA / SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034360578 — c.c.road nirman ballu yadav ke makan se sarnam singh yadav ke makan tak | Completed | 39000 | 38872 | 2017-09-18 | 2018-04-04
DATIA / SEONDHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034370069 — cc road | Closed | 0 | 0 | 2017-04-20
DATIA / SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034386546 — सी0सी0रोड सह नाली निर्माण लालसिंह अहिरवार के मकान से श्‍यामलाल के मकान तक | Physically Completed | 51000 | 56376 | 2018-04-09 | 2021-03-25
DATIA / SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034390964 — C C ROAD SAH NALI NIRMAN KARYA BACHCHI BAGHEL KE MAKAN SE MAHENDRA YADAV KE MAKAN KI OR | Completed | 153468 | 153514 | 2018-07-02 | 2021-11-12
DATIA / SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034439310 — c.c.road sah nali narman work | Closed | 0 | 0 | 2019-01-26
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034462822 — सी0सी0रोड सह नाली निर्माण माता मंदिर से राजवीर यादव के मकान की ओर | Completed | 53500 | 46464 | 2019-05-27 | 2019-11-17
DATIA / SEONDHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034462827 — c.c.road with nali dharm singh dhakad ke makan se gopal yadav ke makan ki or | Closed | 53500 | 0 | 2018-08-15
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034466499 — सी0सी0रोड सह नाली निर्माण पातीराम बघेल के मकान से दुर्जन यादव के मकान की ओर | Completed | 46500 | 51744 | 2019-06-03 | 2021-11-12
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034480124 — सी0सी0रोड सह नाली निर्माण तिलक सिंह के मकान से चन्‍दन यादव के मकान तक धोर्रा | Completed | 60000 | 58080 | 2019-10-07 | 2019-11-17
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034481205 — सी0सी0रोड सह नाली निर्माण गुटटी बघेल के मकान से सोवरन बघेल के मकान तक बसईजीव | Completed | 18600 | 19008 | 2019-11-11 | 2019-11-17
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034481207 — सी0सी0रोड सह नाली निर्माण बच्‍ची बघेल के मकान से उदयभान बघेल के मकान की ओर बसईजीव | Completed | 23250 | 23294 | 2019-11-11 | 2020-05-09
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034481324 — सी0सी0रोड सह नाली निर्माण दुर्जन यादव के मकान से नहर के पुल की ओर धोर्रा | Completed | 93000 | 86592 | 2019-10-14 | 2020-05-09
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034481325 — सी0सी0रोड सह नाली निर्माण रामराजा के मकान से शांतिधाम की ओर रूरा | Completed | 139500 | 107712 | 2019-10-14 | 2020-05-09
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034503072 — सी0सी0रोड सह नाली निर्माण माता मंदिर से सुरेन्‍द्र यादव के मकान तक बसईजीव | Completed | 46500 | 45728 | 2019-11-18 | 2020-05-09
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034508276 — सी0सी0रोड सह नाली निर्माण जगदीश यादव के घर से नहर की ओर | Completed | 88000 | 88682 | 2019-12-02 | 2020-05-09
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034512759 — सी0सी0रोड सह नाली निर्माण भोले सेन के मकान से उदयवीर यादव के मकान की ओर धोर्रा | Completed | 46500 | 47560 | 2020-01-06 | 2020-05-09
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034513832 — c.c.road | Closed | 0 | 0 | 2020-01-01
DATIA / SEONDHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034515730 — सी0सी0रोड सह नाली निर्माण तुलाराम अहिरवार के मकान से सुदामा अहिरवार के मकान तक | Completed | 28000 | 28896 | 2020-02-03 | 2020-05-09
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034520868 — सी0सी0रोड सह नाली निर्माण कार्य प्रधानमंत्री रोड से गब्‍बर के कुंआ की ओर | Completed | 14000 | 11400 | 2020-06-08 | 2021-01-27
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034525739 — CC ROAD NIRMAN MATA MANDIR SE SAHIB YADAV KE MAKAN KI OR | Completed | 51000 | 50160 | 2020-06-29 | 2021-01-27
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034525740 — CC ROAD KARY BALBEER KE MAKAN SE CHANDAN KE MAKAN KI OR | Completed | 38000 | 36480 | 2020-06-29 | 2021-01-27
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034525743 — CC ROAD KARY BABLU YADAV KE MAKAN SE PRAMOD KE MAKAN KI OR | Completed | 14000 | 12540 | 2020-06-29 | 2021-01-27
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034536392 — CC road sah nali sahit LAXMINARAYAN KE MAKAN SE RAMMILAN KE MAKAN KI OR | Completed | 51000 | 51300 | 2020-08-31 | 2021-01-27
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704001027/RC/22012034539426 — PAHUCH MARG NAHAR KE PUL SE BALKHANDEWER MANDIR TK | Completed | 1499042.32 | 1286666.46 | 2020-09-21 | 2022-08-02
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034561642 — CC ROAD MUNNA BAGHEL SE RAMJI BAGHEL KE MAKAN KI OR | Completed | 46000 | 44460 | 2021-03-08 | 2021-11-12
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034561643 — CC ROAD JASVANT YADAV KE MAKAN SE BAHADUR YADAV KE MAKAN KI OR | Completed | 27000 | 29640 | 2021-03-08 | 2021-11-12
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034577721 — CC ROAD BABUJI KE MAKAN SE MAGAL YADAV KE MAKAN KI OR | Completed | 51000 | 49794 | 2021-08-09 | 2022-04-13
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034577722 — CC ROAD VIRENDRA KE MAKAN SE PURAN SETH KE MAKAN KI OR | Completed | 46000 | 44004 | 2021-08-09 | 2022-04-13
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034596650 — c.c.road nali nirman kary rakesh yadav se pradhan mantri road tak | Closed | 18000 | 0 | 2021-08-15
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034596658 — c.c.road nali nirman karya pappu yadav ke makan se bhole sen ke makan tak | Completed | 18000 | 17370 | 2021-11-29 | 2022-07-19
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034596664 — c.c.road nirman karya ramji bapu se jagram vanshkar ke makan ki or | Completed | 46000 | 31266 | 2021-11-29 | 2022-07-07
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034600667 — c.c.road sah nali nirman karya khuman ke makan se rajendra yadav ke makan tak | Closed | 32000 | 0 | 2021-10-02
DATIA / SEONDHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034604503 — c.c.road | Closed | 0 | 0 | 2021-10-02
DATIA / SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034641715 — CC ROAD NALI NIRMAN NAHAR KI PULIYA SE RAMESH YADAV KE MAKAN KI OR | Completed | 49000 | 47736 | 2023-07-17 | 2024-05-31
DATIA / SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034649574 — CC ROAD NIRMAN RAMSIYA KE MAKAN SE RAMVEER YADAV KE MAKAN KI OR | Completed | 31000 | 30940 | 2023-09-11 | 2024-05-31
DATIA / SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034649577 — CC ROAD NIRMAN NALI NIRMAN SAHIT SYAMSUNDAR KE MAKAN SE RAJENDRA PATEL KE MAKAN KI OR | Completed | 26000 | 17459 | 2023-09-11 | 2024-05-31
DATIA / SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034649579 — CC ROAD NIRMAN NALI NIRMAN SAHIT RAMJI BABU KE MAKAN SE MUNNALAK KE MAKAN KI OR | Closed | 21000 | 0 | 2023-04-14
DATIA / SEONDHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034652459 — cc road nirman karya ramji babu ke makan se munalal ke makan ke or | Completed | 20000 | 18954 | 2023-09-26 | 2025-12-20
DATIA / SEONDHA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1704001027/RC/22012034818597 — cc road nirman karya bablu yadav ke makan se munna yadav ke makan ke or | Completed | 77000 | 72900 | 2024-06-17 | 2025-12-20
DATIA / SEONDHA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1704001027/RC/22012034823377 — cc road evm nali nirman karya mangal singh jatav ke makan se antram baghel ke makan ki or | Approved | 67000 | 0 | 2024-04-14
DATIA / SEONDHA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1704001027/RC/22012034824521 — सी.सी.रोड सह नाली निर्माण कार्य धौर्रा के पुल से हनुमानजी मंदिर की ओर | Approved | 102000 | 0 | 2024-04-01
DATIA / SEONDHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704001027/RC/943 — पहुंचमार्ग धौर्रा से पश्‍िचम की ओर | Completed | 244000 | 52500 | 2010-10-12 | 2014-11-06
DATIA / SEONDHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704001027/RS/22012034263816 — home sochalay rubaha 1113-15 | Deleted | 10800 | 0 | 2014-08-25
DATIA / SEONDHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1704001027/RS/22012034505873 — सामुदायिक स्वछता परिसर निर्माण रूरा | Completed | 44000 | 42180 | 2021-01-18 | 2021-11-12
DATIA / SEONDHA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1704001027/RS/22012034657434 — samudhyak sochalya nirman karya hauman mandir gram dhorra | Completed | 44000 | 43452 | 2022-05-30 | 2023-05-05
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704001027/WC/22012034572388 — PERCOLATION TANK DHORRA | Completed | 419180.59 | 296400 | 2020-08-10 | 2021-07-30
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034608950 — NALA NIRMAN KARY AGANBADI SE SHNTIDHAM KI OR | Closed | 0 | 0 | 2020-10-02
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1704001027/WC/22012034608952 — NALI NIRMAN JAGMOHAN YADAV KE MAKAN SE SCHOOL KI | Completed | 114500 | 102220 | 2021-01-25 | 2021-07-30
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1704001027/WC/22012034608954 — AVRODHAK DEEVAL phuch Marg pr | Closed | 0 | 0 | 2020-11-30
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644857 — CTR WATER HARVESTING MADHMIK SCHOOL RUBAHA | Closed | 0 | 0 | 2021-04-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644861 — WATER HARVESTING AGANBADI KENDRA RUBAHA | Closed | 0 | 0 | 2021-04-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644866 — WATER HARVESTING PS SCHOOL DHORAA | Closed | 0 | 0 | 2021-04-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644875 — WATER HARVESTING AGANBADI KENDRA DHORRA | Closed | 0 | 0 | 2021-04-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644880 — WATER HARVESTING PS school rura | Completed | 22229.14 | 2316 | 2021-08-09 | 2023-05-06
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644884 — WATER HARVESTING SAMUDAYIK BHAVAN RURA | Completed | 22229.14 | 2316 | 2021-08-09 | 2023-05-06
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644887 — WATER HARVESTING PS SCHOOL BASAI JIV | Closed | 0 | 0 | 2021-04-02
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012034644893 — WATER HARVESTING AGANBADI BASAI JIV | Closed | 0 | 0 | 2021-04-02
DATIA / SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1704001027/WC/22012034903995 — ramraja ke makan se bariya ke or nala nirman | Closed | 0 | 0 | 2022-04-01
DATIA / SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1704001027/WC/22012034903996 — nala nirman karya aganbadi bhawan se shantidham ke or | Closed | 0 | 0 | 2022-04-01
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034907442 — bandvistar evm atirikt karya | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034907443 — bandvistar evm atirikt karya | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034907444 — bandvistar evm atirikt karya | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034907446 — bandvistar evm atirikt karya | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034908140 — bund vistar soundrykaran evm atirikt nirman karya dhorra | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034908141 — bund vistar soundrykaran evm atirikt nirman karya roor | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034908142 — bund vistar soundrykaran evm atirikt nirman karya roora | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704001027/WC/22012034908143 — bund vistar soundrykaran evm atirikt nirman karya basijeev | Closed | 0 | 0 | 2022-01-26
DATIA / SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704001027/WC/22012034999682 — Khet Talab Nirmad Karya Rambhusan ke khet par Rubaha | Closed | 0 | 0 | 2022-08-16
DATIA / SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704001027/WC/22012034999683 — Khet Talab Nirmad Karya Bhogiram ke khet par Basai jeev | Closed | 0 | 0 | 2022-08-16
DATIA / SEONDHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704001027/WC/22012035027203 — कच्चा नाला निर्माण नहर के पुल से मंगल सिंह यादव के खेत की ओर | Closed | 20033.17 | 0 | 2022-10-02
DATIA / SEONDHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704001027/WC/22012035203065 — nala nirman karya bhadur yadav ke makan se sunil yadav ke makan ke or rubaha | Completed | 78000 | 33534 | 2024-07-29 | 2025-12-20
DATIA / SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704001027/WC/22012035282937 — dug well recharge school ke pass rubaha | Completed | 25899.46 | 24011.95 | 2025-05-07 | 2026-03-11
DATIA / SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704001027/WC/22012035282945 — dug well recharge lalta baghel ke makan se pass basai | Completed | 25899.46 | 24011.95 | 2025-05-07 | 2026-03-11
DATIA / SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1704001027/WC/22012035282958 — dug well recharge school ke pass rubaha | Approved | 25899.46 | 0 | 2025-04-14
DATIA / SEONDHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1704001027/WC/22012035284124 — amrit sarobar nirman kary 2 0 village dorra | Ongoing | 1999833.96 | 561 | 2025-05-06
DATIA / SEONDHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1704001027/WC/VB/22012035334902 — roof harvesting kary aganbadi bhavan roora | Approved | 23460.69 | 0 | 2026-08-15
DATIA / SEONDHA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1704001027/WC/VB/YD/22012035335628 — roof harvesting kary aganwadi bhavan roora | Approved | 0 | 0 | 2026-09-22
DATIA / SEONDHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1704001027/WH/19963624 — talab gahrikaran gram rura | Deleted | 48000 | 0 | 2017-06-12
DATIA / SEONDHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1704001027/WH/22012034443208 — TALAB GAHRIKARAN KUBER BABA KE PAS | Completed | 489965.87 | 270180 | 2020-06-15 | 2021-01-27
DATIA / SEONDHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704/RC/22012034154645 — DHOURRA TO DHOURRI | Completed | 1892000 | 416825.9 | 2012-12-03 | 2015-05-18