## Work List
Exported on: 2026-10-05 00:31:41
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: ORINA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DATIA / DATIA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1704002006/AV/22012034566576 — puliya nirman kary kuryai nala par | Completed | 118600 | 118578 | 2021-05-22 | 2022-07-07
DATIA / DATIA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704002006/AV/22012034566720 — chopal narmad kary prathimik vidhalay ke paas | Completed | 12000 | 15054 | 2021-11-05 | 2022-01-24
DATIA / DATIA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704002006/AV/22012034566722 — chopal nirmad kary mandhata ke duyare ke paas | Completed | 20000 | 17370 | 2021-11-05 | 2022-05-22
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1497 — नि‍र्मल वाटि‍का डरू / मौजी अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-21 | 2012-09-21
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1498 — नि‍र्मल वाटि‍का सरू / ग्‍यासी अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-21 | 2012-09-21
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1499 — नि‍र्मल वाटि‍का अशोक / भगोनी अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-25 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1500 — नि‍र्मल वाटि‍का बनमाली / लालू अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 3536.5 | 2012-01-25 | 2012-10-08
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1501 — नि‍र्मल वाटि‍का ग्‍याप्रसाद / मथुरी बुनकर ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-21 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1502 — नि‍र्मल वाटि‍का वालि‍कदास / भग्‍गू कोरी ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-29 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1503 — नि‍र्मल वाटि‍का सुरेश / हरपे अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-09 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1504 — नि‍र्मल वाटि‍का संतोष / नत्‍थू अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-13 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1505 — नि‍र्मल वाटि‍का श्‍यामा / ग्‍यासी अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-13 | 2013-03-20
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1506 — नि‍र्मल वाटि‍का कोमि‍ल / करन्‍जू अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-09 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1507 — नि‍र्मल वाटि‍का कल्‍यान / लालू अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-17 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1508 — नि‍र्मल वाटि‍का श्‍यामलाल / हरूआ बरार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-17 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1509 — नि‍र्मल वाटि‍का मुलाम / बादाम खंगार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-13 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1510 — नि‍र्मल वाटि‍का श्रीलाल / जगन्‍नाथ अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-13 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1511 — नि‍र्मल वाटि‍का भगवानदास / डब्‍बू अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-09 | 2012-08-04
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1512 — नि‍र्मल वाटि‍का खल्‍कू / मदारी अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-09 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1513 — नि‍र्मल वाटि‍का काशीराम / मथुरी बुनकर ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-13 | 2012-09-21
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1514 — नि‍र्मल वाटि‍का रामप्रसाद / भग्‍गू कोरी ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-17 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1515 — नि‍र्मल वाटि‍का मनीराम / धनुआ अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-17 | 2012-09-21
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1516 — नि‍र्मल वाटि‍का प्रेमनारायण / कामता अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-17 | 2012-09-21
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1517 — नि‍र्मल वाटि‍का उमेश / रामचरन अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-09 | 2012-07-10
DATIA / DATIA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1518 — नि‍र्मल वाटि‍का जगराम / धन्‍नू अहि‍रवार ग्राम पंचायत औरीना | Completed | 6000 | 5423.5 | 2012-01-25 | 2012-07-10
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1878 — नि‍र्मल वाटि‍का गजेन्‍द्र / लाल सिंह ग्राम पंचायत | Completed | 6000 | 5492 | 2012-06-11 | 2013-05-20
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1879 — नि‍र्मल वाटि‍का रामकुमार / रामदास ग्राम पंचायत और | Completed | 6000 | 5492 | 2012-06-11 | 2013-05-20
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1880 — नि‍र्मल वाटि‍का श्रीमती कुशमा / प्रताप ग्राम पंचा | Completed | 6000 | 5492 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1881 — नि‍र्मल वाटि‍का मि‍थलेश / राजेन्‍द्र सिंह ग्राम प | Completed | 6000 | 5492 | 2012-06-11 | 2013-05-20
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1883 — नि‍र्मल वाटि‍का नवल / रामस्‍वरूप ग्राम पंचायत औरी | Completed | 6000 | 5499 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1884 — नि‍र्मल वाटि‍का भूरा / लन्‍चू ग्राम पंचायत औरीना | Completed | 6000 | 5499 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1885 — नि‍र्मल वाटि‍का रती / कल्‍यान सिंह ग्राम पंचायत औ | Completed | 6000 | 5386 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1886 — नि‍र्मल वाटि‍का श्रीमती जशोदा / हरकि‍शन ग्राम पंच | Completed | 6000 | 5385 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1889 — नि‍र्मल वाटि‍का माया / अतरसिंह ग्राम पंचायत औरीना | Completed | 6000 | 5385 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1894 — नि‍र्मल वाटि‍का नीमा / रामदास ग्राम पंचायत औरीना | Completed | 6000 | 5385 | 2012-06-11 | 2013-03-28
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/1927 — नि‍र्मल वाटि‍का हरि‍ओम / जगदीश ग्राम पंचायत औरीना | Completed | 6000 | 5630 | 2012-07-30 | 2013-05-20
DATIA / DATIA | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1704002006/DP/797 — उर्जा वन p-105 ओरीना फॉरेस्‍ट | Completed | 445000 | 102495 | 2007-12-15 | 2011-10-15
DATIA / DATIA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704002006/IF/1000069785 — काऊ शेड रमेशचन्द्र /सूरजभान पुजारी ओरीना | Completed | 41000 | 2060 | 2014-02-13 | 2015-07-20
DATIA / DATIA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1704002006/IF/1000069786 — बकरी शेड अजर्ुन / भगवानदास आदिवासी ओरीना | Completed | 32300 | 2060 | 2014-02-13 | 2015-07-20
DATIA / DATIA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704002006/IF/1000069787 — काऊ शेड भूरी वेवा लालाराम कुशवाहा ओरीना | Completed | 41000 | 11202 | 2014-02-13 | 2015-07-20
DATIA / DATIA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704002006/IF/1000069788 — काऊ शेड भूरा / नत्थू अहिरवार ओरीना | Completed | 41000 | 32407 | 2014-02-13 | 2015-07-20
DATIA / DATIA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1704002006/IF/22012034336202 — शौचालय निर्माण धुमनिया /ज्ञाशिराम अहिरवार | Completed | 12000 | 11716 | 2017-04-29 | 2018-05-14
DATIA / DATIA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Soak Pits / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1704002006/IF/22012034336298 — शौचालय निर्माण उषाराजा/ गोविन्द | Completed | 12000 | 2064 | 2017-04-29 | 2020-03-17
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704002006/IF/22012034349365 — बृक्षारोपण कार्य सिद्दबाबा के परिसर मेँ | Completed | 335000 | 125759 | 2017-06-17 | 2022-05-22
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704002006/IF/22012034349373 — बृक्षारोपण कार्य अमरिया की नरिया पर | Completed | 335000 | 30144 | 2017-06-12 | 2020-11-18
DATIA / DATIA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation(Coast) - horti-trees (Individuals) / Along the coast Line Plantation of Horticulture Trees for Individuals | Plantation | 1704002006/IF/22012034592979 — Niji Khet ki Med Per Phalodyan Brajesh/Asharam Pal | Completed | 116265.03 | 72174 | 2020-08-25 | 2026-05-31
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704002006/IF/22012035477217 — Khet talab Nirman kary brajpal singh ke khet per | Completed | 199562.34 | 153729 | 2025-05-09 | 2026-01-02
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704002006/IF/22012035477313 — Khet talab Nirman kary rajdeep singh ke khet per | Completed | 199562.34 | 156861 | 2025-05-09 | 2026-01-02
DATIA / DATIA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704002006/IF/639 — सार्वजनि‍क कूप र्नि‍माण बाघला मोहल्‍ला ग्राम पंचायत औरीना | Completed | 93800 | 3910 | 2008-06-06 | 2008-06-06
DATIA / DATIA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704002006/IF/641 — कपि‍ल धारा कूप पातीराम / लालचन्‍दग्राम पंचायत औरीन | Completed | 121000 | 49332 | 2008-05-24 | 2016-02-05
DATIA / DATIA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704002006/IF/642 — कपि‍ल धारा कूप र्नि‍माण ग्राम पंचायत औरीना | Completed | 93800 | 10445 | 2008-05-24 | 2008-06-04
DATIA / DATIA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704002006/IF/643 — कपि‍ल धारा कूप नि‍मार्ण ग्राम पंचातय औरीना | Completed | 93800 | 13655 | 2008-06-01 | 2008-06-01
DATIA / DATIA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704002006/IF/700 — grever road nirmaan g p orina | Completed | 88100 | 12958 | 2009-02-26 | 2011-12-12
DATIA / DATIA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704002006/IF/9926699902 — काऊ शेड भुलिया वेवा भुनुआ खंगार ओरीना | Completed | 41000 | 30975 | 2014-08-08 | 2015-07-20
DATIA / DATIA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1704002006/IF/9926699929 — बकरी शेड रामराजा / भगुन सिंह परमार ओरीना | Completed | 32300 | 24790 | 2014-06-29 | 2015-07-20
DATIA / DATIA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704002006/IF/9926714005 — Cattle shed ramssuroop / Gyasi Ahirwar | Completed | 41000 | 30190 | 2014-08-08 | 2015-07-20
DATIA / DATIA | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1704002006/IF/9926714362 — Goat Shed Ater singh / Daru Ahirwar | Completed | 32300 | 5652 | 2014-08-08 | 2015-07-20
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1583482 — Construction of IAY House -IAY REG. NO. MP1137185 | Completed | 15480 | 14964 | 2018-07-14 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1583802 — Construction of IAY House -IAY REG. NO. MP2343317 | Completed | 15480 | 14964 | 2018-07-07 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1583803 — Construction of IAY House -IAY REG. NO. MP2343321 | Completed | 15480 | 14964 | 2018-07-21 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1583832 — Construction of IAY House -IAY REG. NO. MP2385248 | Completed | 15480 | 14964 | 2018-07-14 | 2018-09-25
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1583894 — Construction of IAY House -IAY REG. NO. MP2526375 | Completed | 15480 | 14964 | 2018-07-21 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1598799 — Construction of IAY House -IAY REG. NO. MP2413258 | Completed | 15660 | 14964 | 2018-07-21 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1599337 — Construction of IAY House -IAY REG. NO. MP2383693 | Completed | 15660 | 16356 | 2018-07-07 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1599651 — Construction of IAY House -IAY REG. NO. MP2486248 | Completed | 15660 | 14616 | 2018-07-21 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1600719 — Construction of IAY House -IAY REG. NO. MP2527164 | Completed | 15660 | 14964 | 2018-07-07 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1608851 — Construction of IAY House -IAY REG. NO. MP2414857 | Completed | 15660 | 14964 | 2018-08-04 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1608854 — Construction of IAY House -IAY REG. NO. MP2415646 | Completed | 15660 | 14616 | 2018-07-28 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1612089 — Construction of IAY House -IAY REG. NO. MP2945937 | Completed | 15660 | 14964 | 2018-07-07 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1654202 — Construction of IAY House -IAY REG. NO. MP3692617 | Completed | 15660 | 14616 | 2018-07-21 | 2018-11-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1656042 — Construction of IAY House -IAY REG. NO. MP3752723 | Completed | 15660 | 14616 | 2018-07-14 | 2018-10-08
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1656406 — Construction of IAY House -IAY REG. NO. MP3765915 | Completed | 15660 | 14964 | 2018-07-07 | 2018-10-08
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1829855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2410541 | Completed | 15660 | 14478 | 2018-07-28 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1834632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2287881 | Completed | 15660 | 14964 | 2018-07-28 | 2018-09-25
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1834705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2369190 | Completed | 15660 | 14616 | 2018-08-04 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1834706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2372189 | Completed | 15660 | 14616 | 2018-07-28 | 2018-10-21
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1834790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2526155 | Completed | 15660 | 14616 | 2018-07-28 | 2018-09-22
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1834793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2536753 | Completed | 15660 | 14964 | 2018-07-28 | 2018-09-29
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1834863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2617734 | Completed | 15660 | 14616 | 2018-07-28 | 2018-10-24
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1835621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3694925 | Completed | 15660 | 14964 | 2018-07-28 | 2018-11-11
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1849849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2343281 | Completed | 15660 | 15660 | 2018-09-01 | 2018-10-24
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1871416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4589933 | Completed | 15660 | 14616 | 2018-08-18 | 2018-10-08
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1871925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5015647 | Completed | 15660 | 14616 | 2018-09-01 | 2018-11-11
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1872391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5444249 | Completed | 15660 | 14616 | 2018-08-18 | 2018-10-24
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1888912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4687516 | Completed | 15660 | 14964 | 2018-09-01 | 2018-11-11
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1891077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2415133 | Completed | 15660 | 14616 | 2018-09-01 | 2018-11-11
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1904868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4626754 | Completed | 15660 | 14616 | 2018-09-15 | 2018-11-11
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1921635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2963724 | Completed | 15660 | 14616 | 2018-09-01 | 2018-11-11
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1933960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4661587 | Completed | 15660 | 15312 | 2018-09-08 | 2018-10-30
DATIA / DATIA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/1934142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5309248 | Completed | 15660 | 14616 | 2018-09-08 | 2018-11-11
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2107502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4285256 | Completed | 15840 | 14608 | 2019-09-24 | 2020-03-17
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2120704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4560849 | Completed | 15840 | 14784 | 2019-11-09 | 2020-03-17
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/214996 — Construction of IAY House -IAY REG. NO. MP1134774 | Completed | 15030 | 15046 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2157644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5452341 | Completed | 15840 | 14784 | 2019-09-14 | 2020-03-17
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/216186 — Construction of IAY House -IAY REG. NO. MP1151001 | Completed | 15030 | 15360 | 2017-02-11 | 2018-04-25
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2238240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5098096 | Completed | 15840 | 14608 | 2019-09-24 | 2020-03-17
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2238798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5464855 | Completed | 15840 | 14784 | 2019-09-24 | 2020-03-17
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2238919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2558973 | Completed | 15840 | 14784 | 2019-09-24 | 2020-03-17
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2238920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3751425 | Completed | 15840 | 14608 | 2019-09-24 | 2020-03-17
DATIA / DATIA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/2238924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2577115 | Completed | 15840 | 14608 | 2019-09-24 | 2020-03-17
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/223942 — Construction of IAY House -IAY REG. NO. MP1134824 | Completed | 15030 | 15068 | 2017-02-11 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/223944 — Construction of IAY House -IAY REG. NO. MP1134830 | Completed | 15030 | 14986 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/223946 — Construction of IAY House -IAY REG. NO. MP1134836 | Completed | 15030 | 14298 | 2017-02-11 | 2018-01-06
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/223997 — Construction of IAY House -IAY REG. NO. MP1137383 | Completed | 15030 | 15008 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/224001 — Construction of IAY House -IAY REG. NO. MP1137687 | Completed | 15030 | 15360 | 2017-02-11 | 2018-03-01
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/224043 — Construction of IAY House -IAY REG. NO. MP1139964 | Completed | 15030 | 14874 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/225402 — Construction of IAY House -IAY REG. NO. MP1205547 | Completed | 15030 | 15098 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/230133 — Construction of IAY House -IAY REG. NO. MP1307621 | Completed | 15030 | 15008 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/234914 — Construction of IAY House -IAY REG. NO. MP1403345 | Completed | 15030 | 15046 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/258817 — Construction of IAY House -IAY REG. NO. MP2251743 | Completed | 15030 | 15076 | 2017-02-18 | 2018-01-29
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/258879 — Construction of IAY House -IAY REG. NO. MP2257399 | Completed | 15030 | 14358 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/259127 — Construction of IAY House -IAY REG. NO. MP2280129 | Completed | 15030 | 14866 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/259144 — Construction of IAY House -IAY REG. NO. MP2282588 | Completed | 15030 | 15128 | 2017-02-18 | 2018-01-06
DATIA / DATIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/3074146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2386624 | Completed | 17370 | 16984 | 2021-06-28 | 2022-12-01
DATIA / DATIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/3087959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3828384 | Completed | 17370 | 15440 | 2021-06-18 | 2022-12-01
DATIA / DATIA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/3120406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2387211 | Completed | 17370 | 15440 | 2021-06-18 | 2022-12-01
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/353142 — Construction of IAY House -IAY REG. NO. MP1134786 | Completed | 15030 | 15046 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/361306 — Construction of IAY House -IAY REG. NO. MP1150947 | Completed | 15030 | 15076 | 2017-02-18 | 2018-02-15
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/410297 — Construction of IAY House -IAY REG. NO. MP1264003 | Completed | 15030 | 15046 | 2017-02-25 | 2018-02-15
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/410619 — Construction of IAY House -IAY REG. NO. MP1267210 | Completed | 15030 | 14799 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/413922 — Construction of IAY House -IAY REG. NO. MP1137693 | Completed | 15030 | 15270 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/436038 — Construction of IAY House -IAY REG. NO. MP1437423 | Completed | 15030 | 14358 | 2017-02-25 | 2018-01-06
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152028173 | Completed | 23490 | 21717 | 2024-09-17 | 2026-03-07
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017003 | Completed | 23490 | 21861 | 2024-09-13 | 2026-03-07
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017068 | Completed | 23490 | 21384 | 2024-09-13 | 2026-02-24
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017226 | Completed | 23490 | 22122 | 2024-09-13 | 2026-03-22
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017280 | Completed | 23490 | 22077 | 2024-09-13 | 2026-03-22
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017282 | Completed | 23490 | 21942 | 2024-09-10 | 2026-02-24
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4507748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017464 | Completed | 23490 | 21384 | 2024-09-10 | 2026-03-07
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4514441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152017530 | Completed | 23490 | 21681 | 2024-09-17 | 2026-03-22
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/4803680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146247152 | Completed | 23490 | 21933 | 2024-11-09 | 2026-03-22
DATIA / DATIA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/48417 — Construction of IAY House -IAY REG. NO. MP-04-002-006-001/26 | Completed | 14310 | 13861 | 2015-12-18 | 2016-12-30
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/498882 — Construction of IAY House -IAY REG. NO. MP2239318 | Completed | 15030 | 15090 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/500022 — Construction of IAY House -IAY REG. NO. MP2251734 | Completed | 15030 | 15098 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/500958 — Construction of IAY House -IAY REG. NO. MP2264028 | Completed | 15030 | 14358 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/502274 — Construction of IAY House -IAY REG. NO. MP2282169 | Completed | 15030 | 14874 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/50853 — Construction of IAY House -IAY REG. NO. MP-04-002-006-001/67 | Completed | 14310 | 13861 | 2015-12-18 | 2016-12-30
DATIA / DATIA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5106090 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150105664 | Completed | 23490 | 23382 | 2025-03-25 | 2026-03-07
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5249845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150105723 | Completed | 23490 | 21924 | 2025-07-25 | 2026-03-07
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5265848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150065616 | Completed | 23490 | 21924 | 2025-07-25 | 2026-03-07
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5267199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144639718 | Completed | 23490 | 21924 | 2025-10-09 | 2026-03-07
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5286826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150105818 | Completed | 23490 | 21924 | 2025-07-25 | 2026-03-07
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5333566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150065583 | Completed | 23490 | 21924 | 2025-07-25 | 2026-03-07
DATIA / DATIA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/5610957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152090447 | Completed | 23490 | 21924 | 2025-10-09 | 2026-03-07
DATIA / DATIA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/586063 — Construction of IAY House -IAY REG. NO. MP2287962 | Completed | 15030 | 14388 | 2017-02-25 | 2017-12-10
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/857948 — Construction of IAY House -IAY REG. NO. MP1587064 | Completed | 15480 | 14964 | 2017-10-28 | 2018-01-06
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/871264 — Construction of IAY House -IAY REG. NO. MP1751357 | Completed | 15480 | 15136 | 2017-10-28 | 2018-01-06
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/919585 — Construction of IAY House -IAY REG. NO. MP2414341 | Completed | 15480 | 14448 | 2017-07-29 | 2017-12-10
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/923534 — Construction of IAY House -IAY REG. NO. MP2471000 | Completed | 15480 | 14448 | 2017-07-29 | 2017-12-10
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/923546 — Construction of IAY House -IAY REG. NO. MP2471238 | Completed | 15480 | 14964 | 2017-09-16 | 2017-12-10
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/927646 — Construction of IAY House -IAY REG. NO. MP2559606 | Completed | 15480 | 14792 | 2017-10-14 | 2018-01-06
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/929321 — Construction of IAY House -IAY REG. NO. MP2596851 | Completed | 15480 | 14964 | 2017-09-16 | 2017-12-10
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704002006/IF/IAY/929972 — Construction of IAY House -IAY REG. NO. MP2609534 | Completed | 15480 | 14964 | 2017-10-07 | 2017-12-10
DATIA / DATIA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704002006/LD/22012034299569 — खेल मैदान निर्माण औरीना | Completed | 320000 | 315394.5 | 2017-03-18 | 2019-08-30
DATIA / DATIA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704002006/LD/22012034299576 — शांतिधाम निर्माण औरीना | Completed | 245000 | 239569 | 2017-03-11 | 2018-05-20
DATIA / DATIA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704002006/LD/3799382506 — शांति‍धाम र्नि‍माण औरीना | Completed | 499000 | 52406 | 2012-07-18 | 2015-05-15
DATIA / DATIA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704002006/RC/120 — graver road nirmand choutelal ke baghiya to dada tak | Completed | 7000 | 34603 | 2009-02-18 | 2009-02-17
DATIA / DATIA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/132 — ग्रेवर रोड औरीना से वडगोर पहुज मार्ग | Completed | 405000 | 129251 | 2008-01-06 | 2015-02-08
DATIA / DATIA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034177807 — सी सी रोड एवं नाली मोहन के घर से पाण्‍डे के घर की | Completed | 120000 | 110957.82 | 2013-09-17 | 2015-01-11
DATIA / DATIA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034184544 — सी सी रोड् नि‍र्माण हरी अहि‍रवार के घर से माता मंद | Completed | 91223 | 69104 | 2013-10-01 | 2015-02-08
DATIA / DATIA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/22012034208700 — Barar ki Nariya se lodi ghat ki oer. | Completed | 1445000 | 58404 | 2014-03-05 | 2016-03-12
DATIA / DATIA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/22012034211473 — G.S.B. Road Lkuryai Nella se Sirman Aadiwasi ke dera ki ore | Completed | 1407000 | 221369 | 2014-03-05 | 2016-09-24
DATIA / DATIA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/22012034211575 — G.S.B. Road Phool Singh ke Gate se Gram Seida ki o | Completed | 1393000 | 258008 | 2014-03-05 | 2016-09-24
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Kharanja (Brick/Stone) / Construction of Kharanja (brick/stone) Roads for Community | Construction of Road and Culvert | 1704002006/RC/22012034283598 — Rapta Nirman Orina Se Sahida Marg Par Mar ki nariya | Completed | 391000 | 353131.8 | 2015-09-29 | 2017-03-30
DATIA / DATIA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/22012034319122 — sudur sadak nirman bundela mandir orina se khati baba mandir ki or | Completed | 1191000 | 111456 | 2016-12-31 | 2017-12-10
DATIA / DATIA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034324115 — सीसी रोड एवं नाली निर्माण विशुनलाल चिड़ार गड़रियाना मोहल्ला की ओर | Completed | 55692 | 55368 | 2017-02-18 | 2017-12-10
DATIA / DATIA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/22012034331718 — सुदूर सड़क निर्माण सरमन डेरा से मोहन बाबा की ओर | Completed | 1192000 | 710411.1 | 2017-03-18 | 2020-05-12
DATIA / DATIA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034447829 — Cc road avm nali nirman Maandhata ki athayi se patwa ke handpump ki or | Completed | 43200 | 38916 | 2019-03-02 | 2019-08-30
DATIA / DATIA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034447830 — Cc road avm nali nirman Ramcharan ke makan se kashiram aadiwasi ke makan tak | Completed | 81400 | 80888 | 2019-03-02 | 2020-01-04
DATIA / DATIA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034447831 — Cc road avm nali nirman Hudda se vinod choudhri ke makan ki or | Completed | 51300 | 48376 | 2019-03-02 | 2019-08-30
DATIA / DATIA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034447832 — Cc road avm nali nirman mohan chidar ke makan se Ater singh kushwaha ke makan ki or | Completed | 58000 | 57000 | 2019-03-02 | 2020-03-17
DATIA / DATIA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034507569 — सीसी रोड एवं नाली निर्माण राजेन्‍द्र राजपुत के मकान से सुनारी मार्ग घटिया की ओर | Completed | 112000 | 111600 | 2019-12-21 | 2020-06-08
DATIA / DATIA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034528950 — Cc road avm nali nirman Bagla Muhalla ke handpump se Kashiram Pal ke Beda tak | Completed | 58000 | 58140 | 2020-07-20 | 2020-10-27
DATIA / DATIA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034540932 — cc Road avm nali nirman maandaha ki athai se darji ke makan se hote huy munna dubey ki makan ki aur | Completed | 70000 | 72960 | 2020-09-24 | 2021-01-20
DATIA / DATIA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034626294 — cc road avm nali nirman devlal ke makan se mata mandir ki aur + 15 vit | Completed | 72500 | 69139 | 2023-07-02 | 2025-01-15
DATIA / DATIA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034637622 — सीसी सह नाली निर्माण रामकिशोर कुशवाह के मकान से प्रेमी अहिरवार के मकान की ओर +15 वित्त | Completed | 87500 | 78234 | 2023-06-28 | 2025-01-15
DATIA / DATIA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/22012034821351 — cc road avm nali nirman raghvendar parmar ke makan se shivnarayan dubey ke makan ki aur | Completed | 76500 | 74889 | 2024-08-22 | 2026-03-07
DATIA / DATIA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/51110 — सीमेन्‍ट कंक्रीट रोड एवं नाली मुख्‍य मार्ग से रूपस | Completed | 143200 | 85230 | 2012-09-23 | 2012-10-08
DATIA / DATIA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/630 — grever road nirmaan chote lal ki bhagia se danda tak g p orina | Completed | 88100 | 84445 | 2008-09-27 | 2008-07-22
DATIA / DATIA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/638 — ग्रेवर रोड र्नि‍माण औरीना से बगडोर मार्ग ग्राम पंचायत औरीना | Completed | 93800 | 64376 | 2008-04-03 | 2008-04-03
DATIA / DATIA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704002006/RC/714 — ग्रेवल रोड निर्माण बीजा सेन से रायपहाडी ग्राम पंचा | Completed | 88100 | 10248 | 2011-01-04 | 2013-02-25
DATIA / DATIA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704002006/RC/904 — pahuch maarg orina se mohan baba g p orina | Completed | 351000 | 169417 | 2009-03-06 | 2014-12-20
DATIA / DATIA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704002006/RS/22012034262038 — maryadha abhian orina(mahendra singh/narayansingh) | Completed | 5400 | 3835 | 2014-10-01 | 2015-05-26
DATIA / DATIA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704002006/RS/22012034262150 — maryda abhiyan orina(ravraja/bhagun singh) | Completed | 5400 | 3835 | 2014-10-01 | 2015-07-16
DATIA / DATIA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704002006/RS/22012034270974 — maryada abhiyan orina(rajendra singh/gyan sigh) | Completed | 5400 | 3835 | 2014-10-01 | 2015-07-16
DATIA / DATIA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704002006/RS/22012034271913 — maryada abhiyan orina(ganeshsingh/pratipalsingh) | Completed | 5400 | 3835 | 2014-10-12 | 2015-07-16
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292844 — shochalay nirman latori/ghashi adivasi | Completed | 12000 | 11945 | 2016-01-06 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292846 — shochalay nirman shreelal/jagnnath ahirbar | Completed | 12000 | 11929 | 2016-01-06 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292858 — sochalay nirman chandansingh/bad am parihar | Completed | 12000 | 11929 | 2016-01-06 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292862 — shochalay nirman kishori/bharoshi | Completed | 12000 | 11611 | 2016-01-20 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292866 — shochalay nirman mulam/badam parihar | Completed | 12000 | 11929 | 2016-01-06 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292870 — shochalay nirman ashok/kishori Chinar | Completed | 12000 | 11929 | 2016-01-13 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292874 — shochalay nirman asharam/dhanju ahirbar | Completed | 12000 | 11929 | 2016-01-13 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034292879 — shochalay nirman atarsingh/michchu chinar | Completed | 12000 | 11929 | 2016-01-13 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293004 — shochalay nirman aayodeya/Nandan darji | Completed | 12000 | 11929 | 2016-01-13 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293006 — shochalay nirman badam/pannalal chiran | Completed | 12000 | 11929 | 2016-01-13 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293010 — shochalay nirman balikdash/bhangu kori | Completed | 12000 | 11929 | 2016-01-20 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293032 — shochalay nirman balram/lalchandra kori | Completed | 12000 | 11929 | 2016-01-20 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293033 — shochalay nirman banmali/shabdal ahirbar | Completed | 12000 | 11929 | 2016-01-20 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293225 — shochalay nirman bhagvandas/ Sarman ahirbar | Completed | 12000 | 11929 | 2016-01-20 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293226 — shochalay nirman bhagvandas/ bhajanlal ahirbar | Completed | 12000 | 11929 | 2016-02-01 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293309 — sochalay nirman bhura/lanchu kory | Completed | 12000 | 11929 | 2016-02-01 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293310 — sochalay nirman brajmohan/harcharan chinar | Completed | 12000 | 11929 | 2016-02-01 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293311 — sochalay nirman damodar/harcharan ahirbar | Completed | 12000 | 11921 | 2016-02-01 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293312 — sochalay nirman dharmendra/shayamlal banshkar | Completed | 12000 | 11945 | 2016-03-22 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293313 — sochalay nirman sunil/Parma bankar | Completed | 12000 | 11929 | 2016-03-22 | 2016-12-30
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293314 — sochalay nirman ramprasad/bhaggu kory | Completed | 12000 | 11929 | 2016-03-22 | 2017-01-01
DATIA / DATIA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034293315 — sochalay nirman hardyal/ramgopal ahirbar | Completed | 12000 | 11961 | 2016-03-22 | 2016-12-30
DATIA / DATIA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704002006/RS/22012034373533 — Sochalay nirman premnarayan/ babulal chidar | Completed | 12000 | 11716 | 2017-09-29 | 2018-05-14
DATIA / DATIA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1704002006/WC/22012034323592 — नट बारे हार की नारिया पर स्टाप डेम निर्माण | Completed | 100000 | 74304 | 2017-05-13 | 2019-01-07
DATIA / DATIA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704002006/WC/22012034330976 — farm pond sanat pujari ke khet ke pass | Completed | 202600 | 175896 | 2017-08-05 | 2019-01-08
DATIA / DATIA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704002006/WC/22012034395438 — Earthen check dem Nirman Siddh baba mandir ke pass Orina | Completed | 216000 | 117432 | 2018-12-29 | 2019-08-30
DATIA / DATIA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704002006/WC/22012034447743 — RMS Nirman sarman dera ki nariya per Ramcharan ke khet ke pass orina | Completed | 947000 | 939803.11 | 2019-11-27 | 2021-07-15
DATIA / DATIA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704002006/WC/22012034466759 — Earthen check dem Nirman Mohan baba naala per Gabdu ki bandiya ke neeche orina | Completed | 499000 | 308988 | 2019-06-15 | 2020-07-31
DATIA / DATIA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1704002006/WC/22012034466760 — Earthem Check dem nirman Barar bale nala per thuli bali jhadiya ke pas orina | Completed | 517000 | 264720 | 2019-06-15 | 2020-07-31
DATIA / DATIA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1704002006/WC/22012034597941 — पोखर निर्माण कार्य लटोरी आदिवासी के खेत के पास औरीना | Completed | 182012.81 | 142690 | 2020-12-14 | 2022-05-22
DATIA / DATIA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1704002006/WC/22012034597942 — पोखर निर्माण कार्य जगदीश आदिवासी के खेत के पास औरीना | Completed | 180602.12 | 140220 | 2020-12-14 | 2022-05-22
DATIA / DATIA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704002006/WC/22012034639261 — CTR पोखर निर्माण कार्य हल्के आदिवासी की डाडी के पास। | Completed | 337715.44 | 257790 | 2021-04-17 | 2022-07-07
DATIA / DATIA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704002006/WC/22012034639265 — CTR पोखर निर्माण कार्य सुरेन्द्र आदिवासी की डाडी के पास। | Completed | 337715.44 | 250128 | 2021-04-17 | 2022-07-07
DATIA / DATIA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704002006/WC/22012034639267 — CTR पोखर निर्माण कार्य सरमन डेरा के नीचे। | Completed | 337715.44 | 267498 | 2021-04-17 | 2022-07-07
DATIA / DATIA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704002006/WC/22012034639274 — CTR पोखर निर्माण कार्य विजय राम पाल की डाडी के पासे। | Completed | 337715.44 | 251828 | 2021-04-24 | 2022-07-07
DATIA / DATIA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704002006/WC/22012034639276 — CTR पोखर निर्माण कार्य जगन्नाथ चिडार के खेत के पास । | Completed | 337715.44 | 252804 | 2021-04-24 | 2022-07-07
DATIA / DATIA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1704002006/WC/22012034942463 — नवीन तालाब निर्माण ओरिना | Completed | 905572.92 | 765107 | 2022-04-25 | 2025-01-15
DATIA / DATIA | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1704002006/WC/22012035017806 — नाली निर्माण अतर सिंह कुशवाह के मकान से पठार की ओर 15 vit | Completed | 102000 | 102000 | 2022-12-01 | 2023-05-09
DATIA / DATIA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704002006/WC/22012035030653 — परकोलेशन टेंक निर्माण कार्य खेल मैदान के पास ग्राम ओरिना मे | Completed | 360853.32 | 273942 | 2023-09-04 | 2025-08-02
DATIA / DATIA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704002006/WC/22012035030654 — परकोलेशन टेंक निर्माण कार्य दीपक की दाडी के पास ग्राम ओरिना मे | Completed | 360853.32 | 198235 | 2023-09-04 | 2025-07-29
DATIA / DATIA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704002006/WC/22012035070895 — परकुलेशन टेंक निर्माण देवलाल के खेत के पास | Completed | 397435.62 | 284079 | 2023-09-30 | 2025-08-02
DATIA / DATIA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704002006/WC/22012035109869 — percolation tank nirman kary rajendra chohan ki dadi ke pass gp orina | Completed | 489864.85 | 257070 | 2023-09-30 | 2026-03-01
DATIA / DATIA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704002006/WC/640 — सार्वजनि‍क कूप र्नि‍माण स्‍कूल के पास ग्राम पंचायत औरीना | Completed | 93800 | 10370 | 2008-05-21 | 2008-05-21