## Work List
Exported on: 2026-10-20 00:13:35
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: CHANDNI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1704003012/AV/22012034368299 — shantidham nirman gram kurgaon | Completed | 180000 | 175509.56 | 2017-09-13 | 2018-07-15
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034391150 — Samudayik Bhavan nirman Kurganv | Completed | 129000 | 128850 | 2018-10-11 | 2020-02-18
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034578448 — Maa ki bagiya Nirman New Madhmik shala | Closed | 0 | 0 | 2021-05-28
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034578494 — Maa ki bagiya Nirman New Madhyamik shala Chandni | Ongoing | 16000 | 13332 | 2021-07-08
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034588685 — Dining Hall Nirman Kary Shaskiye Madhyamik vidhyalay Chandni | Closed | 24818.26 | 0 | 2021-08-10
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034588686 — Dining Hall Nirman Kary Shaskiye Prathmik vidhyalay Kurgaon Gp Chandni | Closed | 24818.26 | 0 | 2021-08-10
DATIA / BHANDER | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1704003012/AV/22012034640127 — Baundarywall avam saundarykaran nirman kary-shantidham parisar jurgaon | Completed | 88000 | 86264.95 | 2024-07-22 | 2025-07-17
DATIA / BHANDER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704003012/DP/22012034240115 — Braksharopan kary sarvjanik sthan school parisar chandni | Completed | 335000 | 110516 | 2017-05-10 | 2019-03-05
DATIA / BHANDER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1704003012/DP/22012034587025 — Amrit vatika plantataion work -gp chandni | Closed | 55847.4 | 0 | 2023-04-14
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1704003012/FP/22012034364886 — Jal nikasi Nala nirman Magan Lal ke makan se Gajju Kori ke makan ki oar Chandni | Closed | 0 | 0 | 2020-04-14
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1704003012/FP/22012034365083 — Jal nikashi Nala nirman Chandan singh ke makan ke samne se Ashok Kori ke makan ki oar Chandini | Ongoing | 487460.75 | 413382 | 2020-09-15
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1704003012/FP/22012034367513 — 15वित्त$मनरेगा जल निकासी नाला निर्माण चन्दन के मकान से अर्जून पाल के मकान की ओर चांदनी | Completed | 8200 | 7980 | 2020-09-29 | 2020-12-10
DATIA / BHANDER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704003012/IF/1000062241 — Cattleshed Arvindra/Parsuram dohre | Completed | 80000 | 73956 | 2014-01-08 | 2016-08-09
DATIA / BHANDER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704003012/IF/1000062245 — Cattle shed Shyamlal / Chhadami dohre | Completed | 80000 | 74676 | 2014-01-08 | 2016-08-09
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/22012034306307 — Varmik compost Nirman Balmukund /Channi shakya | Completed | 13000 | 11975 | 2016-12-07 | 2017-12-01
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/22012034306309 — Vermi compost Nirman Udaybhan /channi shakya | Completed | 13000 | 11975 | 2016-12-07 | 2017-12-01
DATIA / BHANDER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034306310 — Vermi compost Nirman Harkishan/Chhagge kori | Completed | 13000 | 11975 | 2016-12-07 | 2017-12-08
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/22012034308056 — Varmik compost Nirman Rameshwer/gyadeen shakya | Deleted | 13000 | 0 | 2016-12-21
DATIA / BHANDER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034308065 — varmik compost nirman ashok kumar/makundi kori | Completed | 13000 | 9195 | 2016-12-21 | 2018-05-05
DATIA / BHANDER | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Vermi Composting / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034308066 — Varmik compost Nirman Asharam/Parshuram jatav | Deleted | 13000 | 0 | 2016-12-21
DATIA / BHANDER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704003012/IF/22012034345213 — Braksharopan kary Road side chandni se kurgaon road per | Completed | 335000 | 23880 | 2017-06-18 | 2019-01-04
DATIA / BHANDER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704003012/IF/22012034348809 — Braksharopan kary road side pradhanmantri road chandni se sohan kee or | Completed | 335000 | 23880 | 2017-06-28 | 2018-12-06
DATIA / BHANDER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1704003012/IF/22012034348866 — Braksharopan kary gram kurgaon mai talab par | Completed | 335000 | 23880 | 2017-06-28 | 2018-12-06
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012034423163 — Khet Talav Vimlesh Kumar Sharma Chandni | Closed | 91000 | 0 | 2018-07-18
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1704003012/IF/22012034436419 — Braksharopan kary khet ki med per Brahmadeen/gyadeen savita | Completed | 188000 | 72861 | 2018-10-04 | 2026-02-07
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034437036 — Nadep Compost Mangali Prajapati/Ramdeen Chandini | Closed | 14500 | 0 | 2018-04-14
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034437045 — Nadep Compost Chhotelal Prajapati/Ramdeen Chandni | Closed | 14500 | 0 | 2018-04-14
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034437052 — Nadep Compost Gopal Kori/Gyadeen Chandini | Completed | 14500 | 14404 | 2018-12-12 | 2020-01-15
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034437093 — Nadep Compost Siyasharan Dohare/Ramdas Chandni | Closed | 14500 | 0 | 2018-04-14
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/22012034437094 — Nadep Compost Atar singh Dohare/Sujan Chandni | Closed | 14500 | 0 | 2018-04-14
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012034438864 — Khet talav Pista Kori w/o Dev Prasad Chandni | Completed | 288000 | 199116 | 2018-10-04 | 2020-09-16
DATIA / BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012034549747 — Khet talav nirman Govind Singh Dohare S/O Shri Tularam Dohare Chandini | Completed | 332572.21 | 212040 | 2020-05-03 | 2020-10-01
DATIA / BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1704003012/IF/22012034590789 — Nandan phlodhan kayre Ramprasad parihar / Sopat Parihar Chandni | Closed | 139176.18 | 0 | 2020-08-09
DATIA / BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1704003012/IF/22012034590805 — Nandan phlodhan kayre Jasmant Dohare / Narayan Dohare Chandni | Ongoing | 139176.18 | 10900 | 2020-08-13
DATIA / BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1704003012/IF/22012034590806 — Nandan phlodhan kayre Sirovan Dohare / Narayan Dohare Chadani | Closed | 139176.18 | 0 | 2020-07-05
DATIA / BHANDER | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1704003012/IF/22012034590807 — Nandan phlodhan kayre Chatursingh Dohare / Narayan Dohare Chandni | Ongoing | 139176.18 | 12980 | 2020-08-13
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012034995833 — Khet Talab Nirman Santram/Raghuveer shakya Chandni | Ongoing | 356340.1 | 94044 | 2022-05-30
DATIA / BHANDER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035124580 — Khet talab nirman Bhagvandas /Hargovind Kourab kugaon,chandni | Closed | 0 | 0 | 2023-04-16
DATIA / BHANDER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035124582 — Khet talab nirman Dinesh/Raghuveer Shrivastava kugaon,chandni | Closed | 0 | 0 | 2023-04-16
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035360500 — Khet Talab Koushal/Ramkishan soni Kurgaon Gp Chandni | Physically Completed | 247805.01 | 112010 | 2025-04-28 | 2026-06-05
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035360506 — Khet Talab Nirman Ajmer singh /Nannu singh Kurgaon Gp Chandni | Physically Completed | 247805.01 | 159210 | 2025-05-01 | 2026-06-06
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035360515 — Khet Talab Nirman Rajpal singh/Maansingh Kurgaon Gp Chandni | Closed | 237015.23 | 1566 | 2025-05-01
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035360525 — Khet Talab Nirman Swaraj/Malkhan singh Kurgaon Gp Chandni | Closed | 247805.01 | 261 | 2025-05-14
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035360527 — Khet Talab Nirman Ramesh/Raghuveer singh Shrivastava Kurgaon,GP Chandni | New | 0 | 0 | 2025-04-01
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/IF/22012035360529 — Khet Talab Nirman Ramesh/Raghuveer singh Shrivastava Kurgaon,GP Chandni | Closed | 247805.01 | 261 | 2025-05-14
DATIA / BHANDER | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1704003012/IF/9926708087 — cattle shed Damru /summer | Completed | 80000 | 73110 | 2014-02-27 | 2016-06-07
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1704003012/IF/9993692731 — shochalay nirman kary balkishun s/o channi kori | Deleted | 12000 | 0 | 2015-12-06
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692852 — sochhalay nirmaan balkishans/ochanni kori | Deleted | 12000 | 0 | 2015-12-04
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692858 — sochalay nirman chhotelal s/o ramdeen kumhar | Deleted | 12000 | 0 | 2015-12-04
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692863 — sochalay nirman udaysingh s/o chhanni kori | Deleted | 12000 | 0 | 2015-12-04
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692868 — sochalay nirman gajjus/o chhingi kori | Deleted | 12000 | 0 | 2015-12-04
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692872 — sochalay nirman ganjju s/o chhinge kori | Deleted | 12000 | 0 | 2015-12-04
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692886 — sochalay nirman bhagvatdaas s/o harkishun kori | Deleted | 12000 | 0 | 2015-12-04
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993692999 — shochalay nirman ashok /bharose dohare | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693012 — shochalay nirman bitty w/o hardyal khagar | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693024 — shochalay niman dashrath/parshu kumhar | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693029 — shochalay nirman kasola/sukhdeen kumhar | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693042 — shochalay nirman sankar/bahoran dohare | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693049 — shochalay nirman siyasharan /ramdas dohare | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693051 — shochalay nirman viran/ramdas dohare | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693053 — shochalay nirman shyamvati/shyamkishor | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693057 — shochalay nirman raghuveer/ramsingh dohare | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693060 — shochalay nirman parshura /dalu kori | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693062 — shochalay nirman mansingh/godan kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693065 — shochalay nirman bhagvat singh/mannulal kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693069 — shochalay nirman maganlal/badri kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693185 — shochalay nirman mehndra singh/ramswaroop kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693187 — shochalay nirman raghuveer/pannalal kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693190 — shochalay nirman madho/radhesyam kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693191 — shochalay nirman himmat singh/sankar prasad kaurav | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693193 — shochalay nirman kishun/uday kori | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693194 — shochalay nirman maithelisharan/swamisharansharma | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1704003012/IF/9993693644 — shochalay nirman shivkumar/chandraprakas khaimaria | Deleted | 12000 | 0 | 2015-12-08
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/1880675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4481871 | Completed | 15660 | 15660 | 2018-07-18 | 2018-09-15
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/1881133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4973459 | Completed | 15660 | 15660 | 2018-07-18 | 2018-09-15
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/1881204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5050108 | Completed | 15660 | 15660 | 2018-07-18 | 2018-09-17
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/1906665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2591493 | Completed | 15660 | 15660 | 2018-08-01 | 2018-11-01
DATIA / BHANDER | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/1906667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2575909 | Completed | 15660 | 15660 | 2018-08-01 | 2018-09-20
DATIA / BHANDER | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/2157452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5446836 | Completed | 15840 | 15664 | 2019-07-18 | 2020-04-10
DATIA / BHANDER | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/2282562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5443781 | Completed | 15840 | 15840 | 2019-09-23 | 2020-01-31
DATIA / BHANDER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/2894745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4994489 | Completed | 17100 | 16791 | 2021-04-16 | 2022-01-10
DATIA / BHANDER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/2945426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5743865 | Completed | 17100 | 17370 | 2021-07-04 | 2021-12-17
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4044522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122371004 | Completed | 18360 | 17136 | 2022-09-11 | 2023-05-06
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4046336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126150825 | Completed | 18360 | 18360 | 2022-08-13 | 2023-02-20
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4046686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127395476 | Completed | 18360 | 16728 | 2022-12-25 | 2023-12-20
DATIA / BHANDER | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4047191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128285293 | Completed | 18360 | 17367 | 2023-07-13 | 2024-11-20
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4048923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129197470 | Completed | 18360 | 15606 | 2022-12-25 | 2023-12-20
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4049261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127676077 | Completed | 18360 | 17544 | 2022-08-13 | 2023-11-30
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4049706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126745389 | Completed | 18360 | 17646 | 2022-09-11 | 2023-11-30
DATIA / BHANDER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4049974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126524237 | Completed | 18360 | 17496 | 2024-06-05 | 2024-11-20
DATIA / BHANDER | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4218501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128297845 | Completed | 18360 | 17136 | 2022-09-11 | 2023-06-10
DATIA / BHANDER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4218502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128300667 | Physically Completed | 23490 | 8748 | 2024-11-13 | 2025-07-21
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/437580 — Construction of IAY House -IAY REG. NO. MP1449273 | Completed | 15030 | 15150 | 2017-02-01 | 2017-12-15
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4526344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127681936 | Ongoing | 23490 | 18792 | 2025-04-22
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4713784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126196393 | Ongoing | 23490 | 18792 | 2025-04-22
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4714496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127830315 | Ongoing | 23490 | 20358 | 2025-04-22
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4714500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127830853 | Completed | 23490 | 20358 | 2025-04-22 | 2026-08-14
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4715387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129197317 | Completed | 23490 | 18792 | 2025-04-22 | 2026-08-14
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4965780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127681573 | Ongoing | 23490 | 23229 | 2025-12-23
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4965787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127683951 | Physically Completed | 23490 | 18792 | 2025-12-23 | 2026-03-15
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4966048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127393583 | Ongoing | 23490 | 20358 | 2025-06-05
DATIA / BHANDER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4966051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127394893 | Approved | 23490 | 0 | 2025-02-19
DATIA / BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4966267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127834892 | Ongoing | 23490 | 21924 | 2026-05-01
DATIA / BHANDER | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4966271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127837096 | Ongoing | 23490 | 21924 | 2025-08-04
DATIA / BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4968864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128289518 | Completed | 23490 | 18792 | 2026-05-01 | 2026-08-14
DATIA / BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4968865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128290582 | Ongoing | 23490 | 22446 | 2026-05-01
DATIA / BHANDER | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4968992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128402371 | Physically Completed | 23490 | 17226 | 2026-05-15 | 2026-06-14
DATIA / BHANDER | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/4970137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128654020 | Approved | 23490 | 0 | 2025-02-19
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/51026 — Construction of IAY House -IAY REG. NO. MP-04-003-012-001/138918283 | Completed | 14310 | 14195 | 2016-06-15 | 2017-10-01
DATIA / BHANDER | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1704003012/IF/IAY/750935 — Construction of IAY House -IAY REG. NO. MP2575904 | Completed | 15030 | 15480 | 2017-08-16 | 2017-12-15
DATIA / BHANDER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034228123 — Khel maidan nirman chandni | Completed | 163000 | 147483.8 | 2015-08-21 | 2016-06-07
DATIA / BHANDER | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034228124 — Shantidham nirman chandni | Completed | 182000 | 139759 | 2015-08-21 | 2016-08-28
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1704003012/LD/22012034259857 — Med-Bandhan Ka Kary Chhote Lal | Deleted | 0 | 0 | 2016-01-26
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1704003012/LD/22012034259859 — Med-Bandhan Ka Kary Chhote Lal | Deleted | 0 | 0 | 2016-01-26
DATIA / BHANDER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034274587 — Medbandhan Nirman makundi/channi kori | Completed | 16000 | 13360 | 2016-06-04 | 2016-08-28
DATIA / BHANDER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034274589 — Medbandhan Nirman Rambhushan/Radhacharan | Completed | 32000 | 26720 | 2016-06-04 | 2016-08-28
DATIA / BHANDER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034274590 — Medbandhan Nirman Rakesh/rukumsingh | Completed | 29000 | 22712 | 2016-06-04 | 2016-08-28
DATIA / BHANDER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034276133 — Medbandhan Nirman Vimlesh/Sitaram Sharma | Completed | 17000 | 11022 | 2016-06-15 | 2016-08-28
DATIA / BHANDER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034276134 — Medbandhan Nirman Rukum singh/Prabhudayal Kourab | Deleted | 38000 | 0 | 2016-06-22
DATIA / BHANDER | 1899-1900 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1704003012/LD/22012034299169 — shantidham Nirman Kurgaonv | Closed | 0 | 0 | 1899-12-31
DATIA / BHANDER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1704003012/LD/22012034519843 — Medbandhan kary Prakash Dohare / Damru Dohare Kurgaon | Closed | 18640.08 | 0 | 2020-06-05
DATIA / BHANDER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1704003012/LD/22012034520277 — Medbandhan kary Seetaram Kori / Dabbu Kori Kurganw | Closed | 32138.06 | 0 | 2020-06-05
DATIA / BHANDER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1704003012/LD/22012034520553 — Medbandhan kary Seetaram Kori / Dabbu Kori Kurgaon | Closed | 13176.61 | 0 | 2020-06-05
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559978 — CTR Medbandhan Nirman Kary Chhote lal/Chhadami Dohre Chandni | Completed | 32647.08 | 16212 | 2021-06-23 | 2022-04-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559979 — CTR Medbandhan Nirman Kary Shyamlal/Chhadami Dohre Chandni | Completed | 31558.85 | 16212 | 2021-06-23 | 2022-04-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559981 — CTR Medbandhan Nirman Kary Bharoshe/Palu Dohre Chandni | Closed | 30470.6 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559983 — CTR Medbandhan Nirman Kary Laxman/Gyadeen kori Chandni | Closed | 31558.85 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559984 — CTR Medbandhan Nirman Kary Rameshwer/Gyadeen kori Chandni | Completed | 30470.6 | 11580 | 2021-06-23 | 2022-05-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559985 — CTR Medbandhan Nirman Kary Ater singh/Surjan Dohre Chandni | Completed | 30470.6 | 8106 | 2021-06-23 | 2022-04-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559986 — CTR Medbandhan Nirman Kary Pratapsingh/Surjan Dohre Chandni | Completed | 33735.31 | 16212 | 2021-06-23 | 2022-04-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559987 — CTR Medbandhan Nirman Kary Sitaram/Dalthu dohre Chandni | Closed | 31558.85 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559988 — CTR Medbandhan Nirman Kary Prakash/ Damru dohre Chandni | Completed | 32647.08 | 15054 | 2021-06-23 | 2022-04-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034559989 — CTR Medbandhan Nirman Kary Harkishan/Chhigge kori Chandni | Closed | 32647.08 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564936 — CTR med Bandhan kary Hukum Kori S/O Halku Kori gram chandni gp Chandni | Closed | 32647.08 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564937 — CTR med bandhan kary chatur Singh dohare/narayan dohare gram chandni gp chandni | Closed | 23941.2 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564938 — CTR med bandhan kary jasmant dohare /Narayan dohare gram chandni gp chandni | Closed | 23941.2 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564939 — CTR med bandhan kary Balkishun Kori/channi Kori gram chandni gp chandni | Closed | 22852.95 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564940 — CTR med bandhan kary ramprasad parihar / sopat parihar gram chandni gp chandni | Closed | 25029.43 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564941 — CTR med bandhan kary Ajmer parihar /sopat parihar gram chandni gp chandni | Closed | 23941.2 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/22012034564942 — CTR med bandhan kary parmanad dohare/ Gyasi dohare gram chandni gp chandni | Closed | 25029.43 | 0 | 2021-04-01
DATIA / BHANDER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/3799394709 — medbandan govendra singh/tularam dohre | Completed | 20000 | 19856 | 2013-06-10 | 2013-08-14
DATIA / BHANDER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/3799398569 — (medbandhan chandraprakash/tularam dohre) | Completed | 20000 | 19126 | 2013-07-03 | 2014-12-10
DATIA / BHANDER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1704003012/LD/3799400616 — medbandhan ramdas/ratti dohre | Completed | 30500 | 28622 | 2013-07-24 | 2014-12-10
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1704003012/PG/22012034358538 — gramidkridangan khelmedan nirman kurgaon | Completed | 190000 | 344 | 2017-09-06 | 2018-06-15
DATIA / BHANDER | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704003012/RC/09 — मिटटी मुरम संडक चांदनी से कुरगांव | Completed | 495500 | 542878 | 2007-09-22 | 2013-03-30
DATIA / BHANDER | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704003012/RC/22012034178160 — (PANCH PARMESHWAR) CC KALICHARAN KE MAKAN SE TALAB | Completed | 109000 | 108024 | 2013-08-12 | 2016-08-09
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034288426 — PPcc abm nali nirman Kallu kourab ke makan se bade talab ki or | Completed | 84000 | 83589 | 2015-11-04 | 2016-06-07
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034290810 — PPcc nirman Mangal bakeel ke makan se Shaskiy madhaymik vidhayalay ki or | Completed | 68000 | 62361 | 2015-12-01 | 2016-06-07
DATIA / BHANDER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704003012/RC/22012034317399 — N Sudur sadak Nirman chandni gaon se sojna gaon ki or | Completed | 1218000 | 1106235.6 | 2016-12-07 | 2019-04-24
DATIA / BHANDER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034327005 — N PPcc Vikram kori ke makan se Bade Hanumanji mandir ki or Chandni | Completed | 100000 | 41882 | 2017-02-15 | 2018-04-11
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034350551 — Panch permeswer cc abm nali kamlesh dohre ke makan se Neher Tak chandni | Completed | 90000 | 68112 | 2017-08-23 | 2019-05-02
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034361804 — c c road evm nali nirman Thakur das ke makan se jagdas kori ke makan tak chandani | Completed | 13600 | 13626 | 2017-10-04 | 2018-04-11
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034362880 — cc road abm nali nirman harkishun ke makan se kalyan savita ke makan tak | Closed | 0 | 0 | 2017-09-16
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034362881 — cc road abm nali nirman harkishun ke makan se kalyan savita ke makan tak | Completed | 145000 | 21672 | 2017-10-04 | 2018-01-24
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034364023 — cc rode evm nali nirman chandan ke makan ke samane se prathimik school tak | Ongoing | 19000 | 516 | 2017-11-01
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034364024 — cc rode evm nali nirman narayandas ke makan se radhesyam ke makan tak chandani | Completed | 16000 | 17046 | 2017-10-25 | 2019-06-02
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034370863 — PP+N CC road with nali nirman | Closed | 0 | 0 | 2017-10-02
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034398647 — PP+N CC road avam nali Shankarji mandir se Bhagvand singh Kourav tak Kurganv | Closed | 18000 | 0 | 2018-04-14
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034434686 — PP+N cc road avam nali Shankar ji mandir se Bhagvan singh Kaurav ke makan tak Kurganw | Completed | 18000 | 17748 | 2019-01-09 | 2019-03-18
DATIA / BHANDER | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034439264 — Cc road avm nali nirman | Closed | 0 | 0 | 2019-04-01
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034445522 — PP+N cc road avam nali Arvind Kaurav ke makan se Shantidham tak Kurganv | Completed | 100000 | 98586 | 2019-02-20 | 2020-09-22
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034447079 — PP+N cc road avam nali Gambhir Pal ke makan se Nahar ki oar Chandani | Completed | 76500 | 76386 | 2019-02-27 | 2019-03-27
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034447954 — PP+N cc road avam nali Lakshman Shaky ke makan se Mangal Savita ke makan tak Chandni | Completed | 29200 | 29156 | 2019-03-06 | 2020-01-28
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704003012/RC/22012034524825 — Sudoor gram sadak nirman Gram Kurganv se Gram Khuja Distt.Bhind ki seema tak Kurganv | Ongoing | 1759855.99 | 1030268.15 | 2020-07-14
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034538305 — 14वां वित्त$मनरेगा सीसी रोड सह नाली निरंजन कौरव के मकान से कालीचरण सविता के मकान की ओर सिंगल कोट कुर | Completed | 70600 | 70490 | 2020-09-15 | 2020-12-10
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034540739 — 15वित्त$मनरेगा सीसी रोड सह नाली चन्दन कौरव के मकान से सीताराम खैमरिया के मकान की ओर(सिंगल कोट)चांदनी | Completed | 53700 | 53580 | 2020-09-29 | 2020-12-10
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034561844 — Cc road avm nali nirman harkishun kori ke makan se umrao prajapati ke makan tak vidhayak nidhi+nrega | Completed | 37000 | 36863 | 2021-04-10 | 2025-02-13
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704003012/RC/22012034583277 — Sudur sadak road Awas basti se Ghanshyampur ki or Chandni | Closed | 0 | 0 | 2021-06-10
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1704003012/RC/22012034584112 — Aproch road Nirman PM road se panchayat ki or Chandni | Closed | 0 | 0 | 2021-09-10
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034590965 — Cc road avm nali nirman Kurgaon miner se MS School tak chandni 15vitt+nrega | Ongoing | 48000 | 46614 | 2022-03-24
DATIA / BHANDER | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034606044 — Cc road evm nali Nirman | Closed | 0 | 0 | 2022-04-01
DATIA / BHANDER | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034640886 — Naala Nirman Mulam Savita ke makan se Bharat Kourav ke makan ki or kurgaon 5 vitt+ntrega | Deleted | 51000 | 0 | 2023-05-29
DATIA / BHANDER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034821846 — Cc road sah nali nirman kary-ramprasad dohre ke makan se ravindra dohre ke makan tak | Approved | 0 | 0 | 2024-06-08
DATIA / BHANDER | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034821849 — Cc road sah nali nirman kary-main road se khajelu mata mandir kee or chandani | Completed | 76000 | 68769 | 2024-12-11 | 2026-02-07
DATIA / BHANDER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034837161 — CC Road av nali nirman Hariram Dohare ke makan se Manoj Dohare ke makan ki oar Chandni 05th vit+NRGS | Ongoing | 126000 | 98397 | 2025-04-10
DATIA / BHANDER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034845078 — CC Road Sah Nali Nirman Karya Gopal Kori Ke Makan Se Hanuman Ji Prangad Ki OR | Approved | 162000 | 0 | 2025-04-14
DATIA / BHANDER | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/22012034847947 — CC road sah nali Shriram Pal ke makan se Hanuman mandir ke Prangan tak Kurganv 05th Vitt GP+N | Approved | 102000 | 0 | 2025-04-14
DATIA / BHANDER | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1704003012/RC/252 — grebal rod nehar se gao tak | Completed | 196000 | 106682 | 2010-09-25 | 2016-02-01
DATIA / BHANDER | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1704003012/RC/324 — (panch parmeshwar) cc abm nali nirman pal ke mkan se mukhuymantri ke or | Completed | 77000 | 53064 | 2012-10-23 | 2013-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034259920 — maryad abhiyan gopal/gyadeen koree | Deleted | 5400 | 0 | 2014-08-23
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034260041 — maryada abhiyan ramprasad/sopat parihar | Deleted | 5400 | 0 | 2014-08-23
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262282 — maryadaabhiyan sochalay Ajmer/sopat parihar | Deleted | 5400 | 0 | 2014-08-23
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262283 — maryadaabhiyan sochalay Raghunath singh/Ramcharan | Completed | 5400 | 5355 | 2014-08-23 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262284 — maryadaabhiyan sochalay beba bitti/hardayal | Deleted | 5400 | 0 | 2014-08-23
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262285 — maryadaabhiyan sochalay madansingh /Ramsingh dohre | Deleted | 5400 | 0 | 2014-08-23
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262286 — maryadaabhiyan sochalay Lakhansingh/Nanu kurgaon | Completed | 5400 | 5355 | 2014-08-23 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262287 — maryadaabhiyan sochalay kalicharan /gyadeen sabita | Completed | 5400 | 5355 | 2014-08-23 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262288 — maryadaabhiyan sochalay Ramprasad /daleepe dohre | Completed | 5400 | 5355 | 2014-08-23 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262289 — maryadaabhiyan sochalay Ganbhirsingh/Anandi dohre | Completed | 5400 | 5355 | 2014-08-23 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262290 — maryadaabhiyan sochalay Ravindrasingh /gambhir doh | Deleted | 5400 | 0 | 2014-08-23
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034262291 — maryadaabhiyan sochalay gajrajsingh /dalpe dohre | Completed | 5400 | 3978 | 2014-08-23 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034263835 — maryadaabhiyan Naresh/baliram barar | Deleted | 5400 | 0 | 2014-08-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034263836 — maryadaabhiyan kamlesh/amarju dohre | Deleted | 5400 | 0 | 2014-08-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034263837 — maryadabhiyan Veersingh/gambhir dohre | Completed | 5400 | 5355 | 2014-08-30 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034267645 — marayadaabhiyan Hukum singh/majboot pal | Completed | 5400 | 5355 | 2014-09-11 | 2015-03-30
DATIA / BHANDER | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034267646 — maryadaabhiyan Mahendrasingh/rajaram dohre | Completed | 5400 | 5355 | 2014-09-11 | 2015-03-30
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034291989 — Shochalay nirman gajju/chhimge kori | Closed | 12000 | 0 | 2018-01-20
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034291990 — Shochalay nirman kary pratap singh s/o surjan dohare | Closed | 12000 | 0 | 2015-11-16
DATIA / BHANDER | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034291992 — Shochalay nirman kary kalyan s/o bhagonidohare | Closed | 1200000000 | 0 | 2015-11-16
DATIA / BHANDER | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034293745 — Sochalay nirman | Deleted | 12000 | 0 | 2016-04-01
DATIA / BHANDER | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034381513 — SBM Harcharan/Jagadeesh chadani | Completed | 12000 | 11924 | 2017-11-01 | 2018-05-05
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1704003012/RS/22012034438136 — PMAY Shochalay Akhlesh Prajapati/Magali MP4481871 Chandni | Completed | 12000 | 11980 | 2019-02-20 | 2020-01-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1704003012/RS/22012034496803 — Soakpit Nirman MS school ke handpump per chandni | Closed | 14283.77 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1704003012/RS/22012034496804 — Soak pit Nirman Dilabarkourab ke makankesamne handpump per | Closed | 14283.77 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1704003012/RS/22012034496805 — Soak pit Nirman PS school ke handpump ke pass Kurgaon | Closed | 14283.77 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1704003012/RS/22012034496806 — Soak pit Nirman dwarkaprasad kourab ke samne handpump per kurgaon | Closed | 14283.77 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1704003012/RS/22012034496807 — Soak pit Nirman shankarji mandir ke pass handpump per kurgaon | Closed | 14283.77 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496808 — Nadep Compost Nirman Chhota Talab ke pass Chandni _Bhag_1 | Closed | 12480.05 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496809 — Nadep Compost Nirman Chhota Talab ke pass Chandni _Bhag_2 | Closed | 0 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496810 — Nadep Compost Nirman Chhota Talab ke pass Chandni _Bhag_3 | Closed | 12480.05 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496811 — Nadep Compost Nirman Chhota Talab ke pass Chandni _Bhag_3 | Closed | 12480.05 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496812 — Nadep Compost Nirman Talab ke pass Kurgaon_Bhag_1 | Closed | 12480.05 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496813 — Nadep Compost Nirman Talab ke pass Kurgaon_Bhag_2 | Closed | 12480.05 | 0 | 2020-08-20
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1704003012/RS/22012034496814 — Nadep Compost Nirman Talab ke pass Kurgaon_Bhag_3 | Closed | 12480.05 | 0 | 2020-08-20
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/WC/22012034295469 — Khet Talab Nirman Jasbantsingh/narayan dohre | Completed | 36000 | 14740 | 2016-06-04 | 2018-05-14
DATIA / BHANDER | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/WC/22012034295471 — Khet Talab Nirman Nihalsingh/gangaprasad | Completed | 82000 | 5511 | 2016-06-04 | 2017-12-15
DATIA / BHANDER | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/22012034312840 — Talab band ka sundrikaran abm bestbear nirman chandni | Completed | 399000 | 264784 | 2016-10-19 | 2019-09-01
DATIA / BHANDER | 2018-2019 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1704003012/WC/22012034427329 — Nala nirman Bhart Korav ke makan se Talab tak Kurganw | Closed | 46000 | 0 | 2018-04-14
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1704003012/WC/22012034432974 — PP+N Jal nikasi Nala nirman Bharat Kaurav ke makan se Talav Tak Kurgaw | Completed | 46000 | 43320 | 2020-07-08 | 2020-09-22
DATIA / BHANDER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/22012034582518 — Khajelu mata mandir ke Talab Ka ghat Nirman Avm reterningwall Nirman | Completed | 1498336.19 | 1463839 | 2020-09-22 | 2025-07-17
DATIA / BHANDER | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1704003012/WC/22012034587885 — Mata mandir Talab ke ghat ka retuening wall avm ghat nirman khudayi kary kurgaon | Closed | 0 | 0 | 2020-09-20
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637609 — CTR Roof top rain water harvesting Shaskiye madhaymik vidhyalay chandni | Completed | 28777.92 | 23614.62 | 2021-05-09 | 2024-11-18
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637611 — CTR Roof top rain water harvesting Shaskiye Prathmik vidhyalay chandni | Closed | 28777.92 | 0 | 2021-05-09
DATIA / BHANDER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637614 — CTR Roof top rain water harvesting Anganwadi Bhavan chandni | Physically Completed | 28777.92 | 22619.46 | 2022-11-20 | 2026-04-11
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637616 — CTR Roof top rain water harvesting Samudayak Bhavan chandni | Closed | 28777.92 | 0 | 2021-05-09
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637618 — CTR Roof top rain water harvesting Shaskiye Prathmik vidhyalay Kurgaon | Closed | 28777.92 | 0 | 2021-05-09
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637620 — CTR Roof top rain water harvesting Anganwadi Bhavan Kurgaon | Closed | 28777.92 | 0 | 2021-05-09
DATIA / BHANDER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637622 — CTR Roof top rain water harvesting Bahuudeshiye Bhavan Chandni | Physically Completed | 28777.92 | 23595.35 | 2022-11-20 | 2026-04-11
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1704003012/WC/22012034637624 — CTR Roof top rain water harvesting Panchayat Bhavan Chandni | Completed | 28777.92 | 22366.35 | 2021-05-10 | 2024-11-18
DATIA / BHANDER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1704003012/WC/22012034644667 — CTR Talab Jirdodwar bada Tlab shankarji ke pass Gp Chandni | Closed | 0 | 0 | 2021-04-01
DATIA / BHANDER | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1704003012/WC/22012034644671 — CTR Talab Jirdodwar Matamandir ke pass Kurgaon Gp chandni | Physically Completed | 540613.44 | 276865 | 2021-07-03 | 2026-04-16
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1704003012/WC/22012034792035 — Naali Nirman Veeran Kourab ke makan se Kaushal Soni ke makan ki or Kurgaon 15 vitt+nrega | Completed | 27000 | 27792 | 2021-07-11 | 2022-04-24
DATIA / BHANDER | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1704003012/WC/22012034797713 — Naala Nirman Gulab ke makan se Mulayam singh ke makan tak kurgaon PP +nrega | Completed | 24000 | 24318 | 2021-08-12 | 2022-04-24
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/22012034817541 — Naala Nirman Shankar Dohre ke makan se naher tak chandni | Completed | 743459.65 | 706867.97 | 2021-12-04 | 2025-04-08
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/22012034826556 — Talab Bund Vistarikaran kary gram chandni | Completed | 1497014.71 | 1430934.4 | 2021-10-06 | 2022-10-20
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/22012034862594 — Naala Nirman Kary Dayaram Pal ke maka se Talab ki or Kurgaon 15vitt+nrega | Closed | 38000 | 0 | 2021-10-22
DATIA / BHANDER | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1704003012/WC/22012034907234 — Pokhar Nirman Kary | Closed | 0 | 0 | 2022-04-01
DATIA / BHANDER | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1704003012/WC/22012034980629 — kachcha nala nirman nirman Alvel kaurav ke Khet se shanti dham Ki or gram rakhra | Closed | 0 | 0 | 2022-04-10
DATIA / BHANDER | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1704003012/WC/22012035005991 — Drain khudayi Kary Talab se Shriram Pal ke khet ki or Kurgaon Gp Chandni | Physically Completed | 979923.11 | 583785 | 2023-06-20 | 2026-04-11
DATIA / BHANDER | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/22012035080527 — Naala Nirman Mulam Savita ke makan se Bharat Kourav ke makan ki or kurgaon 5 vitt+ntrega | Closed | 51000 | 0 | 2023-05-29
DATIA / BHANDER | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1704003012/WC/22012035176660 — Nala nirman kary-dwakra kaurav ke makan se arvindra kaurav ke makan tak kurgao | Ongoing | 45000 | 33009 | 2024-03-16
DATIA / BHANDER | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1704003012/WC/22012035216494 — Nala nirman kary shankar ji mandir se shantidham kee or kurgaon | Approved | 53000 | 0 | 2024-06-08
DATIA / BHANDER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704003012/WC/22012035291087 — JGSA 2025 Recharge Structure Sarvajanik Koop Rampal ke pass Kua par GramKurgaon | Physically Completed | 25033.43 | 21676.74 | 2025-05-12 | 2026-04-12
DATIA / BHANDER | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1704003012/WC/22012035291096 — JGSA 2025 Recharge Structure Sarvajanik Koop Chandrbhushan ke pass Kua par Gram Kurgaon | Physically Completed | 25033.43 | 22198.74 | 2025-05-12 | 2026-04-12
DATIA / BHANDER | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Continuous Contour Trench / Construction of Continuous Contour Trench for Community | Construction of Trench | 1704003012/WC/229 — nali nirman chandni gao se nahar ke or | Deleted | 117000 | 36600 | 2011-02-08
DATIA / BHANDER | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704003012/WC/360 — soke phit nirman dilabar ke makan ke pass | Completed | 17000 | 4392 | 2012-01-27 | 2013-03-30
DATIA / BHANDER | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/WC/394 — sok phit nirman aabash muhlla ke pass hed pamp | Completed | 17000 | 4392 | 2012-04-29 | 2013-03-30
DATIA / BHANDER | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1704003012/WC/395 — sok phit nirman shaskey prathmil vidhyalay | Completed | 17000 | 4392 | 2012-04-21 | 2013-03-30
DATIA / BHANDER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704003012/WC/9993642234 — sokpit nirman Sarkari kua hanuman mandir chandni | Completed | 25000 | 13140 | 2014-01-08 | 2015-02-27
DATIA / BHANDER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704003012/WC/9993642235 — sokpit nirman aanganbadi bhavan handpump | Completed | 25000 | 8760 | 2014-01-08 | 2015-02-27
DATIA / BHANDER | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704003012/WC/9993647335 — sokpit nirman shaskiya prathmik vidhyalay kurgoan | Deleted | 25500 | 0 | 2014-02-27
DATIA / BHANDER | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1704003012/WC/9993653369 — Talab Bistarikaran kary kurgaon | Completed | 327000 | 261679 | 2014-06-17 | 2016-02-01
DATIA / BHANDER | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1704003012/WC/9993653879 — PP nali nirman purani nali se nahar ke or | Completed | 95933 | 77218 | 2014-07-03 | 2016-06-02
DATIA / BHANDER | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1704003012/WH/22012034445840 — Talab Jirdodhar mata mandir Talab gram chandni | Physically Completed | 166901.04 | 86130 | 2021-12-03 | 2026-04-16
DATIA / BHANDER | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1704003012/WH/22012034446526 — तालाब गहरीकरण मंदिर के पास ग्राम चाँदनी | Closed | 0 | 0 | 2021-02-20
DATIA / BHANDER | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1704/RC/100024 — चॉदनी से कुरगांव | Completed | 2493000 | 1766926.2 | 2011-02-10 | 2016-02-02