## Work List
Exported on: 2026-08-18 09:18:30
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: NETWAS
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHIVPURI / KOLARAS | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1705005015/AV/22012034641702 — hampapip calvart nirman raghunath pura bhataua | Ongoing | 1175000 | 0 | 2023-10-24
SHIVPURI / KOLARAS | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1705005015/AV/22012034641781 — hampaipe culvrt bhataua pharm ke raste par | Ongoing | 1175000 | 0 | 2023-10-24
SHIVPURI / KOLARAS | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1705005015/DP/22012034432038 — PLANTATION GUJARI NADI KE KINARE SHASKIYE BHUMI PAR NETWAS | Ongoing | 544000 | 0 | 2018-10-07
SHIVPURI / KOLARAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1705005015/DP/22012034588571 — Braksharopan karya meri mati mera desh khel medan | Ongoing | 55847.4 | 0 | 2023-09-11
SHIVPURI / KOLARAS | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1705005015/IF/22012034573705 — phodh ropan aguri ke khet par bhataua | Ongoing | 115360 | 0 | 2020-07-02
SHIVPURI / KOLARAS | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012034667708 — KHET TALAB NIRMAN ANGURI KE KHET PAR BHATUA | Ongoing | 332962.02 | 0 | 2021-03-16
SHIVPURI / KOLARAS | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1705005015/IF/22012034668119 — PASHUSHAID NIRMAN SUSHILA BHATUA | Ongoing | 63531 | 0 | 2021-06-18
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012035334271 — KHET TALAB NIRMAN KASHUMAL RAWAT KE KHET PAR BHATAUA | Approved | 0 | 0 | 2025-04-01
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012035334299 — KHET TALAB NIRMAN KASHUMAL RAWAT KE KHET PAR BHATAUA | New | 0 | 0 | 2025-04-01
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012035334718 — Khet talab nirman karya kasumal rawat | Approved | 0 | 0 | 2025-04-01
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012035404089 — khet talab nirman ramsingh ke khet par gram bhatua | Ongoing | 366209.53 | 0 | 2025-05-02
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012035490880 — KHET TALAB NIRMAN KARYA INDAR SINGH KE KHET PAR | Ongoing | 387190.81 | 0 | 2025-05-29
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1705005015/IF/22012035568803 — khet talab nirman ramlata ke khet par | Approved | 0 | 0 | 2025-04-01
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1705005015/IF/22012035648503 — Ek bagiya ma ke name pista rawat/laxman rawat gram netwas | Ongoing | 263511.37 | 0 | 2026-02-01
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1705005015/IF/22012035659668 — ek bagiya maa ke naam anita/bhagirath jatav ke khet par netwas | Ongoing | 263511.37 | 0 | 2026-02-22
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1705005015/IF/22012035659691 — Ek bagiya maa ke naam vijalesh/kalyan singh rawat netwas | Ongoing | 263511.37 | 0 | 2026-01-23
SHIVPURI / KOLARAS | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1705005015/IF/IAY/4124533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127115268 | Approved | 23490 | 0 | 2022-05-19
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1705005015/IF/IAY/4964040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125674971 | Ongoing | 23490 | 0 | 2025-06-12
SHIVPURI / KOLARAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1705005015/IF/IAY/4968269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129701308 | Ongoing | 23490 | 0 | 2025-04-30
SHIVPURI / KOLARAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1705005015/IF/IAY/5818901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129700160 | Approved | 23490 | 0 | 2025-03-03
SHIVPURI / KOLARAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1705005015/IF/IAY/61717 — Construction of IAY House -IAY REG. NO. MP-05-005-015-001/015 | Approved | 23490 | 0 | 2015-11-10
SHIVPURI / KOLARAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1705005015/LD/22012034941550 — SAMUDAYAK BRAKSHAROPAD AMRAT SAROVAR TALAB KE PASS BHATAUA | Ongoing | 1471888 | 0 | 2024-08-23
SHIVPURI / KOLARAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1705005015/WC/22012035052658 — talab niraman kary mansingh av surendra ke pas bale nale par bhataua | Ongoing | 2474000 | 0 | 2023-10-01
SHIVPURI / KOLARAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1705005015/WC/22012035211007 — DAGPOINT NIRMAN KARYA RAGHUNATH SADAR KE KHET KE PASS BHATAUA | Approved | 0 | 0 | 2024-04-01
SHIVPURI / KOLARAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1705005015/WC/22012035248601 — PARCULATION TANK NIRMAN KARYA KASHMIR SARDAR KE KHET KE PASS BHATUA | Approved | 0 | 0 | 2025-01-24